## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-140-RAIL-BRUNT-Track Formation - Capping Layer Rev.0 | itp |  |  |  |  | ITP-140-RAIL-BRUNT-Track Formation - Capping Layer Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-140-RAIL-BRUNT-Track Formation - Capping Layer
label | ITP Description: Track Formation - Capping Layer
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 14/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference - L1-CHE-SPE-178 (VERSION 3)
checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference - L1-CHE-STD-029 (VERSION 4)
checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
label | Reference - AS 1289
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Capping Material Conformance (1 of 2)
label | Reference - L1-CHE-SPE-178 - Clause 5.12.3. Table 6
label | Acceptance Criteria - Capping material shall comply with the following grading requirements:
label | ○ % passing 53.0mm sieve 100%
label | ○ % passing 37.5mm sieve 100%
label | ○ % passing 26.5mm sieve 100%
label | ○ % passing 19.0mm sieve 95-100%
label | ○ % passing 9.5mm sieve 60-90%
label | ○ % passing 4.75mm sieve 40-70%
label | ○ % passing 2.36mm sieve 30-60%
label | ○ % passing 0.075mm sieve 6-10%
label | Method - Document Review
label | Frequency - Once, for each material type - prior to works commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Capping Material Conformance (2 of 2)
label | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
label | Acceptance Criteria - The following tests shall be carried out on samples of the capping layer material:
label | ○ Soaked CBR - minimum 50% compacted to 98% modified dry density
label | ○ Liquid Limit - 30% Max
label | ○ Plastic Limit - 20% Max.
label | ○ Plasiticity Index - 4-15%
label | ○ Linear Shrinkage - 4.5%
label | ○ Dry Density - 2.0t/m³ MIn.
label | – Refer to AS 1289 for Tests
label | Method - Document Review
label | Frequency - Once, for each material type - prior to works commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Pre-Commencement of Fill Works
label | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
label | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off, MTM representative signoff
label | Attach: Site Photos
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Set Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Capping Layer Preparation and Installation (1 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.12.4.
label | Acceptance Criteria - Capping layer shall be constructed in one layer and compacted to a total compacted thickness of no less than 150mm.
label | Method - Visual / Measure, Review Test
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Sign ITP Signed Off, MTM representative Signoff
checkpoint | 5.2 - Capping Layer Preparation and Installation (2 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
label | Acceptance Criteria - The following tests shall be carried out on samples of the capping layer material:
label | • Soaked CBR - minimum 50% compacted to 98% modified dry density
label | • Liquid Limit - 30% Max
label | • Plastic Limit - 20% Max.
label | • Plasiticity Index - 4-15%
label | • Linear Shrinkage - 4.5%
label | • Dry Density - 2.0t/m³ MIn.
label | Method - Modified Compaction Test
label | Frequency - Each lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Capping Layer Preparation and Installation (3 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.12.6. AS 1289
label | Acceptance Criteria - 99% Compaction (Modified Compaction Test)
label | Method - Modified Compaction Test
label | Frequency - 3 tests per 500m³
label | ○ atleast 2 tests if < 500m³
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Proof rolling
label | Reference - L1-CHE-SPE-178 - Clause 4.6.
label | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | Method - Proof roll
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP Signed Off, MTM representative Signoff
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-Construction Activities
checkpoint | 6.1 - Survey Conformance / Capping Layer Finishing and Tolerances
label | Reference - L1-CHE-SPE-178 - Clause 5.12.7.
label | Acceptance Criteria - The finished surface level of capping layer shall:
label | ○ Be within -25 to +0mm of approved design level
label | ○ Be within 10mm of algebraic difference of the deviations from the correct level for any two points 20m apart on the centreline
label | ○ Be within -0mm to +10mm of 3m straightedge laid on final capping layer surface parallel and perpendicular to centreline
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Conformance Report
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP