## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-142-RAIL-BRUNT-Track Formation - Structural Fill Rev.0 | itp |  |  |  |  | ITP-142-RAIL-BRUNT-Track Formation - Structural Fill Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-142-RAIL-BRUNT-Track Formation - Structural Fill
label | ITP Description: Track Formation - Structural Fill
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 14/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference - L1-CHE-SPE-178 (VERSION 3)
checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference - L1-CHE-STD-029 (VERSION 4)
checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
label | Reference - AS 1289
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Structural Fill Material Conformance (1 of 2)
label | Reference - L1-CHE-SPE-178 - Clause 5.11.2.1. Table 4
label | Acceptance Criteria - Structural fill materias shall have the following properties:
label | ○ % passing 53.0mm sieve 80-100%
label | ○ % passing 2.36mm sieve 15-100%
label | ○ % passing 0.425mm sieve 0-70%
label | ○ % passing0.075mm sieve 0-30%
label | Method - Document Review
label | Frequency - Once, for each material type - prior to works commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Structural Fill Material Conformance (2 of 2)
label | Reference - L1-CHE-SPE-178 - Clause 5.11.4.1. Table 5 AS 1289
label | Acceptance Criteria - Structural fill must comply with the following requirements:
label | ○ Soaked CBR 8% min compacted to 100% standard dry density
label | ○ Liquid Limit 40% Max.
label | ○ Plasticity Index 20% Max.
label | ○ Dry Density 1.8t/m³ Min.
label | – Refer to AS 1289 for Tests
label | Method - Document Review
label | Frequency - Once, for each material type - prior to works commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Pre-Commencement of Fill Works
label | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
label | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off, MTM representative signoff
label | Attach: Site Photos
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Set Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Structural Fill Preparation and Installation - (1 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
label | Acceptance Criteria - Where Rail Subgrade CBR < 3%:
label | ○ Required minimum depth of structural fill is 1000mm
label | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ Atleast 2 tests if < 500m³
label | Method - Standard Compaction Test
label | Frequency - each lot
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Structural Fill Preparation and Installation - (2 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
label | Acceptance Criteria - Where Rail Subgrade 3% < CBR < 8%:
label | ○ Required minimum depth of structural fill is 500mm
label | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ Atleast 2 tests if < 500m³
label | Method - Standard Compaction Test
label | Frequency - each lot
label | Category - HP
label | Responsibility - SE/
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Structural Fill Preparation and Installation - (3 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
label | Acceptance Criteria - Where Rail Subgrade CBR > 8%:
label | ○ Structural fill can directly be placed onto subgrade and compacted to 100%
label | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
label | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
label | ○ 3 tests per 1000m³
label | ○ 3 tests if 500-1000m³
label | ○ Atleast 2 tests if < 500m³
label | Method - Standard Compaction Test
label | Frequency - each lot
label | Category - HP
label | Responsibility - SE
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Proof rolling
label | Reference - L1-CHE-SPE-178 - Clause 4.6.
label | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | Method - Proof roll
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - This ITP Signed Off, MTM representative Signoff
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-Construction Activities
checkpoint | 6.1 - Structural Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance
label | Reference - L1-CHE-SPE-178 - Clause 5.11.6.
label | Acceptance Criteria - Structural fill shall be within +0 to -35mm of approved design surface level
label | ○ Structural fill shall be within +0 to +50mm of 3m straightedge laid on final structural surface parallel and perpendicular to centreline
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Conformance Report
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP