## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-143-RAIL-BRUNT-Track Formation - Subgrade Rev.0 | itp |  |  |  |  | ITP-143-RAIL-BRUNT-Track Formation - Subgrade Rev.0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-143-RAIL-BRUNT-Track Formation - Subgrade
label | ITP Description: Track Formation - Subgrade
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 26/03/2024
label | ITP created by: Mac Cameron
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
label | Reference - L1-CHE-SPE-178 (VERSION 3)
checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
label | Reference - L1-CHE-STD-029 (VERSION 4)
checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
label | Reference - AS 1289
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Subgrade Description
label | Reference - L1-CHE-SPE-178 - Clause 5.5.1. Table 1 AS1289 Tests 5.1.1 & 5.3.1
label | Acceptance Criteria - Subgrade shall comply with the following criteria:
label | ○ Soaked CBR - 3% min nominal
label | ○ Plasticity Index 9-20%
label | ○ Dispersion (pin hole dispersity) - ND1/ND2
label | ○ Dispersion (Emerson class number of soil) - not to be class 1 or 2
label | ○ Collapse strain - to be agreed by MTM geotechnical engineer
label | ○ Free swell index - 2.5% max.
label | ○ Soil soluble salt content - 3%
label | ○ Organic content (dry weight) - 2% max.
label | – Refer to AS 1289 for Tests
label | Method - Document Review
label | Frequency - Once, for each material type - prior to works commencement
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Supplier Material Conformance Certificate
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Pre-Commencement of Fill Works
label | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
label | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off, MTM representative signoff
label | Attach: Site Photos
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Approval of IFC drawings
label | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
label | Acceptance Criteria - Approved IFC Drawings
label | Method - Document review and approval
label | Frequency - Prior to works commencing
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Set Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Subgrade Preparation and Installation - For track constructed on embankment (1 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.4.
label | Acceptance Criteria - If min CBR < 3%:
label | ○ Install min 1m structural fill
label | If general fill is to be placed directly over subgrade:
label | ○ Subgrade to be compacted to 98%
label | If structural fill is to be placed directly over subgrade:
label | ○ Subgrade shall be scarified to 200mm and re-compacted to 100%
label | – One test per 1000m³
label | – Volume < 1000m³ atleast one set of tests shall be carried out
label | Method - Standard Compaction Test
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Subgrade Preparation and Installation - For track constructed on embankment (2 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.4.
label | Acceptance Criteria - If min 3%< CBR < 8%:
label | If general fill is to be placed directly over subgrade
label | – Subgrade to be compacted to 98% (Standard Compaction Test)
label | If structural fill is to be placed directly over subgrade
label | – Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | ○ One test per 1000m³
label | ○ Volume < 1000m³ atleast one set of tests shall be carried out
label | Method - Standard Compaction Test
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Subgrade Preparation and Installation - For track constructed on embankment (3 of 3)
label | Reference - L1-CHE-SPE-178 - Clause 5.4.
label | Acceptance Criteria - If min CBR > 8%
label | – Excavation can be stopped to suit capping layer or at top of section with CBR > 8%
label | – Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
label | ○ One test per 1000m³
label | ○ Volume < 1000m³ atleast one set of tests shall be carried out
label | Method - Standard Compaction Test
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
label | Attach: Compaction Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Proof rolling
label | Reference - L1-CHE-SPE-178 - Clause 4.6. and 5.4.1.
label | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
label | Method - Proof roll
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE
label | Verifying Documents - This ITP Signed Off, MTM representative Signoff
holdpoint | AUTHORITY HOLDPOINT
section | 6. Subgrade Finishing and Tolerances
checkpoint | 6.1 - Subgrade Finishing and Tolerances - For track constructed on embankment / Survey Conformance
label | Reference - L1-CHE-SPE-178 - Clause 5.7.
label | Acceptance Criteria - Subgrade on embankments shall be installed within +/- 40mm of approved design surface level
label | Method - Document Review
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP Signed Off
label | Attach: Survey Conformance Report
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP