## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-015 - Kerb and Channel Rev2 | itp |  |  |  |  | FHC-ITP-015 - Kerb and Channel Rev2
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Site Foreman
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Setting Out
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.17
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Temporary Drainage Provisions
note | FREQUENCY: If Required
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.18
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Bedding
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
note | • Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.21
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Pre-concrete check
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
note | • Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
note | • Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.08 610.17(a)(b)(c)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
note | – – – – – – – – –
note | HP*/WP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Concrete Placement
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: VicRoads Spec 703.23
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Finish Surfaces
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
note | • Concrete to have a neat appearance and uniform colour.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.25
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Tolerances
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of ‑0 to +10 mm. Except on curves or in shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.15(b)
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.8 Joints
note | FREQUENCY: Each joint
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
note | • Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.26
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.9 Backfilling
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
note | • Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
note | • Layers shall not exceed 150mm compacted depth.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: 703.29
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: ITP Signed
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
section | 3 - Completion
checkpoint | 3.1 Survey data captured for as-built purposes
note | FREQUENCY: Completion of each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: IFC Drawings/survey records
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Document review
note | – – – – – – – – –
note | RECORD OF CONFORMITY: As-built survey records
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Project Engineer/Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: