## Table 1
[7 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-DP1-PM-ITP010
Client: APAM (Melbourne Airport) | [8 empty] | Contract No: CP1002 | [10 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 – Minor Asphalt Works | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 10/07/2023
Construction Process: Linemarking | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 10/07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component: Airfield Pavement Markings
Lot No: |  |  | Lot Details: | [9 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. |  |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  | Responsibility | Checked by:
[5 empty] | Frequency | Acceptance Criteria |  |  |  |  | Reference Documents |  |  | Inspection/ Test Method | Record of conformity | [7 empty] | AECOM |  |  |  |  | Fulton Hogan | Date
1 |  |  | Preliminary Activities
1.1 |  |  | Check for correct documentation |  | Prior to commencing any activity | Current revision drawing is being used including the subcontractors copy. Current revision to be obtained via Aconex |  |  |  |  | Drawings and Aconex |  |  | Visual inspection | This Signed ITP |  |  |  | HP* |  |  | Project Engineer
1.2 |  |  | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP |  |  |  |  | PSP, EMP, TMP, WP, SWMS |  |  | Visual Inspection | Site and Office Inspection |  |  |  | HP* |  |  | Project Engineer Site Supervisor
1.3 |  |  | Plant and Equipment |  | Prior to placing works | Plant and equipment used in the works are appropriate to achieve specification requirements |  |  |  |  | Cl 19.4 |  |  | Verify | This Signed ITP |  |  |  | HP* |  |  | Project Engineer
1.4 |  |  | Setting out |  | Prior to commencing works | The contractor shall carry out the setting out of the pavement Markings as shown on the drawings. Accuracy of survey set-out to be confirmed to be within +/- 25mm. |  |  |  |  | Cl 19.6.4 |  |  | Verify | This Signed ITP |  |  |  | HP |  |  | Project Engineer Principal’s Representative
2 |  |  | Construction
2.1 |  |  | Removal of Existing Line Marking |  | Each Lot | Existing and temporary paint markings shall be removed prior to application of permanent markings, where indicated on drawings or no longer needed, by the use of high-pressure water blasting |  |  |  |  | Cl 19.6.1 |  |  | Verify | This Signed ITP |  |  |  | HP |  |  | Project Engineer Principal’s Representative
[7 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-DP1-PM-ITP010
Client: APAM (Melbourne Airport) | [8 empty] | Contract No: CP1002 | [10 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 – Minor Asphalt Works | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 10/07/2023
Construction Process: Linemarking | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 10/07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component: Airfield Pavement Markings
Item No. |  |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  |  | Responsibility | Checked by:
[5 empty] | Frequency | Acceptance Criteria |  |  |  |  | Reference Documents |  |  | Inspection/ Test Method | Record of conformity | [7 empty] | AECOM |  |  |  |  | Fulton Hogan | Date
2.2 |  |  | Surface preparation |  | Each Lot | Immediately before application of paint, surfaces are to be dry and free from curing compound, dirt, grease, oil, laitance, or other foreign material that would reduce the bond between the paint and the pavement. The contractor shall verify in writing that the surface has been prepared in accordance to the manufacturers requirements. This shall be approved by the Principal’s Representative. |  |  |  |  | Cl 19.6.2.1 MAS-CVL-003 (Airside) |  |  | Visual Inspection | This Signed ITP |  |  |  | HP |  |  | Project Engineer Principal’s Representative
2.3 |  |  | Weather Conditions |  | Each Lot | Pavement marking must not proceed during wet weather or when the pavement surface is wet or when rain is likely or during high winds. |  |  |  |  | Cl 19.7 |  |  | Verify & Visual Inspection | This Signed ITP |  |  |  | IP |  |  | Project Engineer
2.4 |  |  | Application |  | Each Lot | The paint must be applied in two even coats to provide the required minimum total dry film thickness as specified by the manufacturer. |  |  |  |  | Cl 19.6.5 |  |  | Approval and Visual Inspection | This Signed ITP |  |  |  | HP* |  |  | Project Engineer
2.5 |  |  | Application Rate and Conformity of Application |  | Each Lot | Daily records of paint usage and area covered shall be maintained to ensure that the specified coverage is being obtained consistently. |  |  |  |  | Cl 19.6.6 |  |  | Daily Records | This Signed ITP |  |  |  | IP |  |  | Project Engineer
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-DP1-PM-ITP010
| Client: APAM (Melbourne Airport) | [8 empty] | Contract No: CP1002 | [10 empty] | Prepared By: Brad Carroll
| Project: MAPMP 2.0 – DP1 – Minor Asphalt Works | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 10/07/2023
| Construction Process: Linemarking | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 10/07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component: Airfield Pavement Markings
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. FULTON HOGAN SIGN OFF: Print Name: Position: Signature: Date: / /
Legend:
| HP |  |  | Hold Point | Work shall not proceed past the HP until released by the Superintendent | [6 empty] | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  |  | Witness Point | An inspection which must be witnessed by the Superintendent | [6 empty] | SCP |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  |  | Approval Point | Written or verbal approval given by the Superintendent
[7 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-DP1-PM-ITP010
Client: APAM (Melbourne Airport) | [8 empty] | Contract No: CP1002 | [10 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 – Minor Asphalt Works | [14 empty] | Reviewed By: Giuliano Follacchio | [10 empty] | Date: 10/07/2023
Construction Process: Linemarking | [14 empty] | Approved By: Jordan Nicolaou | [10 empty] | Date: 10/07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component: Airfield Pavement Markings
Notes: