## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP010 – Linemarking | itp |  |  |  |  | ITP010 – Linemarking
section | 1. Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy.
label | • Current revision to be obtained via Aconex
label | Reference Documents - Drawings and Aconex
label | Inspection/ Test Method - Visual inspection
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, WP, SWMS
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - Site and Office Inspection
label | HP*
label | Responsibility - Project Engineer Site Supervisor
checkpoint | 1.3 - Plant and Equipment
label | Frequency - Prior to placing works
label | Acceptance Criteria - Plant and equipment used in the works are appropriate to achieve specification requirements
label | Reference Documents - Cl 19.4
label | Inspection/ Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - Project Engineer
checkpoint | 1.4 - Setting out
label | Frequency - Prior to commencing works
label | Acceptance Criteria - The contractor shall carry out the setting out of the pavement Markings as shown on the drawings.
label | • Accuracy of survey set-out to be confirmed to be within +/- 25mm.
label | Reference Documents - Cl 19.6.4
label | Inspection/ Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
section | 2. Construction
checkpoint | 2.1 - Removal of Existing Line Marking
label | Frequency - Each Lot
label | Acceptance Criteria - Existing and temporary paint markings shall be removed prior to application of permanent markings, where indicated on drawings or no longer needed, by the use of high-pressure water blasting
label | Reference Documents - Cl 19.6.1
label | Inspection/ Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Surface preparation
label | Frequency - Each Lot
label | Acceptance Criteria - Immediately before application of paint, surfaces are to be dry and free from curing compound, dirt, grease, oil, laitance, or other foreign material that would reduce the bond between the paint and the pavement.
label | • The contractor shall verify in writing that the surface has been prepared in accordance to the manufacturers requirements. This shall be approved by the Principal’s Representative.
label | Reference Documents - Cl 19.6.2.1 MAS-CVL-003 (Airside)
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This Signed ITP
label | HP
label | Responsibility - Project Engineer Principal’s Representative
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Weather Conditions
label | Frequency - Each Lot
label | Acceptance Criteria - Pavement marking must not proceed during wet weather or when the pavement surface is wet or when rain is likely or during high winds.
label | Reference Documents - Cl 19.7
label | Inspection/ Test Method - Verify & Visual Inspection
label | Record of conformity - This Signed ITP
label | IP
label | Responsibility - Project Engineer
checkpoint | 2.4 - Application
label | Frequency - Each Lot
label | Acceptance Criteria - The paint must be applied in two even coats to provide the required minimum total dry film thickness as specified by the manufacturer.
label | Reference Documents - Cl 19.6.5
label | Inspection/ Test Method - Approval and Visual Inspection
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - Project Engineer
checkpoint | 2.5 - Application Rate and Conformity of Application
label | Frequency - Each Lot
label | Acceptance Criteria - Daily records of paint usage and area covered shall be maintained to ensure that the specified coverage is being obtained consistently.
label | Reference Documents - Cl 19.6.6
label | Inspection/ Test Method - Daily Records
label | Record of conformity - This Signed ITP
label | IP
label | Responsibility - Project Engineer
checkpoint | Final Inspection
label | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP