## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 561482-DOW-ITR-EL-0001 | [5 empty] | 561482-DOW-ITR-EL-0001
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0001
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 50mm 3c+e Circular
label | Source: Site MCC
label | Destination: Pump 2 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: R-E |  |  | Results - MΩ
textbox | Core Designation: W-E |  |  | Results - MΩ
textbox | Core Designation: B-E |  |  | Results - MΩ
textbox | Core Designation: R-W |  |  | Results - MΩ
textbox | Core Designation: R-B |  |  | Results - MΩ
textbox | Core Designation: W-B |  |  | Results - MΩ
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0002 | [5 empty] | 561482-DOW-ITR-EL-0002
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0002
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 50mm 3c+e Circular
label | Source: Site MCC
label | Destination: Pump 3 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: R-E |  |  | Results - MΩ
textbox | Core Designation: W-E |  |  | Results - MΩ
textbox | Core Designation: B-E |  |  | Results - MΩ
textbox | Core Designation: R-W |  |  | Results - MΩ
textbox | Core Designation: R-B |  |  | Results - MΩ
textbox | Core Designation: W-B |  |  | Results - MΩ
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0003 | [5 empty] | 561482-DOW-ITR-EL-0003
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0003
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 50mm 3c VSD Cable
label | Source: Pump 2 VSD
label | Destination: Pump 2
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: R-E |  |  | Results - MΩ
textbox | Core Designation: W-E |  |  | Results - MΩ
textbox | Core Designation: B-E |  |  | Results - MΩ
textbox | Core Designation: R-W |  |  | Results - MΩ
textbox | Core Designation: R-B |  |  | Results - MΩ
textbox | Core Designation: W-B |  |  | Results - MΩ
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0004 | [5 empty] | 561482-DOW-ITR-EL-0004
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0004
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 50mm 3c VSD Cable
label | Source: Pump 3 VSD
label | Destination: Pump 3
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: R-E |  |  | Results - MΩ
textbox | Core Designation: W-E |  |  | Results - MΩ
textbox | Core Designation: B-E |  |  | Results - MΩ
textbox | Core Designation: R-W |  |  | Results - MΩ
textbox | Core Designation: R-B |  |  | Results - MΩ
textbox | Core Designation: W-B |  |  | Results - MΩ
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0005 | [5 empty] | 561482-DOW-ITR-EL-0005
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0005
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 95mm -final details tbc
label | Source: Site MCC
label | Destination: Generator Connection box
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: R-E |  |  | Results - MΩ
textbox | Core Designation: W-E |  |  | Results - MΩ
textbox | Core Designation: B-E |  |  | Results - MΩ
textbox | Core Designation: R-W |  |  | Results - MΩ
textbox | Core Designation: R-B |  |  | Results - MΩ
textbox | Core Designation: W-B |  |  | Results - MΩ
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0006 | [5 empty] | 561482-DOW-ITR-EL-0006
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0006
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561483
label | Area: Pumps
label | Discipline: EICA
textbox | Reference Drawing:
label | System Reference: Pump 2
textbox | System Description:
textbox | Motor Size:
textbox | Motor Brand:
textbox | Motor Serial:
button | Motor Connection: | Δ,Υ
textbox | Tag Number:
label | PAU/ Skid Number: N/a
section | INSPECTION - Completion Verification
checkpoint-no-status | Equipment, sub-system or system to be function tested during pre-commissioning must be subject to safety measures including, but not necessarily limited to: SWMS, Notice of Energisation, erection of safety barriers with warning signs and an open communication channel between testing personnel. Energisation and site acceptance test procedures are to be conducted with subcontractor/ supplier representative(s) as required.
checkpoint | Cable test and inspection completed
checkpoint | Motor switchgear ITR completed
checkpoint | Punch list "A" items completed from cable test sheet
checkpoint | Hazardous area check sheets completed and accepted
section | INSPECTION - Equipment Specific Pre Commissioning
checkpoint-no-status | Ensure interlocks are healthy (force status/ link out). Apply control voltage to motor starter circuit. Verify control/ trip functions. Ensure motor is safe to start – close MCC breaker.
checkpoint | Prove electrical isolation
checkpoint | Verify operation of local control station
checkpoint | Rotating parts guarded
checkpoint | Confirm motor frame earth
checkpoint | Confirm motor alignment checks completed
checkpoint | Confirm motor is safely uncoupled
checkpoint | Record frame earth continuity
textbox | Ω
checkpoint | Confirm motor lubrication
checkpoint | Feeder protection settings match motor (record in Tests section below)
checkpoint | Emergency stop
checkpoint | Circuit earth fault
checkpoint | Motor oil temperature trip/ alarm
checkpoint | Motor winding temperature trip/ alarm
checkpoint | Local stop
checkpoint | Remote stop
checkpoint | Phase differential trip
checkpoint | Duty/ standby
checkpoint | Other:
textbox | (specify)
checkpoint | Verify motor rotating in correct direction
checkpoint | Verify motor local stop
checkpoint | Confirm run up time
checkpoint | Verify DCS/ remote stop
checkpoint | Confirm starting current (as required for larger motor KW)
checkpoint | Verify trips and interlocks as per above control circuit function tests
checkpoint | Ensure all temporary links/ forces are removed and isolations re-instated/ locked out
section | Tests
checkpoint-no-status | As required carry out no load run until winding temperatures stabilise and confirm vibration levels. Enter "N/A" for non-applicable fields.
checkpoint | Record Bearing Temperatures:
textbox | DE: |  |  | °C
textbox | NDE: |  |  | °C
checkpoint | Record Winding Temperatures:
textbox | W1: |  |  | °C
textbox | W2: |  |  | °C
textbox | W3: |  |  | °C
checkpoint | DE(X)
textbox | DE(X): |  |  | m/s2
checkpoint | DE(Y)
textbox | DE(Y): |  |  | m/s2
checkpoint | NDE (X)
textbox | NDE (X): |  |  | m/s2
checkpoint | NDE (Y)
textbox | NDE (Y): |  |  | m/s2
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0007 | [5 empty] | 561482-DOW-ITR-EL-0007
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-EL-0007
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561483
label | Area: Pumps
label | Discipline: EICA
textbox | Reference Drawing:
label | System Reference: Pump 2
textbox | System Description:
textbox | Motor Size:
textbox | Motor Brand:
textbox | Motor Serial:
button | Motor Connection: | Δ,Υ
textbox | Tag Number:
label | PAU/ Skid Number: N/a
section | INSPECTION - Completion Verification
checkpoint-no-status | Equipment, sub-system or system to be function tested during pre-commissioning must be subject to safety measures including, but not necessarily limited to: SWMS, Notice of Energisation, erection of safety barriers with warning signs and an open communication channel between testing personnel. Energisation and site acceptance test procedures are to be conducted with subcontractor/ supplier representative(s) as required.
checkpoint | Cable test and inspection completed
checkpoint | Motor switchgear ITR completed
checkpoint | Punch list "A" items completed from cable test sheet
checkpoint | Hazardous area check sheets completed and accepted
section | INSPECTION - Equipment Specific Pre Commissioning
checkpoint-no-status | Ensure interlocks are healthy (force status/ link out). Apply control voltage to motor starter circuit. Verify control/ trip functions. Ensure motor is safe to start – close MCC breaker.
checkpoint | Prove electrical isolation
checkpoint | Verify operation of local control station
checkpoint | Rotating parts guarded
checkpoint | Confirm motor frame earth
checkpoint | Confirm motor alignment checks completed
checkpoint | Confirm motor is safely uncoupled
checkpoint | Record frame earth continuity
textbox | Ω
checkpoint | Confirm motor lubrication
checkpoint | Feeder protection settings match motor (record in Tests section below)
checkpoint | Emergency stop
checkpoint | Circuit earth fault
checkpoint | Motor oil temperature trip/ alarm
checkpoint | Motor winding temperature trip/ alarm
checkpoint | Local stop
checkpoint | Remote stop
checkpoint | Phase differential trip
checkpoint | Duty/ standby
checkpoint | Other:
textbox | (specify)
checkpoint | Verify motor rotating in correct direction
checkpoint | Verify motor local stop
checkpoint | Confirm run up time
checkpoint | Verify DCS/ remote stop
checkpoint | Confirm starting current (as required for larger motor KW)
checkpoint | Verify trips and interlocks as per above control circuit function tests
checkpoint | Ensure all temporary links/ forces are removed and isolations re-instated/ locked out
section | Tests
checkpoint-no-status | As required carry out no load run until winding temperatures stabilise and confirm vibration levels. Enter "N/A" for non-applicable fields.
checkpoint | Record Bearing Temperatures:
textbox | DE: |  |  | °C
textbox | NDE: |  |  | °C
checkpoint | Record Winding Temperatures:
textbox | W1: |  |  | °C
textbox | W2: |  |  | °C
textbox | W3: |  |  | °C
checkpoint | DE(X)
textbox | DE(X): |  |  | m/s2
checkpoint | DE(Y)
textbox | DE(Y): |  |  | m/s2
checkpoint | NDE (X)
textbox | NDE (X): |  |  | m/s2
checkpoint | NDE (Y)
textbox | NDE (Y): |  |  | m/s2
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0008 | [5 empty] | 561482-DOW-ITR-EL-0008
section | Details
checkpoint-no-status | Details
textbox | Area (L0):
textbox | System (L2)
textbox | SubArea (L1)
textbox | Element (L3)
section | 1. GENERAL DATA
checkpoint | Details
textbox | Schematic Drawing
textbox | kW rating
textbox | Manufacturer
textbox | Model Number
textbox | Serial Number
textbox | Supply Voltage
textbox | Supply Label
textbox | Control Label
section | 2. TEST PROCEDURE - 2.1 Readiness for test
checkpoint | Drive power isolated
checkpoint | Control power connected
checkpoint | ITR completed and signed
checkpoint | Area signposted & controlled
checkpoint | All field IO Correct
checkpoint | 24V DC supply energised
checkpoint | Confirm potentiometer rating
checkpoint | Mechanical Installation as per Fig 1
section | 3. COMMISSIONING PROCEDURE - 3.1 Configuring the VFD
checkpoint | Verify DI1 is not active
checkpoint | Energize VFD
checkpoint | Set Date/Time/Language
checkpoint | Select Simply Start (1)
checkpoint | Motor Standard Freq
textbox | Hz:
checkpoint | Nominal Motor Power
textbox | kW:
checkpoint | Nominal Motor Voltage
textbox | Vac:
checkpoint | Nominal Motor Current
textbox | A:
checkpoint | Nominal Motor Freq
textbox | Hz:
checkpoint | Nominal Motor Speed
textbox | RPM:
checkpoint | 2/3 - Wire Control (2C)
checkpoint | Maximum Frequency
textbox | Hz
checkpoint | Motor Thermal Current
textbox | A
checkpoint | Clear Area of Personnel
checkpoint | Select Simply Start (1)
checkpoint | Select Autotuning
checkpoint | Set Apply Autotuning (Yes)
checkpoint | Select Simply Start (1)
checkpoint | Set Acceleration
textbox | s:
checkpoint | Set Deceleration
textbox | s:
checkpoint | Set Low Speed Freq
textbox | Hz:
checkpoint | Set High Speed Freq
textbox | Hz:
section | 3. COMMISSIONING PROCEDURE - 3.2 VFD Module Tests
checkpoint | Confirm VFD starts/stops
checkpoint | Simulate Overload Fault
checkpoint | Reset VFD
checkpoint | Confirm comms VFD-PLC
checkpoint | Inputs verified into PLC
checkpoint | Outputs operate as per design
section | 3. COMMISSIONING PROCEDURE - 3.3 Other Tests Conducted
checkpoint | Other Tests Conducted
textbox | Details:
section | 4. COMPLETION
checkpoint | Temporary supplies disconnected
checkpoint | Temporary bridges removed
checkpoint | All covers reinstated
checkpoint | All equipment left in fit state for energisation
checkpoint | As built drawings marked up
section | 5. REMARKS OR REMEDIAL ACTIONS REQUIRED
checkpoint | Remarks / Remedial Actions Required
textbox | Punch List ID
dropdown | Priority (A/B/C) | A,B,C
textbox | Description
date | Date Due
dropdown | Responsible Team (M/E/C/P) | M,E,C,P
checkpoint | Remedial Actions Completed
textbox | Commissioning Eng/Tech:
textbox | Commissioning Manager:
textbox | Client:
holdpoint | Add Signature
checklist | 561482-DOW-ITR-EL-0009 | [5 empty] | 561482-DOW-ITR-EL-0009
section | Details
checkpoint-no-status | Details
textbox | Area (L0):
textbox | System (L2)
textbox | SubArea (L1)
textbox | Element (L3)
section | 1. GENERAL DATA
checkpoint | Details
textbox | Schematic Drawing
textbox | kW rating
textbox | Manufacturer
textbox | Model Number
textbox | Serial Number
textbox | Supply Voltage
textbox | Supply Label
textbox | Control Label
section | 2. TEST PROCEDURE - 2.1 Readiness for test
checkpoint | Drive power isolated
checkpoint | Control power connected
checkpoint | ITR completed and signed
checkpoint | Area signposted & controlled
checkpoint | All field IO Correct
checkpoint | 24V DC supply energised
checkpoint | Confirm potentiometer rating
checkpoint | Mechanical Installation as per Fig 1
section | 3. COMMISSIONING PROCEDURE - 3.1 Configuring the VFD
checkpoint | Verify DI1 is not active
checkpoint | Energize VFD
checkpoint | Set Date/Time/Language
checkpoint | Select Simply Start (1)
checkpoint | Motor Standard Freq
textbox | Hz:
checkpoint | Nominal Motor Power
textbox | kW:
checkpoint | Nominal Motor Voltage
textbox | Vac:
checkpoint | Nominal Motor Current
textbox | A:
checkpoint | Nominal Motor Freq
textbox | Hz:
checkpoint | Nominal Motor Speed
textbox | RPM:
checkpoint | 2/3 - Wire Control (2C)
checkpoint | Maximum Frequency
textbox | Hz
checkpoint | Motor Thermal Current
textbox | A
checkpoint | Clear Area of Personnel
checkpoint | Select Simply Start (1)
checkpoint | Select Autotuning
checkpoint | Set Apply Autotuning (Yes)
checkpoint | Select Simply Start (1)
checkpoint | Set Acceleration
textbox | s:
checkpoint | Set Deceleration
textbox | s:
checkpoint | Set Low Speed Freq
textbox | Hz:
checkpoint | Set High Speed Freq
textbox | Hz:
section | 3. COMMISSIONING PROCEDURE - 3.2 VFD Module Tests
checkpoint | Confirm VFD starts/stops
checkpoint | Simulate Overload Fault
checkpoint | Reset VFD
checkpoint | Confirm comms VFD-PLC
checkpoint | Inputs verified into PLC
checkpoint | Outputs operate as per design
section | 3. COMMISSIONING PROCEDURE - 3.3 Other Tests Conducted
checkpoint | Other Tests Conducted
textbox | Details:
section | 4. COMPLETION
checkpoint | Temporary supplies disconnected
checkpoint | Temporary bridges removed
checkpoint | All covers reinstated
checkpoint | All equipment left in fit state for energisation
checkpoint | As built drawings marked up
section | 5. REMARKS OR REMEDIAL ACTIONS REQUIRED
checkpoint | Remarks / Remedial Actions Required
textbox | Punch List ID
dropdown | Priority (A/B/C) | A,B,C
textbox | Description
date | Date Due
dropdown | Responsible Team (M/E/C/P) | M,E,C,P
checkpoint | Remedial Actions Completed
textbox | Commissioning Eng/Tech:
textbox | Commissioning Manager:
textbox | Client:
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0001 | [5 empty] | 561482-DOW-ITR-IN-0001
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0001
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 4 pr CS
label | Source: MCC
label | Destination: Pump 2 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - MΩ
textbox | Core Designation: B1 |  |  | Results - MΩ
textbox | Core Designation: W2 |  |  | Results - MΩ
textbox | Core Designation: B2 |  |  | Results - MΩ
textbox | Core Designation: W3 |  |  | Results - MΩ
textbox | Core Designation: B3 |  |  | Results - MΩ
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0002 | [5 empty] | 561482-DOW-ITR-IN-0002
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0002
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 2 pr CS
label | Source: Site MCC
label | Destination: Pump 2 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0003 | [5 empty] | 561482-DOW-ITR-IN-0003
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0003
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 1 pr ES
label | Source: Pump 2 VSD
label | Destination: Pump 2
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0004 | [5 empty] | 561482-DOW-ITR-IN-0004
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0004
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 4 pr CS
label | Source: Site MCC
label | Destination: Pump 3 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0005 | [5 empty] | 561482-DOW-ITR-IN-0005
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0005
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 2 pr CS
label | Source: Site MCC
label | Destination: Pump 3 VSD
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0006 | [5 empty] | 561482-DOW-ITR-IN-0006
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0006
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 1 pr ES
label | Source: Pump 3 VSD
label | Destination: Pump 3
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0007 | [5 empty] | 561482-DOW-ITR-IN-0007
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0007
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 2 pr CS
label | Source: Site MCC
label | Destination: E-Stop Button 1
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0008 | [5 empty] | 561482-DOW-ITR-IN-0008
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0008
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 2 pr CS
label | Source: Site MCC
label | Destination: E-Stop Button 2
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature
checklist | 561482-DOW-ITR-IN-0009 | [5 empty] | 561482-DOW-ITR-IN-0009
section | GENERAL DETAILS
checkpoint-no-status | GENERAL DETAILS
label | ITR Number: 561482-DOW-ITR-IN-0009
label | Project Name: Pump Station Renewals – Silverstream Pumps
label | Contract/ Project No: 561482
label | Area: Silverstream Pumps
label | Sub-System: Pumps
textbox | Reference Drawing:
label | Discipline: EICA
label | Work Pack Number: N/A
label | Lot Number: N/A
label | Cable Number: TBC
label | Cable Specification: 1.5mm 2 pr ESCS
label | Source: Site MCC
label | Destination: Generator Connection Panel
label | Standards: AS/NZS 3000, AS/NSZ 3008.1.1:2017, AS/NZS 4836 and AS/NZS 3017
section | INSPECTION
checkpoint-no-status | Ensure circuits are de-energised before connecting test equipment. ELV and comms cables must not be insulation resistance tested.
checkpoint | Cable size and type correct
checkpoint | Cores terminated as per drawing & terminals tight
checkpoint | Cable numbered correctly and applied at both ends
checkpoint | Permanent core markers attached both ends
checkpoint | Cable supported and protected as per specification
checkpoint | Continuity of earth conductor/ screen satisfactory
checkpoint | Cable ties trimmed
checkpoint | Connection of shielding/ armour as per drawings
checkpoint | Cable ends made up satisfactorily
checkpoint | Protective earth complies with Table 3.2 AS/NZS 3017
section | Field Test
checkpoint | Field Test
textbox | Core Designation: W1 |  |  | Results - Ω
textbox | Core Designation: B1 |  |  | Results - Ω
textbox | Core Designation: W2 |  |  | Results - Ω
textbox | Core Designation: B2 |  |  | Results - Ω
textbox | Core Designation: W3 |  |  | Results - Ω
textbox | Core Designation: B3 |  |  | Results - Ω
textbox | Core Designation: W4
textbox | Core Designation: B4
textbox | Cable Size:
textbox | E Continuity: |  |  | Ω
textbox | Lead Resistance: |  |  | Ω
section | Completion
checkpoint | All cores reconnected and secure
checkpoint | Source connection tension
textbox | Nm:
checkpoint | Destination connection tension
textbox | Nm:
checkpoint | All connections visually and physically checked
checkpoint | All test leads and bridges removed
checkpoint | Drawings & schedules marked up to 'As Built' status
section | VERIFICATION
checkpoint | VERIFICATION
textbox | Deficiencies Identified:
bool | Rectified/ Closed-Out
bool | Punch Listed
section | TEST EQUIPMENT
checkpoint | TEST EQUIPMENT
textbox | Type of Meter
textbox | Make/ Model
textbox | Serial No.
date | Calibration: Date
date | Calibration: Due
section | ACCEPTANCE
checkpoint | I hereby confirm the work has been completed in accordance with contract specified/ referenced drawings, technical specifications, and standards.
holdpoint | Add Signature