## Sealing CE
sealing2020
Inspection and Test Plan - Chipsealing
| Site Location: |  |  |  |  | Sealing Date:
Contract:
ITP Prepared By: |  |  | ITP Approved By:
Date: |  |  | Date:
Activity Description | Verification Activity | Methods or Reference | Frequency | Acceptance Criteria | Hold / Witness Point | Records | Responsible Person | Completed?
Chipseal Surfacing
HOLD POINT: A mandatory verification point beyond which work cannot proceed without approval by the Client/Engineer. The work cannot proceed until one of these parties is able to verify acceptance and releases the Hold by means of approval. |  |  |  | Witness Point: An identified point in the process where the designated authority, typically the Contract Management team, Client / Engineer or Consultant or 3rd Party Inspector may review, witness, inspect method or process of work. The activities, however, may proceed provided the activity is documented and evidence gathered.
Design
Treatment Selection | Physical / Site video/photographic record | Asset Team - Base Preservation | Annually Pre-reseal | Documented approval from at time of Tender -Team/Client | Mandatory HOLD POINT - Client Approval | Approved Seal Designs | Sealing Contract Manager / Engineer
Chipseal Design | Peer review by Authorised Seal Design Approver | Chipsealing in NZ | One per design prior to commencing onsite | Design meets requirements of P17 | Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval | Peer Reviewed Seal Designs | Sealing Contract Manager / Engineer
Materials Testing
Size (Grades 2-5) & Shape (Grades 2-4) | Lab Test | NZTA M/6 | 1/500m3 | Size (ald mm) G2 9.5-12.0 G3 7.5-10.0 G4 5.5-8.0 G5 Report | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer
Shape AGD/ALD Ratio G2,3,4 = 2.25 max G2,3,4 = min 98% with 2+ broken faces
Cleanliness (Grades 2-6) | Lab Test | NZTA M/6 | 1/500m3 | Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 & G6 Report only | Witness Point
Compatibility (Multi Layered seals) | Comparison Of Chip ALD | Chipsealing in New Zealand NZTA (NZTA 2005) | 11.5 |  | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer
7.2
Bitumen Distributor | IANZ Lab E/2 Results | Code of Compliance | Annual | Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%) | Mandatory HOLD POINT - Client - Engineer Witness | RNZ E2 Certificate | Sealing Contract Manager / Engineer
Emulsion/PME Testing | Lab Testing | Manufacture Specification | Per Emulsion/Bitumen Production Batch | Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02 | Witness Point | IANZ Lab Reports | Road Science
Crushing Resistance | Lab Testing | NZS 4407:3.10 | 1/10000m3 | < 10% passing 2.36mm sieve at 230kN | Hold Point | IANZ Lab Reports | Sealing Contract Manager / Engineer
Weather Quality Index | Lab Testing | NZS 4407:3.11 | 1/10000m3 | AA or BA | Hold Point | IANZ Lab Reports
Surface Inspection
Surface Texture - Measurement | Sandcircle Measurement | NZTA T/3 | At time of Seal Inspection | Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Witness Point | Sandcircle Data | Sealing Contract Manager / Engineer
| ARRB Hawkeye or |  |  |  |  | Hawkeye Data
| NZTA HSD |  |  |  |  | High Speed Data
Pre Seal Survey | Downer Survey or MS Forms Pre Reseal Inspection | Downer Survey or MS Forms Pre Reseal Inspection | At time of Seal Inspection | Record & any noted issues / Client | Witness Point | Lucidity | Sealing Contract Manager / Engineer
Construction Compliance testing |  |  | 24 hours in advance of seal construction commencement | Confirmation from renewals manager all testing has met requirements | Hold Point | Email Confirmation | Sealing Contract Manager / Engineer
Seal Construction
Go/No Go Survey | Visual, Zeus, Iris | Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager | Witness Point | Lucidity | Supervisor / Foreperson / QA
Pavement Markings/RRPMs | Tagging of existing Pavement Markings, Removal of RRPMs | Pavement Marking Set Out Sheet, CBP | Prior to sealing on each site | All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required | Witness Point | None | Foreperson / QA
Road Furniture & Sumps protected | Visual Inspection | Crew Breifing Plan / Visual | Prior to sealing on each site | Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps. | Witness Point | None | Foreperson
Surface Condition/Temp | Physical / Visual Inspection | Visual / NZTA T/3 | Prior to sealing on each site | Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing | Witness Point | None | Foreperson / QA
Stockpiles | Visual Inspection | CBP | Each Stockpile | Correct Source, Grade and quantity. Uniquely Identified. | Witness Point | Sealing Data Docket | Foreperson
Spraying | Paper Start and Finish all runs | Spray Runs | All Runs | Mark out start / Finish | Witness Point |  | Sealing Contract Engineer / QA
Sealing | Longitudinal Joints out side of wheel tracks | Spray Runs | All Runs | Mark out lane lines by construction team | Witness Point |  | Sealing Contract Engineer / QA
Binder Application Rate | Tank Level dips prior to and after spray run | Dipstick | At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading | Quantities used to be within the desired tolerance of design Spray Rate | Mandatory HOLD POINT | Spray Sheets | QA
Chip Spread Rate | Visual | Crew Briefing Plan/Visual | On going whilst seal being constructed | Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan | Witness Point | Data Docket | QA/Foreperson
Removal of Surplus Chip | Physical / Visual | Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection | At conclusion of positive traffication within 48 hours | All sump and road furniture protection removed. Meets requirements of P/17 Table 2. | Witness Point | Post Seal Inspection | Sealing Contract Engineer / QA
Post Seal Construction
Post Seal Traffic Management | Physical / Visual | As per TMP | Full length and width of carriageway | Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours | Hold Point | Zeus or suitable recorded weather data | Sealing Contract Manager / Engineer
Post Seal Inspection | On Site Visual | Lucidity Post Seal Inpsection | After sealing is complete | Engineers requirements. Any defects identified, repairs programmed and costs estimated | Witness Point | Post Seal Inpsection | Sealing Contract Engineer / Manager / QA
Asbuilts and RAMM data | RAMM Update Sheet | RAMM Database | After sealing is complete | RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete. | Witness Point | As built information / RAMM Update Sheet | Sealing Contract Manager/ QA/QE
Quality Record Close Out: |  |  | Date:
(digital signature)
(name)

## DATA
Two Coat Seal Aggregate Compatibility
Upper Limit |  | Lower Limit
x | y | x | y
0 | -0.44 | 0 | -1.42
1 | 0.27 | 1 | -0.84
2 | 0.98 | 2 | -0.26
3 | 1.69 | 3 | 0.32
4 | 2.4 | 4 | 0.9
5 | 3.11 | 5 | 1.48
6 | 3.82 | 6 | 2.06
7 | 4.53 | 7 | 2.64
8 | 5.24 | 8 | 3.22
9 | 5.95 | 9 | 3.8
10 | 6.66 | 10 | 4.38
11 | 7.37 | 11 | 4.96
12 | 8.08 | 12 | 5.54
13 | 8.79 | 13 | 6.12
14 | 9.5 | 14 | 6.7
15 | 10.21 | 15 | 7.28
16 | 10.92 | 16 | 7.86
Compatibility Point
| x | y
| 11.5 | 7.2