## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
Management documents, as-builts, and Completion | Setting Out/Survey Control Report | Survey control report
Survey control inspection (email)
| As built information | NTE with asbuilts in PDF and DWG, outputs as to be as per HDCECOP
| Methodology Statement/s | NTE
| Environmental Management Plan | NTE
| Health and Safety Management Plan | NTE
| Practical Completion | NTE
F300 Pipework (Gravity Pipelines) | Qualifications of Personnel | NTE
| Materials | Material report bedding aggregate
Material report hardfill
| Bedding, Laying, Jointing and Manholes | Pipe Jointing | photos
|  | Joints at pipes and manholes | photos
|  | Manhole Benching | photos
F5000 Rock Riprap | Material Acceptance | Test certificate
| Batter Slope (subgrade) | Scala Penetrometer
| Geotextile Placement | Correctly placed and overlapped
| instalation/completion of Rock Riprap | photos
F500 Earthworks for Road Construction | Subgrade verification | CBR verification testing, every 10m per lane
photos of subgrade, clear of organics or construction debris
| hardfill material acceptance | Material testing as per NZS4402
| hardfill compaction | NDM report av 98% min 95% MDD
F600 Pavement Construction | materials | subbase aggregate | material report , grading and MDD
|  | basecourse aggregate | material report , grading and MDD
| Subgrade verification | level and alignment | String sheet
|  | Proof roll | Photos and engineers inspection
|  | CBR verification testing, every 10m per lane, alternating between wheel paths | CBR>8% or undercut as per table in dwg sheet C007
| Sub-base layer construction | Stabilising application rates | Mat test, +/- 0.5kg/m2 target cement value
|  | Compaction | Nuclear densometer teting 92% min 95% average
|  | level and alignment (post stabilisation) | Horizontal: -20mm / +100mm Vertical: -20mm / +5mm (String sheet)
| Basecourse layer construction | Compaction | Nuclear densometer density testing
Clegg impact test CBR >8%
Basecourse verification testing - Benkelman beam deflections
|  | level and alignment | TNZ B2 5.1b table | #VALUE!
|  |  | 3m straight edge checks | #VALUE!
F700 Kerb, Footpath & Landscape Construction | materials | subbase aggregate | material report , grading and MDD
|  | Swale riprap | material report , grading and MDD
| subbase verification (for swales and kerbs) | Compaction | Clegg impact test
|  | Surface shape | survey check (witness)
| Kerbing | set-out level and alignment | survey check (witness)
pre-pour inspection
| topsoiling | suitability of imported topsoil | stockpile inspection
|  | topsoil finish | photos, inspection
F800 Surfacing Construction | materials | seal design, including application rate and chip size.
chip lab report Reference NZTA M/6: 2011
| Pre-seal inspection | swept road, pre-seal inspection
| post seal | seal report
photos
F1500 Road Safety Barrier and road furniture | Position and alignment (set-out) | Sight Rail
Guard Rail (witness)
pavement marking
| instalation photos | Sight Rail
Guard Rail (witness)
pavement marking
F2000 Structural Steelwork | material approvals | Steel certificates, including for fixing, bolts washers etc. to be in accordance with NZS3404
| installation | Inspection report of materials prior to installation
F4200 Geotechnical Steel Soldier Pile and Ground Anchor | materials | UC collumns | Steel certificates, manufacturer reports
|  | Anchors | Steel certificates, manufacturer reports
| Suitability | UC pile drilling | confirmation of depth on site by engineer
|  | Anchor drilling | during drilling of first 2 anchors
|  | Pull out test | Geotechnical engineer inspection of drilling
Geotechnical engineer inspection pull out test
Pull out test report
| Construction | Steel erection | site visit report sheet with photos
|  | Fastening and finishing | site visit report sheet with photos
| Back-fill | Materials | Lab-report or confirmation of previously approved material
|  | Compaction | NDM
| Precast Panels | Shop Drawings | Shop drawing approval correspondance
|  | Precast panel inspection | Inspection report
|  | Installation inspection | Correspondance
| Waler Beams | Shop drawing assessment | Shop drawing approval correspondance
|  | Pre-galvansing assessment | Correspondance
|  | Weld assessment | Inspection report
|  | Corrosion Protection assessment | Inspection report
F4300 Geotechnical Earthfill and Shotcrete Facing | Materials | steel (mesh) | Steel certificates, manufacturer reports , In accordance with NZS 3404
|  | steel (anchors) | Steel certificates, manufacturer reports , In accordance with NZS 3404
|  | concrete (shotcrete) | mix approval
| Foundation Inspection | site visit report sheet with photos

## Resources
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name