## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Management documents, as-builts, and Completion
section | Setting Out/Survey Control Report
checkpoint | Survey control report
checkpoint | Survey control inspection (email)
holdpoint | Client Signoff
section | As built information
checkpoint | NTE with asbuilts in PDF and DWG, outputs as to be as per HDCECOP
holdpoint | Client Signoff
section | Methodology Statement/s
checkpoint | NTE
holdpoint | Client Signoff
section | Environmental Management Plan
checkpoint | NTE
holdpoint | Client Signoff
section | Health and Safety Management Plan
checkpoint | NTE
holdpoint | Client Signoff
section | Practical Completion
checkpoint | NTE
holdpoint | Client Signoff
checklist | F300 Pipework (Gravity Pipelines)
section | Qualifications of Personnel
checkpoint | NTE
holdpoint | Client Signoff
section | Materials
checkpoint | Material report bedding aggregate
holdpoint | Client Signoff
checkpoint | Material report hardfill
holdpoint | Client Signoff
section | Bedding, Laying, Jointing and Manholes
checkpoint | Pipe Jointing
label | Photos
checkpoint | Joints at pipes and manholes
label | Photos
checkpoint | Manhole Benching
label | Photos
checklist | F5000 Rock Riprap
section | Material Acceptance
checkpoint | Test certificate
holdpoint | Client Signoff
section | Batter Slope (subgrade)
checkpoint | Scala Penetrometer
holdpoint | Client Signoff
section | Geotextile Placement
checkpoint | Correctly placed and overlapped
section | Installation/completion of Rock Riprap
checkpoint | Photos
holdpoint | Client Signoff
checklist | F500 Earthworks for Road Construction
section | Subgrade verification
checkpoint | CBR verification testing, every 10m per lane
holdpoint | Client Signoff
checkpoint | Photos of subgrade, clear of organics or construction debris
section | Hardfill material acceptance
checkpoint | Material testing as per NZS4402
holdpoint | Client Signoff
section | Hardfill compaction
checkpoint | NDM report av 98% min 95% MDD
holdpoint | Client Signoff
checklist | F600 Pavement Construction
section | Materials
checkpoint | Subbase aggregate
label | Material report, grading and MDD
holdpoint | Client Signoff
checkpoint | Basecourse aggregate
label | Material report, grading and MDD
holdpoint | Client Signoff
section | Subgrade verification
checkpoint | Level and alignment
label | String sheet
holdpoint | Client Signoff
checkpoint | Proof roll
label | Photos and engineers inspection
holdpoint | Client Signoff
checkpoint | CBR verification testing, every 10m per lane, alternating between wheel paths
label | CBR>8% or undercut as per table in dwg sheet C007
holdpoint | Client Signoff
section | Sub-base layer construction
checkpoint | Stabilising application rates
label | Mat test, +/- 0.5kg/m2 target cement value
holdpoint | Client Signoff
checkpoint | Compaction
label | Nuclear densometer teting 92% min 95% average
holdpoint | Client Signoff
checkpoint | Level and alignment (post stabilisation)
label | Horizontal: -20mm / +100mm
label | Vertical: -20mm / +5mm (String sheet)
holdpoint | Client Signoff
section | Basecourse layer construction - Compaction
checkpoint | Nuclear densometer density testing
holdpoint | Client Signoff
checkpoint | Clegg impact test CBR >8%
holdpoint | Client Signoff
checkpoint | Basecourse verification testing - Benkelman beam deflections
holdpoint | Client Signoff
section | Basecourse layer construction - Level and alignment
checkpoint | TNZ B2 5.1b table
checkpoint | 3m straight edge checks
holdpoint | Client Signoff
checklist | F700 Kerb, Footpath & Landscape Construction
section | Materials
checkpoint | Subbase aggregate
label | Material report, grading and MDD
holdpoint | Client Signoff
checkpoint | Swale riprap
label | Material report, grading and MDD
holdpoint | Client Signoff
section | Subbase verification (for swales and kerbs)
checkpoint | Compaction
label | Clegg impact test
checkpoint | Surface shape
label | Survey check (witness)
section | Kerbing - Set-out level and alignment
checkpoint | Survey check (witness)
holdpoint | Client Signoff
checkpoint | Pre-pour inspection
holdpoint | Client Signoff
section | Topsoiling
checkpoint | Suitability of imported topsoil
label | Stockpile inspection
holdpoint | Client Signoff
checkpoint | Topsoil finish
label | Photos, inspection
holdpoint | Client Signoff
checklist | F800 Surfacing Construction
section | Materials
checkpoint | Seal design, including application rate and chip size.
holdpoint | Client Signoff
checkpoint | Chip lab report Reference NZTA M/6: 2011
holdpoint | Client Signoff
section | Pre-seal inspection
checkpoint | Swept road, pre-seal inspection
holdpoint | Client Signoff
section | Post seal
checkpoint | Seal report
checkpoint | Photos
checklist | F1500 Road Safety Barrier and road furniture
section | Position and alignment (set-out)
checkpoint | Sight Rail
holdpoint | Client Signoff
checkpoint | Guard Rail (witness)
holdpoint | Client Signoff
checkpoint | Pavement marking
holdpoint | Client Signoff
section | Installation photos
checkpoint | Sight Rail
checkpoint | Guard Rail (witness)
checkpoint | Pavement marking
checklist | F2000 Structural Steelwork
section | Material approvals
checkpoint | Steel certificates, including for fixing, bolts washers etc. to be in accordance with NZS3404
holdpoint | Client Signoff
section | Installation
checkpoint | Inspection report of materials prior to installation
holdpoint | Client Signoff
checklist | F4200 Geotechnical Steel Soldier Pile and Ground Anchor
section | Materials
checkpoint | UC columns
label | Steel certificates, manufacturer reports
holdpoint | Client Signoff
checkpoint | Anchors
label | Steel certificates, manufacturer reports
holdpoint | Client Signoff
section | Suitability - UC pile drilling
checkpoint | Confirmation of depth on site by engineer
holdpoint | Client Signoff
section | Suitability - Anchor drilling
checkpoint | During drilling of first 2 anchors
holdpoint | Client Signoff
section | Suitability - Pull out test
checkpoint | Geotechnical engineer inspection of drilling
holdpoint | Client Signoff
checkpoint | Geotechnical engineer inspection pull out test
holdpoint | Client Signoff
checkpoint | Pull out test report
holdpoint | Client Signoff
section | Construction
checkpoint | Steel erection
label | Site visit report sheet with photos
holdpoint | Client Signoff
checkpoint | Fastening and finishing
label | Site visit report sheet with photos
holdpoint | Client Signoff
section | Back-fill
checkpoint | Materials
label | Lab-report or confirmation of previously approved material
holdpoint | Client Signoff
checkpoint | Compaction
label | NDM
section | Precast Panels
checkpoint | Shop Drawings
label | Shop drawing approval correspondance
holdpoint | Client Signoff
checkpoint | Precast panel inspection
label | Inspection report
holdpoint | Client Signoff
checkpoint | Installation inspection
label | Correspondance
section | Waler Beams
checkpoint | Shop drawing assessment
label | Shop drawing approval correspondance
holdpoint | Client Signoff
checkpoint | Pre-galvansing assessment
label | Correspondance
holdpoint | Client Signoff
checkpoint | Weld assessment
label | Inspection report
holdpoint | Client Signoff
checkpoint | Corrosion Protection assessment
label | Inspection report
checklist | F4300 Geotechnical Earthfill and Shotcrete Facing
section | Materials
checkpoint | Steel (mesh)
label | Steel certificates, manufacturer reports, In accordance with NZS 3404
holdpoint | Client Signoff
checkpoint | Steel (anchors)
label | Steel certificates, manufacturer reports, In accordance with NZS 3404
holdpoint | Client Signoff
checkpoint | Concrete (shotcrete)
label | Mix approval
holdpoint | Client Signoff
section | Foundation Inspection
checkpoint | Site visit report sheet with photos
holdpoint | Client Signoff