## Sheet1
type | name | values
checklist | Kina Processing Area
section | Deliveries
checkpoint | Notification of Delivery Inbound to Site.
checkpoint | Site access defined and
checkpoint | Material is not damaged upon delivery.
checkpoint | Delivery con-note match the material picking slips.
section | Material Storage
checkpoint | Laydown area is clear and unobstructed.
checkpoint | Panel is as per Specifications (Colour, Core and Profile correct).
checkpoint | Material is as per Specifications (Mill Finish / Powdercoated).
checkpoint | Material has been stored in an area that is clear and safe from other workers.
checkpoint | Material has been stored inside.
checkpoint | Material has been stored outside.
section | Pre-Construction
checkpoint | Area is clean and unobstructed from debris and other works material.
checkpoint | Demolition has been completed to enable Bondor scope to proceed.
checkpoint | Set out of room is as per drawings and has been completed.
checkpoint | Aluminium extrusion has been wiped down with a clean cloth and cleaner.
checkpoint | DRI Extrusions supplied are as per drawings.
checkpoint | Panel inspection has been carried out and panel appears to have no defects.
section | Base Build
checkpoint | Area is clean and unobstructed from debris and other works material.
checkpoint | Nibs are formed level, straight and to the correct height.
checkpoint | Packers and aluminuim flast installed as per drawings.
checkpoint | DRI Extrusions have been fixed down to the correct spacing.
checkpoint | Base channel has been installed to the correct width.
signoff | Bondor Project Manager sign off before proceeding.
section | Installation (Panel Build)
checkpoint | Base Channel have been brushed down to clear concrete dust debris.
checkpoint | Insulated Panel has been installed plumb and level.
checkpoint | Corners have been cut at 45 degrees and are tight and true.
checkpoint | Ceilings have been installed flat and level.
checkpoint | Ceilings have had packers installed between structure and panel.
checkpoint | Ceilings that are over span have had mid span supports fitted correctly.
checkpoint | Mid span support fixings have been installed correctly.
checkpoint | Internal angles have been installed correctly
checkpoint | External angles have been installed correctly
checkpoint | Doors have been cut out ready for door installation.
checkpoint | Door tracks and surrounds have been installed in readingness for Doors to be hung.
checkpoint | Windows have been cut out ready for installation.
signoff | Bondor Project Manager sign off before proceeding.
section | Penetrations
checkpoint | Location and size marked out by others.
checkpoint | Aluminium and flashing trims installed with neat joins.
checkpoint | Patched completed
section | Completion
checkpoint | Panel surface trade cleaned.
checkpoint | Panel joins have been points sealed.
checkpoint | DRI Extrusions / Panel junctions have been sealed correctly with no visable gaps.
checkpoint | Rivets done by us have been point sealed
checkpoint | Rubbish removed or placed in bin provided.
checkpoint | Area clean and tidy.
signoff | Client to sign off as accepting of completion of works and quality assurance.