## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | a20e68e3-7eb9-4a4b-9030-61b18ae528c5 |  | checklist | Cesspit |  |  |  |  | Yes | Cesspit Checklist | 11a147f9-0e56-455d-9faa-0452afbc3197
checkpoint-status | 494bdc57-4e33-46e9-a62c-0e87c23ca4e0 |  | checkpoint | Is the sump set on correct LL
checkpoint-status | 526d8dde-c8a8-46d2-90f6-d412dd03cab6 |  | checkpoint | Installation Process
checkpoint-status | a7212117-10b5-4a9b-a978-6d427e879dfc |  | checkpoint | Council Inspection and As-Built
checklist-flat | 53f98e2f-9a9c-4a0a-93d7-130be8e81650 |  | checklist | Pressure Testing Checklist |  |  |  |  | Yes | Pressure Testing Checklist | 1fca0c44-23b5-4bcc-b19e-1487a6cd5a28
checkpoint-status | e2cf2b45-5a27-4d28-a3ae-a6ae00f331bd |  | checkpoint | Pump Up To 1500kpa Minimum
checkpoint-status | a643e13c-35e2-40d2-941f-d87759229079 |  | checkpoint | Take Photos Of Testing
checklist-flat | 66384c00-55b3-4125-913c-2cf04d73cbfd |  | checklist | Manhole Checklist |  |  |  |  | Yes | Manhole Checklist | 367b13d5-30d2-4e16-bf40-9af7af99c3d9
checkpoint-status | db8a8b1f-9530-4038-8db3-82d7db71fcb8 |  | checkpoint | Check Existing RL's Of Manhole
checkpoint-status | 9410a10c-db1b-4793-806b-42cc0c3e8049 |  | checkpoint | Check Invert And Grade
checkpoint-status | 5feb693d-39dc-473e-9ee6-3f8e7a5ecafd |  | checkpoint | Seal Pipe Into Manhole
checkpoint-status | 9bd64721-1563-40ab-b339-6463dc1fdfbe |  | checkpoint | Install Manhole Lid At Finished Height
checkpoint-status | 5927935e-ab35-461c-b726-ebacdad0a67b |  | checkpoint | Benching To Be Complete
checklist-flat | 23b0fa05-c39f-475f-b75e-7c5c04cb973c |  | checklist | Hose Taps Checklist |  |  |  |  | Yes | Hose Taps Checklist | 3b43dfe4-c39a-4ba0-926e-28ff413dce76
checkpoint-status | f14daf99-184e-43cd-8e71-e0d1a632dbaa |  | checkpoint | Position Correct
checkpoint-status | dc3e0edd-d88a-47e2-9009-e37d58bbef4e |  | checkpoint | Pipes coming out of wall straight
checkpoint-status | 6b6895b6-222c-4b6a-96fd-1efdd91f2704 |  | checkpoint | Fixings nogs in place
checkpoint-status | b851ba2d-3c5c-4d6a-bb06-2ebf66e2a4bb |  | checkpoint | Prevention against waterhammer
checkpoint-status | c042ab4a-abdc-41e6-a9c1-10c5de84226a |  | checkpoint | All joints watertight and tested
checkpoint-status | 04ee3717-6b75-4837-bbe5-146f24e77822 |  | checkpoint | Has fire rating been completed?
checklist-flat | 6447f5a2-288f-4bcd-ab2b-4bb487153fd0 |  | checklist | Stacks + Vents Checklist |  |  |  |  | Yes | Stacks + Vents Checklist | 43c479f6-f7da-4a54-adb1-54da612d913f
checkpoint-status | 6023af4b-179b-4615-9ba7-3722f0f10582 |  | checkpoint | Inspection Junction Installed For Testing
checkpoint-status | de66bd31-586a-48b7-b976-cb5040296207 |  | checkpoint | Pipe Labels Installed
checkpoint-status | b3dd689e-200d-45e4-8cb0-bb187459886c |  | checkpoint | Mid Level Supports
checkpoint-status | 243817d1-77a0-4ae9-8560-05e81388adfe |  | checkpoint | Write On Test Cap Date Of Test
checklist-flat | f20ae623-e0a3-422e-b067-7afde98532d1 |  | checklist | Underslung PVC |  |  |  |  | Yes | Underslung PVC | 4e1df58a-82ab-4fb7-955f-d182448975f6
checkpoint-status | 13dd0cd2-e2bc-44b6-b06a-9f3822827cda |  | checkpoint | Pvc installed To Correct Gradient
checkpoint-status | ec9764e6-5873-432a-b7b9-3f91ac66235e |  | checkpoint | Flood Tested (Add Photos Of Test)
checkpoint-status | b7b2482c-17e5-4c49-9a8d-bde79eaf2bb0 |  | checkpoint | Take Photos Of Testing
checklist-flat | 2d95c44e-551c-40b3-b0e6-63a81a754793 |  | checklist | Toilet Checklist |  |  |  |  | Yes | Toilet Checklist | 4e5c2ca8-6c21-478d-9c60-e7e87b457e9d
checkpoint-status | 61aa7749-7510-43ae-9537-8292083fde9b |  | checkpoint | Wingback Installed To Correct Height
checkpoint-status | f7fdd1fa-b129-4759-8fb5-ba3160a28d9f |  | checkpoint | Waste Installed Correct Distance From Wall
checklist-flat | bf5d6b03-eda1-43b3-933b-3f58554d4afa |  | checklist | Hand Basin |  |  |  |  | Yes | Hand Basin | 5d6b7a60-962c-4f47-8da8-802b96d4e97b
checkpoint-status | cb1245d2-d6e8-4fa9-b6de-019c91132448 |  | checkpoint | Nogs for all Fixing
checkpoint-status | afe15888-5c33-493c-9a55-be00632c78ce |  | checkpoint | Check plan to confirm Heights
checkpoint-status | b110901c-80f9-498b-970d-1d9d1679c3e3 |  | checkpoint | Check Water Hammering, Silicone Pipes
checkpoint-status | 2904fa2a-a10a-4229-8dd1-78ff75dbf0e3 |  | checkpoint | Acoustic Lagging
checkpoint-status | ee0f64f7-4008-4eee-9892-4aff9a83ba84 |  | checkpoint | Test All Pipework To 1500 Kpa
checklist-flat | 9f1c590e-eb0f-4246-a3d4-a19cbc3ea952 |  | checklist | Kitchen Checklist |  |  |  |  | Yes | Kitchen Checklist | 6d003014-da52-4b2d-92bc-685534a0b33e
checkpoint-status | b5c29ac7-976a-4c88-bbe8-57d17ac386b4 |  | checkpoint | Hot And Cold Water Installed Correct Height
checkpoint-status | 2799255e-adbc-4052-963d-cf3b68cbdfdd |  | checkpoint | Waste Installed Correct Height
checkpoint-status | 1afb469b-b6d9-4506-9980-7224360ebb2f |  | checkpoint | Check Hot And Cold For Crossover
checkpoint-status | cdd92ac6-8ad9-4134-98b3-37d3d1595e4a |  | checkpoint | Tested To 1500Kpa
checklist-flat | 1f583fec-697d-4b31-be09-586daf6e97a6 |  | checklist | Acoustic Lagging Checklist |  |  |  |  | Yes | Acoustic Lagging Checklist | 7a815c34-d19a-4c50-8112-beac87f7a8c8
checkpoint-status | b7f30c84-cfeb-4f61-856f-9552a88ff26c |  | checkpoint | Relevant Pipework Lagged
checkpoint-status | 0dfa6d25-f6f4-4261-a16c-06dce13507d2 |  | checkpoint | Lagging Tape Around Joints
checkpoint-status | f769ffb8-e65a-466e-9ae7-cd9fb9a464e5 |  | checkpoint | Blue Strapping And Buckles Every 1 Metre
checkpoint-status | a5eef90f-2ea7-42a3-8870-58026426283e |  | checkpoint | Pipe Labels After Lagging
checklist-flat | ebcdff9a-5b24-4137-b02f-43da965cf8b2 |  | checklist | Photos |  |  |  |  | Yes | Photos | 90bd34f5-aca3-417f-b9f2-acffc71d50de
checkpoint-status | eaf46dab-c322-40f6-9c55-8386eb9c8090 |  | checkpoint | Attach Photos
checklist-flat | 7438db03-162a-417f-aecf-281da8a727f2 |  | checklist | Shower Tray Checklist |  |  |  |  | Yes | Shower Tray Checklist | 92260d3e-ad70-4732-b280-3e3fc29751a9
checkpoint-status | 3491a82e-394d-41ff-89a2-a3e24b068f7b |  | checkpoint | Shower Tray Installed
checkpoint-status | fbc47a97-6eb1-4307-bfcf-c6d00b30b34d |  | checkpoint | Flood Test Shower Tray
checklist-flat | a6e96eff-a5bb-4572-b8d1-465776ad3ddb |  | checklist | Laundry |  |  |  |  | Yes | Laundry | 99c792d9-975a-4fc2-99cd-d30b388d9b35
checkpoint-status | 061fea6a-e6d6-44c8-99ae-6b444ecea66f |  | checkpoint | Nogs for all Fixing
checkpoint-status | 7040cc71-a338-4398-9dce-6fc6045b620d |  | checkpoint | Check plan to confirm Heights
checkpoint-status | 33fe3585-b939-42e4-8245-1d14c259e793 |  | checkpoint | Check Water Hammering, Silicone Pipes
checkpoint-status | 7154e476-4790-432e-b99a-51b352647b27 |  | checkpoint | Acoustic Lagging
checkpoint-status | ca124b97-f294-4485-9264-46d0b350c4c3 |  | checkpoint | Test All Pipework To 1500 Kpa
checklist-flat | b1a2e8fb-411a-40a6-b8f9-001b93339226 |  | checklist | Hot Water Cylinder Checklist |  |  |  |  | Yes | Hot Water Cylinder Checklist | 9f3a7537-2e02-4f2f-bcd1-c82756fb43d2
checkpoint-status | cdbb5f93-ee70-4e47-84a7-1e0452769a5d |  | checkpoint | Cold Feed With Isolator
checkpoint-status | 6e5b9cd0-e842-42cd-998f-bb6e2b3af87a |  | checkpoint | Hot And Cold Installed
checkpoint-status | 9115cd7f-45b5-4bec-8b9d-c011f2b06e1f |  | checkpoint | Tundish In
checkpoint-status | 5f330947-cda0-4752-aa38-169a41962d93 |  | checkpoint | Has Nogs Been Installed For Seismics
checkpoint-status | f7dd63fa-4c2d-4c43-8286-93b7cd46906c |  | checkpoint | Correct Positioning & Heights
checklist-flat | 89ec616a-8f8a-42a2-b742-cf0ef11c025a |  | checklist | First Fix Checklist |  |  |  |  | Yes | First Fix Checklist | a739616b-b154-4706-a0bc-b02299772b08
checkpoint-status | 704e4fc3-a6ca-497c-8cb4-bea6d9f692d6 |  | checkpoint | Nogging For All Fixtures
checkpoint-status | 78a90238-4916-4d9a-a1d7-8a3695bed8af |  | checkpoint | Check Plan To Confirm Heights And Centres
checkpoint-status | a9f779a4-0319-426a-a752-cdff50cb2e5c |  | checkpoint | Check Water Hammer, Silicone Pipes
checkpoint-status | 768847af-cb9b-49be-935e-8d61c32fb7b8 |  | checkpoint | Acoustic Lagging
checkpoint-status | e3d2e86d-9c14-462a-a295-c7a0f2fc84fa |  | checkpoint | Test All Pipework To 1500Kpa
checklist-flat | e7757b00-750f-443f-8aa4-c358e513517e |  | checklist | PipeWork Checklist |  |  |  |  | Yes | PipeWork Checklist | a89ad8f9-ad64-4276-8ba3-548a4d7c6e09
checkpoint-status | b5a79840-071d-4f21-8fcf-ea47405b5f84 |  | checkpoint | Bedding Put In At Correct Height
checkpoint-status | bd4f2b3b-d14b-4165-9637-1299adfefe4b |  | checkpoint | Grade Right
checkpoint-status | 180af3e8-42ba-456b-a827-664841ad77d5 |  | checkpoint | Check Pipes Is All The Way In
checkpoint-status | 96d6cfdb-4b5f-4cb2-853d-373220029359 |  | checkpoint | Check Pipe Connections (No Gaps)
checkpoint-status | 6b348886-63dd-4913-8f60-3f5d50835dd3 |  | checkpoint | Compact Around Pipe
checklist-flat | dcca4e90-3819-48a4-a2fa-e444ffdd0555 |  | checklist | Downpipes + Decks Checklist |  |  |  |  | Yes | Downpipes + Decks Checklist | abed844c-f8a3-4aff-867b-54aec3f9e1d5
checkpoint-status | 6c1cf451-5ef1-4ec2-bf6d-755c5d4cc5b3 |  | checkpoint | Flanges Installed
checkpoint-status | 6da22664-2c27-4088-8e63-a3ac993299b4 |  | checkpoint | Domes Installed
checkpoint-status | 8cbdd723-8cc6-4e00-9026-e80d54c8a2bc |  | checkpoint | All Through Installed
checklist-flat | 8f0d1b66-38cf-4b7a-ae22-5b5033be8c08 |  | checklist | Shower Checklist |  |  |  |  | Yes | Shower Checklist | bcf5d849-a885-486b-b063-32c89124e0cf
checkpoint-status | 96778cee-b87e-4858-b328-8722f78e72e5 |  | checkpoint | Nogs for all Fixing
checkpoint-status | 45e3ef71-3617-4159-ad0a-d48e9582bb9f |  | checkpoint | Check plan to confirm Heights
checkpoint-status | 976c8665-7b32-4db0-a4bf-f9715697e3ff |  | checkpoint | Check Water Hammering, Silicone Pipes
checkpoint-status | 1c2e8129-ebc4-4d51-9dcd-813204832d2a |  | checkpoint | Acoustic Lagging
checkpoint-status | cfe55684-2f5c-48e7-b079-de046b337d19 |  | checkpoint | Test All Pipework To 1500 Kpa
checkpoint-status | 3430e833-1a2b-4604-8298-c8e05463b7d4 |  | checkpoint | Mixer Sticking Out The Correct Length
checkpoint-status | 3e58b120-bd8e-4da8-92d4-8095d8040d93 |  | checkpoint | Mixer Wingback Above 1700 To Prevent Backflow
checklist-flat | 565e0245-7dcf-4a21-8fd4-9e73f4766db3 |  | checklist | Stormwater Checklist |  |  |  |  | Yes | Stormwater Checklist | d28b11cf-da04-43be-9481-cd06bc8ef5f3
checkpoint-status | 5543ee2b-b498-4d36-9fed-f0a8dbbe348a |  | checkpoint | Relevant Pipework Lagged
checkpoint-status | 048533e2-f6e0-4eb6-85e6-b8f9557edc38 |  | checkpoint | Lagging Tape Around Joints
checkpoint-status | 0ecdf736-56f3-4a1a-87a3-a4c99b541581 |  | checkpoint | Blue Strapping And Buckles Every 1 Metre
checkpoint-status | a3868371-aea9-4332-92b8-58482a52b2b9 |  | checkpoint | Pipe Labels After Lagging
checkpoint-status | 82c5fdd2-4397-46a9-9372-fd12b636ce8b |  | checkpoint | Pipe Tested For Leaks
checklist-flat | ff457fef-aa5c-4574-85fa-4632397ce4c4 |  | checklist | ORG Checklist |  |  |  |  | Yes | ORG Checklist | ea302075-a059-410a-97bc-2812519f23d5
checkpoint-status | cdd72e15-bedb-4394-a879-c562d61085f8 |  | checkpoint | Installed in correct location
checkpoint-status | 148fe040-a82f-4e8d-a3cb-11e36c9a88d8 |  | checkpoint | Riser level
checkpoint-status | 9dd90fbe-1286-4532-9184-00ca982b6e03 |  | checkpoint | Is the ORG fixture connection done
checkpoint-status | 1fda1adc-4e43-4e6e-a6e4-bf0906f0ccad |  | checkpoint | Concrete placed under the gully base
checkpoint-status | c669cd36-bab5-4709-bfff-e2e146bd306e |  | checkpoint | Gully dish installed
checklist-flat | 9a8198f5-4c5f-426b-9ff1-44a161bc40bf |  | checklist | Drainage Checklist |  |  |  |  | Yes | Drainage Checklist | ece54f6a-2552-462b-bf66-a0f291f2f1ec
checkpoint-status | 8fed3ff9-0b41-44f4-b7da-c800940edc89 |  | checkpoint | Is Pipe Sitting On Bedding
checkpoint-status | 8bea4e37-d8d1-4828-a7be-66f32369496e |  | checkpoint | Is Pipe Installed To Correct Falls On Plan
checkpoint-status | 74bde68c-906c-4484-9914-a94d72a4eacc |  | checkpoint | Has Pipe Been Photographed For Q + A
checkpoint-status | 53cf0450-ee7c-4319-acb3-5b05578904c2 |  | checkpoint | Is Pipe Free From Debree
checkpoint-status | 3f36e4e2-ab95-4c04-bc33-87e069f89ee5 |  | checkpoint | Has Fines Been Installed On Top Of Pipe
checklist-flat | 92117e16-434a-493f-9851-fccc3993980f |  | checklist | RFI |  |  |  |  | Yes | RFI | f4c43fd7-4506-44db-845c-6ed3a8766565
checkpoint-status | ed53d105-7cf3-477c-a754-fffdab868faf |  | checkpoint | RFI name
text | 5ad17e2d-ebe9-53ae-bcee-7b253ef07c2b |  | textbox
checkpoint-status | 140d85ec-51f1-478b-a398-cc2e50285e0c |  | checkpoint | Submission Date
text | 04eeafe3-5786-5502-ab64-7c6878028cf6 |  | textbox
checkpoint-status | 1c7d159f-3c5d-4145-8ab9-2b959ca78e7f |  | checkpoint | Due Date
text | 7c73d33a-5cd0-5ac3-939a-95e5ec6c8e0c |  | textbox
checkpoint-status | d37c645f-12a7-4e22-b6d2-d9085e843f4b |  | checkpoint | Submit By
text | 804a7cde-2f43-5a1c-8241-d67c3bf38b87 |  | textbox
checkpoint-status | 9fa03048-e457-4a5a-8750-f042dff25d2f |  | checkpoint | Reference/ Drawing No
text | 091d89dc-5b8a-513b-a520-272a5b3a6e12 |  | textbox
checkpoint-status | d46848a2-9a5e-4325-aa6e-0df39d9e2bd8 |  | checkpoint | Request/ Clarification Required
text | 4fad1512-c032-503b-83df-9b0c183e21cc |  | textbox
checkpoint-status | 2e00e63a-2740-4460-b75d-401735a0ba35 |  | checkpoint | Resonse
text | b2977015-8501-524d-9fd9-0202005288bb |  | textbox