## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | dbb376ca-113b-453d-8dc4-ffdf7f074d41 |  | checklist | ITP-019 - Line / Road Marking | itp |  |  |  | Yes | ITP-019 - Line / Road Marking Rev1 | 1b159c0b-6018-4ee4-ba5f-845f67b10723
checkpoint-group | cd5c97aa-e865-4600-9159-7bf51e9d5f33 |  | section | Preliminary Works
checkpoint-status | 210223ba-a109-401c-914b-9d47a528d41c |  | checkpoint | 1.1 Check for correct documentation
label | 9a8c0f26-a872-5c86-8f19-976070f767ec |  | note | FREQUENCY: Prior to commencing any activity
label | ed61244b-9dda-5381-8261-0089028fea2e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 7760e379-b38d-5c39-b791-48e257eba3aa |  | note | – using the correct and complete set of drawings
label | ff52061b-3ad1-5cb0-82bc-dd0bd14e5453 |  | note | – all drawings are the latest revision
label | 504fe615-b239-56d7-aa35-c5ea6fab747a |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | 8b8f6575-08b6-5f3d-b4b1-a7a07985db7a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 828598b5-5f79-560b-8966-d7a4ec8ff3bc |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c4d0c818-2b88-57b3-876b-820d718a48a5 |  | note | WP
label | 171da28c-d417-5177-84b4-0113ac9285ef |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ace4284b-325b-5d2b-b0ac-c232605e4998 |  | textbox | DATE:
checkpoint-status | 1b176e3a-f0a7-4d2a-ace6-cb4d4b03fc3f |  | checkpoint | 1.2 Implementation of all measures and controls
label | a92846b7-c8d9-5172-8d2c-c88fd4514448 |  | note | FREQUENCY: Prior to commencing any activity
label | 8ac2a404-5fdc-596c-9804-ef475a4feb50 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | d9a6a333-ffaa-5110-8443-a002008074b0 |  | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | 08fcc02b-e31d-560f-85c2-cbf876baa656 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9f2a1c2a-63c1-5254-a4bd-0fdcd84c40f7 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 3ddfa7f3-dd6b-5de6-9e7d-59bf0b0df830 |  | note | WP
label | 98bbe643-bf6d-5c2d-a9c9-cda2b15cb73c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | ee1199fe-01e3-5e6f-be13-12431d7f560c |  | textbox | DATE:
checkpoint-group | 2330e927-55f8-4d92-805e-f0f8377fb1ff |  | section | Construction Works
checkpoint-status | e00a2f57-5cc5-48f1-8242-99e7a5953ab1 |  | checkpoint | 2.1 Setting Out
label | 61abe97d-f186-5a1f-9375-83ae10f3390d |  | note | FREQUENCY: Prior to start
label | 85ef4da6-b783-5652-8bc8-d155badf41f8 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | d57de8e6-f732-5388-ae72-3ef2f8b8ab9e |  | note | REFERENCE DOCUMENTS: Drawings
label | 8a3a58de-94ab-5204-946c-d52049cb28fd |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 9b63f999-c835-5743-9f43-506e1ac6d0a5 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 7a3c98d7-368f-5696-81d7-607e8d287e1c |  | note | IP
label | 82dad704-7d90-57f1-8b9a-6ec6a0410368 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 3b8941b6-0bb3-5d8a-b7f8-c13da46342b8 |  | textbox | DATE:
checkpoint-status | 1828d6c3-5d93-4051-81ec-9c315b9b4629 |  | checkpoint | 2.2 Position of Markings
label | 6682d70e-8685-5773-8b73-e321dd412091 |  | note | FREQUENCY: Prior to application
label | 3c8f1eda-bb71-5091-98c9-67ab17cd7dde |  | note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
label | 2bc0a49d-ad34-5ac0-9549-63d1a0d2df61 |  | note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
label | 7a5fca7c-4852-51bd-8eaf-35873e4c52c4 |  | note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2 Drawings
label | 41ae7485-0857-5e4b-8b9d-6e33e6fc4811 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 43e70655-f2b5-5d76-9176-8598893cce31 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dd1011ae-75cf-5a55-9f28-a477bf6e04ac |  | note | HP
label | 357bb288-7b1f-599d-8292-199eaa7fdd1c |  | note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
text | ab6ffc05-7753-504e-a41a-0c38ea03833c |  | textbox | DATE:
holdpoint | bba0cd06-6b3a-4223-8712-6863761307ba |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 5fbed60f-73e6-4700-8142-b4c1b81fe471 |  | checkpoint | 2.3 Materials
label | 55e2678c-8b34-578b-b1dc-c8073f8a6863 |  | note | FREQUENCY: Prior to commencement
label | 2f8b5baf-60cf-5b4d-95a4-8f87f7ff7577 |  | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
label | b142fb4c-1e50-5f5c-9ec6-9864d7ae4d66 |  | note | REFERENCE DOCUMENTS: 712.A04(c)
label | 5061eccb-2031-5488-95f1-6e460f0fcf0a |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 1a2d6a47-ddd1-501e-b54c-178fb7cfb608 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | bc59de81-a847-51ea-a6d3-cfd31ae1c714 |  | note | HP*
label | e3058a4a-fb79-5dca-8b16-73fd17d541e2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | d837cdcb-5e7e-545f-b08e-389cfda39fc4 |  | textbox | DATE:
checkpoint-status | 1268c019-6b4b-478e-a99a-ab9ca2dba41c |  | checkpoint | 2.4 General Markings
label | 24886f0c-7e27-5484-9722-bb7963e95bea |  | note | FREQUENCY: Prior to commencement
label | 4e19e89a-21b8-5b65-8fc9-fd554c58137f |  | note | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
label | 47ef605b-dab0-57aa-9275-016c7befd131 |  | note | • All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
label | c5695735-30a5-5a7f-909b-96b1998289ea |  | note | REFERENCE DOCUMENTS: 712.D01(c)
label | 34a99c24-0840-50bc-8771-779bfdc0c9d1 |  | note | INSPECTION/TEST METHOD: Visual inspection
label | b54b296d-95fd-5dd2-99dd-09916107abe6 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a29a81c1-f553-5e61-9cca-786520bae46b |  | note | HP*
label | f8e196e5-e243-51dc-ab8d-710639ea16d2 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b708ad4f-d5c5-5beb-84e1-c716e8cbfaa1 |  | textbox | DATE:
checkpoint-group | f2115c1b-b183-4c8c-b11a-ed2357b830d4 |  | section | Completion
checkpoint-status | 06e80b21-4474-4202-8f76-e7801a6b50dc |  | checkpoint | 3.1 Tolerances
label | f3b132c1-cb53-5ec9-b3d0-d5fd47bbc0d6 |  | note | FREQUENCY: Each marking
label | 04525e1d-34ce-5464-9762-aabba96be35d |  | note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
label | f13e3935-129d-5130-816d-b50d1fdef2f3 |  | note | (i) Distance between centreline of marking and set out marks <30mm
label | 5bb2c3da-d426-5705-b959-80e7c05848aa |  | note | (ii) Width of completed paint markings <15mm
label | 651b7975-15df-58c6-93e0-1e620f9e8784 |  | note | (iii) Length of completed stripes and blocks 0 to +10% of specified length
label | 2065a91a-a3f1-5a45-b9b6-2e5bd49a3691 |  | note | REFERENCE DOCUMENTS: Table 712.A101
label | d7c427d6-fa17-5a6d-b34b-c4101c38720c |  | note | INSPECTION/TEST METHOD: Verify
label | fa3889df-da95-5bd9-97c7-a951075ac16a |  | note | RECORD OF CONFORMITY: This ITP signed off
label | c96343bd-da37-5be1-8694-449d553ef0dc |  | note | HP*
label | 2bc2f9c3-738f-5b9d-be5e-00f8195febaf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 89dd2059-64b4-5cd9-ba50-46df0c59c65c |  | textbox | DATE:
checkpoint-status | f4d2fe37-c713-452a-b30d-7df8437bcd9c |  | checkpoint | 3.2 As-Built
label | 31b4551a-0047-596a-9b75-abe14811e27d |  | note | FREQUENCY: Post Completion
label | d006d21c-0a16-592c-8bdc-b1ea65d74b5a |  | note | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
label | bc0363b5-8097-556b-bcb8-98d4b01fd5ec |  | note | REFERENCE DOCUMENTS: IFC Drawings Survey Records
label | 635a59d0-9cbf-5744-b0ea-bd256afa5308 |  | note | INSPECTION/TEST METHOD: Document Review
label | bb7be71e-f497-5afb-9978-71d20b436a7d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 4929bccd-0ad6-57b6-b067-7f2617ec81ea |  | note | SCP
label | 064a8427-6da0-57d8-b3eb-84145dd28617 |  | note | RESPONSIBILITY: Project Engineer/Surveyor
text | 13858deb-4d08-5f88-8c57-cf6f1f520ea7 |  | textbox | DATE:
checkpoint-status | a9c3d631-148e-45be-a085-5c652369d453 |  | checkpoint | Final Inspection
label | 933f15c4-6158-542a-9997-646074804c34 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 3e4021a7-7797-5608-9d8b-83f697fe1ce2 |  | textbox | Print Name:
text | 259bf84b-a4bf-5013-8af9-3d010453bf19 |  | textbox | Position:
text | 44bbc67b-f86c-574c-9b39-bfed7475e630 |  | textbox | Date:
checklist-sectioned | 5f29b919-8dea-4544-9cbc-d7784f04b519 |  | checklist | ITP-016 - Road Sign Installation | itp |  |  |  | Yes | ITP-016 - Road Sign Installation Rev1 | 73af165c-457d-443e-b185-6bb5315dae3d
checkpoint-group | 36fee83c-c28e-4dff-a15b-7c6cc12760ba |  | section | Preliminary Works
checkpoint-status | 57c2495d-0666-4708-81cf-02a9f9771f09 |  | checkpoint | 1.1 Check for correct documentation
label | 3aecc1be-f8c2-5935-ac30-ca8e7c4c6a50 |  | note | FREQUENCY: Prior to commencing any activity
label | a6009f3a-c06d-5237-98bc-f06641810356 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 70e87fbf-de9d-5a38-ada2-46e6a307493a |  | note | – using the correct and complete set of drawings
label | 3473ac89-cead-5eab-a318-e2a6b6a131f0 |  | note | – all drawings are the latest revision
label | 03f37a2d-6769-5356-8a16-e27cfefeebb3 |  | note | REFERENCE DOCUMENTS: Drawings and drawing registers
label | afc3a459-da4f-50f5-aaef-47f5df726f6b |  | note | INSPECTION/TEST METHOD: Visual inspection
label | ee1ec5d6-b871-58ff-9633-0dde03ede476 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | dcc2ca49-aa7f-5087-af9f-b131831679ad |  | note | WP
label | cf41c597-3594-5605-86ef-fea6a176bfa8 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | de61c5de-4ce1-5547-868c-08ebdb550b8e |  | textbox | DATE:
checkpoint-status | a318207e-500c-4548-85f3-f66ec5b5cac1 |  | checkpoint | 1.2 Implementation of all measures and controls
label | 369e93b1-f0a3-5863-9e99-471471d9fcd2 |  | note | FREQUENCY: Prior to commencing any activity
label | 6c0165c9-ff8d-59c4-8d5c-bb98b2932f01 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 79ec3ac2-e693-5058-988d-7f95fef5f842 |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 314e101e-0b51-5b7a-b32a-e1c40376b690 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2724de28-fd06-5491-b406-a170ec59b46b |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 28669795-9289-59c3-a08b-417637eb9cba |  | note | WP
label | cbd9db39-477f-580e-af84-415dbc0b4652 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | cd19c762-9fd7-5b55-92f6-0774b520be82 |  | textbox | DATE:
checkpoint-status | fd44484d-99c2-493e-99f2-a895c3d4c00b |  | checkpoint | 1.3 Signage Conformance
label | 7ed0c4cc-2a75-5322-ad49-21cee2295e87 |  | note | FREQUENCY: Before commencement of activity
label | d97214cf-66b3-5561-b7ab-5645e26f843e |  | note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
label | 0f652f89-d0bf-58d9-b84c-6d8ac2f8e399 |  | note | REFERENCE DOCUMENTS: Drawings AS 1742
label | 24feb20f-5f21-5ac8-b452-9f2a0ebb7588 |  | note | INSPECTION/TEST METHOD: Verify
label | aa7cb6e2-4e87-51f5-93ee-b7c0baa493fe |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 251ac02f-818f-536b-9940-ac21af33f3e0 |  | note | WP
label | 1fa5e426-4bac-59b2-9f69-748404e8395c |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | 9c701122-3ebf-5d1b-98e4-d699fbd46473 |  | textbox | DATE:
checkpoint-status | 72aea78a-6fed-4796-abc7-af766740862b |  | checkpoint | 1.4 Service Identification
label | d0f9c091-f11d-5784-97c2-5437fde4af27 |  | note | FREQUENCY: Prior to start
label | 72d733bb-dab7-57e7-b22a-d455cd4839b1 |  | note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | b6e267c5-d207-53c5-80fa-cf78bca253c8 |  | note | REFERENCE DOCUMENTS: DBYD, Service chart
label | cc09b06c-0439-55e9-9c8a-a41c8df94309 |  | note | INSPECTION/TEST METHOD: Verify
label | cd038839-4666-5fe8-ba49-d6933b11c5b2 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | e9c78b60-3497-5bad-a633-d9437b649cd0 |  | note | WP
label | 2583a34c-4c60-50bd-bcbe-567a09398102 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | fa8bf9c1-3f0f-5c25-a88a-ad21fe5d6ab7 |  | textbox | DATE:
checkpoint-group | 94bcca71-12d3-40fd-a7f9-84c14aafc52a |  | section | Construction Works
checkpoint-status | 941a622b-c223-4f3d-bb83-6481325ad64d |  | checkpoint | 2.1 Setting Out
label | 5a6a18a8-92ce-57f8-a26e-e2387a5fe2bd |  | note | FREQUENCY: Prior to start
label | 8a510332-00c9-5c98-8ba2-c5db8cfc3088 |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
label | 900ac2d5-2931-5431-9fc8-9bb26be54e11 |  | note | REFERENCE DOCUMENTS: Drawings
label | 6b11eddb-bae7-5a82-a532-0cf1aad1e2c8 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2924f108-7cbc-5db8-92a4-6d44c459f54d |  | note | RECORD OF CONFORMITY: This ITP signed off
label | a01d4164-b389-57a3-8d1d-b6e3b4d13b4f |  | note | IP
label | 6412d0e4-34eb-5e49-8bae-f148dca26faf |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | b5bb8f24-0cb5-56b6-8227-860868421b47 |  | textbox | DATE:
checkpoint-status | b6b4034e-8d14-4a73-9e93-6796446f2c30 |  | checkpoint | 2.2 Post & Foundations
label | 19d5eb86-bdc6-55cf-a04d-fbcd54dad524 |  | note | FREQUENCY: Prior to Start
label | ba9679a1-bb8f-5c1f-93e3-65d85a778bd5 |  | note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
label | fa371527-239b-536a-b5b1-eb976a53a44a |  | note | REFERENCE DOCUMENTS: 714.06
label | 76982962-76b2-51df-898d-d1dbd5bf9aca |  | note | INSPECTION/TEST METHOD: Visual inspection
label | 3714a34b-658f-5970-aa57-d92d3a72e462 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 9cf4b883-0f26-5431-8874-62838fcb7a83 |  | note | HP
label | 20c5e42c-f701-5fc4-a386-685bc49a8bd9 |  | note | RESPONSIBILITY: Superintendent
text | 3878669f-cd65-5008-9638-612ad414776f |  | textbox | DATE:
holdpoint | fd242e13-0374-4374-8910-46ee4f14885c |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 84ca08f1-3b00-4928-b135-70e951fc3a03 |  | checkpoint | 2.3 Signage Install
label | cfd69522-3dbb-58f9-8515-00572a367af8 |  | note | FREQUENCY: Each Sign
label | 928be84d-7f80-5c35-abaa-096f0978d195 |  | note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | 3957dc33-05a3-5d29-9e53-7d566b7b6250 |  | note | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | cf8319a3-dafa-5140-b322-0da06aab2b19 |  | note | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | 511d7531-5f55-5e9c-bb9a-1bc806b5e398 |  | note | REFERENCE DOCUMENTS: AS 1742 TS 1313 Drawings
label | f3f24266-9b10-5c9f-8e47-14da5b8128f3 |  | note | INSPECTION/TEST METHOD: Verify
label | 1fd80d9b-be8e-5eff-b1b7-3e814775de20 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 518c5e88-1634-5379-b6ff-e8db271725b4 |  | note | WP
label | 94fd70da-c8b9-5177-a8a4-e9ba656a1570 |  | note | RESPONSIBILITY: Fulton Hogan Engineer
text | c5cf68d4-f1f9-5672-b91b-7c6bb1d20dc0 |  | textbox | DATE:
checkpoint-status | 91b338c9-b896-4d59-87e5-07427d79a678 |  | checkpoint | Final Inspection
label | f3e46cef-ccd7-53b7-8f3b-a26fd1bf2c63 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 4af68b8b-b744-571e-a5d4-9ce12d43c925 |  | textbox | Print Name:
text | 7c3d469d-8ee2-5617-b78a-d9cabcca5493 |  | textbox | Position:
text | bc2d2801-a178-53ec-91bf-15b0761a97e2 |  | textbox | Date:
checklist-sectioned | 2f97c25c-f8c5-4753-a1bd-a39c3b37d3da |  | checklist | ITP-008 - Hot Mix Asphalt Placement | itp |  |  |  | Yes | ITP-008 - Hot Mix Asphalt Placement Rev2 | 951ed16c-9d90-4ed8-bdc1-b0ff8bc89c3c
checkpoint-group | 70e67703-d33c-4c5a-a6e1-e7a392becb4a |  | section | Construction Works
checkpoint-status | d1de04b1-3a0a-4dad-ada0-41546fa045ae |  | checkpoint | 1.1 Submission of Mix Design
label | 04d5cfc3-86ba-5498-8db9-7a91ad0d9f7e |  | note | FREQUENCY: Prior to commencing paving
label | 70b6fb78-0977-5b8a-8e8a-d8810d362d8b |  | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | d53f9617-8f7f-5849-8e68-af56ab3871ff |  | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
label | 9eee9147-2b47-50e9-a301-c739ab4947e5 |  | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | 5989096f-c02e-5a61-b0db-cc13efc8d777 |  | note | RECORD OF CONFORMITY: MRPA approval Completed ITP
label | 984ff638-c1bf-523e-9cb8-30477d48ca0d |  | note | HP
label | 2a07b368-1cf8-563c-8a64-ee6e3761ce70 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | d2aabe64-0615-5fd3-bf91-6bae9212ecd3 |  | textbox | DATE:
holdpoint | 80cacf24-82fc-4f32-89fc-de69fc95525e |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | 16b47d61-021d-4f16-8dec-2b1cc4b9ba0a |  | checkpoint | 1.2 Implementation of all measures and controls
label | d2dd4eca-01be-55de-9620-c269f29dbf8d |  | note | FREQUENCY: Prior to commencing any activity
label | 2d7da552-4bea-51bc-9333-198feaf85f23 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | db15da44-71eb-575c-971a-90c9b36eabdd |  | note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | 9dc67ca7-9766-5a96-871e-a8980c5ac197 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 59d87e2b-4bef-52ae-91be-69ced5195364 |  | note | RECORD OF CONFORMITY: This ITP signed off
label | 281329fa-4f14-5f4c-8754-a444ae5ded2d |  | note | HP*
label | 1218f01f-3a91-525d-b619-b552afe4c91c |  | note | RESPONSIBILITY: Site Engineer / Site Foreman
text | 466e5a5d-3813-5ace-998d-8b29593a2372 |  | textbox | DATE:
checkpoint-status | 70289b90-585d-4090-9813-84cee3530da2 |  | checkpoint | 1.3 Site Inspection and Base Condition
label | 269ee873-7a3d-5b95-a9ff-3373f87088bf |  | note | FREQUENCY: Prior to commencing paving
label | d93d6913-6d25-5880-aed8-50c0c950ddb8 |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | b76628a3-9da7-5f1f-863e-f39a6fe1de6d |  | note | REFERENCE DOCUMENTS: 407.17 AS2150 10.1 AS2150 10.3
label | 57eb4182-a83c-5ac8-9112-92d95b4c742b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 284043c2-d0a5-5c3a-a468-729f85be8584 |  | note | RECORD OF CONFORMITY: ITP Signed
label | dc82f599-d56a-58de-9c23-badd46f46196 |  | note | WP
label | 76b83da3-ecb7-5829-bcfc-0681b4bc7d5a |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | c35209e0-0d56-5d19-ada5-b6017aca0ba2 |  | textbox | DATE:
checkpoint-status | c8df777c-8f6d-4ec5-984c-4769b794d6fc |  | checkpoint | 1.4 Ambient Conditions for Placing
label | 6c15add1-896a-5d2a-9011-2c37a8b8c0e9 |  | note | FREQUENCY: Prior to commencing paving
label | d6ce3967-73f0-5b54-8cd1-9caacad5a678 |  | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | fef861dc-93d5-5020-8f22-4a135f6be148 |  | note | • Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | d75cb009-22c3-534a-a0f6-7894ee5ba896 |  | note | • Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | b7507399-448b-57eb-9b94-3419f4a9ad0d |  | note | REFERENCE DOCUMENTS: 407.17
label | a446dd2c-5d48-5f0f-a1e3-5aec38cec55c |  | note | INSPECTION/TEST METHOD: Verify
label | 04b20322-d9b1-59fe-b91a-4cf0ac958694 |  | note | RECORD OF CONFORMITY: Thermometer
label | 4bef74ee-fedb-5137-8bd8-e9614e9b395e |  | note | IP
label | fe8d8baf-ee01-5a70-8174-e9a5d5c21624 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | a63cf8a2-02ba-5b1b-a332-fae895c8b9f2 |  | textbox | DATE:
checkpoint-status | d78f1d08-1d16-4d1f-8a37-11b07bc09b84 |  | checkpoint | 1.5 Planning of Joints
label | 5ff149c3-9629-5d99-9dd8-f2e0b4cabd87 |  | note | FREQUENCY: Prior to commencing paving
label | e64ad34a-9e35-5afc-a8af-4b1d262722eb |  | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | 4237232d-41a2-5b8a-8d9a-075b6f7f2f47 |  | note | • Transverse Joints Offset from layer to layer by at least 2m
label | b7f88022-24a0-5474-ae45-65bae4023aa3 |  | note | • Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | d4802045-b017-5051-8185-c67396fe1db5 |  | note | REFERENCE DOCUMENTS: 407.21 (b) & (c) Pavement Drawings
label | 0b4eff64-a8d9-520c-854d-55be4cd41012 |  | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | 7e57bd02-e367-57c8-8b30-394ef8ec3210 |  | note | RECORD OF CONFORMITY: Paving Plan
label | 245cd4d0-bf02-5fa4-a74a-8e46a52629da |  | note | WP
label | 6f9b756a-cd18-5332-9bbc-cc6c298777e5 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
text | 0f920c54-4f06-5f03-b4eb-c2c439b1aeb6 |  | textbox | DATE:
checkpoint-status | 206e5c99-d317-4ba0-a65e-8abbe48eac2c |  | checkpoint | 1.6 Longitudinal Joints with existing Pavement
label | 4e28370d-a6b9-50e5-8738-f6a2a282f716 |  | note | FREQUENCY: Prior to commencing paving
label | e48ef907-8f9b-5509-9e9e-ac2f7fff0a54 |  | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
label | 7a15b0c9-6e3e-5bf9-80eb-01ec0fd46495 |  | note | • Depth of step to be cut to the full depth of each indiviual layer.
label | 6db67ad2-b2c0-57e7-9421-cb20c97be298 |  | note | REFERENCE DOCUMENTS: 407.21 (c) (ii)
label | c1071cf6-0772-5427-86bc-1a180d1c62de |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | d030fe0b-bb08-53d6-b324-c6b976a8d614 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 1c5abf13-a4cb-5fa5-b344-46ba37d40ef8 |  | note | WP
label | b8ae2ca5-ba55-5fba-835b-4fbd0da6cc23 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
text | a5f42112-badc-5330-91a9-433a282f2ec7 |  | textbox | DATE:
checkpoint-status | 85797bda-697a-4f18-a0c9-ca048186acc6 |  | checkpoint | 1.7 Lot Size
label | db3bbe3f-d1bf-570a-b5e3-b362f5523233 |  | note | FREQUENCY: Prior to testing
label | b4679a32-40e5-5dc2-b6bc-8290a42fee99 |  | note | ACCEPTANCE CRITERIA: Lot size for determination of testing shall be in accordance with 407.27 (b) (ii), where less than 500 m2, reduced testing may apply
label | ae020b96-2477-5321-b4d7-874fb52fa2fa |  | note | REFERENCE DOCUMENTS: 407.27 (b) (ii)
label | 904b74f2-abf7-5f92-8c32-ad554374d69b |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 080f9a25-f4e5-58fb-b0d9-a3d3cef4c967 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 1f2b78ae-89c3-5396-9a0c-0d86132f6052 |  | note | IP
label | 21d7a5e9-d9a2-56fb-8865-10ba06333de1 |  | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
text | 53c289c3-50ca-530e-a677-a03f1209f2d3 |  | textbox | DATE:
checkpoint-group | 63501a42-ee05-4613-8941-513437c02c1b |  | section | Asphalt Placement works
checkpoint-status | 7a86901e-e0ca-4a25-b502-11f35a93c71f |  | checkpoint | 2.1 Tack Coat
label | b44146da-cd88-5ef8-be72-5fac8605255a |  | note | FREQUENCY: Prior to commencing paving
label | f8dce061-2d2c-5ba8-9e82-53016cd1a9e0 |  | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content).
label | 2cbe77e2-b87f-5746-8765-f1c835622c8b |  | note | • This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | a11780f0-4e63-57d8-960f-ba94c9e42f0c |  | note | REFERENCE DOCUMENTS: 407.19 AS2150 11
label | 183fa441-15a5-559e-809f-4476359d2f0f |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | dc6de749-a23e-59b2-88db-d7ec6e11578a |  | note | RECORD OF CONFORMITY: Spray area
label | fd782f98-e15c-5619-a971-6054435164f1 |  | note | WP
label | 2db92ae7-876c-55c0-bc60-594860a60a28 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 25e7d2e0-730b-52ae-bb8f-23e71c97bb13 |  | textbox | DATE:
checkpoint-status | 3df75081-f4e2-4d1f-8843-8e171a52170a |  | checkpoint | 2.2 Commencement of Placing
label | 8feec51b-2872-5c7d-b6ce-9acdf0d149b9 |  | note | FREQUENCY: Prior to commencing Paving
label | e81f45c5-5c56-56f2-b079-79ba2fa3de8c |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | 1aebb686-ae80-5524-aa97-d65128c87341 |  | note | REFERENCE DOCUMENTS: 407.23
label | 96b4aebc-e18e-5a76-97cf-9e2ecf98b039 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | fbf5fe80-0670-5ad7-8e89-656b7356ed85 |  | note | RECORD OF CONFORMITY: ITP Signed
label | d2d30a15-0415-501b-8415-22a10ee6353e |  | note | HP
label | 69185af5-d4b1-5d23-a780-32722f9218ea |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
text | aaa16fdc-732d-5ca3-bf05-b9cdc584eed1 |  | textbox | DATE:
holdpoint | 188cd99b-cccc-45f6-bc3f-10fc5be805b2 |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status | e5a3b1af-86c1-4407-8792-c25a2fcd4079 |  | checkpoint | 2.3 Mix Design Confirmation
label | ed483cdd-e754-54cf-bccd-c41e68560f65 |  | note | FREQUENCY: Each lot
label | 21dfdd80-dd90-59da-9f63-bf0e0196aa0a |  | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
label | adf30f25-ee7a-5921-9510-98af103daebc |  | note | REFERENCE DOCUMENTS: 407.2
label | e1ac1b4f-08a2-5587-990f-9aaa2a2ae695 |  | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
label | 522fccc8-7f13-5ff4-bcf6-a49e1059697b |  | note | RECORD OF CONFORMITY: Delivery docket Completed ITP
label | 55cb6e3c-d7cd-582c-9a78-92bdd9e680bc |  | note | HP*
label | 85a5b0b3-72a2-525a-874a-66751fdbfb69 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 5516134e-507e-5958-8b80-75214a8aa241 |  | textbox | DATE:
checkpoint-status | 5bd30b8b-15ab-4496-bd4e-659fd316e271 |  | checkpoint | 2.4 Delivery of Mix
label | e9e02cfc-0182-503d-9e3b-5f235064c242 |  | note | FREQUENCY: Each load
label | 1b0ba1b4-ccbf-5ef8-aa8b-ff23baee1168 |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 516934ff-780c-5dc9-a699-c0a56e700b0b |  | note | REFERENCE DOCUMENTS: 407.2
label | e456dee4-4606-5184-8381-0e810a29a2e2 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e84dd6df-fc6c-51c5-b247-d4978b9261f1 |  | note | RECORD OF CONFORMITY: Delivery Docket
label | ba79356c-215b-5891-8425-c9b15b9924d6 |  | note | WP
label | 98778e99-54e2-56e2-a421-f2077d7f6993 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | c57ee9f5-5bf4-5646-b0fd-ec99e11f33f0 |  | textbox | DATE:
checkpoint-status | aceef78b-d884-41b6-b087-93b34c452c1a |  | checkpoint | 2.5 Traceability
label | a39ef450-3dd7-5afa-9fc5-6e261734be45 |  | note | FREQUENCY: Each lot
label | 5f9a1399-e41a-5b05-8070-2296de7cca3f |  | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | cf8d59da-d6ad-51a2-ab42-41930b5ad216 |  | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | 33627c2b-5339-57ea-b312-71c26740e838 |  | note | INSPECTION/TEST METHOD: Verify
label | 8072747a-edb8-51b8-becc-a955c91c9caf |  | note | RECORD OF CONFORMITY: Daily Lot Record
label | 92aeea55-0805-5a68-9ca6-50695957f1a5 |  | note | IP
label | 5c847cb7-6f14-5a79-a14e-c6debf82026a |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 5f51311c-bb6c-542b-9524-4f6c55073ef5 |  | textbox | DATE:
checkpoint-status | 14844900-fea1-4ebb-9cb5-b4bedcbca93d |  | checkpoint | 2.6 Layer Thickness and Level Control
label | 30023a77-3422-5577-b344-e819a8a42e74 |  | note | FREQUENCY: Regularly during paving
label | ef247be9-aaac-5409-9e9d-d04e57cc6019 |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | f628c188-1d99-5ac8-a4bf-a651d7c2c9b3 |  | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | 7904e5f5-1554-5688-9f66-4647f0d3ad82 |  | note | INSPECTION/TEST METHOD: Verify
label | b37d548d-7329-5af7-b2dd-102ead9c9d8a |  | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | f5cb5048-2dff-5cd2-bbef-a0e3f24cd668 |  | note | WP
label | d5382d31-e4e1-59f2-abce-4b35b833a7b7 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 4488b278-78e6-55fa-ad14-5650a60a4c17 |  | textbox | DATE:
checkpoint-status | 52a2073c-e6a6-4bb7-b119-6b186886ff69 |  | checkpoint | 2.7 Paver Stoppages
label | 7861876d-0213-5672-8e44-762f26e9f561 |  | note | FREQUENCY: If paver stops
label | 33506b64-ea37-54b2-ba8e-cb0ddf808abb |  | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | 5128c319-d49b-5edc-b7ae-b8839066e474 |  | note | REFERENCE DOCUMENTS: 407.25 (c)
label | 76153f90-afb6-557e-a359-c3966471a1f6 |  | note | INSPECTION/TEST METHOD: Verify
label | eaec9d41-4b36-5916-b73d-5511b2560b59 |  | note | RECORD OF CONFORMITY: Thermometer
label | 489971fe-4a9f-5968-bc41-71a4655aa5cc |  | note | WP
label | d1cf2df8-a7ea-53ab-a2c0-dafe86ff5c10 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | d6f0abfb-47ae-595c-9178-2e90e1244386 |  | textbox | DATE:
checkpoint-status | 934423a6-a4fa-4076-9daf-a19d5630af09 |  | checkpoint | 2.8 Surface Finish of Wearing Course
label | a01bb02e-b76d-55a2-bb26-a65240914a55 |  | note | FREQUENCY: During paving and after final roll
label | 2f2d01d8-6096-52a0-8392-4eda648306a6 |  | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | 2cb9a975-e064-5ff9-b8c3-f8bc19d39013 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
label | 7a724d90-cb10-5aaf-ba68-ee35c48798e5 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | e92cca94-6171-5ba0-98e3-75d2870deb54 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 3b98ea1f-1acf-5e8b-90e0-a73b1f7cc34d |  | note | WP
label | 3bfc923a-34a0-5898-9542-cfa907ebe41b |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 896455c8-86c6-5dcb-a702-e15eb3450da7 |  | textbox | DATE:
checkpoint-status | b1cd727d-c1b7-41dd-bd23-01c45c518257 |  | checkpoint | 2.9 Kerb and Channel
label | 0cc35353-810c-5934-9901-1050669a12e1 |  | note | FREQUENCY: During paving and after final roll
label | 76911630-c195-57a7-ad2e-d0554c4bc0ac |  | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | e43e927b-325d-5bb6-8bda-c27dd59c8274 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
label | 556af525-fdd2-5870-a456-95fa2691d740 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 0e2fa12c-7344-59db-b903-184189eee7f1 |  | note | RECORD OF CONFORMITY: ITP Signed
label | 8a47b2bf-4a9f-5d4d-a2d6-8132242c563b |  | note | WP
label | 4333c556-5810-5bcb-ac0d-a624fb384ca9 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | fae35d92-0400-524f-813f-120d53296664 |  | textbox | DATE:
checkpoint-status | cdcf0abd-335d-4e80-a598-4e95dfa4226b |  | checkpoint | 2.10 Alignment of layers not placed against concrete edge
label | 567953d6-3529-5e33-9153-e8de4e2d6f94 |  | note | FREQUENCY: During paving and at completion of work
label | a6d19f3f-a8dd-5bf1-8b77-787a7eb4e232 |  | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | de6580f9-83e8-503c-9bbf-e5eee5bc78c5 |  | note | • The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | 525b35d1-50ed-5ab3-842a-be2876a83944 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
label | c4d262fb-62b9-551d-8cae-572ff2a37399 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 5735e511-2100-5a58-8848-c662d912c7dc |  | note | RECORD OF CONFORMITY: ITP Signed
label | 112c04f4-6cfe-5565-957c-b7e0c0eaa6ed |  | note | IP
label | 01470efc-e24c-5712-a9aa-6aa2494859d6 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | 74d4bf40-b2a6-5ded-8d77-ed7104cca478 |  | textbox | DATE:
checkpoint-status | e3cef450-57ea-4c16-ad8a-462aebc47cc7 |  | checkpoint | 2.11 Width of layers not placed against concrete edge
label | 4a59abab-c4f4-5c81-826b-903a959fdd47 |  | note | FREQUENCY: During paving and at completion of work
label | f90676ea-ef75-5a9c-99bc-a2fc9a89c484 |  | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
label | 5ba36ca9-3b10-5ccb-980a-2f43b971f7be |  | note | • The average width over any 300m shall not be less than the design or specified width
label | 17c71eaa-4cd3-5543-b470-a0a3079fc7d3 |  | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
label | 7822c367-ff9f-58dd-8638-cf969f52ef30 |  | note | INSPECTION/TEST METHOD: Visual Inspection
label | 2cb123c2-5d67-5856-82c6-59e55ace6202 |  | note | RECORD OF CONFORMITY: ITP Signed
label | d8c05b7c-0bac-5904-8cf1-a87aff01d587 |  | note | IP
label | 42d2ccef-4d29-59a5-b773-e381fdcd8e34 |  | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
text | c752a02b-b859-57ee-89aa-7e1ff4277810 |  | textbox | DATE:
checkpoint-group | 7bfb5889-d5c3-46c1-a7fa-8285062e05d2 |  | section | Testing
checkpoint-status | 6b0acb81-2d13-43e2-ad85-c9c2a5f5684e |  | checkpoint | 3.1 Compaction
label | f2c56396-acab-5fab-b689-3a3944632e25 |  | note | FREQUENCY: Per Lot
label | f9b7373e-3ae4-5b9c-a3ab-5e7e9cd8012a |  | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | da2b6283-a8f1-5f49-9459-5940e2b7bd68 |  | note | • 95.0% or greater Accept lot
label | ef8fd46e-ad33-5460-b630-e8b0717d6707 |  | note | • 93.0% to 94.9% Lot may be accepted at reduced rate
label | c799a2e7-3a6e-527b-9ae9-f133cada6b1c |  | note | ○ For layers ≥50mm, if characteristic thickness is:
label | 517aa5de-ef0e-5621-906e-43b03dd7956f |  | note | • 96.0% or greater Accept lot
label | eab5eed4-6ca1-524e-a5e1-c32040b2c0d9 |  | note | • 94.0% to 95.9% Lot may be accepted at reduced rate
label | a441826c-abab-53e7-9dd7-4481c07aa48b |  | note | REFERENCE DOCUMENTS: 407.27
label | 1ae3a636-a4f5-5739-bf2d-ccb0da911c06 |  | note | INSPECTION/TEST METHOD: Verify
label | a6c79694-4d7e-53f9-9405-bed247871306 |  | note | RECORD OF CONFORMITY: Test Report
label | eb877c2a-75d4-55b1-b2ca-c9a100fd53b0 |  | note | TP
label | a8044912-d90c-53a0-b85f-79948c71c199 |  | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
text | cba5ec84-40ea-5298-a95c-a1070dae57d1 |  | textbox | DATE:
checkpoint-status | f83525ce-1ef9-416c-bd3f-93ed87f3d982 |  | checkpoint | 3.2 Level Conformance
label | 106a0f69-1635-5487-8955-e7f4554851b2 |  | note | FREQUENCY: Per 4,000m2 at completion of work
label | 57844d75-fa44-55be-9ed4-c2172f7e7f09 |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | 4d2dd46e-61ab-57fb-a8cb-92f9042c7d02 |  | note | REFERENCE DOCUMENTS: Table 407.293
label | bbe5fe46-887b-5a8f-adec-9bb1ed317ab5 |  | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
label | 50ba5bf4-4c23-5e4b-97bb-9c1ff251bcbb |  | note | RECORD OF CONFORMITY: Survey Conformance
label | 6f1746dd-cce8-54d2-bd38-50761b767dcf |  | note | SCP
label | 89a4adda-063e-5ac1-add5-37ae2f877307 |  | note | RESPONSIBILITY: Site Engineer/ Surveyor
text | c71a4003-f022-5d1f-be40-e1cd272ad83b |  | textbox | DATE:
checkpoint-status | 988c5f99-4c55-478c-ae7f-90f5eb46a7cb |  | checkpoint | Final Inspection
label | ef6d829f-d13c-5cee-bb15-96230d7e9224 |  | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | 0202e14a-b0c4-5bb5-a457-7d96b6eeb8ea |  | textbox | Print Name:
text | d4330431-7cac-5432-867b-b728112d1a7d |  | textbox | Position:
text | b068f5b7-abf4-530c-bb99-f6fcb81180ef |  | textbox | Date:
checklist-flat | f2fde9e7-9c31-4b6a-b1b5-5c987f27409a |  | checklist | Contract HoldPoint Checklist |  |  |  |  | Yes | Contract HoldPoint Checklist | a106244b-7f45-4f96-858e-265413bed1cd
checkpoint-status | 96a78813-95b0-48fa-9a93-357ec9a1b8cb |  | checkpoint | Holdpoint Release
text | e37a2a86-d6e9-5a29-aadc-aad1b77ad6c5 |  | textbox | Enter Name
text | 1a23eb1a-cd8f-5c38-b50b-5bc9b39bbe1b |  | textbox | Enter Description
holdpoint | 60a1eb35-e850-40c9-a4b9-af7b0196da59 |  | signoff | Contract Holdpoint Release