## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Subgrade Preparation | itp |  |  |  |  | ITP-001 - Subgrade Preparation Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan
textbox | DATE:
checkpoint | 1.3 Selection and approval of disposal site
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the authorities controlling disposal of material at that location.
note | REFERENCE DOCUMENTS: Site Classification Report, CE-019- ST-0033 CL. 4.2.1.5.
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan
textbox | DATE:
section | Construction Works
checkpoint | 2.1 Excavation
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of works.
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3. , 4.2.4. Subgrade Preparation Work Procedure
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Fulton Hogan
textbox | DATE:
checkpoint | 2.2 Reinstatement of bonds
note | ACCEPTANCE CRITERIA: Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | IP
note | RESPONSIBILITY: Fulton Hogan
textbox | DATE:
checkpoint | 2.3 Inspection of subgrade material
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the standard.
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP Signed Off
note | HP
note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Width and level conformity
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings. No point in the general surface shall vary more than 12mm from a 3m straight edge.
note | • Finished formation widths shall not vary more than -0 mm, +50mm from dimensions shown on the drawings
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
note | INSPECTION/TEST METHOD: Survey Report
note | RECORD OF CONFORMITY: Survey Record
note | IP
note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
textbox | DATE:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: