## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004a - Class 2 Base Course Placement | itp |  |  |  |  | ITP-004a - Class 2 Base Course Placement Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that employees and sub contractors are using the most current and complete set of construction drawings.
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary project measures and controls are being implemented, that is: EMP, TMP, SWMS & WP
note | REFERENCE DOCUMENTS: EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 1.3 Material Compliance
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that the base course material complies with the requirements of VicRoads Standard Specification Section 820.
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | INSPECTION/TEST METHOD: Document Review
note | RECORD OF CONFORMITY: Test Reports from supplier
note | HP*
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
section | Construction Works
checkpoint | 2.1 Sub Base
note | FREQUENCY: Each Lot
note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
note | • ITP-001 HP for subgrade inspection signed off
note | REFERENCE DOCUMENTS: VicRoads 173.03
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.2 Spreading material
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Material shall be spread in such a manner as to minimise segregation of the material into fine and coarse components. The pavement material shall be spread in even and equal layers more than 60 mm but not exceeding 120 mm in compacted thickness
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.2.
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 2.3 Compaction
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Immediately after spreading the material, compaction is to take place and moisture is to be applied to maintain moisture content within 1% of optimum moisture content.
note | • Each layer of material shall be separately compacted to a density of not less than 95 percent Modified Relative Compaction. Compaction of earthworks shall be carried out at a moisture content appropriate to the compacting equipment being used and between 85% - 125% of the optimum moisture content found in the compaction test.
note | • Compaction testing shall be carried out once per days production and shall comprise of three samples
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.7.8.1 & CL4.2.8.2.
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: Test Results
note | TP
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 2.4 Level Checking and Conformance
note | ACCEPTANCE CRITERIA: Any deficiencies in the level or surface of the base course are to be rectified within the same day of placement
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL4.2.8.3. & CL4.2.8.4.
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: FH Engineer
textbox | DATE:
checkpoint | 2.5 Finished surface
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Base course shall be constructed to the compacted thickness, levels, lines and grades shown on the drawings
note | • Layer to be finished to a smooth and uniform surface and after compaction shall conform to acceptable limits.
note | REFERENCE DOCUMENTS: CE-019-ST- 0033 CL4.2.2.8
note | • Contract drawings
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | SCP
note | RESPONSIBILITY: Surveyor/FH Engineer
textbox | DATE:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: