## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-004b - Cement Treated Crush Rock Sub Base | itp |  |  |  |  | ITP-004b - Cement Treated Crush Rock Sub Base
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and complete design drawing.
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.3 Confirm CTCR is appropriate mix
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Cement treated crushed rock proposed for use shall be current, registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
note | • CTCR shall be tested in accordance with 815.141 by supplier
note | REFERENCE DOCUMENTS: Design mix specifications
note | INSPECTION/TEST METHOD: Inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
section | Construction Works
checkpoint | 2.1 Sub base
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Sub grade has been inspected, no visible ponding, springing presence, or visible deformation.
note | • ITP-001 HP for subgrade inspection signed off.
note | REFERENCE DOCUMENTS: VicRoads 173.03
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.2 Moisture content
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Moisture content shall be within 0.5 to 1% percentage of mass during time of spreading and compaction
note | REFERENCE DOCUMENTS: VicRoads 306.05
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | RECORD OF CONFORMITY: Record of conformity
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.3 Jointing
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Material shall be spread to minimise number of joins.
note | • Transverse joints in adjoining paver runs shall be offset by >2m
note | • Longitudinal joints shall be offset from each layer >150mm
note | • Longitudinal Joins shall be within 300mm from traffic lane lines or centre of traffic lane
note | REFERENCE DOCUMENTS: VicRoads 306.08
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.4 Conformity with drawings
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: Pavement sub base shall be finished to smooth and uniform surface
note | • Surface of sub grade shall not lie more than 12mm below a 3m straightedge
note | • Subgrade height shall lie within +15 to -25mm
note | • Sub base height shall lie within +10 to -25mm
note | REFERENCE DOCUMENTS: VicRoads 306.03 306.11
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.5 Curing
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
note | • As per VicRoads, 4000m2 shall be maximum lot size
note | • No trafficking before 24hrs unless approved by superintendent
note | REFERENCE DOCUMENTS: VicRoads 306.11
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.6 Compaction testing
note | FREQUENCY: Each lot
note | ACCEPTANCE CRITERIA: CT material shall be placed, trimmed to level and compacted within allowable working time (306.091)
note | • At completion of compaction, any segregation shall be rectified
note | • >500m2 96% modified compaction 6 tests
note | • <500m2 98% modified compaction 3 tests
note | REFERENCE DOCUMENTS: VicRoads 306.09 306.11
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed
note | TP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: