## Structure
Job Name: 106100 The Greenhouse
Main area/First click | Level/2nd click | Apartment/3rd click | checklist needed
External
Mezzanine
|  | G05 | Framed Baluster Checklist
|  | G06 | Framed Baluster Checklist
|  | G07 | Framed Baluster Checklist
|  | G08 | Framed Baluster Checklist
Level 1
|  | 101 | Framed Baluster Checklist
|  | 102J | Framed Baluster Checklist
|  | 102B | Framed Baluster Checklist
|  | 103 | Framed Baluster Checklist
|  | 104 | Framed Baluster Checklist
|  | 105 | Framed Baluster Checklist
|  | 106 | Framed Baluster Checklist
|  | 107 | Framed Baluster Checklist
|  | 108 | Framed Baluster Checklist
|  | 109 | Framed Baluster Checklist
|  | 110 | Framed Baluster Checklist
|  | 111 | Framed Baluster Checklist
|  | 112 | Framed Baluster Checklist
|  | 113 | Framed Baluster Checklist
|  | 114 | Framed Baluster Checklist
|  | 115 | Framed Baluster Checklist
|  | Canopy | Canopy Panels
Level 2
|  | 201 | Framed Baluster Checklist
|  | 202J | Framed Baluster Checklist
|  | 202B | Framed Baluster Checklist
|  | 203 | Framed Baluster Checklist
|  | 204 | Framed Baluster Checklist
|  | 205J | Framed Baluster Checklist
|  | 205B | Framed Baluster Checklist
|  | 206 | Framed Baluster Checklist
|  | 207 | Framed Baluster Checklist
|  | 208 | Framed Baluster Checklist
|  | 209 | Framed Baluster Checklist
|  | 210 | Framed Baluster Checklist
|  | 211 | Framed Baluster Checklist
|  | 212 | Framed Baluster Checklist
|  | 213 | Framed Baluster Checklist
|  | 214 | Framed Baluster Checklist
Level 3
|  | 301 | Framed Baluster Checklist
|  | 302J | Framed Baluster Checklist
|  | 302B | Framed Baluster Checklist
|  | 303 | Framed Baluster Checklist
|  | 304 | Framed Baluster Checklist
|  | 305J | Framed Baluster Checklist
|  | 305B | Framed Baluster Checklist
|  | 306 | Framed Baluster Checklist
|  | 307 | Framed Baluster Checklist
|  | 308 | Framed Baluster Checklist
|  | 309 | Framed Baluster Checklist
|  | 310 | Framed Baluster Checklist
|  | 311 | Framed Baluster Checklist
|  | 312 | Framed Baluster Checklist
|  | 313 | Framed Baluster Checklist
|  | 314 | Framed Baluster Checklist
Level 4
|  | 401 | Framed Baluster Checklist
|  | 402J | Framed Baluster Checklist
|  | 402B | Framed Baluster Checklist
|  | 403 | Framed Baluster Checklist
|  | 404 | Framed Baluster Checklist
|  | 405J | Framed Baluster Checklist
|  | 405B | Framed Baluster Checklist
|  | 406 | Framed Baluster Checklist
|  | 407 | Framed Baluster Checklist
|  | 408 | Framed Baluster Checklist
|  | 409 | Framed Baluster Checklist
|  | 410 | Framed Baluster Checklist
|  | 411 | Framed Baluster Checklist
|  | 412 | Framed Baluster Checklist
|  | 413 | Framed Baluster Checklist
|  | 414 | Framed Baluster Checklist
Level 5
|  | 501 | Framed Baluster Checklist
|  | 502 | Framed Baluster Checklist
|  | 503 | Framed Baluster Checklist
|  | 504 | Framed Baluster Checklist
|  | 505 | Framed Baluster Checklist
|  | 506 | Framed Baluster Checklist
|  | 507 | Framed Baluster Checklist
|  | 508 | Framed Baluster Checklist
|  | 509 | Framed Baluster Checklist
|  | 510 | Framed Baluster Checklist
|  | 511 | Framed Baluster Checklist
|  | 512 | Framed Baluster Checklist
Level 6
|  | 601 | Framed Baluster Checklist
|  | 602 | Framed Baluster Checklist
|  | 603 | Framed Baluster Checklist
|  | 604 | Framed Baluster Checklist
|  | 605 | Framed Baluster Checklist
|  | 606 | Framed Baluster Checklist
|  | 607 | Framed Baluster Checklist
|  | 608 | Framed Baluster Checklist
|  | 609 | Framed Baluster Checklist
|  | 610 | Framed Baluster Checklist
|  | 611 | Framed Baluster Checklist
|  | 612 | Framed Baluster Checklist
Level 7
|  | 701 | Framed Baluster Checklist
|  | 702 | Framed Baluster Checklist
|  | 703 | Framed Baluster Checklist
|  | 704 | Framed Baluster Checklist
|  | 705 | Framed Baluster Checklist
|  | 706 | Framed Baluster Checklist
|  | 707 | Framed Baluster Checklist
|  | 708 | Framed Baluster Checklist
|  | 709 | Framed Baluster Checklist
|  | 710 | Framed Baluster Checklist
Level 8
|  | 801 | Framed Baluster Checklist
Level 9
|  | 900 | Framed Baluster Checklist
Internal
Stairs
|  | Flight 1 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 2 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 3 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 4 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 5 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 6 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 7 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 8 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 9 | Framed Baluster Checklist | Stairs (add to previous if required)
|  | Flight 10 | Framed Baluster Checklist | Stairs (add to previous if required)
Basement
|  | Ramp 1 | Framed Baluster Checklist
|  | Ramp 2 | Framed Baluster Checklist

## Checklists
type | name | values
checklist | Framed and Semi-Framed Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Frameless Glass Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers, Backing Channel and Clamps
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | Install Front covers, Inner and Top Rail and End Caps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Framed Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install posts and Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Postless Baluster Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers and Backing Channel
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Panels
checkpoint | Install Inner and Top Rail and Endcaps
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Frameless Glass arena point Checklist
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type | Wood, Concrete, Steel
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size | 6mm, 8mm, 10mm, 12mm, 14mm
select | Length of Rod/Coach Screw/Bolt Size | 80mm, 90mm, 100mm, 110mm, 120mm, 130mm, 140mm, 150mm, 160mm, 170mm, 180mm, 190mm, 200mm,210mm, 220mm
select | Epoxy Type | Ramset C6, Ramset CX801, Sika Supergrip 2 hour, Zink Galvanising Spray Paint
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Spacers,
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | Install Glass, wedges and glazing rubbers as per PS1
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications
checklist | Stairs (add to previous if required)
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Silicone gaps, Confirm not bigger than 2mm
checkpoint | All work completed, reviewed and approved
checklist | Arena point hand rails
checkpoint | Install J-Mounts, Leada Rail and End Caps
checkpoint | Ends fixed to wall and polished
checkpoint | All work completed, reviewed and approved
checklist | Canopy Panels
checkpoint | Work area acceptable & approval to start work
label | PS1 read and understood
label | PS1 Document number as by Engineer
label | Latest drawings available, checked and referenced
label | Relevant drawings & revisions for reference:
checkpoint | Fixing Details checked
select | Fixing Substrate Type
checkpoint | Setout as per CAD drawings
checkpoint | Position materials and mark drill points
text | Drill depth
select | Threaded Rod/Coach Screw/Bolt Size
select | Length of Rod/Coach Screw/Bolt Size
select | Epoxy Type
checkpoint | Neoprene Gasket Installed as per PS1
checkpoint | Install Panels
checkpoint | Confirm Plumb/level/Square final positions
checkpoint | All work completed, reviewed and approved
label | Area left clean & tidy (Photo Required)
label | Works meet PS1 specifications