## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Earthworks Cut 01 | itp |  |  |  |  | ITP - Earthworks Cut 01 Rev 1
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personnal starting work
label | Conformance Criteria - Ensure all crew members are briefed on the CWP
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.02 - IFC issued
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Approved SCWMP
label | Specifications and Standards - Consent conditions
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - TRC review and approval
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint | 1.04 - Investigation Anchorage testing
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693 Clause 7.2.2
label | ○ MMA-DES-GEO-E1-SPC-9349 Clause 5.9.2
label | Method/Description - Test
label | Test frequency - Pre-construction
label | Conformance Criteria - See table
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Anchorages
label | Specifications and Standards - MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Approval
label | Test frequency - Prior to commencing
label | Conformance Criteria - Material Approval if deviating from design
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.02 - Headworks
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693 Clause 5.2
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Conformance Criteria - Material Approval if deviating from design
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.03 - Grout
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693 Clause 5.5
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Conformance Criteria - Material Approval if deviating from design
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.04 - Erosion Control Mesh / Drapery Mesh / Active Mesh
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693 Clause 5.3
label | ○ MMA-DES-GEO-E1-SPC-9349 Clause 5.1
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Conformance Criteria - See table
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.05 - Boundary Cables
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 5.2
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Conformance Criteria - See table
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.06 - Wire Rope Fittings
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 5.3
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Submit
label | Test frequency - Prior to commencing
label | Conformance Criteria - Designer approval
label | ○ Receipt of all required Quality Assurance and Verification Testing documentation from the manufacturer(s) / supplier(s), including assessment of corrosion protection applicability.
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Material Approval if deviating from design
checkpoint | 2.07 - Delivery of all Slope Stabilisation system components
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 5
label | Method/Description - Visual
label | Test frequency - Each delivery
label | Conformance Criteria - Check all materials delivered to site, collect dockets for each delivery
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Delivery Docket, Material Inspection Checklist
section | 3.0 During Construction
checkpoint | 3.00 - Set out extents
label | Specifications and Standards - IFC drawings
label | Method/Description - Survey/visual
label | Test frequency - Prior to Commencement
label | Conformance Criteria - Consistent with latest IFC drawings and marked out within specification tolerances
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Survey record, GPS model, DSR reports
checkpoint | 3.01 - Verify Machine Control
label | Specifications and Standards - IFC drawings
label | Method/Description - Survey/visual
label | Test frequency - Daily
label | Conformance Criteria - Consistency with datums
label | Contractor - W
label | Verifying Records Checklists, Test and Supplier Certificates - Plant Pre Starts
checkpoint | 3.02 - Assess Crest detail
label | Specifications and Standards - IFC drawings
label | ○ Relevant CPSA
label | Method/Description - Hand augers/ slope assess/Window Samples
label | Test frequency - Prior to Excavation
label | Conformance Criteria - Consistency with latest IFC Construction Drawings
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - DSR reports, CPSA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.03 - Set out Ground Nails
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Survey/Visual and Geo walk over
label | Test frequency - Prior to drilling
label | Conformance Criteria - Designer to confirm set out
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Set Out Inspection Checklist, DSR reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.04 - Install crest detail - Ground Nailing
label | Specifications and Standards - MMA-DES-GEO-E1-DRG-4021 to 4032
label | ○ MMA-DES-GEO-E1-SPC-32693
label | ○ Relevant CPSA
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Conformance Criteria - Designer to confirm extents of ground nailing
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Ground Nail Checksheet, DSR Reports
checkpoint | 3.05 - Install crest detail - Erosion Matting
label | Specifications and Standards - MMA-DES-GEO-E1-DRG-4021 to 4032
label | ○ MMA-DES-GEO-E1-SPC-32693
label | ○ Relevant CPSA
label | Method/Description - Visual Inspection
label | Test frequency - Prior to cutting rock slope
label | Conformance Criteria - Designer to confirm extents of erosion matting
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Ground Nail Checksheet, DSR Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.06 - Set out Rockfall Drapery Anchors
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Survey/Visual and Geo walk over
label | Test frequency - Prior to drilling
label | Conformance Criteria - Designer to confirm set out
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Set Out Inspection Checklist, DSR reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.07 - Install Rockfall Drapery Anchors
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Drill and grout records. Stressing records.
label | Test frequency - During construction and at end
label | Conformance Criteria - Signed Rock Drape Checksheet
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Sub Contractor QA Records, Rock Drape Checksheet, DSR Reports
checkpoint | 3.08 - Install Rockfall Drapery Mesh
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349
label | ○ MMA-DES-GEO-E1-DRG-4021 to 4032
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Conformance Criteria - Geobrugg TECCO Product manual
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Rock Drape Checksheet, DSR Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.09 - Cut Face inspection - Cut Face inspection
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
label | ○ And latest IFC drawings
label | Method/Description - Survey check by construction team, visual inspection by designer.
label | Test frequency - 100m2 or maximum 5m vertical cut
label | Conformance Criteria - Surveyor to confirm cut slope profile is within specification tolerances.
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Survey scan, DSR reports
checkpoint | 3.10 - Cut Face inspection - Cut face material verification - Geo mapping
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
label | ○ And latest IFC drawings
label | Method/Description - Geo inspection and face mapping
label | Test frequency - At soil-rock interface, each Each 100m2 or maximum 5m vertical cut
label | Conformance Criteria - Designer to confirm ground conditions are in accordance with design. If not confirm remedial works required.
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - DSR reports, Face map from geotechnical engineer/geologist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Catch Ditch Inspection
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-3859
label | ○ And latest IFC drawings
label | Method/Description - Visual inspection
label | Test frequency - During construction and at end
label | Conformance Criteria - Catch ditch to be consistent with IFC drawings
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - DSR Report
section | 4.0 Post Construction
checkpoint | 4.01 - Production nail acceptance tests
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-32693 Clause 7.3
label | Method/Description - Test
label | Test frequency - At Completion
label | Conformance Criteria - Designer to confirm approval
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Production drape anchorage acceptance tests
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 5.9.3
label | Method/Description - Test
label | Test frequency - At Completion
label | Conformance Criteria - Designer to confirm approval
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Throughout construction period prior to road opening
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 4.3 Table 1 & Clause 5.9.4
label | Method/Description - Monitor
label | Test frequency - At least once during construction, A minimum of 5% of the rockfall drapery system anchors shall be monitored throughout the construction period prior to road opening
label | Conformance Criteria - Designer to confirm anchorage performance is satisfactory
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Monitoring report, photographic
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Red Line Mark Up Drawings
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 4.3 Table 1
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Red Line Mark Up Drawings
checkpoint | 4.05 - Operation and maintenance report
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 4.3 Table 1
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Client - R
label | Verifying Records Checklists, Test and Supplier Certificates - Operation and maintenance report
checkpoint | 4.06 - Final Handover Package
label | Specifications and Standards - MMA-DES-GEO-E1-SPC-9349 Clause 4.3 Table 1
label | Method/Description - Submit
label | Test frequency - At Completion
label | Contractor - H
label | Designer - R
label | Client - R
label | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE