## ITP Summery
Job | 2025-08 NPWS Bridge Comp 10M &12M | values | Check list | options
checklist-sectioned | Precast Components ITP
section | Documentations
checkpoint | Special Instructions |  |  | attachments/photos/Sign
checkpoint | approved Shop Drawings |  |  | attachments/photos/Sign
tick Box | 4.2m Wide Deck Panels (DP)
tick Box | Abutment Base (UB)
tick Box | Upper Wall (UW)
checkpoint | Other |  |  | attachments/photos/Sign
section | Job Approval Documents/Construction Documents
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction" |  | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | Formwork |  |  | attachments/photos/Sign
checkpoint | Reinforcement(Reo) |  |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  |  | attachments/photos/Sign
checkpoint | Lift Procedure
checkpoint | Concreting (mix design |  |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  |  | attachments/photos/Sign
Repeating items
This is a General Section
No repeating Items

## Deck Panel Type B-12M
Checkers Checklist - Type B-12M- Bridge Plank
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double Check the Ferrule placment -Type BB | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check,allignment check -150mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel length check, allignment check -4500mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Diaganal length check, allignment check | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcement (Reo) placed, cleaned, tightned | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photoes/Coments
Installers Checklist - Type B-12M- Bridge Plank
section | Job Aproval Documents/Constrction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - 2.5T - 04 | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Ferrules - M20 x 96mm - 10 | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photoes/Coments | Repeating items
text box |  |  |  | 12MDP-B01
section | Pre-Pour Check Approvals |  |  | 12MDP-B02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B03
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B04
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B05
checkpoint | Double Check the Ferrule placment -Type BB | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B06
checkpoint | Reinforcment Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B07
checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B08
tick box | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos |  |  | 12MDP-B09
tick box | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  |  | 12MDP-B10
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photoes/Coments | 12MDP-B11
section | Quality Assuarance |  |  | 12MDP-B12
checkpoint | QA - Final Check of ALL measurerments | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged | Pass/Fail/NA | attachments/photoes/Coments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photoes/Coments

## Abutment Base Type B-12M
Checkers Checklist - Abutment Base -Type B-12M
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -4400x800mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - Type B-12M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  | 12MAB-B01
section | Pre-Pour Check Approvals | Pass/Fail/NA | attachments/photos/Comments | 12MAB-B02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embeded Items - Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/Comments
tick box | Ferrules - Position,Size,Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
tick box | Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
tick box | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments

## Upper Wall Type B-12M
Checkers Checklist - Upper Wall -Type B-12M
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 694mm
dropdown |  | 582mm
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -5000x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (5034 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Upper Wall l -Type B-12M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  |  | 12MUW-B01
section | Pre-Pour Check Approvals |  |  |  | 12MUW-B02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type BB Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 694mm
dropdown |  | 582mm
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
tick box | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Deck Panel Type A-10M
Checkers Checklist - Type A-10M- Bridge Plank
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double Check the Ferrule placment -Type AA | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check,allignment check -150mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel length check, allignment check -4500mm | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Diaganal length check, allignment check | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcement (Reo) placed, cleaned, tightned | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photoes/Coments
Installers Checklist - Type A-10M- Bridge Plank
section | Job Aproval Documents/Constrction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - 2.5T - 04 | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Ferrules - M20 x 96mm - 10 | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photoes/Coments | Repeating items
text box |  |  |  | 10MDP-A01
section | Pre-Pour Check Approvals |  |  | 10MDP-A02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A03
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A04
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A05
checkpoint | Double Check the Ferrule placment -Type AA | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A06
checkpoint | Reinforcment Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A07
checkpoint | Lifters, Ferrules Fixed Firm & alligned -Check | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A08
tick box | Embeded Item - Ferrules - Position,Size,Orientation -M20 (96mm) - 10Nos |  |  | 10MDP-A09
tick box | Embeded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal |  |  | 10MDP-A10
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photoes/Coments | 10MDP-A11
section | Quality Assuarance |  |  | 10MDP-A12
checkpoint | QA - Final Check of ALL measurerments | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged | Pass/Fail/NA | attachments/photoes/Coments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photoes/Coments

## Abutment Base Type A-10M
Checkers Checklist - Abutment Base -Type A-10M
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube to form VOIDS - Position, Size -50mm Dia ,300mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -4400x800mm | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (4472 mm or close to this) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Abutment Base - Type A-10M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  | 10MAB-A01
section | Pre-Pour Check Approvals | Pass/Fail/NA | attachments/photos/Comments | 10MAB-A02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embeded Items - Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/Comments
tick box | Ferrules - Position,Size,Orientation -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
tick box | Ferrules for Dowels - Position, Size -M24 (96mm) | Pass/Fail/NA | attachments/photos/Comments
tick box | Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments

## Upper Wall Type A-10M
Checkers Checklist - Upper Wall -Type B-12M
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 694mm
dropdown |  | 582mm
checkpoint | Overall Measurements of construction Element |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double check ferrules are firmly positioned & Fixed with Reo |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel Thickness check,allignment check -150mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Panel length check, alignment check -5000x800mm |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Diagonal length check, alignment check (5034 mm or close to this) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photos/Comments
Installers Checklist - Upper Wall l -Type B-12M
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Eye Anchor - 2.5T(170mm) - 04 |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | ID Plate |  | Pass/Fail/NA | attachments/photos/Comments | Repeating items
text box |  |  |  |  | 10MUW-A01
section | Pre-Pour Check Approvals |  |  |  | 10MUW-A02
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Double Check the Ferrule placement -Type AA Wall Height - |  | Pass/Fail/NA | attachments/photos/Comments
dropdown |  | Other
dropdown |  | 694mm
dropdown |  | 582mm
checkpoint | Reinforcement Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item - Lifters, Ferrules Fixed Firm & aligned -Check |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item -75x75x8EA galvanized Edge strip - Position,Size,Orientation-4000mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Grout Tube - Position, Size -50mmDia ,290mm |  | Pass/Fail/NA | attachments/photos/Comments
tick box | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T(170mm)
tick box | Embedded Item - Edge Lifters Correct - Position,Size,Orientation-as per the site requirement |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Concrete cover Check - minimum 30mm |  | Pass/Fail/NA | attachments/photos/Comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER |  | Pass/Fail/NA | attachments/photos/Comments
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged |  | Pass/Fail/NA | attachments/photos/Comments
dropdown | Fine finish
dropdown | Broom finish
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photos/Comments

## Sheet5 (hidden)
Repeating items | FFBP-A1 | FFBP-B1
| FFBP-A2 | FFBP-B2
| FFBP-A3 | FFBP-B3
| FFBP-A4 | FFBP-B4
| FFBP-A5 | FFBP-B5
| FFBP-A6 | FFBP-B6
| FFBP-A7 | FFBP-B7
| FFBP-A8 | FFBP-B8
| FFBP-A9 | FFBP-B9
| FFBP-A10 | FFBP-B10
| FFBP-A11 | FFBP-B11
| FFBP-A12 | FFBP-B12
| FFBP-A13 | FFBP-B13
| FFBP-A14 | FFBP-B14
| FFBP-A15 | FFBP-B15
| FFBP-A16 | FFBP-B16
FFBP-B17
FFBP-B18
FFBP-B19
FFBP-B20
FFBP-B21
FFBP-B22
FFBP-B23
FFBP-B24
FFBP-B25
FFBP-B26
FFBP-B27
FFBP-B28
FFBP-B29
FFBP-B30
FFBP-B31
FFBP-B32