## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | FHC-ITP-006 - Class 3 Crushed Rock | itp |  |  |  |  | FHC-ITP-006 - Class 3 Crushed Rock Rev4
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — Using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Material Mix Design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175
label | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.3 Material Approval
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: Material intended for use is to be submitted to the client prior to placement to verify it conforms to required specifications.
label | REFERENCE DOCUMENTS: Material specification sheets
label | INSPECTION/TEST METHOD: Verfiy
label | RECORD OF CONFORMITY: Teambinder Acceptance
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Longitudinal joints offset from one layer to next by not less than 150mm. Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: . Cl.304.08 (b)(ii), Table 304.111
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP, Delivery Dockets
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Layer Thickness
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm. The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | REFERENCE DOCUMENTS: Cl 304.08(b)(v), Cl 304.08(b)(vi)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.5 Proof Rolling
label | FREQUENCY: Proof Roll each layer
label | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
label | REFERENCE DOCUMENTS: 173.03
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP/ WP
label | RESPONSIBILITY: Site Engineer & Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Testing Requirements
checkpoint | 3.1 Determine Testing Scale & Initial Testing Frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification. Testing of every lot shall continue until three consecutive lots of like material and/or work have achieved the standards specified.
label | ○ Scale B - The first lot of each pavement course shall be tested for post-compaction grading and PI. If the first lot each pavement course satisfies the specified post compaction requirements in Clause 304.10(a) and (b), as applicable, no further post-compaction testing will be required for that pavement course.
label | REFERENCE DOCUMENTS: Table 204.161, Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i), Table 304.111
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | AP
label | RESPONSIBILITY: Project Engineer
textbox | Date Completed:
checkpoint | 3.2 Compaction Testing
label | FREQUENCY: Every Lot, Every second lot (reduced frequency)
label | ACCEPTANCE CRITERIA: Minimum Characteristic Density Ratio (CDR) of not less than 98%, using Modified compaction effort.
label | REFERENCE DOCUMENTS: Cl304.08, Table 3040.061, Cl 304.11 (b), Table 304.111
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.3 Compaction Testing (Small Lots)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Any lot which has a surface area less than 500 m2 may be treated as a small area. Acceptance of the lot shall be based on the mean values of 3 individual tests. Minimum Compaction shall be 100% modified compaction effort.
label | REFERENCE DOCUMENTS: 173.04 d
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.4 Material Grading - Post Compaction
label | FREQUENCY: First Lot Only
label | ACCEPTANCE CRITERIA: Post compaction material grading results must comply with the following:
label | ○ Class 4 - As per Table 304.101 - VR Spec. 304.10
label | ○ Class 3 - As per Table 304.101 - VR Spec. 304.10
label | ○ Class 2 - As per Table 304.101 - VR Spec. 304.10
label | REFERENCE DOCUMENTS: Cl 304.101, Cl 304.111
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.5 Plasticity Index - Post Compaction
label | FREQUENCY: First Lot Only
label | ACCEPTANCE CRITERIA: Post compaction PI results must comply with the following:
label | ○ Class 4 - 0 to 10
label | ○ Class 3 - 0 to 10
label | ○ Class 2 - 0 to 6
label | REFERENCE DOCUMENTS: Cl 304.10, Cl 304.11, Table 304.103
label | INSPECTION/TEST METHOD: Test point
label | RECORD OF CONFORMITY: This ITP signed off; Test reports
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.6 Survey Conformance
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
label | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
label | Surface level tolerances:
label | ○ Range x = +6, -16mm
label | ○ Max S = 15 mm
label | ○ 40 measurements per lot (Minimum)
label | REFERENCE DOCUMENTS: Cl 304.06(b, d, i) Drawings, Table 304.062
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP signed off; Survey Report, Lot Markup
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
checklist | FHC-ITP-013 - General Concrete Paving | itp |  |  |  |  | FHC-ITP-013 - General Concrete Paving Rev2
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Submission & Approval of Concrete Mix Design
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
label | REFERENCE DOCUMENTS: 610.07(b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Mix design approval in teambinder
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.3 Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | REFERENCE DOCUMENTS: 703.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.4 Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
label | ○ 100mm thick layer of 20mm Class 3 crushed rock bedding for median infill
label | ○ 150mm thick layer of 20mm Class 4 crushed rock bedding for footpath/pram crossing
label | ○ Bedding trimmed, moistened, and compacted as per Section 304
label | REFERENCE DOCUMENTS: 703.21 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: 703.12, AS 3610
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL82 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
label | REFERENCE DOCUMENTS: 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.7 Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | REFERENCE DOCUMENTS: 703.05(a), 703.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Surface Finish
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces in accordance with AS 3610.
label | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.9 Pram Crossings
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | — For pram crossings within concrete kerb refer to Figure 24A of AS 1428.1
label | REFERENCE DOCUMENTS: Figure 24A AS1428.1 Design Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 2.10 Joints
label | FREQUENCY: Each Joint
label | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
label | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
label | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 2.11 Protection of concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | REFERENCE DOCUMENTS: 703.27
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.12 Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
label | REFERENCE DOCUMENTS: 703.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 2.13 Ambient Weather
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for limits, restrictions and treatments to be applied for concreting in hot, cold and wet weather, except that curing shall be in accordance with clause 703.10.
label | REFERENCE DOCUMENTS: 610.17(a), 610.17(b), 610.17(c), 610.17(d), 703.09
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Carry out sampling of concrete - strength and consistency
label | FREQUENCY: Each 50m3
label | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | REFERENCE DOCUMENTS: 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: ITP Signed/Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 3.2 Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | Section dimensions shall be constructed within the following tolerances:
label | ○ 5mm and 15mm for width; or
label | ○ ±3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
textbox | Date Completed:
checkpoint | 3.3 Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
label | ○ Topsoil compacted in layers < 150mm
label | ○ Width ≥ 300mm behind edging to top of edging
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: