## Table 1
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-ZU2-QU-ITP036 REV: 0
Client: Melbourne Airport | [7 empty] | Contract No: CP14038-01 | [9 empty] | Prepared By: Jamal Khodr
Project: Taxiway Zulu | [13 empty] | Reviewed By: Jamal Khodr | [7 empty] | Date: 25/11/2024
Construction Process: ALER 3 Mechanical | [13 empty] | Approved By: Marco Poggenberg | [7 empty] | Date:
Specifications: ZULU-BECA-001-SPC-00005, Drawings
Structure / Component: Mechanical works
Lot No: |  | Lot Details: | [9 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. |  | Task/Activity Description |  | Inspection/Test | [13 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility | Checked by:
|  |  |  | Frequency |  |  | Acceptance Criteria |  |  | Reference Documents |  |  | Inspection/ Test Method |  | Record of conformity |  |  |  |  | Project Engineer Principal’s Rep. Surveyor Foreman | Principal’s Rep. |  |  | FH | Date
1 |  | Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
1.1 |  | Check for correct documentation |  | Prior to commencing activity |  |  | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings. - all drawings are the latest revision. |  |  | Drawings / Aconex Register |  |  | Verify |  | Drawings and drawing registers |  |  | HP* |  | Project Engineer
1.2 |  | Implementation of all measures and controls |  | Prior to commencing activity |  |  | All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP. |  |  | PSP, EMP, TMP, JSEA, SWMS, WP |  |  | Visual inspection |  | This ITP signed |  |  | HP* |  | Project Engineer
1.3 |  | Survey Checks |  | Prior to commencing activity |  |  | Survey set out to be completed for all assets |  |  | Drawings |  |  | Verify |  | This ITP signed |  |  | HP* |  | Project Engineer / Surveyor
1.4 |  | Submission & approval of shop drawings |  | Prior to commencing activity |  |  | HOLD POINT Submit shop drawings to the principal’s representative for approval prior to fabrication commencement. |  |  | ZULU-BECA- 001-SPC- 00005 Drawings Shop drawings |  |  | Verify |  | Aconex Reference |  |  | HP |  | Project Engineer / Principals Representative
1.5 |  | Material Submissions |  | Prior to commencing activity |  |  | HOLD POINT Items to include but not limited to: - Refer to materials register and list items |  |  | ZULU-BECA- 001-SPC- 00005 Drawings |  |  | Verify |  | Aconex Reference |  |  | HP |  | Project Engineer / Principals Representative
1.6 |  | Temporary Works |  | Prior to commencing activity |  |  | Submission and approval of the following documentation (not limited to): - Certification of Lifting Points - Lift Plan - Certification of Ground Platform for lift - Lifting inserts |  |  | ZULU-BECA- 001-SPC- 00005 Drawings |  |  | Verify |  | Temporary Works Geo Report |  |  | HP* |  | Project Engineer
1.8 |  | Certificates of Compliance |  | Each Lot |  |  | Provide Suppliers Certificate of Compliance and Spatial Certificate of Compliance for  Split system/process cooler air conditioning units.  Control systems. |  |  | ZULU-BECA- 001-SPC- 00005 Drawings C1900.6 |  |  | Verify |  | Supplier’s Certificate of Compliance Spatial Certificate of Compliance (where required) |  |  | HP*
2 |  | Construction
2.1 |  | Delivery of Materials to site |  | Each Lot |  |  | Inspection of materials whilst still loaded on the truck prior to accepting the delivery on site. Identify any damage/defects prior to unloading of the material. |  |  | ZULU-BECA- 001-SPC- 00005 Drawings |  |  | Visual Inspection |  | This ITP Signed Materials Inspection Checklist on Conqa |  |  | IP |  | Project Engineer / Site Engineer
2.11 |  | Pipework installation – General and Refrigeration |  | Each Lot |  |  | Confirm the following items are constructed in accordance with IFC design and specification. ○ Brass fittings ○ Mechanical joints/couplings ○ Bends/Branches ○ Sleeves ○ Drains ○ Escutcheons ○ Pipe Supports |  |  | ZULU-BECA- 001-SPC- 00005, C1910, C1912, Drawings, AS 4041, AS 1432 |  |  | Visual Inspection |  | This ITP Signed Building Eng ITP |  |  | IP |  | Project Engineer / Site Engineer
2.12 |  | Ductwork Installation |  | Each Lot |  |  | Confirm the following items are constructed in accordance with IFC design and specification. ○ Ducts ○ Duct Sealing ○ Bends, tees, transitions, ○ Test holes for commissioning ○ Outdoor air intakes and exhausts ○ Duct and fan Intakes ○ Duct support and restraint ○ Access hatches ○ Balancing/motorised dampers ○ Smoke and fire dampers |  |  | ZULU-BECA- 001-SPC- 00005, C1940 Drawings, AS 4254 |  |  | Verify |  | This ITP Signed Building Eng ITP |  |  | IP |  | Project Engineer / Site Engineer
2.13 |  | Mechanical Components Installation |  | Each Lot |  |  | Confirm the following items are constructed in accordance with IFC design and specification. ○ Split system air-conditioning/heat pump units ○ Grilles, diffusers, louvres ○ Fans ○ Filters ○ Insulation ○ Vibration Isolation |  |  | ZULU-BECA- 001-SPC- 00005 Drawings |  |  | Visual Inspection |  | This ITP Signed Building Eng ITP |  |  | IP |  | Project Engineer / Site Engineer
2.19 |  | Survey As Built |  | Prior to Covering Services |  |  | Survey to pick up services prior to covering |  |  | FH QMP |  |  | Verify |  | Survey |  |  | IP |  | Project Engineer/Survey or
[6 empty] | Inspection and Test Plan - Control and Supervision of the Works | [16 empty] | Doc ID: FH-ZU2-QU-ITP036 REV: 0
| Client: Melbourne Airport | [7 empty] | Contract No: CP14038-01 | [9 empty] | Prepared By: Jamal Khodr
| Project: Taxiway Zulu | [13 empty] | Reviewed By: Jamal Khodr | [7 empty] | Date: 25/11/2024
| Construction Process: ALER 3 Mechanical | [13 empty] | Approved By: Marco Poggenberg | [7 empty] | Date:
Specifications: ZULU-BECA-001-SPC-00005, Drawings
Structure / Component: Mechanical works
Final Inspection The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point | Work shall not proceed past the HP until released by the Principal’s Representative | [6 empty] | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
| WP |  | Witness Point | An inspection which must be witnessed by the Principal’s Representative | [6 empty] | SCP |  | Survey conformance point |  |  |  | A qualified surveyor to check product/section/structure and report
| AP |  | Approval Point | Written or verbal approval given by the Principal’s Representative
Notes