## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP036 - ALER 3 Mechanical | itp |  |  |  |  | FH-ZU2-QU-ITP036 - ALER 3 Mechanical - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings.
label | — all drawings are the latest revision.
label | Reference Documents - Drawings / Aconex Register
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.3 - Survey Checks
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Survey set out to be completed for all assets
label | Reference Documents - Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 1.4 - Submission & approval of shop drawings
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | ○ Submit shop drawings to the principal’s representative for approval prior to fabrication commencement.
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings, Shop drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Material Submissions
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - HOLD POINT
label | Items to include but not limited to:
label | — Refer to materials register and list items
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project Engineer / Principals Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Temporary Works
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Submission and approval of the following documentation (not limited to):
label | — Certification of Lifting Points
label | — Lift Plan
label | — Certification of Ground Platform for Lift
label | — Lifting inserts
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings
label | Inspection/Test Method - Verify
label | Record of conformity - Temporary Works Geo Report
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.8 - Certificates of Compliance
label | Frequency - Each Lot
label | Acceptance Criteria - Provide Suppliers Certificate of Compliance and Spatial Certificate of Compliance for
label | ○ Split system/process cooler air conditioning units.
label | ○ Control systems.
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings C1900.6
label | Inspection/Test Method - Verify
label | Record of conformity - Supplier’s Certificate of Compliance, Spatial Certificate of Compliance (where required)
label | HP*
label | Responsibility -
date | Date Completed:
section | 2.0 - Construction
checkpoint | 2.10 - Delivery of Materials to site
label | Frequency - Each Lot
label | Acceptance Criteria - Inspection of materials whilst still loaded on the truck prior to accepting the delivery on site.
label | ○ Identify any damage/defects prior to unloading of the material.
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Materials Inspection Checklist on Conqa
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.11 - Pipework installation – General and Refrigeration
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm the following items are constructed in accordance with IFC design and specification.
label | ○ Brass fittings
label | ○ Mechanical joints/couplings
label | ○ Bends/Branches
label | ○ Sleeves
label | ○ Drains
label | ○ Escutcheons
label | ○ Pipe Supports
label | Reference Documents - ZULU-BECA- 001-SPC-00005, C1910, C1912, Drawings, AS 4041, AS 1432
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Eng ITP
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.12 - Ductwork Installation
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm the following items are constructed in accordance with IFC design and specification.
label | ○ Ducts
label | ○ Duct Sealing
label | ○ Bends, tees, transitions,
label | ○ Test holes for commissioning
label | ○ Outdoor air intakes and exhausts
label | ○ Duct and fan Intakes
label | ○ Duct support and restraint
label | ○ Access hatches
label | ○ Balancing/motorised dampers
label | ○ Smoke and fire dampers
label | Reference Documents - ZULU-BECA- 001-SPC-00005, C1940 Drawings, AS 4254
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed Building Eng ITP
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.13 - Mechanical Components Installation
label | Frequency - Each Lot
label | Acceptance Criteria - Confirm the following items are constructed in accordance with IFC design and specification.
label | ○ Split system air-conditioning/heat pump units
label | ○ Grilles, diffusers, louvres
label | ○ Fans
label | ○ Filters
label | ○ Insulation
label | ○ Vibration Isolation
label | Reference Documents - ZULU-BECA- 001-SPC-00005 Drawings
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP Signed, Building Eng ITP
label | IP
label | Responsibility - Project Engineer / Site Engineer
date | Date Completed:
checkpoint | 2.19 - Survey As Built
label | Frequency - Prior to Covering Services
label | Acceptance Criteria - Survey to pick up services prior to covering
label | Reference Documents - FH QMP
label | Inspection/Test Method - Verify
label | Record of conformity - Survey
label | IP
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: