## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | ST - S - Rib & Infill Installation | 1bd084fa-0851-4ad3-80bc-b1e8ac307b8f
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Ribs inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Infill boards inspected on arrival. No knots, no cracks or other weaknesses across 25% of the width.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" and attached.
checkpoint-status |  |  | checkpoint | Area cleared for propping to be
checkpoint-status |  |  | checkpoint | Structural Steel Brackets fitted and fixed (correct height and as per design)
checkpoint-group |  |  | section | Propping/Falseworks
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Props tagged and fixings as per approved design.
checkpoint-status |  |  | checkpoint | U Head brackets rotated to support bearers, bearers clipped to U head brackets.
checkpoint-status |  |  | checkpoint | All back propping completed, checked and approved as per design
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Inspect against rib install and propping layout drawings. Mark up hard copy drawings accordingly and upload to this checkpoint to verify the specification has been met.
checkpoint-status |  |  | checkpoint | No visual damage to ribs
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Rib Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill boards tightly constructed as panels, including 'backbone', 6 to 10 boards in length.
checkpoint-status |  |  | checkpoint | Infill panels fitted tightly between ribs.
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined.
checkpoint-status |  |  | checkpoint | Infill panels locked with timber blocks to prevent lateral movement.
checkpoint-status |  |  | checkpoint | Infill boards secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-status |  |  | checkpoint | All gaps filled, infills installed, PF rod/expanding foam installed (No gaps)
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive Infill Panel Installation inspection results. Pass this checkpoint after sending the email.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Foundations) |  |  |  |  | Yes | QA - Concrete Pour (Foundations) | 5610813c-5fd8-4cca-ba77-21ec62277629
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | 691a13df-1c8c-5d3d-8b0c-6ee0dbb17281 |  | textbox | Area to be poured
text | bce64366-063c-5d30-ab23-306d54e142f7 |  | textbox | Date of pour
boolean | 5c74ec5b-fa47-5bd6-8854-dd637e9cdb2c |  | tickbox | Latest drawings available, checked and referenced
boolean | 4a86c2af-d857-5096-b948-9faac5b907c3 |  | tickbox | Marked up drawing of area to be poured completed & attached
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
checkpoint-status |  |  | checkpoint | Cold joints set up correctly
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate, sufficiently fixed in place/braced)
checkpoint-status |  |  | checkpoint | Engineer inspection completed & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Council inspection completed (if required) & any remedial item(s) closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Concrete Supplier Specifics & Test Results
checkpoint-status |  |  | checkpoint | Concrete Supplier Details
text | 76e920fa-dc40-5611-a44c-7218780bc059 |  | textbox | Supplier Name
text | 6617c244-4759-5f48-97cc-fe9fe77139ef |  | textbox | Specified concrete strength
text | a968c132-1a68-5776-b13e-b143db718eca |  | textbox | Concrete strength ordered
text | 7a8a726e-956d-52e5-8fea-d4bb74badd38 |  | textbox | Concrete quantity ordered
button | 8b468d6f-3d23-59e0-a98a-d5b614871151 |  | button | Test blocks booked | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & acceptable
boolean | 4e7fd0fa-8bf4-5c9f-a506-c15556b23259 |  | tickbox | Correct specifications & strength
checkpoint-status |  |  | checkpoint | All concrete dockets photographed & attached here
label | 748b6614-4e8d-5cbd-aa1c-28d42e45695c |  | note | "PASS" only once all concrete dockets relating to this pour have been attached here
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | bbe81248-9168-53d4-8e92-24f7ebd07ff8 |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | 05652d81-f692-59c2-a238-08a5f51c1885 |  | button | 7 day test results recorded | Yes, No, N/A
text | 94ac4f36-e1cc-5706-a5eb-db1b21acc1b6 |  | textbox | 7 day test - strength achieved
button | 345e014f-46ef-5ab1-ae94-8cbb96ad5e85 |  | button | 28 day test results recorded | Yes, No, N/A
text | 57cc9bea-4cce-5123-a760-6b6544f4ad75 |  | textbox | 28 day test - strength achieved
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-status |  |  | checkpoint | Concrete Distribution Details
text | eb0cf9f2-df18-59db-ab36-9f415de28955 |  | textbox | Who is distributing/pumping the concrete
text | 153410a8-d7d7-5cca-923c-303e71655ac4 |  | textbox | How is the concrete distributed
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
checkpoint-group |  |  | section | Concrete Placement
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | ce0a4281-376a-5338-b8c0-8d75de06f4e5 |  | textbox | Who is placing the concrete
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
label | 94f2c557-0b6c-59db-88ef-1d88f8a9e7d0 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
label | 11acad56-807e-5741-9789-8616d04cf518 |  | note | Select "N/A" if there is no remedial work identified
label | 7475ab45-834c-5e43-a5ee-b4e8a0327ab3 |  | note | Select "FAIL" if there is remedial work identified and "PASS" once it has been resolved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
label | 1c25d1dc-baf3-515f-9074-ac3b48bdd0b8 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Formwork |  |  |  |  | Yes | QA - Formwork | 6646e4c8-dc68-4b17-a240-384efa57c855
checkpoint-status |  |  | checkpoint | Fines placed to specification and area clear for polythene
checkpoint-status |  |  | checkpoint | DPM placed correctly
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
boolean | c83760e5-5457-5985-8eaf-8b818dd3ff76 |  | tickbox | Sufficiently braced
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
label | 97735801-369e-5907-8059-3ede8c6efd4b |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | QA - Insitu Stich Joints |  |  |  |  | Yes | QA - Insitu Stich Joints | 66cbbf06-2e8e-4229-b0da-67322341f84f
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour Details Recorded
text | e53b2b1d-7132-5131-a600-f7063234d285 |  | textbox | Area to be poured:
text | 2cc799ba-1314-5151-a142-c98b68883db5 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Formwork braced & fixed correctly
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Size and type correct to specification
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete Strength Test Records
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | ST - S - Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - S - Precast Shell Beam Lintel Installation | 6f1fed76-9851-40d7-9d4c-60ec92321cbc
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | SYS - Compliance Documentation Checklist |  |  |  |  | Yes | SYS - Compliance Documentation Checklist | 7e252aa9-25f9-44f2-b3eb-67297ba8f320
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 4a7b40b2-5634-5962-ab52-aacc86a690c0 |  | button | PS3 - Completed and Attached | Yes, N/A
button | eaecc651-73b2-5a96-a295-977eaa73d355 |  | button | LBP Memorandum/ Record of works | Yes, N/A
button | eac5a8cc-0bef-5b41-9964-fc1b19c0d071 |  | button | Concrete Test Results & Mill Certs | Yes, N/A
button | abb4b4f7-afbd-555f-9396-f725920e61aa |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | 4ba5b2ac-08b5-5bb1-8592-8d15cc6597eb |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | QA - Concrete Pour (Blockwork Footings) |  |  |  |  | Yes | QA - Concrete Pour (Blockwork Footings) | 815b7eb0-b3c3-4905-b078-a8471ab3adf5
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
label | 96330318-2a10-59f0-a5ca-d69b1bde53a8 |  | note | Size and type correct to specification
label | 41f5d3a6-e21f-582b-845d-50ea8f05d115 |  | note | Reinforcing spacing and location correct
label | f2777ffb-8bd9-5f74-ab4d-b496f2b27e45 |  | note | Specified covers checked/correct
label | abbdf7f1-30d7-51b5-a4c3-b843fbc1c787 |  | note | Splice laps checked/correct
label | 4fd5626a-f66f-54f4-ac34-dbbd3a8f93ff |  | note | Any starter bars are installed correctly (location, size and spacing )
label | 5d2ca0c1-e2e1-54d3-8b9d-a13eead73031 |  | note | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Pre Pour completed - Approval to pour
label | a95052b1-2749-5aa0-adea-b683227c68b2 |  | note | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | bc2b58b5-4302-5d94-924a-dd9ac77d7c0f |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | 8a06dcc9-c184-58fc-97c4-6d9581cd4a82 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ST - S - Precast Wall Panel Installation |  |  |  |  | Yes | ST - S - Precast Wall Panel Installation | 959588b9-239d-460a-9788-0ed35b0cd862
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and Braces to be tagged
checkpoint-status |  |  | checkpoint | Grout sleeves correctly grouted
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checklist-flat |  |  | checklist | ST - S - Precast Wall Bracket Installation |  |  |  |  | Yes | ST - S - Precast Wall Bracket Installation | 96a60d3d-2550-4ddb-98ca-f153417f2f91
checkpoint-status |  |  | checkpoint | Bracket correct size as per drawing
checkpoint-status |  |  | checkpoint | Cast in weld plate in correct position
checkpoint-status |  |  | checkpoint | Adequately braced and braces to be tagged
checkpoint-status |  |  | checkpoint | Bracket installed in correct position, plumb and level
checkpoint-status |  |  | checkpoint | Welding inspected and correct as per drawing
checkpoint-status |  |  | checkpoint | Paint repair completed
checkpoint-status |  |  | checkpoint | Bracket installation completed correctly (checked location & level)
checklist-flat |  |  | checklist | QA - Reinforcing |  |  |  |  | Yes | QA - Reinforcing | 9e4c9065-0308-4a33-816c-dda476cf667d
checkpoint-status |  |  | checkpoint | Correct drawings referenced and attached
checkpoint-status |  |  | checkpoint | Construction Joint (location, Roughened and clean)
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | All couplers/flange nuts installed correctly (if reid bar couplers have been used, has epconC8 epoxy been used as specified)
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size, length and spacing)
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Area cleaned and all debris removed
checkpoint-status |  |  | checkpoint | Consideration for welding certificates (sited and attached)
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved (including couplers & flange nuts)
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
label | f43bec88-fcae-5663-a526-7ce6d830d187 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ST - S - Precast Edge Beams Installation |  |  |  |  | Yes | ST - S - Precast Edge Beams Installation | b172d5bd-f71e-42dc-92db-3960514bf01a
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Edge Beams installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | ST - S - Precast Flat Slab Installation |  |  |  |  | Yes | ST - S - Precast Flat Slab Installation | cce84209-6089-446d-aee8-6f35bff04161
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | ST - S - Precast Beam Installation |  |  |  |  | Yes | ST - S - Precast Beam Installation | d1091901-54ad-4e7e-8e87-64ba6930b721
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Beam Installation completed (checked location & level) and no damages
checklist-sectioned |  |  | checklist | QA - Blockwork |  |  |  |  | Yes | QA - Blockwork | d92f7fe1-0879-4bbf-9ed4-0e60a773d3fa
checkpoint-group |  |  | section | Blockwork Setout/Pre Start QA
checkpoint-status |  |  | checkpoint | Grids available for reference and base of wall marked accurately
checkpoint-status |  |  | checkpoint | RL reference/TOW confirmed
checkpoint-status |  |  | checkpoint | Starter bars correct (location, length and strength)
checkpoint-status |  |  | checkpoint | Concrete/footing clean, tidy and level (ready for first course)
checkpoint-status |  |  | checkpoint | Blockwork reinforcing steel delivered correct and accessible (attach photos of respective reinforcing docket)
checkpoint-status |  |  | checkpoint | Any additional pre start observations
checkpoint-status |  |  | checkpoint | Approval given to start laying blockwork
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pre Pour
checkpoint-status |  |  | checkpoint | Base of wall in correct location
checkpoint-status |  |  | checkpoint | Horizontal reinforcing installed correctly (centres/size/splicing etc)
checkpoint-status |  |  | checkpoint | Ties/Control joints installed as required
checkpoint-status |  |  | checkpoint | Vertical reinforcing installed as required with appropriate splice
checkpoint-status |  |  | checkpoint | Openings checked and correct - location, height and width
checkpoint-status |  |  | checkpoint | Washouts correct/openings covered correctly and wall braced adequately (if required)
checkpoint-status |  |  | checkpoint | Any additional observations/inspections attached
checkpoint-status |  |  | checkpoint | Wall built within tolerance - straight, level and to the correct height (Approval to pour)
label | aa26c44b-079c-5eec-89e9-53bda25e6279 |  | note | Mortar Joints installed within tolerances
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Block wall Pour
checkpoint-status |  |  | checkpoint | Any remedial work completed/observations closed out and approval given to pour
checkpoint-status |  |  | checkpoint | Concrete specifications checked and correct - delivery docket(s) photographed
text | b777d635-a655-5f61-8548-6ace6768b61b |  | textbox | Method used to pour concrete (e.g. boom/line pump):
checkpoint-status |  |  | checkpoint | Concrete Strength Test Results Records
label | 81519ca4-73e3-5f6a-ae8c-1d22d6d909e5 |  | note | "PASS" only once all test results required for this pour have been attached here & a satisfactory strength has been achieved
button | 41554a86-c9c0-583e-a4c4-59989006cee3 |  | button | 7 day test results recorded | Yes, No, N/A
text | b059e5d4-4eaa-5480-901c-b2e6d9361b8d |  | textbox | 7 day test - strength achieved
button | 672a10f2-3de3-5b46-bdc8-c3e55aa8086b |  | button | 28 day test results recorded | Yes, No, N/A
text | 042012bc-884e-56fd-b9b7-57b2677521d4 |  | textbox | 28 day test - strength achieved
checkpoint-status |  |  | checkpoint | General photos and any additional observations
checkpoint-status |  |  | checkpoint | All blocks filled to correct height
checkpoint-status |  |  | checkpoint | Starter bars in centre of block (if applicable)
checkpoint-status |  |  | checkpoint | Any concrete spillage/splatter cleaned up
checkpoint-status |  |  | checkpoint | Blockwork wall(s) complete to required specification (2-3 photos uploaded)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | ST - S - Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - S - Precast Spandrel Panel Installation | e2333e6e-7268-41f5-8cd6-b9f0cc4e4f0c
checkpoint-status |  |  | checkpoint | Inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Installed in correct location
checkpoint-status |  |  | checkpoint | Adequately braced and braces are tagged
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
checklist-flat |  |  | checklist | QA - Footing Excavation |  |  |  |  | Yes | QA - Footing Excavation | ee9836ab-042b-415c-8dd3-36cb7b09c81a
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | General Photos / Comments / Observations during excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | 8d53f79f-6456-5556-bac4-cf4a9956bf7c |  | tickbox | Location accurate
boolean | 20c7862d-823d-5733-8ec5-46ff86392af7 |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 68b63e76-8b11-5227-9789-66abd5be1bf7 |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
checkpoint-status |  |  | checkpoint | Excess Material Cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Excavation completed, reviewed and approved
holdpoint |  |  | signoff | Request Signoff