## Clearwater Construction__Kevin
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
a2144dcb-067c-40dc-a29f-742599b23bc5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01
c17e91bf-e529-4b88-a6bf-4f8106030466 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure
d4651d04-bd05-4f87-b95c-60819950865d |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B
b8c89a4d-95b0-4a01-814d-fa55d6999c82 |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Blockwork Footing Excavation
9abfe538-34d7-46eb-8c1e-d440a045b6b8 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Foundation Blockwork Footings
c475bf9c-7dd5-4107-a5fb-28b7823b328e |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Blockwork
2f02a5c5-1861-4329-adf0-3ab751df25c6 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits
847ca6ec-49ca-40cb-827d-1175740340df |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R
5fd52d38-5809-4fb1-8786-abb280e430be |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Lift Pit 1 & Lift Pit 2
07307adb-ccf1-4f3e-8f1f-9f828898245b |  | checklist-sectioned | pass | QA - Insitu Stich Joints | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Lift Pit 1 & Lift Pit 2 | Lift Pit base
f6826779-b6dc-4671-a85c-0760e9a49e2e |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Plat Lift 5
f2419231-2574-4e1d-85e4-f682a7c243a8 |  | checklist-sectioned | pass | QA - Insitu Stich Joints | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Plat Lift 5 | Lift Pit base
0fd694e8-b352-4f14-8afe-7f3aa9cca977 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Floor Slab Pour - Area 1
1c1a6788-3048-4939-bd42-924813181299 |  | checklist-flat | pass | QA - Formwork | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Floor Slab Pour - Area 1 | Formwork
6c09152f-9662-4a2d-bf63-3802a32e0126 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Floor Slab Pour - Area 1 | Reinforcing
0195dd9a-3890-4eb3-a18c-6f7516faea4a |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 1 - Grid Lines V-R | Floor Slab Pour - Area 1 | Concrete Pour
858f43f6-7ced-45ec-aca8-e6423de3c6d6 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L
0f133698-fa8b-4444-bd65-583fd0ea9e3d |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Lift Pit 3
2e3f40cd-ca76-461f-8b41-ef9905037b48 |  | checklist-sectioned | pass | QA - Insitu Stich Joints | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Lift Pit 3 | Lift Pit base
6318d249-1762-4665-a08f-3caa70bd54f0 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Plat Lift 4
43d3031d-1257-48a4-8a1d-1bbccc586ef8 |  | checklist-sectioned | pass | QA - Insitu Stich Joints | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Plat Lift 4 | Lift Pit base
b2ccc8cc-5540-46cc-8b25-e86fab9d0b8d |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Floor Slab Pour - Area 2
7cbba9eb-2949-416d-bf23-e96d79f440b4 |  | checklist-flat | pass | QA - Formwork | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Floor Slab Pour - Area 2 | Formwork
3185a5d0-7bf3-4ea2-b6d4-5569e83db240 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Floor Slab Pour - Area 2 | Reinforcing
a6b17f8a-5271-4235-b46b-a0590a9b6c5e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Slabs and Lift Pits | Area 2 - Grid Lines R-L | Floor Slab Pour - Area 2 | Concrete Pour
7b29ed77-e8d8-4465-8000-7fc2c294b1f5 |  | checklist-sectioned | pass | QA - Insitu Stich Joints | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Columns (6x freestanding)
3e4a97da-fb20-42f4-a88a-0757daa47c24 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Site concrete - strip footings, lift pits and crane base
42855bc2-5954-4430-95e5-6596a363299d |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Site concrete - strip footings, lift pits and crane base | QA - Site Concrete Pour
bcde681d-1f17-4926-bddb-c3c61409475a |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Lint pit
aabc6700-e796-4e95-8020-a8e0a83092dd |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Lint pit | QA - Reinforcing
7e542866-488c-4a80-8f60-9ec12e58543c |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Lint pit | QA - Concrete Pour
9df07be8-00c7-4e49-b8d8-71216bd7e93b |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Site concrete - main slab
5ccd64c6-d7a1-486e-b83f-528d64d7ab61 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Site concrete - main slab | QA - Site Concrete Pour V - R
3d175dfc-066d-41e5-b405-02e2e22035f0 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Site concrete - main slab | QA - Site Concrete Pour R - L
49f32b21-8941-4869-9484-00e7274d3c81 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Foundation Blockwork Footings @ rampway
dae043d9-3a57-4959-88cd-8d9350578506 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Foundation Blockwork Footings @ rampway | QA - Concrete Pour (Blockwork Footings)
325ebc8d-dba4-461f-8aa1-e573bee07090 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Grid # V+ & 12-18 up to Grid # U insitu walls
c2679cb0-8da0-420a-aea1-cf59b807c5ab |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Columns (grid 12)
b85284e5-3ffb-4feb-9483-c69429049685 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Columns (grid 12) | QA - Concrete Pour
8c98583b-0df2-4e3b-a221-55d28799dce8 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Columns (grid 12) | QA - Reinforcing
2b4d713f-a7a1-447a-aab7-d10423933b85 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | 2x columns and stitch joint on grid R+ and M
9ba96735-c382-4a9e-9d4b-7e39d0f3d6f8 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu walls grid V, grid 18 to ~S, grid T
d677033b-f87e-4bc9-932b-552a99d71f1b |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu walls grid V, grid 18 to ~S, grid T | QA - Concrete Pour
6cd78c44-fe74-4989-aef5-2bcd094365c9 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu walls grid V, grid 18 to ~S, grid T | QA - Reinforcing
c3765dd0-a388-425c-8af9-f85a60847b01 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Grid L+ wall
cab7ea06-7055-4009-81a3-6e21a2c14180 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu wall Grid # 12 & 12+
89179f76-810d-4e25-9496-a8399887e777 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu wall Grid # 12 & 12+ | QA - Reinforcing
86e38336-a2a0-480e-b747-8e5d1cccd3b3 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu wall Grid # 12 & 12+ | QA - Insitu wall pour
a9aa51c8-12ab-4d1c-9e4c-aca8d2d124d5 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu wall grid 18 T-R
8339a10b-d35b-4a9f-8f02-39e4d6667492 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Insitu wall grid 18 T-R | QA - Concrete Pour
ffb251c0-aaf7-476f-a01f-3e15de101267 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Area B. In-situ Beam, Q+ beam & 12+ beam and stitch joint
4ad80a76-9bd3-45d3-8fdd-7fb4f286a520 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Area B. In-situ wall Grid 18, N to P
abce7d1a-89e6-4704-9b55-ca9e52f0fa2e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Area B. In-situ wall Grid 13
1819c54a-3c50-4bec-a111-92bdc4a880ae |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Area B. In-situ Beam Grid N
f85fdde8-27fd-45d5-9e61-f0ea6a6ff544 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Basement Area B | Area B. Grid P wall
a093cc92-abda-4bd8-844e-2997f2e4f5a6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor
328cabe3-2081-41f3-9e16-b2718598720c |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A
48d841fd-33b0-47f7-baef-3c37c009572d |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10
1f975c61-6ac7-432c-96a2-6673f6aa911e |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10 | QA - SF1 Footing Excavation
5c9a75a5-9247-4363-8fe6-795833c48083 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10 | QA - Concrete Pour SF1 Foundations
a4bf36db-05ca-43b6-8846-c1e25e1056bd |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10 | QA - Concrete Pour Site Concrete
2bd6b9f3-f640-4ac0-b1d7-f10e4f87e3a9 |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10 | QA - Blockwork
e47568bb-49e6-46f9-bcf2-508e84ab483a |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A grid 4-10 | QA - Grid 4-10 Slab Concrete Pour
c996c683-0fb6-47a4-baf0-f7c4fad4a285 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25)
072f2f8e-4b8d-4283-a038-38e6d287d7e4 |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25) | QA - SF1 Footing Excavation
f33abd23-9b19-4353-bf36-7c6d9491fd36 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25) | QA - Concrete Pour SF1 Foundations
f6a89089-ef4d-4958-b08a-e352392e136e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25) | QA - Concrete Pour Site Concrete up to grid ~17
85cdf4dd-4ec9-4b61-a240-15d4304d9d7a |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25) | QA - Blockwork
daf8b82d-01f3-43f2-a85c-15b06b5cd575 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 10 - 25) | QA - Concrete Pour slab grid 10-25
d47a3cba-861f-4626-9548-5fa217ae1b4a |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 17 - 25)
970f8ccc-7e17-4f19-ac00-db5b403a768d |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 17 - 25) | QA - SF1 Excavation
39885b94-7afb-4dbc-b492-0f7b4f719f16 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 17 - 25) | Area A Grid # V Blockwall form 18 to 21
f91febfd-1ac9-49eb-ad39-fd49961d8ef1 |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A (grid 17 - 25) | Area A Grid # V Blockwall form 18 to 21 | QA - Blockwork
63e17f6c-7b6b-4459-a68a-18ae79974688 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A Insitu Walls and Columns Grid 4 - 9+
7b328882-19cc-4e38-b734-afd6986d3dc8 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A Insitu Walls and Columns Grid 4 - 9+ | QA - Concrete Pour
87eeca1f-0544-4abc-8410-6205dd69b2dc |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A Insitu Walls Grid 8
e2ff4593-1611-4e12-9419-69d914105085 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A Insitu Walls Grid 8 | QA - Concrete Pour
ad4cf43a-914c-4a28-aeb4-5768b90cb251 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Insitu Walls Grid 10 &V and Columns Grid 6
4ab829a8-af21-476e-89d6-9f16c93cf69d |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. Stitch Joints Grid 24+
f619ac7d-95e0-4027-b84f-f31922076683 |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | ST - S - Precast Panel 12
199dcd4a-4744-4a5c-8bc4-325783442026 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. In-situ walls 9+, Grid W12-16. Columns Grid 9, 12
f48d5bb3-8a96-42ca-8823-fa15350b1cc7 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. In-situ wall Grid W 14-21
c6375e0c-b03d-47ab-b949-fceb9f053e2f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. In-situ wall Grid 21 V+
f46fbda8-b496-4557-be93-cee571d78d60 |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | ST - S - Precast Panels 20, 14, 11, 15, 19, 13, 16, 18, 17
816221be-9729-442c-99f4-3140ef6bdc52 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. In-situ Beam Grid 8-4
bedb401a-b40d-4e60-99ce-5604f8c043d1 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. Floor Slab Grid 4-8
2550d524-6363-4f0d-b953-e17b35ac5b71 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. Column Grid V/ Grid 12
b3f42a75-2991-4f55-872d-e4820f52a4c7 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area A | Area A. Nibs - Building Perimeter
e7864d61-eb6a-42f8-ac64-3a243197e3a5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B
4b668def-ae83-4ec4-99b9-bda19784e82c |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Beam Installation
3b6f2a76-68d0-44cc-8540-fd9426e0d25a |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Edge Beams Installation
4d397c61-230a-4da5-b655-a66fcece92fb |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Flat Slab Installation
f8b215dd-f67f-44de-8cb0-ccdab9943d16 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Shell Beam Lintel Installation
c3625795-c03c-475f-9dbe-bbc05b0eee0f |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Spandrel Panel Installation
d0a336c2-e8ea-479b-8eeb-88d937459772 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Wall Bracket Installation
62b5cc7c-0e6f-4de7-b43c-c0f1e94b4ce3 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Wall Panel Installation
8f0cffb4-7832-4947-8f11-8e27f20aafc0 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Rib & Infill Installation
a287fc18-f121-44b0-b4d3-e4b05ae46922 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | QA - Concrete Pour - Grid # 12+ beam stop end 1800mm back off Grid # Q+ beam
eebd41f0-e4e0-4bc2-ab56-dbafc333d13c |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu wall Grid 18, R to P
ec8fce69-09a9-4f0d-b889-c102b291c391 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu wall Grid 18, R to P | QA - Reinforcing
be464fde-87c9-404c-b5d3-ff2c595d2ff6 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu wall Grid 18, R to P | QA - Concrete Pour (Foundations)
da9fbd08-1c54-470e-b68a-33545a955ba0 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu Wall Grid S+2390
0617bdd4-cb0e-4aef-bd79-efec825b6181 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu Wall Grid S+2390 | QA - Reinforcing
6033b289-aaf0-4f70-a8e1-62e06420ffab |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Insitu Wall Grid S+2390 | QA - Concrete Pour (Foundations)
1f302656-0463-428b-95fe-31258713cc7f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. Slab V-S+
67562952-6baf-4c0e-9627-9f1c20ca5ae7 |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Panels 1, 2, 4, 3, 5
dac669f6-57fb-4e17-a5d3-bb5182926061 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. Floor Slab G S-R + 3 Type CC3 columns
b1c7ba5f-13f4-4575-ac73-33a3a810bd11 |  | checklist-flat | work-in-progress | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | ST - S - Precast Wall Panel 6, 7
ff044931-14f7-49a9-a561-a4bcc6a1a042 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. 3 Columns Grid S-R
2f685bd3-e13c-4246-aeea-af935a2489d2 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. In-situ wall Grid T
a170a47e-7778-4584-9a81-41d11f8566b0 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. In-situ wall Elevation Grid R +4700 and Grid S +2930
11413bac-788d-456e-8818-60c48f6e38f4 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. Grid T Header Beam
6b4e0091-0fb0-4b1c-b3af-b0ac2c4d24b2 |  | checklist-sectioned | not-started | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. Floor Slab Level G Q- L
ec271601-bd50-40d5-81eb-870dff4f6b68 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | CAN #104 - Area B No connection between GL T & Riser Wall
32b35ce2-2aa8-4c24-aba2-9f0069615e0c |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area B | Area B. Stitch joint off of Panel 7
73b2f1ee-3c8b-468a-9e95-c9fdb64f0b8b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C
2281cf95-75c4-4f19-a150-e9d14cd21319 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Beam Installation
d75f688c-2893-4ad7-891c-e68e52afd1a2 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Edge Beams Installation
1521e1da-a74e-479c-bb2a-f05b5edade85 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Flat Slab Installation
d10c91e9-5fa5-4d08-980b-78e3a092e9c0 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Shell Beam Lintel Installation
3cab9c60-0867-498c-8e09-0ee500d16f29 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Spandrel Panel Installation
3b02b55b-95af-4440-b8ba-a4f764fa2bd7 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Wall Bracket Installation
940cdc58-9c65-4a32-9424-b5ace36996ff |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Precast Wall Panel Installation
15f45e1a-5aef-4c02-b8e0-4a1f9c20b8a4 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | ST - S - Rib & Infill Installation
8d6cc515-f2fd-41ac-bdd6-93107f88005f |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | QA - SF1 Concrete Pour
acf74663-ff59-43bb-870c-7febd84faa69 |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | QA - Blockwork
f173c8c5-8d48-4d73-bde4-faa62c0e6a02 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | QA - Concrete Pour - Area C, Level G, Grid 1-7
7492e93f-b8d3-440a-9940-88fff427bdf4 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | QA - Concrete Pour (Foundations) Area C Grid 7+ to Grid 12
2e152334-9a32-4687-86d6-5f56892b2c81 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C SF1 foundation from Grid # 1 to 9
0e04374c-03ef-446f-a042-44ba98d5fdbc |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C SF1 foundation Grid # I & P from 8 to 12 / Site concrete Area C from Grid # 8 to 12
691e9c48-48f0-4e66-ad84-aa001c77e681 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. 5 Columns on Grid 1-3
697e2842-1b07-47f1-a923-f43801adc141 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. 10 Columns Grid 1-8
751202f5-118a-4b82-8781-99c9e17747f1 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. 3 Columns on Grid 5-8
168e6d33-3f80-4e1a-9138-40b73dc58d0d |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. 8 Columns Grid 8 to Grid 12
d8cd2fcd-5bf0-4386-910b-241290ba5948 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. Grid 2+ wall
0ba2f51d-637d-4ad3-a8a5-a3a07d827a04 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. Grid 4+ wall
4e8c2d6f-80b1-41c3-9669-fc821c71cf60 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C - In-situ wall Grid K
ed5966ab-17d7-45eb-b3e9-6cfaa914710e |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C Insitu wall Grid #12 & corner of Grid # K
ab03972c-f07a-4bcd-9096-78942208a30b |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. Insitu wall Grid 7
353a51ac-ae6f-441e-8d4f-c308e3c0a10e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area C | Area C. Insitu wall Grid 7
9067130f-e423-4933-b25e-8f1a9e4f1b1d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D
019ae8a1-d458-4dbf-9ef7-978e4fe6af5f |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Beam Installation
7823af7d-0443-4eb1-9899-2854e1979287 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Edge Beams Installation
50864763-9365-4afd-a4eb-9f73235e2db4 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Flat Slab Installation
3d0b4857-2269-4ca2-b2aa-aeba34cc4e38 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Shell Beam Lintel Installation
524e2728-0250-4363-84dc-d637aea6e0e1 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Spandrel Panel Installation
9e85bd65-90b3-4179-97cb-66b565e1892c |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Wall Bracket Installation
4c0edd2e-90a5-477c-ae1d-4c9bf5b7bee2 |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Wall Panels 76, 99, 100, 101, 102, 83, 84, 85, 66, 62, 54, 56, 58, 86, 87, 64
212e5679-ea1a-41dd-bf01-773243075eba |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Rib & Infill Installation
4152f35b-25ea-4ad1-b3c3-16bc35516f2b |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | QA - Footing Excavation
292abf42-1048-41a3-840d-156e2adfd2ac |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | QA - Concrete Pour (Site Concrete Footing - Stage 1)
da2b8f0f-8478-4827-84d7-35fec8704197 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | QA - Concrete Pour (Site Concrete Footing - Stage 2)
927a0c1d-31a7-4959-844d-9f8abd3c5b1b |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | QA - Blockwork
10260975-a46e-4ed7-8597-c53c1f5caa78 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | QA - Concrete Pour (Site Concrete Footing - Stage 3)
1d47be3c-ff5d-4ab2-b6cb-f687ef77102f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | Area D. Slab Grid 34 - 23
4222a4f4-ec24-444a-9805-b24fcdf27154 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | Area D. Slab Grid 23 - 12
688b3a1b-381c-4e53-8d73-25b25eb8bf4b |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | ST - S - Precast Wall Panels 46, 48, 50, 52, 58, 72, 74, 80, 8
e8d89837-e872-4753-8a54-2238c7591a2b |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area D | Area D. Stitch joints
8eebc5eb-5636-48a1-adee-73971672bfb8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1
d4528082-86c2-45b4-ba52-a7cdf2f1d183 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Beam Installation
6b824b05-41a7-48b9-b5a4-5f631efb34aa |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Edge Beams Installation
c4a3fac0-f6c8-4157-8f00-04ecc09b4c18 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Flat Slab Installation
24eb0ee4-b50e-4ce1-bb09-c65c35e9038a |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Shell Beam Lintel Installation
8e52403a-43a2-4a10-b130-6ce0b9d8e934 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Spandrel Panel Installation
a2d4d4c4-7e7f-48c1-ac2a-01c29c230aa7 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Wall Bracket Installation
7e27fb83-4088-4dcc-8b68-a207e9708f22 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Precast Wall Panel Installation
3844dfd1-2c3b-422f-894b-b5dc12684d33 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | ST - S - Rib & Infill Installation
25d1782a-e20d-479c-bde5-d9642ba37109 |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid 12, Grid I (31.03.2022)
eb1f88d4-070c-4bfd-9cce-e842f159207f |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid 12, Grid I (31.03.2022) | QA - Concrete Pour (Blockwork Footings)
76ba48ea-dafe-43a7-a216-c277471eb769 |  | checklist-sectioned | pass | QA - Blockwork | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid 12, Grid I (31.03.2022) | QA - Blockwork
3a51aaf0-ec7e-4539-bc71-e0908ed795ce |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid17, Grid I
ef52a79b-0627-4d15-ba83-248d67947e7f |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid17, Grid I | QA - Concrete Pour (Site Concrete 6.04.2022)
e9fd7dd8-3020-46cb-80c5-65fa3bbead30 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | QA Blockwork Grid17, Grid I | QA - Concrete Pour (Blockwork Footings - 19.04.2022)
700d9683-7fa6-49d9-9fb1-cf0710d5c0ba |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | Area E. Blockwork Footing - H to G
07f300a5-8ed0-4884-ae10-a56a85f8d1ba |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | Area E. Site Concrete
d2704c5c-84cf-454c-8ef0-80ab6ed64346 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | Area E. Grid I to Grid G
d477be93-996e-495c-885c-bc502f94f759 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | Area E. Floor Slab Grid F+ to D
b405b4a7-cf3c-41b0-b316-73ef69a6ac47 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E1 | Area E. GL-H in-situ wall (P126)
56f60b20-43fd-41b0-b25f-a6867b843b76 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2
023f8542-0c72-4ea4-81d5-a919ad2f833c |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Beam Installation
9df21de4-96ad-4b61-9767-3ebfdb6ef8fd |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Edge Beams Installation
9f3f6d53-c9bd-4738-a2a3-8632536b8bdf |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Flat Slab Installation
172aff1f-6827-4419-afdb-3ed3f76f1ff6 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Shell Beam Lintel Installation
8cf71f6d-6d18-4702-8c20-3f60053f13bb |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Spandrel Panel Installation
470c71de-86b8-4dd6-ab47-94a37914595d |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Wall Bracket Installation
3700796e-0e8a-4023-bcdd-96add4a261c2 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Precast Wall Panel Installation
065a5a47-52b2-42ce-8b71-a3d2a54bb0e8 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area E2 | ST - S - Rib & Infill Installation
aeaa311d-1beb-47a2-9fe6-e6e66119332c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F
84ff4002-d504-4183-bfc3-e1997a9202c2 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Beam Installation
f4c6666c-3a28-49d6-a82f-606ca84f5849 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Edge Beams Installation
d0767e12-f362-408a-b665-b4d811c3dd0e |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Flat Slab Installation
3432b52d-8720-4509-9ae7-9efba15fe1cb |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Shell Beam Lintel Installation
f56c77cf-e3bf-4d6a-9af4-67370f1c1714 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Spandrel Panel Installation
ce971fc0-e744-4de7-a092-969f2bfab16f |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Wall Bracket Installation
b0590b8b-651f-4889-9002-e1e6ca98f794 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Precast Wall Panel Installation
c0c44ac3-536e-4c5b-81cb-d55021dee46d |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST - S - Rib & Infill Installation
dba704c7-ebcf-4b77-bc0c-ab792094dbbe |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Site Concrete - Stage 1
69a93048-0ab6-499a-8383-f8c1d35589d5 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Site Concrete - Stage 2
702990dd-07d2-457d-bf3e-29784d8c9399 |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Site Concrete - Stage 3
142a78c8-3d31-4537-b002-55bc3256dcdb |  | checklist-sectioned | pass | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Site concrete - Stage 4
7e11d56a-df72-4ec4-b786-011a934af787 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. SF1 Foundations
29f3ab55-f2bd-42a2-92e6-29f798a1988f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Floor Slab Grid 12 to 21+
fec0008b-a19a-4b17-9e47-7c51dda16759 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Floor Slab Grid 21-30
19962b3e-7035-4b20-bece-074daded6008 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. Floor Slab Grid 30-36
edea4de2-8288-4c40-9a66-a3a73e56318e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | Area F. In-situ columns Grid 12
883b25e8-8261-441b-bd92-ea0bd2be2b1f |  | checklist-flat | pass | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Ground Floor | Area F | ST-S - Precast Wall Panels Area F GL-21 to GL-36
befe8fea-0252-4a74-8d4c-9e0bec3c2162 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1
42458e9e-c236-4f2d-ba21-de444295624b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A
cf9ec8a7-a921-4676-9352-994a527ef402 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Beam Installation
1195375f-464c-4835-8569-8fad741d9f9c |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Edge Beams Installation
eaf7bf99-1b2e-4afb-8c9d-de704717f3c9 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Flat Slab Installation
cbafed11-044f-45ff-b4cf-e501437bddd0 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Shell Beam Lintel Installation
643b6eb8-3924-4c61-ace5-dc0725c576c8 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Spandrel Panel Installation
d1f03590-e735-4c6d-af59-0846138a03f7 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Wall Bracket Installation
3c37f3ef-6c26-4eff-a3d4-052b74896519 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Precast Wall Panel Installation
cc1e3d71-720d-4ff8-86d9-037e43a8247f |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | ST - S - Rib & Infill Installation
b0b7faf0-f614-42be-bc79-fcc4cd19c246 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | Area A. Floor slab L1 Grid 25-13
97d79a85-1b34-4a5c-a71e-6e5e43976614 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | Area A. Floor Slab GL-8 to GL-13
c5b74ad3-e10b-4d53-8f7c-8dc9271b0059 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | Area A. GL W and GL-X Stitch Joints, Grid 7+
aea28fa8-9daa-421d-9b70-6b039997f79f |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | Area A level 1 grid 10 190 insitu wall (ex-panels 184 and 185)
704dd1dd-c7a1-4555-bcf9-de461579ceb2 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | CAN #86 - Area A. Grid 24+ and 25 hydro blast Area
bb1bacc7-bcce-494b-944a-acbe5a72edc7 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | CAN #110 - Area A. GL W Panel Starters
9e312b92-cc9a-4aca-820a-3ac09bc61d61 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area A | CAN #117 - Area A. GL-10 Post Rotated
8ac6003a-2472-4be3-9487-d4009865cb76 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B
64c7a9e2-f973-422d-89d5-ce961563bfd3 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Beam Installation
6b6871cd-a251-4b91-9ced-3c505cd15a2c |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Edge Beams Installation
65ed60f0-3e70-4169-aa82-5b0459276573 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Flat Slab Installation
b02b3242-6830-4331-b802-6540ef0162f1 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Shell Beam Lintel Installation
292c7709-7982-490f-8bb2-e8acedbacd1c |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Spandrel Panel Installation
ffffbb66-ce55-460c-b43a-6382a11e2659 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Wall Bracket Installation
6e674286-84a9-4a54-83c3-98d53822d4a7 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Precast Wall Panel Installation
fdb39349-f427-422f-90b1-6d1197914b3a |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area B | ST - S - Rib & Infill Installation
01d88d9c-15a4-4926-8f29-ae2f44b1d151 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C
ee21b94c-b600-4654-865f-2eb66724b921 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Beam Installation
6bc872d4-2b18-4508-b7dd-be8dfdee4781 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Edge Beams Installation
816457d4-f49c-4f5e-abaf-93f9b70f6e64 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Flat Slab Installation
5e705b10-54e9-4d85-99bd-0fefd536a3d6 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Shell Beam Lintel Installation
c5710acf-ba54-4ee3-9d88-3a1564f1777a |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Spandrel Panel Installation
6524e241-600c-4f6f-b2b2-8c19f1e7c831 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Wall Bracket Installation
2adf078d-1cdd-4302-b9d5-d36040920dc3 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Precast Wall Panel Installation
8a6b78d0-b5b4-4c63-931b-1bb17fa8f756 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area C | ST - S - Rib & Infill Installation
61791000-9f81-4ddd-9e46-31ae801946c7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D
27e6b76a-05b3-4887-936a-e3951f3a970b |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Beam Installation
e7ef3ec1-32b6-4947-a1ab-8b9d90091b77 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Edge Beams Installation
2c7566e5-2133-4a48-b665-c75891b2a2a7 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Flat Slab Installation
6496ca8d-9a28-490c-b257-97ad07993e81 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Shell Beam Lintel Installation
2c4f4365-e298-4f9c-8d02-07afdbbf1a94 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Spandrel Panel Installation
482368b3-fc14-4328-a660-48f6b028e3b7 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Wall Bracket Installation
afabe238-6356-434d-a54b-412ca4b85315 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Precast Wall Panel Installation
598d7f27-19d9-4da5-9fd6-fe7380ceee5f |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | ST - S - Rib & Infill Installation
a5a7157c-45c4-4e57-9346-7ec45f761ef2 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | Area D. Floor slab L1 Grid 32 - 22
57bdc4e3-ecde-4d5a-96b3-87eb28da826d |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area D | Area D. L1. 6 x Stitch joints GL 22- 34
f6bb16f3-cb29-4a07-bdcb-e1009eba965d |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1
a4f31c55-d576-4793-b47a-346a56b5ee32 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Beam Installation
67d18613-f0fb-4671-9793-bfa3cae7ffb3 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Edge Beams Installation
e11be3a8-81a6-4ddf-9bae-4a7df078b0ed |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Flat Slab Installation
6636371b-62a1-4861-9f43-634b1a2338ff |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Shell Beam Lintel Installation
2f16e7c2-58a7-49d7-b4b1-8b20825103e7 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Spandrel Panel Installation
e828cff8-579d-4464-b3a8-1715fecf7058 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Wall Bracket Installation
a269d044-ffd4-44cb-a05f-594398c3b8c4 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Precast Wall Panel Installation
7aa78944-7124-440a-898c-71d8a3c3907a |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E1 | ST - S - Rib & Infill Installation
f094954b-4fcd-4e79-aef8-74579102de15 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2
73b460a7-b7ec-4e7a-81ed-88fd9ff9a70c |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Beam Installation
e2fe76b5-3ac0-4ff6-92ba-7b7442ad5e5f |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Edge Beams Installation
a31bf661-5209-4730-86a1-ea22041c2f14 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Flat Slab Installation
a465b1c2-3372-40d5-b409-a0ad3c5bf2d7 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Shell Beam Lintel Installation
3cf65b74-d0ef-442b-ad84-c99216f12f5e |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Spandrel Panel Installation
0e83fd44-9259-40c1-ad1d-5f8062040083 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Wall Bracket Installation
18af708a-5f35-48ee-b441-fe8a28c981e6 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Precast Wall Panel Installation
5656524e-aa26-4e9f-a5ce-e6322635164a |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area E2 | ST - S - Rib & Infill Installation
fd2f50e3-553a-411a-81b2-b8d24f655c7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F
b7e9980b-671b-4a20-aee9-6002a9fa7698 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Beam Installation
4cbc139c-a874-4bad-9a0e-f88d11cf421d |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Edge Beams Installation
3dd8db42-d9d5-4e92-91b4-0e9221b7a5d0 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Flat Slab Installation
a0c3a5ce-774a-488e-99a9-59dfb9bf36f3 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Shell Beam Lintel Installation
49c8ebdd-a422-4107-a38c-847337c633d8 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Spandrel Panel Installation
0f232610-f4bc-4724-823e-d678d2e188ae |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Wall Bracket Installation
b4892651-af53-49ee-b929-786fc45295ea |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Precast Wall Panel Installation
79320236-e7c3-4f06-8f08-eb1a6f22f3ec |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 1 | Area F | ST - S - Rib & Infill Installation
79573706-f236-4212-9fb8-56fc2b9c19cd |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2
043070c2-b5d4-4dfa-b042-f078ba1fa1e0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A
ca678dd6-c70f-42ef-bafb-cc6d184c63aa |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Beam Installation
7e6eb684-fa33-4d73-80e6-c86f585c9217 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Edge Beams Installation
3f65ec95-bf44-49fe-bcfd-cb187134d08b |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Flat Slab Installation
bbce653e-9304-4d14-9d18-9f0c14de69d0 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Shell Beam Lintel Installation
cdd71ce2-afc3-4582-a422-7cff2a5aa090 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Spandrel Panel Installation
1a22d4c1-6586-45e8-a319-436edd740806 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Wall Bracket Installation
0677bf9e-3a8d-4045-814a-20041a610dfb |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Precast Wall Panel Installation
03eef15d-8cea-4ff3-8419-11f6048f659a |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | ST - S - Rib & Infill Installation
13bd3148-159e-483f-85cd-66241b656b35 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area A | Area A. Floor slab L2 Grid 4-10
454324c2-1828-4ce9-b0e9-1c6d41338f26 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B
817fe5b3-0afc-43a1-8055-cf3ed599f1ff |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Beam Installation
3760e6f9-baef-4ff9-bc45-2ba384e10aec |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Edge Beams Installation
6964f0cb-f33f-4b7a-8b9c-5a93c13bb3a5 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Flat Slab Installation
2fa31c37-e83d-49ba-8afe-38e3e3c13d05 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Shell Beam Lintel Installation
7fa2bc7e-ac38-4667-8b1d-15150e54b5cf |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Spandrel Panel Installation
5a469e7c-b2bf-4877-92d4-b2030da18dac |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Wall Bracket Installation
910d414a-1a99-42d4-bd20-a31fc78d78f9 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Precast Wall Panel Installation
ee7923a1-aab4-4327-977b-a9634637ee7c |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area B | ST - S - Rib & Infill Installation
3a995cbf-7020-466c-81e7-f484f7c0dbb0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C
16d44acd-e6b6-4ca8-afa2-3c6a698454dc |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Beam Installation
1214a13e-d1c7-4961-a7b6-73f002d0ba46 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Edge Beams Installation
afe1e095-0c3a-4533-a163-1e5010335d97 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Flat Slab Installation
2425366d-db9a-48dd-85f2-08415937f8ab |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Shell Beam Lintel Installation
59a8126c-dd0e-4464-bb60-ced6db85513b |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Spandrel Panel Installation
452ffca9-cd9b-451b-aa49-3aeadeed9688 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Wall Bracket Installation
e30e0ef4-b3d1-4103-9635-987d1e023aa9 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Precast Wall Panel Installation
f9b1e702-6f79-4be7-a9ef-46f7ff5998aa |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area C | ST - S - Rib & Infill Installation
7748c988-37a2-4c6a-90ed-4f2397af268c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D
a2ba8b60-5078-4072-b6b5-87b796f659bb |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Beam Installation
3193a679-b10b-4b4c-990d-571dbb8827a7 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Edge Beams Installation
4c5c948a-db75-4575-933e-2fcc6038c7a8 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Flat Slab Installation
65bd41d0-0f70-45d8-b575-1bf91d99b0d7 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Shell Beam Lintel Installation
9f8a75ae-84fd-4a6d-87be-412d11ec7465 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Spandrel Panel Installation
dca96c17-cc3b-4ad4-92aa-95ebde7e2385 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Wall Bracket Installation
0e68cf29-bac7-43c4-b0d5-3e8118206acf |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Precast Wall Panel Installation
271810c6-3c2b-4c4b-954c-d5ec87b471c3 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | ST - S - Rib & Infill Installation
c0e65292-16df-4d5b-9021-f24ede1b98be |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area D | Area D. Two stich joints P176 and 177
ba6696dd-348c-4368-af0d-9c65aeecf399 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1
4944cd60-252e-45a1-af0d-a57213079487 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Beam Installation
2dac298d-4f51-4f7e-9363-fee7095639d0 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Edge Beams Installation
df145bb1-d15b-49ee-8855-ecf180e6bb01 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Flat Slab Installation
bcf0ad59-eed6-495e-839e-7e0e340d8bda |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Shell Beam Lintel Installation
ded41c7c-1c5c-4ba9-9491-723c2458e7c7 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Spandrel Panel Installation
17380d54-6e70-462c-b868-c5ef2974e9ea |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Wall Bracket Installation
00868701-977b-4f85-9343-1dd4c7e09910 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Precast Wall Panel Installation
53306190-0efd-40c0-9444-f66b565b94e5 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E1 | ST - S - Rib & Infill Installation
c9fa71e6-bdc7-4286-9680-4a42ddf06858 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2
e120d294-50ce-40b4-a498-74f3e546b55e |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Beam Installation
af2389a4-049c-42f3-b3c8-9bf6cdbc1ce9 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Edge Beams Installation
ffc60c03-2686-4a4d-a906-fa4dda677cc9 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Flat Slab Installation
64fb5836-d721-49fc-933e-5cd538740a65 |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Shell Beam Lintel Installation
2d8fc025-8873-4f96-ba23-3aceb2c7220a |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Spandrel Panel Installation
2166ec2b-acf6-4cab-a168-4f99e5d1ac92 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Wall Bracket Installation
535ea854-a8d2-419e-a3ed-de0668fa123d |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Precast Wall Panel Installation
d813efe5-6e31-4d6d-82dc-f671a5d88adb |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area E2 | ST - S - Rib & Infill Installation
11579550-929a-43db-9bbb-7a75d1b8b733 |  | folder-normal | not-started |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F
0bed4cfc-179e-4501-978c-4767cd828e40 |  | checklist-flat | not-started | ST - S - Precast Beam Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Beam Installation
dcb2b2f3-b5ed-4c2e-9bc6-a597b9c22274 |  | checklist-flat | not-started | ST - S - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Edge Beams Installation
e7e44d41-483c-4714-b085-f25ec9d349a9 |  | checklist-flat | not-started | ST - S - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Flat Slab Installation
d71d0fba-a436-4d87-919f-64da2ff01c8f |  | checklist-flat | not-started | ST - S - Precast Shell Beam Lintel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Shell Beam Lintel Installation
96f91b39-5009-4f0d-a771-29f219074738 |  | checklist-flat | not-started | ST - S - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Spandrel Panel Installation
18c1f6c2-b7d7-4e0b-a944-ada6457fef65 |  | checklist-flat | not-started | ST - S - Precast Wall Bracket Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Wall Bracket Installation
d9f332b1-b670-4bdd-8aab-c56fc3df9219 |  | checklist-flat | not-started | ST - S - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Precast Wall Panel Installation
b87fad72-251a-4857-848b-816c9e92c5f1 |  | checklist-sectioned | not-started | 6248f9f5889ec5db85a364cc952caf91a25297ef19a3f78eefae37a7e9fad76b | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Level 2 | Area F | ST - S - Rib & Infill Installation
eb439c30-ef68-414b-824b-fe5cb20567cd |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Foundation / Structure | Crane Base
a52a4bdb-1b7d-47c3-be5c-8cd95262ec01 |  | checklist-flat | pass | QA - Footing Excavation | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Crane Base | QA - Excavation
10d5cf18-aa48-4716-9aba-aa73d27711b0 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Crane Base | QA - Reinforcing
e23b30f2-c23d-4e57-9abb-dde5167c0589 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | Foundation / Structure | Crane Base | QA - Concrete Pour
8e6a5ff4-f3f0-44ff-8fef-c1e1bd3188fc |  | checklist-flat | not-started | af0c587ed69576ccf3c03c06092f00772130d45079e28ca7b69e5fa8d96db37f | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Compliance Documentation - Stage 1 - B01 Main Building
7d0ba3b1-3766-42e1-b3da-ee018608db6c |  | folder-normal | pass |  | step | TRUE | FALSE | Stage 1 - B01 | Mill Certificates
5a5191ac-aa27-47cc-a5a7-40c633dabb9e |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Mill Certificates | Mill Certificates as at 2022.07.26
d0059766-5f5e-415f-a06e-1a39a985524f |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Mill Certificates | Mill Certificates received 2022.09.15
e9329371-9480-406c-b811-1b17665ada88 |  | checklist-flat | pass | QA - Reinforcing | checklist-flat | FALSE | FALSE | Stage 1 - B01 | Mill Certificates | Mill Certificates received 2022.09.16
4bffffc2-a86d-4438-aa14-be96d28e7934 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Stage 1 - B01 | CANs
42ab2a89-a46e-4b62-86a8-e33d8aa2c3e0 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | Can #44
94065c00-d65e-4438-bbb7-2e0bfef3e491 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | Can #48
267bebc0-28be-44e1-a895-36dbc052a43e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #55
882cc92b-3204-4f94-92ae-6aa4d0a70dcb |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | Can #38
b56ed85a-4298-4a9d-bc5f-f4c75b8c5ed0 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #59
0cbcb830-f2a8-4455-a90f-5efee0acc74e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #74
9407179c-e0fe-41ea-a900-c48b20daeecf |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #72
2c0b3d44-587d-41db-a051-a4f42119a23a |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | Can #60
0f7c002a-13a8-4893-b50a-d5a1ebd1e04a |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #64
fa30de39-9dd1-473f-b41c-0dfe15d06778 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #96
2ff9376e-50e4-47e2-852a-6105b5e2cb1f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN # 93
a25949b2-aa34-4002-8d2f-3dcafece4f3c |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #87
2ad5029d-91db-453c-9b2f-0c223dd7eadb |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #97
5e422ac3-765f-4207-946a-8ce34210d284 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #117
59da4287-ec80-4300-b08f-f3368d0c5f7b |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #86
3ee1be54-044a-409f-a06a-ff4c9ba256c0 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #73
2144ab49-a5c3-4733-ad62-007f395e7512 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #71
6f6ba060-1c33-474f-b559-ac9be1f35236 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #81
b556da62-d19c-4b34-bbfb-1ec9ea36fd3d |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #68
f01c2b60-42ca-4d2b-bb92-f5c27395a599 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #101
4ba6a457-dbc0-4c55-adea-fce001f79212 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #57
96c957e8-6407-4d53-b32a-eb875b7185ce |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #42
3cb64ea7-dda4-4f17-9b3f-90820ed9e015 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN#43
665382e9-a62f-418f-b900-3e85a082edf8 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #69
e17b6751-3aed-4e87-8235-dff473370ec7 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #46
4c8ddc09-efcd-4c67-ba44-9e66d86d338f |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #37
73ba705b-a0ae-447a-ba49-bab6bcf3dece |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #35
7a590eaa-4e06-4443-86d7-a8a8710e1132 |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | Stage 1 - B01 | CANs | CAN #34
be8d720a-12f4-4d58-950a-1299694d94c6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | B02/B03 Retaining Walls
f7dfe6eb-fe57-4cf2-878d-8b59e6045435 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | Base to Ring chambers for manholes in tunnel from BO2 to BO3
fd58b129-ea79-4dc6-80f0-d75541ac8ef5 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | BO2 & BO3 Tunnel foundations center section
097b7566-ceeb-4807-8755-8760dca82398 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | Foundation at low section to entrance of BO2
383736fe-f5ea-49e7-b991-d53339fac3a7 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | B02 to B03 foundation to lower section of ramp to BO3 entrance
938bca16-4cd6-44ff-977b-b572e429cc08 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | BO2 & BO3 Tunnel to Elevation G Foundations
2ae3d6b5-3738-4946-9943-d888b3ab19e8 |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | B02 B03 - In-situ walls to elevation A / B / J
51d0be8f-6119-4777-bfb5-cdd46f67058e |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | BO2 & BO3 - In-situ walls to elevation F & G and top section elevation A
893568d0-709b-4c8d-aa4d-3950354c41ee |  | checklist-sectioned | pass | QA - Concrete Pour (Foundations) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | B02 & B03 - Ramp foundation
d3a9c263-0e24-41c5-853e-334c68c5f2da |  | checklist-sectioned | work-in-progress | QA - Concrete Pour (Blockwork Footings) | checklist | FALSE | FALSE | B02/B03 Retaining Walls | BO3 Blockwork Footings