## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Project Fern Checklist |  |  |  |  | Yes | SYS - Project Fern Checklist (old version) | 7c604ca0-3d80-4783-8906-ed98b8c1023b
checkpoint-status |  |  | checkpoint | Installation Completed
checkpoint-status |  |  | checkpoint | SubCon QA /Consultant Inspection.
checkpoint-status |  |  | checkpoint | Commissioning
checklist-sectioned |  |  | checklist | Concrete Pour |  |  |  |  | Yes | Concrete Pour | d6785ac5-e8b7-4bf2-9f4b-f6c867e7c282
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Any additional photos and observations
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Heights and falls checked before placement
checkpoint-status |  |  | checkpoint | Engineer Inspection
checkpoint-status |  |  | checkpoint | General photos and observations of placement attached
checkpoint-group |  |  | section | Pour / Post-Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Concrete checked on arrival
checkpoint-status |  |  | checkpoint | Concrete Pour completed
checkpoint-status |  |  | checkpoint | Pour documentation attached
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checklist-sectioned |  |  | checklist | Concrete Pour |  |  |  |  | Yes | Concrete Pour | f979c258-6e86-4873-a775-925bb8c10782
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Any additional photos and observations
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Heights and falls checked before placement
checkpoint-status |  |  | checkpoint | Engineer Inspection
checkpoint-status |  |  | checkpoint | General photos and observations of placement attached
checkpoint-group |  |  | section | Pour / Post-Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Concrete checked on arrival
checkpoint-status |  |  | checkpoint | Concrete Pour completed
checkpoint-status |  |  | checkpoint | Pour documentation attached
checkpoint-status |  |  | checkpoint | Concrete surface to specifications
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Final Pour Sign Off