## Southbase Construction__Project
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
09d4cd0c-6ca6-4820-873a-9696a88fa175 |  | folder-normal | work-in-progress |  | step | FALSE | FALSE | Project QA
fcbe85ba-d898-4d27-b258-8f1403c64eaa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Project QA | Roofing & Cladding
1f5e1ac6-71f8-4e06-8cb8-41a0d35002c8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof
44c7b785-d428-4726-ab04-a558e38df940 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Install perimeter edge protection
edd88f87-72e6-4bf8-8335-b3cdef3d326c |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Install Haki stair access
ec87aa0d-b478-442e-895b-563ae36a6091 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Install traydeck/Comfloor and perimeter upstands
53689227-e7ad-42e3-b799-3ca2b31ac4b5 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Form all penetrations and cast in items
3624db34-d736-421c-a46c-a3aea073103c |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Install Re inforcement
6f09dd7f-e222-4cd7-98aa-224c3117322c |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Ensure all structural penetrations are sealed
e4550e43-a0b5-4ec5-9fd0-15392d881257 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | SBC QA
ec530c8d-dd37-437c-8cdf-6c00f2f3d0b7 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Council/ Constulant Inspections
7d908f62-401c-4d48-b60a-6f4a2b204522 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Pour Concrete
314b570e-038b-4a42-bf42-1dcaa20b0c54 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Apply Aquron 2000
745ea67d-6986-46ce-ae71-e6aed57a3de8 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Concrete Cure & Propping Removal
206de77b-f06e-4d8c-b022-d05a0289c2c1 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Undertake Coring for Radiator & Gen Penetrations
21b2ef86-c5d8-4711-8b97-822d570d5681 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Box and Pour Upstands
57e3efc3-0ac9-4795-8454-f5d5996e7c9d |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Strip Formwork
77d925f2-155b-4d6e-b531-95ce4e570022 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Roof Logic Vapour Control
de8b6d0a-6b4e-402d-821a-00af09aa9aa2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Timber Edge for Facia Angle
080b5840-581a-48bc-ac0f-a0b241da75b6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Timber Support for Monkey Toe Walkway
73ca25eb-569d-4548-a569-7988390ef8ba |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Exterior door Timber Support
72eae6b1-3023-479f-808c-b0d769ecac92 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | PIR Board & HDP Board Roof Install
18601386-7efe-48b5-b283-f3452bb72a88 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Fibretite Membrane Install
8e64485c-5f66-42bd-a6b9-5095c00965d3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Glav Angle Gutter Support Install
8a6e2dd5-202e-44b4-8fd7-a22e5b27ef63 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Ali Facia Install
5e8c6784-3d42-472a-b8df-f3324d4ba403 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Gutter Install GL i
2115b66e-a950-497d-bbe3-7d294e913133 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Drip Angle Install
59730b05-ecf4-4d96-b9c1-067c1286c7b9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Final HDP Board
9d190ef7-5cfa-4663-9b56-756c924159cb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 1 Lower Level - Roof | Dress Fibretite to Gutter and Install Pressue Bar
ffff233c-b18e-4c1f-88de-028c177bfc0d |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre
4c89ee5f-3cea-4767-b2e1-cf3faf583f70 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Scaffold Install
73df0207-8780-454c-a933-71ca7cd6e6aa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Clear Opening Formed
56eb05eb-0977-4c49-87fb-30298cdb0839 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Install Primary Frame
1f6e11ee-0234-4cfe-b835-62a906025240 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Install Louvre Baldes
429206b4-eb9c-48f3-bd97-4621dab3e7a3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Remove Scaffold
b2307eba-173c-43ba-85ac-22795529f51b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators
45c143f1-acc7-4928-8908-995d145f4c51 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators | Shrink Wrap
35431a3a-1385-4c86-aad2-703bd210e2cd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators | Membrane Complete
6d9bee09-159a-4ddf-a84a-3aa7ee7485e9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators | EAF Plenium Cladding x1 Side to be left open
38228560-8ca5-4b4e-9234-0648c6e87a34 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators | Extract Air Fan x7
a45ee62a-a1e4-4f96-8cce-88e4fdfaffb2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | EAF Enclosures Genenerators | Extract Air Fan 2nd fix
4e95cac1-a5ed-4cac-8e2e-d599e3c7ba65 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Exhaust/Radiator Penetrations
fe83ece6-b9d2-436d-9ca1-5914c135d6e0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Exhaust/Radiator Penetrations | Roofing Membrane Complete
e1bc9853-bb0a-49fa-b581-5a20ef4b0caf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Exhaust/Radiator Penetrations | Install Flue Section
e8a5609e-4548-4ad4-ab9a-346980233621 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Exhaust/Radiator Penetrations | Membrane Detailing
eb9f72b2-50d5-4e20-b9cc-d3c17bffa342 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Exhaust/Radiator Penetrations | Circular Drip Flashing
4587bdf7-1439-4d0e-a463-5752fafbf207 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Transformers Roof Cowls
02344c35-025d-4bcf-9be4-b8ad132b812e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Transformers Roof Cowls | Shrink Wrap
950e4491-fbb1-49c5-b4e6-9987911ed6ca |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Transformers Roof Cowls | Roofing Membrane Complete
7d5a86f2-4885-4557-84b7-f37caedbe248 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Transformers Roof Cowls | Install Passive Vent Cowl
f4e4f00f-9d5e-47a0-9155-2bc70835de32 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Spill Air Louvre | Transformers Roof Cowls | Generator Roof Watertight
3572981e-5ab9-4f50-b4da-fdbc405a1a5e |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof
94afe888-8e3d-474d-adc3-d1aac371692d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Install perimeter edge protection
0d22be26-c143-47ce-9b31-b0a956939e6b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Install Haki stair access
ba94a45b-6897-403a-a617-3a7a2022009d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Install Monkey Toe Upstands To Strucutral Steel
c2abd8d3-2b4f-4553-a16c-84adc932e844 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Install kingspan roof panel and flashings
c47243be-b1fd-484b-bcb8-3f00e2b8d238 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Chiller Plant Deck
d9c683fa-16bc-4663-b230-7794c029e4e3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2A Lower level - Monkey Toe Roof | Monkey Toe Walkway - Splits
9b8c3e35-1e30-4c3c-9915-5fcbd73518bd |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Zone 2-3-4 Data Hall Roof
ce8428da-8fc5-466c-a6b5-20cbd5a00b52 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2-3-4 Data Hall Roof | Material Delivery and Distribution
cdf10183-7138-4b43-bfa7-1a663ce05798 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2-3-4 Data Hall Roof | Install Mesh and Liner Tray
14ba993e-3c6a-430f-9ae4-a9494e438371 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2-3-4 Data Hall Roof | Install kingspan roof panel
016387c8-7365-4b87-bf9c-e09808e5da5f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Zone 2-3-4 Data Hall Roof | Roofing Complete
080a88f5-9b63-4772-8cc5-c629ee567055 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof
58b71fc6-72f0-452a-addf-f1a395086ca0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | GL2-4
6ab0ac70-a4d0-4ce2-b8dc-5a6b0c147479 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Roof Complete
d6ba59df-bff5-4228-8810-349b7bcd52f1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Setout Line and Levels
44eb7aa5-427c-4463-9fa6-7a18f1920e09 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Install Rhondo Ceiling after Intumescent
a3902e5c-484c-4a57-a07f-bddc740a9e56 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Nogging For Services & Wall Heads
f5ebcd9f-50f1-4041-ada9-8fce0150c822 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Perimiter Nogs for Facia and Soffits
1d9375d4-e1be-43d6-9fad-8517cd50eca8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Service Hangers
12ff48ec-472c-4ef8-972f-be0efb250b15 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Council Preline - Roof Constraint
014a92ef-5e7a-4ffe-b092-6af8e9bb6095 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Seismic Signoff Consultant
61297ff9-7c52-4386-b62e-7287db03a97c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | 13mm GIB Layer 1
a3d34a5a-571d-4682-82b5-aa26637903b3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Council Postline
d1a8e439-878d-4962-a603-c5f60c2fac35 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | 13mm Layer 2
9f24af76-12c8-4c79-ad84-88e9f81308e5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Council Postline
e9010fee-f0c8-4450-8e99-380d6e7ace08 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Stopping
42e0ab5c-5def-4bec-a308-07b31b281ba7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Painting
b9c47e67-4acb-46f1-a1c5-83161f5a12b5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Passive Fire
1b22d966-44ce-4006-800b-78cb3ac8ba5a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | Commence Fitout
cef1063b-8dee-491f-bf0c-1868e132dc2d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | GL 4-8
fdea9b5e-f8ef-4d4c-b4df-f255dd8bc7e1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | Fire Rating to Data Hall Roof | GL8-12
19922e5a-471e-40d5-acec-f1285c24db2c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew
6a51ff59-976d-4136-ac94-3d1797c01ab7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install galv drip support angle and drip flashing
0a8861f1-4274-4f34-99b1-90fb20eef0bb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Fix panel bearers
b78f3794-7c8b-45ee-96ba-cc9e5008adb3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install EPDM bubble gasket to support primery and secondary steel
7ced8ca6-56a9-47fb-be2a-acb349ee14b2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install KS panel, fastners and mastic seal - progressive
32810f4b-9e9f-4632-8ae4-243f7df2b555 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install PIR insulation between panels - vertically
06d382af-e16d-4e2f-8570-42acf6e02f1c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install Top Hat, Butstap and insert strip
d9b4d697-eee8-4eb0-a285-6ac8eb30f977 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Cut penetrations and trim - Doors and Louvres
132617b4-73e4-4906-90a0-aa0bc0d9ab36 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install Service Lane Louvres - gl. G/3-12
5315c254-f5c0-4a3b-93c7-7dd186ecc308 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 1 Additional Crew | Install external doors and windows
cc51392e-7b5d-4c38-af3c-02a58edf4307 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2
309f8106-0453-49ba-8b4f-e190617cf547 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install galv drip support angle and drip flashing
d0e729bd-311f-4b65-96f5-aed686916d03 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Fix panel bearers
65016903-6387-46bd-b347-d6cc7a66c0f8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install EPDM bubble gasket to support primery and secondary steel
424d1da1-f6ab-46d2-84d6-eb2208fc1888 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install KS panel, fastners and mastic seal - progressive
a4e316de-fa3a-4a3e-9264-4cd4f2cfdcee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install PIR insulation between panels - vertically
ddf18a35-598d-47d9-b5e5-a3959f5606d1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install Top Hat, Butstap and insert strip
e221ca01-b345-49f4-8410-6836b7805530 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Cut penetrations and trim - Doors and Louvres
ee951a8e-37b9-4bac-af4a-086ae421e1a2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install Service Lane Louvres - gl. G/3-12
6a475a87-98ef-4810-b9f1-c2c76616402e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 2 | Install external doors and windows
c548b497-f46c-4b2b-ac75-3902e9dca4ea |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2
35fe1d9f-75ec-427c-b35e-cc01d1526c38 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install galv drip support angle and drip flashing
dc19675e-0bef-4adb-9a24-40cd8e44e38f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Fix panel bearers
1a0ec5e8-8ed3-4d10-abe5-68546e15d28a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install EPDM bubble gasket to support primery and secondary steel
04b93ae2-aa33-4c1d-b52e-a658a80d50f3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install KS panel, fastners and mastic seal - progressive
a8918b84-3531-4404-bf94-f35680eccc30 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install PIR insulation between panels - vertically
04180114-74d6-4c2e-982b-dc882f534246 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install Top Hat, Butstap and insert strip
a9e64c99-3b80-4fa7-a7c4-076787c0c906 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Roof Handrail Install
d567aa52-6406-473b-9ec8-903a8c5ba154 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Install louvres & Doors
83432840-4822-4087-94b9-ccfad169b6c4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Commence Lightinging System
c0a2ff16-a705-4422-b9bd-601818f7f590 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Roofing & Cladding | External wall cladding - Zone 4,3,2 | Zone 2-4 Kingspan Works Complete
255a229e-5d34-43ad-a3f4-f8c05ebd0642 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Access ladders and platforms
1b43371b-7839-4d71-b2a4-36ca5be63bf9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2
6e5dc11f-f8bc-463b-9a1b-305bf06ba14a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2 | Monkeytoe Roof Stair
28f275c5-6070-458a-916e-3425f9d561ca |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2 | Monkey Toe Chiller Plant Stair
9b9117bc-8570-464b-90a9-bc2e38f4b73c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2 | Monkeytoe Lower Roof Stair
241e8c32-49b5-4d77-8afa-c51451bfa3ae |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2 | Monkey Toe Truck Dock Stair
e0083503-fc1a-4af0-b181-6de2f2d365c8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Northern Elevation - Zone 2 | Monkey Toe SVR Stair
cce1818b-46d7-4c71-8169-b65cfa834ab6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Access ladders and platforms | Southern Elevation - Zone 4
09319cb8-30c6-493a-ac30-b795e980df9e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Southern Elevation - Zone 4 | Monkeytoe Grid B Level 1 Stair
22dc08dc-2835-4bc1-8453-3b641e00a6a2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Southern Elevation - Zone 4 | Monkeytoe Grid G Level 1 Stair
b92135d0-3f37-49c2-8e5e-33270ab08221 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Southern Elevation - Zone 4 | Monkeytoe Grid B Ground Floor Stair
cb9f7b0b-18be-4329-b9fd-18ab16324b27 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Access ladders and platforms | Southern Elevation - Zone 4 | Monkeytoe Grid G Ground Floor Stair
0be59cdc-af54-4ddc-bd31-6fd13416062e |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out
12defd57-c0a5-4d75-b5ba-e7f2a0824093 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00
44a5c532-4324-4c5b-883d-4e066d1f0728 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 1 - Generator Build GL G-K/3-12
b62dbabf-d740-42ca-ba1f-bd96c451363d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 1 - Generator Build GL G-K/3-12 | Korok Wall Site Measure
a5c8129a-62b2-4604-98d2-cb54b24b54f3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 1 - Generator Build GL G-K/3-12 | Korok Wall Manufacture and Lead In
e1e80777-88e2-4b03-83d3-df9d710de88c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 1 - Generator Build GL G-K/3-12 | Korok Wall Installation
0d48abcb-6b1d-4bda-b1df-339834950bd8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 1 - Generator Build GL G-K/3-12 | Plant Rooms
8ccfb5db-2c6d-4cf8-8dcc-649324a939bc |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K
2bd4809f-c5a6-4493-b2e1-6bd179d264dc |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall
c3070a3d-ce10-4cbc-ad99-5125155551ad |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Exterior 120/120/120 Wall Framing
2edd66f3-dd17-4cea-9cb7-9431fc78221b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Council Inspection
aba84180-a652-46c9-9dfb-9acd79e6eb31 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Fire Line High Level Ceiling Interface
ac10c326-8fbe-44c8-bf3a-29208ae5b821 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Council Inspection
6be8a122-aac5-4477-b3ac-34a8a9e4aab3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Fire Line High Level Ceiling Interface
ab6d854f-6200-4540-b8c4-c56127b84996 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Exterior Wall | Fire Stop Wall Interface
2f22c546-491b-4f28-a258-21e4bf40d204 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof
5d82aed8-3016-4323-807f-66fa971a4afd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Install Rhondo Ceiling Frame
7f3f2bed-c49a-438a-b251-0a623c0409ee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Service Nogging
43af5c0c-2136-485d-9611-14f8136cb361 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Wall Head Framing Between Purlins
5287a2e4-c99f-4417-bf17-561280525723 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Service Hangers
d9669302-5336-4ca5-9dd3-73a6ac71e857 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Council Preline
196fe64c-4d84-4ece-98b8-c479852c50e8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | GIB Line Layer 1
b22b5bec-c73b-46c4-9263-f2153afd27ee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Fire Seal Edges
3c2a44bc-d63c-4659-b55b-b9720de1c08d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Council Inspection
acc5fb54-42b1-4812-8616-934096bb9c34 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | GIB Line Layer 2
d412689f-b544-4bf2-b9a5-923e53cc9dba |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Council Inspection Screw Fixing
e6d868a2-082d-4845-9ee3-02ee2c161f24 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Stopping
d69daff4-cec3-42a8-b2c9-cb25282e844c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Seal Coat to GIB
b3cf22ba-48ad-49f4-90ec-3bad8e7007ed |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Light Checks
1a8e4e6a-8385-4669-ab98-1e2312570fdf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Colour Paint
c48b0d0c-65bd-4757-9a58-55abbdd49bd3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Fire Rating To Underside of Lower Roof | Passive Fire Penetrations
c1088dd2-9dc1-4955-9dfa-05226e968f75 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners
28f60aaa-0b0c-44b2-b7d4-f0d2f7d3a327 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Fire Line to Underside of Roof Completed
3ab0f088-47a1-48b8-b3cc-d2e009ce83b6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Floor Prep/ QA
e4e2b250-a753-40e0-9de2-c9927adfe40b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Wall Setout
dc6e3435-9936-4cd5-97ae-f2fffdffedfb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Sprinkler High Level
02a5be41-d1d8-4eb8-af60-3a44e4839ec3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | False Wall Frame Installation
c86a991e-c99a-4f8a-b592-04ab2bfe03ce |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Fixing/Nogging for services
564e57cd-e5b6-4bf1-86c5-53303dbafbc0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Electrical High Level
1be49e0e-fdd6-41dd-8b19-c434fa83ff84 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Alarms High Level
e6b116eb-dbb7-4ef9-83c7-63edf5c6e7b4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Line 2.5 affl to Roof
a1eac1f2-8710-4331-966b-ffba54fcb31a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Mechanical High Level
e44fd7e2-76a3-46c5-b65e-7c93f8b3ced0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | DCW Install
d4ba952c-9ba0-4d9b-807c-360d077a1634 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Sprinkler Low Level
840b2c24-88b1-4d75-88b1-1f5689ec2be8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Install Ceiling Grid
e4b65297-549f-4d30-8a5c-6ccf06489681 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Mechanical, Electrical & Hydraulic Install
638c11ef-12f9-44c6-bf8a-1e9e3d274ca0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Ceiling Insualtion
5b4a824e-1fb0-4a04-affd-740412410d8e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Southbase Preline QA
8b1f0550-8f43-49e6-9054-c12688826f9c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Council Sign Off
a96f8f1e-a182-405c-a525-ce9d75f52fa4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | GIB Walls and Ceilings
ec62a8a3-7c33-4dd3-8169-490817623836 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Stopping
67138148-b1be-4ad8-a684-199441fbd4bb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Light Checks
ed087795-6d99-45e9-ab72-80d5ae3b4251 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | 1 Top Coat
98cd9139-aedc-4026-8478-f366694c47d4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Door Installation
9c98b82f-330c-4af8-aa54-783f8970e00e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Door Architraves Install
df5e5fa8-b183-40ef-8c4b-eee1a004334a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Floor Coverings
4c036d6a-bb75-467d-aa52-0e7d44b16e89 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Wall Tile Install
f0028bca-6bcb-49bf-a7ce-e3087f44f39b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Final Paint
da664e4d-dc4d-48d4-8a42-43e6e02ba794 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Services Seccond Fix
3ad345c3-055a-4bc8-8241-2aa87542f248 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | FF&E
c4e37d64-2df7-42ea-b4d6-bfd0aa10ace3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Southbase QA
9b610365-099b-4943-92aa-82527c11acd1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Defect Placeholder
bbf0ce0d-e8a1-4cf1-bb78-9e93cfd25cfb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area A - Toilet Block/Cleaners | Lockout Room
4845b83f-2c38-46ba-abd5-6d95c3374123 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods
b5454f4d-b491-4d4d-8d48-e3ff64bab88b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Fireline to underside of roof
c65dffe8-adbc-43aa-8cab-4e6f1270d4f9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Floor Remedail/ QA
129ae9fe-36c3-4945-88f3-4ebb2019f0b1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Wall Setout
ade0bea9-ab1b-4076-a1a3-6f655bb99762 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Korock Wall Install
5635f36f-8565-4d2a-aeb8-56fe780a5ad9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Sprinkler High Level
d180f440-1cc9-4d01-b616-a5ab9a2040b6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Wall Frame Install
0b573248-04bf-4e48-a3d8-c1aff15d259c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Fixing/Nogging for services
26a3d04e-e770-4865-95a5-a4330a629f26 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Electrical High Level
bdfb69ca-7cee-446a-9e62-ab9b129c172e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Alarms High Level
7a79fb54-b56e-4a1b-ac1a-332b2e56dee0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Line 2.5 affl to Roof
e1057ab2-f95f-4763-bf7d-1a7112cc39e1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Stopping + Painting
5e9ce661-acc0-40d1-b613-20fbd4391819 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Mechanical High Level
fbaadafe-b67e-49c5-9bd3-fd2e1ebc2439 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | DCW Install
39cea7e3-fb77-4b3a-b434-dd209bfba303 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Dock Leveler Instalaltion
da549d75-909d-4b33-8ee7-0f8cabaefb5a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Roller Door Installation
a2178ac6-514f-4c8f-8765-c0e78b9f2f82 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Electrical & Hydraulic Install In Wall
39cdabef-cdcd-4603-a295-aff20fe5ea8e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | GIB Walls
160a317b-92da-467b-8e32-154d9176de90 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Stopping
a232a448-6af3-481b-b94a-e533ff32feab |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Seal Coat +1 Top Coat
35ab0c04-caff-460a-a432-667e15a5191f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Light Checks
7dff2a39-7add-4ae8-a022-c6d30e112330 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Internal Door & Window Installation
c9512cd4-1da5-4d04-b01c-17b9ec1cd297 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Architrave Installation
4b92a9e2-526e-4c2d-b3d0-2ba4c174b448 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Final Paint
8a865762-affb-4fc7-85f7-e51cbf4ab3c7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Cable Tray Installation
1e4f77c0-e796-44b0-89c9-fbf1138016c4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Seismic For Services
8ad51fde-3820-45c8-adfb-6680ab5590a5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Services Seccond Fix
17004215-2a05-4599-a13c-1769af1f5a36 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | FF&E
41642d8a-0c68-419e-8251-078f8b4d011c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Southbase QA
a9f2e97e-cea2-44a7-80b4-b8543b42e0e5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Defect Placeholder
44570f97-6c3e-4bf3-9598-cf541a13d513 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area B - Inward Goods | Lockout Room
1ae696a6-ba4d-4608-b74f-85868ee7c925 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems
0f5a7508-fe0a-43e2-a7f9-d4c58252f83c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Floor Remedail/ QA
da931c01-2f11-4cc9-8f6e-6b152779d1ba |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Wall Setout
5412f98c-99e2-4c0a-949f-7683299fbd12 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Sprinkler High Level
6e90bade-0038-419e-a45b-c87aa40abf25 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Wall Frame Installation
817bb7cc-e866-45c1-bfe1-a5d3adc09159 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Valve Gear Installation SVR
ff5d4d38-a581-410d-b3b2-df321fe953aa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Fixing/Nogging for services
150abec0-adf4-4eec-9f5d-151d18cdcb9a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Electrical High Level
27133208-8082-44fe-a7ab-c0a6d2d41fbe |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Alarms High Level
b9d6507e-9757-40c4-a7b3-56aedcbd81c0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Line 2.5 affl to Roof
eb64c210-a521-4909-b85d-211b2ee39b49 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Mechanical High Level
6c82056c-3c92-43d5-aed0-67c0afe13426 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Sprinkler Low Level
7d2a68ab-de20-4b82-af24-ec65428a45e9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Mechanical, Electrical & Hydraulic Install
6b55d06a-ae73-490b-ad94-42dd0fdd8583 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Southbase Preline QA
62027093-0093-4194-903b-e2babb4390bb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Council Sign Off
a5ad8ec4-b975-42b8-9f01-f4c427befc8e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | GIB Walls and Ceilings
8841e724-7d0e-4099-b976-929f8ccd9e2b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Stopping
db37211d-efb6-418d-a0ea-69a48154c1ff |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Internal Door & Window Installation
31d30d14-2f67-46a6-8756-98a2b1077247 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Seal Coat +1 Top Coat
d02ee2fb-ffe1-4e39-858a-c33da8e7ddd1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Architraves
5395a2ce-6f84-41f8-87ca-a1b431d369bd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Light Checks
08a09d09-b902-49a6-a02c-7d3fc8cc6e19 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Final Paint
f084535f-5a3f-46a0-bb5f-b25d6eafc1ee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Cable Tray Installation
81631491-7486-465f-b32a-78ed3c4428fd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Switchboard Install UPS Rooms
ace30e9d-6131-40f4-ad15-c190cc8ef5c7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | FF&E
cfe03915-1325-4f53-8497-0543c5aa158b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Services Seccond Fix
95431e71-9b64-4607-912e-718ef8d01955 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Southbase QA
c449156e-35c4-4905-a37d-a63b6ae5ba4a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Defect Placeholder
0aeb5adc-fde7-415c-9bdd-712f42ed99d7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Area C - Mechanical Power Systems | Lockout Room
57c875ea-99fb-4cb5-8025-18de229ae738 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1
5b60189f-dbb1-4696-992a-5a8fa3eda5a4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Sprinkler Installation
e2494d23-ba40-4164-980d-b02dc49a0b69 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Hydraulic Installation
11dd0bd8-b07c-495a-ae11-146ba4ed589c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Fixing/Nogging for services
db7cb423-8f1a-4440-bf7f-9e98d2e0b286 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Mechanical, Electrical, Alarms Install
dd58bab1-0a15-48d5-939f-8dcd274df91d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Insulation
3806149b-d183-483c-aa28-cb2568740592 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Southbase Preline QA
44ffc4ad-039c-4e5c-8102-5077a1162fbf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Council Sign Off
0e20e352-b66b-4d80-b91a-fc38ed427dec |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | GIB Walls
2293d25a-49b4-429a-985c-dd1dbf811d96 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Stopping
0f1d1d49-1f8e-4b24-a7e2-46cae859e8ce |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Seal Coat +1 Top Coat
2df15794-5197-4e6c-910f-964e0e609978 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Light Checks
645671f2-6068-49af-a094-552a0b709099 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Cable Tray Installation
6547895b-33d7-477e-8a6c-d842120ec769 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Secure Trunking Installation
0b35cdee-403b-4447-bd81-995161d57cf2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Internal Door & Window Installation
1be473ca-17eb-4d4c-8d1f-5d2a9ccba73f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Final Paint
e80ecf56-7210-43fd-940a-4a1a8f6498ae |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Services Seccond Fix
28a79783-d55a-435d-8cc7-63f92e0f871a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | FF&E
b669440f-6942-44a8-978a-84b97a785d63 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Southbase QA
e82419f0-f3cc-4bfd-9fcf-b4f37c2987d4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Defect Placeholder
0153ef11-bc79-42e8-9ea7-f05708dd61fd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 2 - Administration GL 1-4/J-K | Corridor 1 | Lockout Room
1a95a713-0881-436c-b5f0-41c759ba8d8c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services
88741e59-c522-497b-89d9-686460792810 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8
bea858f0-9d81-4f30-9e20-00f50c03b8a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium
3c0186c9-b904-4dee-8c04-5ac7a9a8dd0e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Floor Remedial
a883a0c0-cdc4-4e3e-8cc7-c0cf74a17a1b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Wall Setout
ee15d348-8dca-4a63-8455-a788b292615b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Wall Construction (AHU Partition)
715f586c-8b9f-4da5-961a-a9de0a2199a1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Wall Construction (White Space)
f9a7adde-2b2b-4af7-9d9d-ca6160619539 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Frame Out Louvre Openings
c2c30120-e430-44c3-b810-075031801259 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Council Framing
44758bc6-8ba2-4e1c-99d7-a2257a79d072 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Gib Air Plenium (Security Wall)
74f3d8b4-2805-449d-b273-3bbb9d463f19 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | GIB Layer White Space
d1a01dc1-7ef6-4223-bc03-4cf400b5acdd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Stopping
d0a4e9ef-d5a7-4544-97a5-1d2705777582 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Light Checks
5f4e43ca-7adc-4cc0-8a94-2ca242871386 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Door Install
98747207-2bac-4de2-adfe-1f2ea5dc9895 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Architrave Install
22fc205b-6f59-41ac-a1f2-5b5f20b52c60 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Paint
9fada40b-6255-45f5-9ae5-847b29f63cc3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Install louvres
a962e8db-b583-44ad-aae3-987622b25141 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Install Security Mesh to Attack side (White Space)
637531f1-cc65-4070-9261-1d90cef3a8a4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Sprinkler Installation
3956056e-5a6d-4582-889d-7db145c83c6f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | DCW Install
b8dcf8b7-0df9-4dc8-85ca-15a8746ae5ac |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Electrical Installation
387a18cf-039f-44c2-a441-ba6c3751be32 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Passive Fire
be6c1840-6a2f-4f23-ba48-28d31bdbcbb5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Southbase QA
a60c58f9-96b4-460d-b4aa-0a7a408cb888 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Defect Period
fb0a403f-1acc-48de-9b0a-44fe1f19d5ab |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Air Plenium | Lockout
7ddfff97-9959-4f39-abdd-ca47bad6755e |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room
c37a9d30-42ab-4a11-ab73-f73c0b06b1bf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Wall Construction Complete
09831072-91c4-4e98-8708-f3d28ddd3e91 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Council Framing
973e776e-eebd-403e-a396-cbcc130a85d8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Gib Wall
488d4145-d7f8-4a11-acf7-db92cee8625f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Stopping
9f904467-eab4-4c2f-91d5-52495b696dcc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Light Checks
aadffd76-cf74-4b72-bf00-fe12989cc407 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Seal and x1 Colour Coat
64dee47c-2237-4653-b479-b7b29e5d4fbe |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Mechanical Electrical Trays
1bcdcbaa-3af2-488e-b3f9-21e1ba314bb5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | E4M First Fix
fc6dff82-6cd5-4c47-8a80-2d921da5f515 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Hydraulic Services
11b6f8f2-7efe-475a-8876-649a89810b86 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid
64ee399a-7422-4a1e-9e6a-15a24e297684 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | AHU1-4
8e632d3d-3ef6-4511-a891-1064e8808ee3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | E4M Second Fix
f112fe5f-a8e7-408b-a502-e7cec7a115e3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | AHU 5-8
2c817d9a-8269-4a09-97e4-851d4a21a125 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | E4M Second Fix
cf949359-bfe0-4527-902e-8edf11db9d79 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | AHU 9-12
8a06b26c-f28b-4faa-af49-230b09287963 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | E4M Second Fix
3e4964f9-d871-4622-8d54-8c3bc8b5b476 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | AHU 13-16
566b9848-1e15-474e-865d-a21de595d74c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | E4M Second Fix
0753a032-cb92-43ef-a0a9-e2412cd402fa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | AHU 17-20
80b9ff8a-8c20-42fc-8a0f-c4084bb720a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | AHU Install Peroid | E4M Second Fix
4c89f841-2422-486d-bd7c-4c040a2f8fc3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up
def566a2-ba2a-4453-8b5d-19a7cb6c165c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Stage 1 Structural Steel
42e5003f-c363-4b79-9970-c453f3ee7ce6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Louvre P1
739e87b5-0b7c-455a-b6bb-9c64543a8175 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Stage 2 Strucutral Steel
2cd50d8a-38dc-4c65-b14d-ff84c53f9339 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Louvre P2
73a010d5-9876-4f9b-ad83-06b7ebcc0c18 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Stage 3 Structural Steel
38c43f46-276d-4032-b577-f8e1f1d167fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Louvre P3
659a7627-73b3-4e6d-b04d-1e69b594e691 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Stage 4 Structural Steel
31ca18a3-139e-460e-800d-4c108eaa802b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Louvre P4
cb6db4e2-ca94-4150-b451-63f252819a9f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Stage 5 Structural Steel
abf60c63-5a58-418b-9a79-d40603ec5ee1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Louvre P5
22130d20-8c6e-49e2-b663-c32a70122578 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | External Louvre Build Up | Filter Bank Installation
9c884acd-c2c3-4afc-acde-e8c545e68d61 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Chilled Pipework
eb9b814d-06e7-481e-9138-209ec51e98d7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Chilled Pipework | Weld Checks and Pressure Testing
c8886cbe-b2bf-4359-b6ad-a2a351e460f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | AHU Plant Room | Chilled Pipework | Lagging Chilled Pipes
0645ed71-860d-40b9-b247-3a2842281307 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding
dc400372-27c0-4954-a477-6e0049e0b8a0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Wall Setout
243893cd-7816-4227-bc98-5660a162debe |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Scaffold 405m2
47bfc4ce-9d40-4b2e-bffa-1c9dfc4fe036 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Framing 405m2
42a11733-384a-47f5-9844-f08e5c336066 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Hoard Fast Wall Lining 405m2
0e554161-63df-4331-8af3-20ae88bd2f45 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Scaffold Removal 405m2
160a6930-2f46-472b-aa70-5c855b6351b8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | External Louvre Hoarding | Tape Install 108lm
0e79a601-a97c-4ae9-8ba5-710f7ccb2be4 | folder-normal has incorrect meta.stepType checklist-flat folder-normal must be display normal but was flat Unsupported Children: checkpoint-status Installation Completed(78a12700-d63f-5e42-bf1f-23d33bd616c0), checkpoint-status SubCon QA /Consultant Inspection.(feb6024f-9ee2-5a13-ad29-a8bf474f96a7), checkpoint-status Commissioning(8521b54a-ac20-5715-a04b-5f10b3fb8e51) | folder-normal | not-started |  | step | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C
db08932c-43ff-4247-a7c4-4016dd04d583 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C | Wall Setout
4849999e-fc52-470f-ab16-a23cc29afba5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C | Scaffold Installl
aa77f0c2-b80f-4530-b8c5-2191485bdddd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C | Head & Base Tracks
cdf00df4-cc7f-4725-abc4-5bef71a44c32 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C | Hoardfast Install
b17ad7cc-7273-4111-a93f-278195d90057 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL2-8 | Internal AHU Seperation GL 7/A-C | Scaffold Removal
277549ef-ef07-41b5-b095-b2219cbf297c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12
96659352-0197-4336-83ed-835be2a74a4c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium
c20e966f-2172-47bf-b960-8aa59b74a5a7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Wall Setout
b85a85e0-ad8d-4461-a86b-fa854a3d21a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Wall Construction
9e667b22-8b0e-4f84-aa92-8aaf63daa411 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Frame Out Louvre Openings
4b94029c-f443-4d97-9340-dd17d7b900b5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Council Framing
0bb724b8-bd16-482a-bb67-6afadff44992 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Gib Air Plenium (Security Wall)
db9a6f2e-ea5c-4e5b-81fa-118e25185299 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | GIB Layer White Space
698050c5-fbec-4518-bdbb-6498ac58f090 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Stopping
2d800978-a438-4f4b-b784-81913c80e8a4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Light Checks
c6442eb1-c097-48c2-81e5-636d0fc94391 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Door Install
63c1e036-5161-4993-87d0-b80fbefa5870 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Architrave Install
3c7af1a9-3574-4ee5-ab34-1d88dd7feec0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Paint
11b085ef-94a2-4b9c-aa58-35a00884d715 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | DCW Install
808e0105-6d6b-4722-bf96-24dcf4b73f52 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Motorised Supply Damper Installation
76b686b3-8cdc-4fd0-b041-413791e6a5af |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Electrical Installation
f620ce32-6527-41ea-806a-65b5d3de0652 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Passive Fire
363273ff-653e-4292-94d4-af75dcc6bf0a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Southbase QA
cd57a197-9ac8-4714-aeee-affcbb5c8a2e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Defect Period
da8c6757-e03a-4fe1-ba61-b3c81c0d97c2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Air Plenium | Lockout
c5d2df14-a124-4896-a804-eb6a50bbfdc4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room
fee24858-60f5-4d03-ab38-3b2a835bfed9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Wall Construction Complete
109e8f74-09c2-4cdc-958f-825e4ce43856 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Council Framing
95e6dd4c-0f61-4091-b6f2-176a98c29314 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Gib Wall
debe79b9-decc-4b4b-abc1-49d4e802145e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Stopping
bef28ece-165a-4a00-97ef-03aeb9c2f006 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Light Checks
3acafa9d-4491-4945-b26e-3e6805d62a14 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Seal and x1 Colour Coat
749b9fd0-3af2-4035-a37e-4454dce208f2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Install louvres
6ded0f19-1508-4339-94f6-f0ea357dc46d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Install Security Mesh to Attack side (White Space)
e13c7864-2b34-4e29-a436-d1d41f3800bf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Mechanical Electrical Trays
9e30ef4e-ee4c-413a-983c-b5d07ae0f41a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Mechanical Electrical
0a8b0768-180f-4048-a5f3-195cf5961bb4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Plant Room | Hydraulic Servcices
ee17e656-91c1-4705-b860-99705b215c96 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Install Peroid
5459d68a-28ad-484e-9279-58ce77ebb201 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Install Peroid | AHU21-24
76f31c8f-808f-42ba-8484-1517a43387d5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Install Peroid | AHU 25-28
b01afac3-c283-4c84-bb5d-e352bedf3752 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Install Peroid | AHU 29-32
01bc409c-8706-4930-9d42-4a8fb9c99dbd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | AHU Install Peroid | AHU 33-36
a988899b-3704-486e-9f91-821086a1ab4e |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up
00f95d32-e278-4cef-a07c-8254eaea57f8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Stage 5 Structural Steel
0cc73955-914c-458e-a701-4c55a7af3077 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Louvre P5
0d14b66f-09c9-4aca-9be4-fd843f76ae0e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Stage 6 Strucutral Steel
1e6d095d-98a5-48cc-9b27-b10a1d000f48 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Louvre P6
46dffda4-e246-4faa-a60c-9e394bb8db9c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Stage 7 Structural Steel
424aad81-3f6c-4090-91ce-32efe8dc171c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Louvre P7
fc895a48-d032-4c1d-b191-498251dc467f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Stage 8 Structural Steel
68be852a-9f40-484b-8e03-e934bb507107 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Louvre P8
5c77bb9a-57f4-4b1e-9c9f-cc2c36b20b9c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 3 - AHU Services | GL 8-12 | External Louvre Build Up | Filter Bank Installation
397a8cdc-cb6a-4578-95cc-6722844643f7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms
53010589-1a40-4842-9380-73cd1f2b976f |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Data Hall 5 Power Board Rooms
304c9dac-f35b-48d0-8b83-0c0c87d85dc1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Data Hall 5 Power Board Rooms | Korok Wall Site Measure
6b7c3dd2-8c1f-4b42-a71c-bafdae49657c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Data Hall 5 Power Board Rooms | Korok Wall Manufacture and Lead In
945fa829-76e7-485a-8bb3-29274f234763 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Data Hall 5 Power Board Rooms | Korok Wall GL G Installation
f9224f22-ffab-475c-9fec-f2c39cfe86ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8
78b682d3-2c53-4ca9-8454-2d26b2cfa252 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Whitespace Wall Setout
b76ae718-fdf2-4c37-91a4-8ea96dfc4d20 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Wall Construction
96fdfdd6-3d79-49cc-98e4-94f05687dcc4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Council Preline
6cc935c0-592c-4429-ac7a-a68361a141c6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | 10mm Layer 1
dd8c7515-2731-4ffc-8b12-83240659e7b0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Council Postline
b34d644b-5550-4fd8-b0d7-f4102e46bd46 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | 10mm Layer 2 & 13mm Nib Wall
6f621145-e306-48de-9c3a-18cf7846c415 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Council Postline
8bc39d99-8e7b-4de5-b390-976aa66e915e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 3-8 | Stop & Paint
f66f2568-492f-4213-bc96-b29cc9e86e08 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8
70331a99-8260-460d-8fe8-8f6adb5eb1f2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Wall Setout
7a011962-49d4-4e91-889f-3892fc6510ad |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Wall Construction
2cc651bf-c8b2-40ae-87e4-fb7ebfc42be9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Council Preline
3285b5bb-e615-4934-b5af-a8a9f55f8bc0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | 13mm GIB Line
9f4b0492-17d8-4190-91ca-875d1d503f2b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Council Postline
0e6a25e2-efcc-46a4-a722-21d598850125 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Stopping
6ef2c00b-ab9f-4ffd-8921-8918a4a79aee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Door Install
06e9ba5c-ea41-44c2-b2c4-6861ede5c023 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Final Paint
eb94b139-aeaa-4a11-ab64-64d4be198f48 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Sprinkler High Level Corridor
ab3e0687-7f44-4b7d-ab27-41ee4225dc61 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/3-8 | Hydraulic High Level Corridor
70be9f67-5c03-4d30-8836-3b1cd407bf9c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12
4b6c1074-885a-49f7-bf25-88e4c268d0e9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Whitespace Wall Setout
33e824f6-f4a9-45d8-9435-f18f633d825a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Wall Construction
72c56dbb-66b7-4134-938f-a80cf7865b7f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Council Preline
0b6d8065-cf41-47e6-9edf-06af38ad7361 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | 10mm Layer 1
0d6057c7-f5b3-404d-8043-5d03a39b21b7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Council Postline
98d72cc9-3425-45f1-83d2-b8768f51f09b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | 10mm Layer 2 & 13mm Nib Wall
f24420f8-f78d-44ac-b48c-427db343bb3e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Council Postline
ba74afa5-b7b1-465a-ba36-d0a635e75dc9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | White Space & Nib Wall 8-12 | Stop & Paint
98619c4b-e20f-4a43-b59b-e1253bc44501 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12
5c995bdf-0d17-4fc5-aa86-2e282c28ea81 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Wall Setout
5b3f9c8f-4e76-47cb-8bfc-d7fec1f9c342 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Wall Construction
bfb7b6e8-8e27-4e39-adce-0ab8cbe0c1e4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Council Preline
c20b1616-5de6-4d2b-8e45-a269748978cb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | 13mm GIB Line
69c36fe7-544e-4891-97cc-c6bc44507302 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Council Postline
ffc65a3a-fb43-4740-8a2f-668ff81e3c4d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Stopping
e868e4c2-6adc-4edb-8db5-487ee929c4a6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Door Install
7bf6df6c-c284-400b-b903-d2034ba6d762 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Corridor Wall GL F+/8-12 | Final Paint
12f475fd-57c9-4add-8371-6af0f23027b8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS
218ffd89-9650-46fe-b440-cbd61c163356 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Sprinkler Range
eab32bbe-4222-43c1-ad2a-71a650a86307 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Mechancial Dampers
50f49ffd-7c04-4938-8fd9-21a693ef2477 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Electrical Board Install
fa87415f-d745-44a6-92a9-e1c9ccaa08a3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Wire boards
287a7e95-a3d3-4197-844d-00a639a6556f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Services First Fix
387754dd-78ee-4524-a98b-ce1237607c37 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Seismic for Services
5fad323b-d4b4-4654-8d7f-c53d47f3f39d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Cable Tray /Bus Duct
759e6d82-cfad-443a-a987-c6d9b1451a0a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Building Services UPS | Second Fix/FFE
91f05877-ad40-495a-81da-4a9a239eab20 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1
ef898c8b-4ea9-4b8e-aa98-42c456fa9a4e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Sprinkler Range
47e967a6-91c3-48b6-885c-2bc5d5ca26ad |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Mechancial Dampers
4c5b3d72-c599-4ac5-b3bc-1bad5ce5d7f3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Services First Fix
9ea343b3-635f-42a7-b815-7da962d35119 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Seismic for Services
7ed21b0d-388e-4424-a039-07277475d386 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Seccond Fix/FFE
ed6137df-3962-4bac-b216-930d8e83a2ce |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 1 | Cable Tray Installation
9120db50-9082-45fc-80e2-bb4b9fd9e1a6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1
78d402cc-1250-40cf-b732-625e670ebd9c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Sprinkler Range
0c85b429-1235-4fd6-b1af-043dd2c09626 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Mechancial Dampers
7077024f-02a5-43a7-8a89-bebac7e1aa88 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Electrical Board Install
a8cd0556-21a6-4381-bc74-06a593d3f964 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Wire boards
71c8d7a7-2777-4e33-8bc3-1a108a0da115 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Services First Fix
0b5f5558-30ac-4ff1-82d1-1f43623974da |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Seismic for Services
a4308cb8-334c-4620-b4e2-37fd5b02b615 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Cable Tray /Bus Duct
708f720b-b792-49a7-b298-f8a39b156868 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 1 | Seccond Fix/FFE
9e766818-51a1-4d17-9e57-53d944e134b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2
3f31bc01-4808-4b50-860f-9bec59300ab2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Sprinkler Range
55e26231-3b71-40b3-a259-ab920beed574 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Mechancial Dampers
e250ebda-f76d-4619-a664-12994c240067 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Electrical Board Install
5cdaab91-65e8-4721-8755-c0ecfc499a35 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Wire boards
e7956c2f-98c4-4721-89e6-b67029dad025 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Services First Fix
64ec6e05-bddd-4940-9ae8-6e0cf7e04c32 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Seismic for Services
2cbbbe4f-c81f-448b-a25f-ad20fd372596 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Cable Tray /Bus Duct
a36655e6-54e7-4ae7-85dc-7357a1612b87 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 2 | Seccond Fix/FFE
a2ea2c36-4372-4302-a42f-24a09555da35 | folder-normal has incorrect meta.stepType checklist-flat folder-normal must be display normal but was flat Unsupported Children: checkpoint-status Installation Completed(7e09b129-9809-558e-92b9-223e37c268ab), checkpoint-status SubCon QA /Consultant Inspection.(25700e69-ab28-5a74-866f-34c99ba6cb30), checkpoint-status Commissioning(0891de5b-58c3-5c31-b7e3-c35cefdce698) | folder-normal | not-started |  | step | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1
26445aba-f85e-464f-ad0d-1ee6ef5e3e82 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Sprinkler Range
e2ee2605-8eda-4817-a3c3-6e65fa241546 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Mechancial Dampers
d1f1e54b-04e0-41f6-bef3-e22070e3ec7c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Electrical Board Install
1ba0e760-e1c9-48b1-b92c-77f999b4092d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Wire boards
0d6e88ee-230a-4a37-84e8-4920559cf43c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Services First Fix
30487785-30a2-4bb9-ac69-ac11166c3a15 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Seismic for Services
3e161e05-d834-48b4-bfe4-1b77ae37d493 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Cable Tray /Bus Duct
5a2e4dba-b744-4faa-bcfd-15032362e459 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 1 | Seccond Fix/FFE
ab3c10cc-7041-4c9b-8608-8694f47629a7 | folder-normal has incorrect meta.stepType checklist-flat folder-normal must be display normal but was flat Unsupported Children: checkpoint-status Installation Completed(4801c86a-d8c4-5af8-8bae-e6da30445541), checkpoint-status SubCon QA /Consultant Inspection.(1a4fd683-69fb-5db1-8a59-1d2cb488b444), checkpoint-status Commissioning(c467dbeb-4210-5f6b-a389-e893daaef322) | folder-normal | not-started |  | step | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2
bf4c4011-1b4d-45d8-ae03-53c6a6dfbace |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Sprinkler Range
d2efc3db-7191-46c6-91e5-1032793b870d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Mechancial Dampers
e57104c7-4266-4e77-b43f-1622bbdcde90 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Electrical Board Install
2816ae3b-ea32-4a06-863b-d7bc37478072 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Cable Tray /Bus Duct
e2ed3227-b89b-4c26-8112-483a658c6b8d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Services First Fix
1886c9bf-725b-41ca-9847-39cc3d5c6d08 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Seismic for Services
3922ea65-0888-430a-b296-4ea319a19c80 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Wire boards
8634276f-72d6-4dc5-bfa4-10132ff926fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | COP 2 | Seccond Fix/FFE
7a2dbfa7-3292-4e1f-aaad-579a87a5249a |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap
cc8f0722-d542-4c70-9734-86cfeabb9d26 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Sprinkler Range
909fac67-ee88-4a7d-bec8-3826ad45c0b5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Mechancial
cea90b1a-f101-4a0b-afbb-52014352847f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Services First Fix
aec2e3a7-ecf6-44e4-99dc-ba7e58b1cd13 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Seismic for Services
5dc1afed-e093-44dc-b1e7-a61730c4c5a1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Seccond Fix/FFE
967d1717-acf6-4ad5-a572-33480c16c5ab |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Man Trap | Cable Tray Installation
b1827472-e671-4a0c-83ae-d76c6922e13d |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3
65969e89-0077-435a-a638-1aa59d4661ea |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Sprinkler Range
6224fd65-6fdc-4e81-b8f0-8b3a599bbeac |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Mechanical
96740423-7331-4d57-ba22-84bfbab48bdd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Services First Fix
7c45322e-5d50-4bbc-9731-b83094584dbf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Seismic for Services
4a12e8e9-9b68-4d66-bee6-b69f59ac7991 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Seccond Fix/FFE
e8103250-8e0c-4eb0-a37c-33d8c64fba85 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | FER 3 | Cable Tray Installation
addaf227-7c78-46e1-bc1a-dace185b8506 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E
c21587c6-6ccf-44fd-ad04-64459730fbc1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | HV Cable Install Brightwater
2bf6e701-6428-477e-a8b0-d350af12996e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Scaff Plank and Ply RMU Floor
5ef61b9c-9509-4f76-9e92-16f1bbd767da |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Sprinklers High Level
76383daf-79b9-4942-a39d-0e3c369c4599 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | First Fix
1c1895d7-7297-4348-9788-59aab76d1736 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | RMU Installation
6e793016-28d3-4e59-a7bd-315311e57dc0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Door Installation
03d2f8d2-3aa6-4644-8f37-08709cad47c0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Wire In RMU
1c07c75b-4f15-43aa-b3ce-471f3f7c352d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Seismic for Services
274221b3-95c0-4f3f-a902-ecbd6a214ad6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Bus Duct Install
a62241fb-9ba3-469f-93ec-12c9fc018925 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Fuel Line Install
574c342c-c708-4714-aaa7-35f5d779facc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | DCW Line Install
c046d343-7049-4b73-bbcb-8ef08371a1c6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Services Seccond Fix
38836397-ae59-48f2-8c97-8ce312f41029 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | Passsive Fire High Level
e4ad0ff6-94cf-43b7-a7a4-35f7d099a0e2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | FRP Installation
8a26338f-3014-4767-b121-537415871621 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU E | FF&E Install
ef0b3d08-df70-44f0-a030-f39a76a35a51 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A
3b5444bc-b809-47bf-9129-6946ef951811 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | HV Cable Install Brightwater
f03e98f3-8e78-457d-bcdc-807d046c5caa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Scaff Plank and Ply HV Floor
9d10dc38-6d0b-4848-82ac-07be8a07c952 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Sprinklers High Level
a6e2bfa2-b0f9-4200-914c-dc89dd82aa50 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | First Fix
7244f5b5-2701-4141-8587-73b7711700b1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Catcher Installation
38048eb3-55e9-44b6-803c-b84056f18020 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Door Installation
e80f6cda-d74e-4e20-8547-1e87a874aca2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Wire In Board
f1e0baf8-5f99-457e-8fb7-3151c17a4d54 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Seismic for Services
850b0b4a-0c6c-4c47-b4b4-0c25bf604888 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Bus Duct Install
d6689668-8512-4735-b410-cd4edf98a655 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Fuel Line Install
367033c3-d7a8-40ec-b622-1a6228cabb3b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | DCW Line Install
e0662974-4990-436b-ace5-2d80fe74ab7f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Services Seccond Fix
855f9912-a15b-4601-b5d8-1065cc19756b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | Passsive Fire High Level
16a8eccc-02f0-40cc-9fbf-6473f2f112bb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | FRP Installation
a5aa4d19-8683-410b-93a0-87b8c2d3f541 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher A | FF&E Install
fd274c43-7c06-4813-9eec-c2692a514d4c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B
e972a4ad-5f40-4d3e-b15e-3db609261bd8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | HV Cable Install Brightwater
cac7e367-1496-4f9b-81c7-6c5aa60028d7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Scaff Plank and Ply HV Floor
c3c2c55e-6152-4e72-a92d-9ec66c55e46e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Sprinklers High Level
e9970f0c-a4e4-4435-a508-12e9c3cca1a0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | First Fix
86d04a75-0016-464d-9be9-32e0d253de54 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Catcher Installation
909f179f-a00e-4556-bef6-296e81b882cb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Door Installation
7324cf5e-decc-4914-975f-a9253ef74b35 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Wire In Board
4ed54157-db40-4110-8e31-a088b0f5e65d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Seismic for Services
553794f7-457b-4460-bb01-0fb38617146f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Bus Duct Install
e70d52f4-335b-4119-879b-ca510555699a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Fuel Line Install
3f3d6fa5-a39d-4808-a721-b0ead3729d3c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | DCW Line Install
5d90eb82-122c-4b69-911b-783de1f208a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Services Seccond Fix
ae2cf4de-b708-46ce-ab4e-49a13250907f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | Passsive Fire High Level
14662b6e-5602-4fd0-8ff7-cfd0aeea11d7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | FRP Installation
d6562025-c374-4115-8df7-377bd57732fd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | Catcher B | FF&E Install
9df3d2c8-de2a-40d0-a54e-893375c4cbf0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F
9c377977-251e-4b10-a534-1b08ca318f84 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | HV Cable Install Brightwater
48f009d6-6720-46e4-9b9d-9f55a280ea3a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Scaff Plank and Ply RMU Floor
23b99b00-9009-4981-a182-5ae19f2b5e1a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Sprinklers High Level
b01aac5b-c95f-40f1-bfca-b61a999f9f13 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | First Fix
0ce39cda-f7aa-4cad-886d-c310a954f859 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | RMU Installation
2c16388d-bc63-4873-881d-7a6ea87e16c5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Door Installation
7c0069d4-f4f4-4465-af26-657826ffffe2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Wire In RMU
5148cb69-384b-45ae-a8a1-e9b28dc9158a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Seismic for Services
21a3ca12-361c-4bc2-bf05-b23be20e036f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Bus Duct Install
a2947ace-2717-4a90-9bca-6e996a6b0e5f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Fuel Line Install
b7a29174-4a71-464d-9b12-6400f92201a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | DCW Line Install
9be86800-8d5a-45ee-8ac4-5e2300787b03 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Services Seccond Fix
873aff62-5572-4914-b9b3-87e0d8923e1f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | Passsive Fire High Level
8905bee2-141c-4ae1-a606-81671361d4c9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | FRP Installation
efad9548-3b6d-4247-ae94-5fa60af995bb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | RMU F | FF&E Install
848960db-22a3-42e1-aca6-71b5892012f2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3
cb1b875e-b137-4993-8ed8-19b056a7a346 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Sprinkler Range
78a8c076-baa5-4cfa-92f4-af5382f1faa3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Mechancial Dampers
f441582a-22fa-4d81-8379-08684041148d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Electrical Board Install
75b89cae-a134-46ce-9563-2c761d4ed61f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Wire boards
d363614f-a37f-431c-b47b-d828dd48e9a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Services First Fix
071c4a19-6387-4d00-b5cc-610ea643a6db |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Seismic for Services
6e34e809-2fd9-42ef-a345-be05e5372997 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Cable Tray /Bus Duct
c72983fc-aced-4e1a-af44-288b0ef46476 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 3 | Seccond Fix/FFE
c27442ae-c9a0-4ab7-b0b6-3d605d86e334 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4
7537a3a5-51f3-4301-a0e4-e45750f251ed |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Sprinkler Range
b938592f-3d29-4a8e-bcf7-02c4636586ba |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Mechancial Dampers
32fc5cfe-8424-4ccb-91fa-e50c4fd0f2bd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Electrical Board Install
0eff5936-a301-4234-9043-fc62fe35a1fc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Wire boards
23eb1423-b895-4f97-965d-027d2c14d6ff |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Services First Fix
72e58dd0-a7a2-49a8-b114-ae8c94f53d7c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Seismic for Services
bf4b1b31-9f35-48fd-a3c1-e32ccabc1a4b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Cable Tray /Bus Duct
1dc165df-eaf4-44a5-ad6f-577edfc78332 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 4 - Power Board Rooms | USB 4 | Seccond Fix/FFE
0053d6f8-7f2e-493f-ac05-ea39f3e6ee34 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5
9af4a5ce-6f2b-4984-a563-37f0f1efc9ad |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Grind Data Hall Slab
6774caf1-608d-4725-9fee-3eb07062212e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Birdcage Drop
d0da9bd1-e8da-4429-a82e-c8a1579b242f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Steel Touchups and Clean
89ce4d2c-ef6e-4f52-b791-0555973c8e26 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Polish Slab
932714cc-7033-413f-9a6f-227d39335016 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Bondor Ceiling & Wall Install
aaed282c-cd2f-4a0c-ac3c-aa5390e928a8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Security Mesh
9e846975-e1b3-4f43-8bab-e4c858e5fcd0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Vesda Install
1509e660-a681-434a-96a8-ef8545c26364 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Hot Isle Containment High Level
ba0e6504-cbc5-4542-bf88-e1e40e3dd77d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Sprinker Install
bd35a4d5-9700-487c-a45e-fa4e5fc2e883 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Services First Fix Lighting
0f19c26e-2368-4aed-978f-51b533472ac1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Seismic for Services
a2ef737e-65f8-4901-93c2-b03d291529ed |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Bus Duct Install
e2dadcec-b450-42d9-b45b-e2e82e79003f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Services Second Fix
37950a5a-0f73-4d68-a802-f4e09ca8abbb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Cable Tray Install
731f65f9-6980-43a2-b8ff-4039587bb6ff |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | HAC Doors & Panels
b2d3f1d4-5489-44fa-9d86-a985c2ef0406 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 5 - Data Hall 5 | Final Paint & Clean
7b1daf83-c7d1-4fcf-8812-37cc888a92ba |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6
2021f440-d941-4f38-b038-ea7ec802d65c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Grind Data Hall Slab
b88f1708-c1d8-40fc-af1f-7dc0e095bb37 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Birdcage Drop
c8b02d2e-4bb9-42e9-b05a-24cfb2933e93 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Steel Touchups and Clean
e0e7cf68-3cdb-43c2-8a20-b9ed1dc24e44 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Polish Slab
e24e21d5-2ad1-43cb-a024-7abc43e68220 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Bondor Ceiling & Wall Install
67442f31-a513-481b-8464-bfa7544d3812 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Security Mesh Hot Isle
a1e4fd2c-2692-453a-9e29-410e4a67c624 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Vesda Install
4e4cf4f1-d7a9-4219-b8eb-d59a9958abcc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Hot Isle Containment High Level
af229741-c00f-43b4-a618-e235b4fb34f2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Sprinker Install
0905f860-304c-471a-bbfe-8f784710b9ca |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Services First Fix Lighting
a19ac142-85b3-413e-82a7-764902474171 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Seismic for Services
8d790dee-5370-4ea0-9634-b47f4ea5ff85 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Bus Duct Install
5bb76a5f-e28a-4ea1-89b0-a2ca0d62a6f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Cable Tray Install
68dd3e51-360b-4dd9-bbe7-52c436c01d48 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Services Second Fix
de9c12d0-e90e-4560-9f28-e0a06e68e354 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | HAC Doors & Panels
12619981-38a5-43bf-a14a-7bcbe15f4a04 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Security Mesh Wall
1076e2fd-068f-4754-b140-a68a183ebf51 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 6 - Data Hall 6 | Final Paint & Clean
0a216e52-e14c-4b78-8466-9729abab6cb9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply
452bb809-59ee-4767-83fc-44b24a4bc2b8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Tank Install x3
70917de5-be61-494f-a49c-6ae75bb75166 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Seismic Bridge Install
2467dcdb-bc00-4cb2-a299-0688c3d60830 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Fuel Lines
1e3d62c8-adb6-4dc0-9f44-fed51f54a6e2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Electrical Works
04e172c6-eeaa-473b-b5c5-2fb985927c15 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Access Platforms
56146505-30e2-4a93-98ef-fe1e8915f0ee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 00 | Zone 7 - Fuel Supply | Handrails
d099919b-aaa2-4dd9-9ee9-7cfda8245a3b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01
29619266-a9f5-45af-b8e0-3e451951cb7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build
0032e143-8f82-461f-8cdd-9b31c9e12126 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Monkey Toe Walkway
2520cead-1adb-4d32-88b6-7b3fe96e0b2f |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators
bed46284-8830-447f-bd7f-d9065d28e905 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators | Shrink Wrap
97d8b312-f3ac-493a-a8a2-7c278201b516 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators | Membrane Complete
9f6f8b82-8dc3-4d78-b3d0-0806d9d59b63 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators | EAF Plenium Cladding x1 Side to be left open
48c2eb0d-1c45-40ab-83b1-1a1a491ddcfa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators | Extract Air Fan x5
d48e0f6a-92bc-4c53-accb-d0c288dc8173 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | EAF Enclosures Genenerators | Close in Final Wall of EAF Enclosure
c33ba5ef-78f7-4689-8651-070faa6df95b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Exhaust/Radiator Penetrations
5bcd809a-1732-4685-b5b2-d232f6b28882 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Exhaust/Radiator Penetrations | Roofing Membrane Complete
cdc3d9b4-a524-4ec2-9c62-1f2994b3f574 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Exhaust/Radiator Penetrations | Install Flue Section
2010b980-1139-48f6-9dde-ca07ad39bba9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Exhaust/Radiator Penetrations | Membrane Detailing
7f9e7653-3a0b-4410-ab7f-d3ffe2c2342c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Exhaust/Radiator Penetrations | Circular Drip Flashing
6c63a1c2-b3a2-4cba-a7b9-b42f794e6841 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Transformers
b08719ba-ba07-4185-b937-03adcc6e3e02 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Transformers | Shrink Wrap
582631fe-8018-4c41-8858-5d1c6801b214 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Transformers | Roofing Membrane Complete
176dfbac-b2a2-4c8b-9b34-ffcf726956ca |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Transformers | Install Passive Vent Cowl
4fd1f03f-109a-44b3-b307-fc7ee29fa000 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Transformers | Generator Roof Watertight
05a30b28-8935-47f1-937a-30487908dd96 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Radiators
45234e54-6aca-4c36-9715-051fedd9c2b8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Radiators | Radiator Deliveries
7a9c8d47-52de-4793-a5e8-9bc4a804217e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Radiators | Radiator Lines Connection
00146b33-8b25-48c4-88fc-4ab1b1cd0d79 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Radiators | Radiator Electrical
362efd91-abd4-40a2-92e3-b5b3321dbcee |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators
5c1d493a-753a-48c2-a2eb-939e4e4df7d0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Fuel Lines Install
558d6488-8c55-4381-8768-0be67475d1df |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Secondary Steel Install
c3e664b1-e692-4aba-ad38-46c2d49c6f1a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Large Muffler
6d47d411-3c96-42c6-9882-2dabaab72ca4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Small Muffler
8491753d-aec4-4e4f-8ad0-695af991e235 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Secondy Steel
f4633be3-9326-473e-9ead-f01d51ee1aef |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 1 - Generator Build | Generators | Flue Install
0d7f2854-d95d-4655-b2d0-34a35ce09373 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant
f6f0ff2d-ae25-4f1f-84d7-d5f37d5ccae6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck
a4133414-b29a-437a-8af1-30e24c24a6cc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Chiller Installation
bd0a89f0-54ff-41a6-ab98-1463f14e61c8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Submains Chillers
2a494a6c-2abf-4cfb-b072-406c59c5beff |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | E4M First Fix
96af5279-278a-4074-b887-dd0b8a412e57 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Buffer Tanks
f051197d-1e38-4519-8f13-838aaad249d8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Chilled Pipework above Plant Deck
3fe87ff0-6cd8-4e86-98fe-cd438b02117b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Pump
479140fc-3cc1-448d-9923-12c768392cee |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | Cladding
76abe602-e6e3-4e85-ac78-be6732b27f8b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Chiller Plant Deck | E4M Second Fix
291838d8-28b2-4b1f-a812-feaf8ea3ff16 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof
7f72d27b-ed98-48e9-980a-a3b19f15ff77 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof | Monkey Toe Complete
74db7bd9-1fd0-4c16-9ded-cb2a8ef5d364 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof | Split Install
314786fe-0eca-4349-855e-79be43b7c140 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof | Refrigeration Pipework
e6b2682a-7d28-4763-97eb-4788a3335a27 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof | E4M First Fix
b7c4081d-194b-4e72-8384-3cee1e10a0b9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 2 - Exterior Chiller Plant | Split Lower Roof | E4M Second Fix
19ca226b-aae5-4db6-bfe7-9a8f2581a7bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air
6f0cd52d-6888-4fa3-88c6-48e5fde94474 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Cable Trays On Bondor
9dda6834-3ad4-4ed0-9018-29f74e2c1c4f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Handrails and Gates
9824552c-012b-4d38-9a21-895777e3b538 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Seismic for Services
199274e4-b41e-4706-a3db-94e8b44ad3ab |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Cable Tray Install
77a3b717-33d6-4859-9307-3e34c3736cd6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fresh Air Supply Ducting
0f8ec913-b5d0-4466-a02f-97513f4937b2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Split Unit Install
db2922a9-843f-409c-b150-60cb4c4d9849 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Split Unit Seccond Fix/ E4M
2f5c8611-3bd1-41db-bc2d-a448df3aef64 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8
c60a227a-ffe1-4dca-899e-bb71a17de178 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8 | Spill Air Fan Install 3-5
efd88c73-0a44-49dc-b884-c15aa7097298 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8 | E4M 1st fix & 2nd fix
8eb5495f-3d68-41f8-82fc-148a246baddb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8 | Spill Air Fan Install 5-8
8731257d-26bd-472f-b467-4af9b6ddb959 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8 | E4M 1st fix & 2nd fix
c46e1900-a938-41cc-bbc6-ba146a2a3408 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 3-8 | Spill Air Wall Carpentry
3939d914-543c-4bbf-937b-529f99178f9c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12
4ea14d93-e7d9-4764-ab77-59280286f736 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12 | Spill Air Fan Install 8-10
2614c042-579b-46b5-9576-f7ea9cd783ce |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12 | E4M
284d1225-e545-480e-af69-072c1aa834e3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12 | Spill Air Fan Install 10-12
b9804067-ffa1-4623-9889-b9319cb9b21d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12 | E4M
98b6d4c2-59fd-4010-b078-e35b8338162a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Fan Array 8-12 | Spill Air Wall Carpentry
c5794797-b687-49c5-b013-1f9fd5d045c6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock
8dda7c49-8c1f-49b2-b842-0a5ee350f67b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Wall Seout
65f40822-faf4-4ee6-ab3c-9f2026709c1a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Wall Construction
e6242665-ebcd-46cb-93f6-787f8f8f0f71 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Services First Fix
9b3c0010-ef55-48ac-a188-efe19c4bb4a7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Council Preline
67f17a3f-4ea5-4bfa-8b74-d91bdc29566f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | 13mm GIB Line
2f06d384-800b-461f-a6d7-61a0be96f97c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Council Postline
604d13f2-a063-45ce-a1af-12558453bbbc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Door Install
54b9f9d4-77e7-4b00-ac1b-e30d9b04dbec |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Stopping
1107f9fa-ae4b-45a7-bce7-20f71d89b323 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Architaves
13a58b77-9b10-472c-b110-8c5460d5a601 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | Air Lock | Paint
ab9434f3-05d9-4569-85a1-cf5643f812bf |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms
85968c60-376d-436f-9db0-e6515007859b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Setout DB Cupboards
b53e480b-afbc-464a-9314-4cf0b5c27e57 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Frame DB Walls
11db87a0-39e8-4554-aa79-4548ea7e05d3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Council Preline
880e5861-dbaf-4188-8bd1-8daf5368d563 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | 13mm GIB Line
e647f4c4-06a2-4b21-b6ae-957b11bc0186 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Postline
3ffb16e7-504e-4e5c-8efa-15d880411ac5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Stopping
effbe071-4ab1-4855-abf2-f3db32a9588c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Door Install
8b159057-e0db-4861-8ff7-e861edf2ff1b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Architrave
5362526e-934a-4ef8-9f78-e4bb4f892976 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Painting
e8abfe34-2fe4-41a1-8950-9c5a1632ef40 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Install Boards
e8551b34-f7d0-40ea-8cb4-77e2acd30eb4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 3 - Spill Air | DB Rooms | Wire Boards
381b60f2-4ea2-43a7-a4cc-5aca23bdd44b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room
88841aff-72c3-47ba-b98f-1d455ffcc14b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Fire Roof Complete
dee8768f-0c56-4253-a816-3c98e1184705 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Sprinkler Install
4e9f30e7-8be3-4fac-bb25-39c70a3e86b2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Wall Setout
59591b68-f1ce-40c1-84c3-2b3cdf5028fc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Wall Construction
a138990f-5f1d-43fc-a1fe-65ab623d20b7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Services First Fix
55bff4c5-8f40-4eb3-a6e7-abd6bce2731f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Council Preline
a806afdf-1a4f-4204-a5d0-2b4f7cca4e2c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | GIB Walls
e5e77ee4-cab5-4774-815b-b4125304699b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Council Postline
f31cb676-eff9-45b4-9657-d5e36702ab33 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | 10mm GIB Wall
23fac1dc-568c-4e07-9644-803b44be266a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Council Postline
5f9bf083-5fda-4c32-97a1-54a69b01ecd4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Stopping
bdff22fc-566a-4bed-b55b-24fe503ee2d4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Paint
58f4c6ec-3f33-43ed-b4d7-d387ef7d8940 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Chilled Seismic For Services
a0a9eb96-fc0e-44aa-aca9-c8d8b7cdc475 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Chilled Pipework
a97bd783-e12d-4007-ab26-3088c36c6376 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Seismic for Services
9a81cb56-5e02-405d-8684-b328ada66c99 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Expansion Tanks Install
50df544d-063d-45d6-9429-800c595570a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Switchboards to Postion
454f2f42-6997-4856-a6f5-3dc5c4404e11 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Seccondary Steel
e5b3ad6a-0631-465c-b1a3-dc9ee33962f8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Heat Recovery Units (ERV's)
3b6429bb-7644-4822-9559-23f8e5c452b8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Ducting Install
b50faf4b-7b93-436d-a2f6-cf650c58d161 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Cable Tray Install
3b7162e7-871b-4719-9a6a-95072c9d2d2e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Hydraulics
2a7e63ae-a388-414d-9124-ed1063e6f112 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Seccond Fix
0f8b20cb-8cba-476f-ad5e-b4ffbf20e05b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 4 - Mezz Plant Room | Wire Up Boards
2c9c9da3-dc13-431e-99ba-cd97f84ba73c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway
f364bcc3-6924-4e9a-8639-8cc33462c8c5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall
9d48ab49-8ad0-4384-b834-da6a965f6d5d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Wall Setout
e1e6ba2c-9528-421d-acab-d55db1d5e636 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Wall Construction
ba73f227-6177-47ac-b300-aeec255b3a50 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Frame out Dampers
5b58b779-ac34-4465-9721-a97ba01ec95f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | First Fix
1475f519-bf12-4e0f-b37a-215e2e0cc515 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Council Preline
9db06209-e5c8-44f1-bce4-630f71d13406 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | 13mm GIB Line
56cb4450-bf05-4c7b-b484-584eaf543f6e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Council Postline
f95e7e33-e3fe-4174-9d62-32f1f531a4fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Stopping
c0198f5f-f14e-4932-accb-088e9af2c9f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Painting
f68d439f-1813-4b78-932f-ab8bc847c40f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | White Space Wall | Return Damper Install
c8e7ae32-cd3a-4960-8201-c0702cb6085a |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards
2ef5c49d-c57e-4763-9b92-6949a0a757e9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Setout DB Cupboards
edb6d42e-f6e1-45b9-b4aa-3a88eff26419 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Frame DB Walls
867ed01f-4b68-48fc-b8db-03e0016fa96a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Council Preline
7639c88b-2f43-4ef2-9c6a-b8dcf0a34387 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | 13mm GIB Line
a4592bfe-8d3b-49e4-b872-bf6df39ba71d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Postline
5609f58f-8280-4117-be5b-dd50b7db3bb8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Stopping
c6b3a8f0-8b15-4ce4-a343-6103d999c2e7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Painting
e33445f5-d4cf-4496-9953-901b521c5fa0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Door Install
565a97ad-3d34-47c6-8cd0-e1f90c0a99f4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | DB Cupboards | Architrave
703449c2-80ea-46c0-9e6b-a619df488428 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways
821343e2-7329-48e5-90ee-4cbf343bfc63 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Handrails
25c30c4d-dd5c-4c18-a19e-936b5af1de58 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Sprinkler Seccond Fix
c0a22281-fda7-40ab-8ec1-aad4ceac6bbc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Chilled Pipework Corridor Runs
bf65aa0b-b975-41ad-b733-01dbb4955151 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Chilled Pipework Take offs
b4006b8f-88d6-44e3-9c14-c507e96256a7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Cable Tray Install
e09a9e38-45ca-44b2-add2-ac371d4064b3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Lagging
e7d00750-ba7e-4af8-8c28-dc17c7fc9365 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Canopy Construction
88b98b4f-4278-4e26-a6e9-e155dc60667c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Bondor Canopies
2aa17b5c-9e49-4b62-a454-bbd7aa6eff09 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Switchboard Install To Cupboards
4fc7e9ad-b4ba-43b1-b994-0108c06ddeeb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | AHU Boards
35c749bf-bacc-4cd1-a976-a2a3343e490f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Wire Boards
20872009-32e3-41a8-8ab5-8d9bc92672fa |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | Second Fix
61f510a9-5e00-4bbc-9e56-195b4abf7951 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Internal Services & Fit Out | Level 01 | Zone 5 - AHU Walkway | Fitout Mezz Walkways | FF&E
e4e93788-6ee6-460e-a895-f1f9557a5fc4 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Project QA | Civil Exterior
9e7329fa-7d36-47fb-85dc-b8dd92ac8ccd |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Site Fencing
17c4c793-794f-48f9-8ea4-54872cadfdb2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm
81f10dc8-e1ae-4900-beec-bfdb8d93b712 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Site Setout
75b7af7b-e1b4-45c5-84cd-892943636e56 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Install Temp Fence
5cd380d3-ee73-40a1-b1d9-82ddb05d4af5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Remove Spark Fence
7b52246c-9127-4561-ab21-443dae42b4dc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Excavate Anti Dig Plinth
97c15165-745a-4f4e-95f8-baf3e669e466 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Post bore Holes
8cadc5a7-8ee4-4785-9075-ecf3b4c8d370 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Place and Brace
e2fe49d4-05d1-4a8b-8a14-5a3bf2c87c1a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Pour Posts 100mm Short
ac18f658-9d0b-40d0-94a8-e31efdc8bd5b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Install Rails
ace6bbaa-7b8b-4edb-8e92-c9489b2f0acf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Pour Antidig
0114156c-f557-47e4-a7a4-2894f7b34eec |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Install Pailing
41c4b1a5-5772-4070-b3fc-db48cf9edeaf |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Remove Site Temp Fence
f3bc9a3c-c8c8-447e-bbb7-7731c34b5f43 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 1 Eastern Boundry 220lm | Complete Phase 1
7255a337-4cc0-48e9-a72b-5742ab60389b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm
5536dce8-7423-4630-ac10-26c82a7fe719 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Site Setout
1f100bad-1e93-46e8-8d62-752e018a6dd8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Excavate Anti Dig Plinth
8ab599d5-2f9e-49bc-9af6-21e40f23fd6c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Post bore Holes
965ec323-77df-4030-8745-56636c1be481 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Place and Brace
c011efb2-e457-4dee-bf2d-e11dc3ec0a0c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Pour Posts 100mm Short
97c62ffe-30c1-43e0-8584-f5b60ea3a065 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Install Rails
826a6caa-5bad-4661-a66d-6d87765932f6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Pour Antidig
77bbfdb1-d54e-4bcb-81f3-abd1f149622b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Install Pailing
530c1707-7476-4922-ae68-5df5226c4116 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 2 Southern Boundry 115lm | Complete Phase 2
dbf75401-e3e4-46c1-8486-a49ca82a21b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm
47342716-8e4b-411d-89cd-94bedb575aae |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Site Setout
0f2e8558-177c-466e-8466-d46f7cc36686 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Install Temp Fence
e8bde745-2edd-4bff-8fa1-487a92963f5a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Remove Spark Fence
115580d6-6f1b-44c2-a8bd-9f75f71c363d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Excavate Anti Dig Plinth
0e73b9da-9fde-4b84-9d0e-53a687e9cb08 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Post bore Holes
40396dd4-5df3-4165-949e-227fd42dec6b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Place and Brace
cfc0c575-1d9d-4a73-afca-e513f5c7d4dc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Pour Posts 100mm Short
006e54ad-f2b3-41b2-828e-9585cf51bb42 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Install Rails
136a6f21-5280-4e43-959a-60501034abb9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Pour Antidig
329448f1-d059-4f91-8693-393a241c7f07 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Install Pailing
ce4029c8-4763-49de-97f8-102985238c74 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Remove Site Temp Fence
719aa95f-13ef-43d5-8a64-7ec9eb592a90 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Site Fencing | Phase 3 Western Boundry 220lm | Complete Stage 3
a2865982-beec-43f2-a4c9-f00291792a4d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway
8f767503-e2cd-4ff9-a05e-0552686157a1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1
dc3e21dc-84ee-4833-a223-3195ebead9b4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Survey Setout
43074073-be34-4bcf-b13f-f51eb852c2d7 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Excavate Conduit Lines
b85a67a8-2e99-440a-8243-a41697c7970e |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Install Pits
4630b38d-6e3b-47b8-b0fa-52f9d090d447 |  | checklist-flat | work-in-progress | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Install Conduits
440b0926-077a-4d41-935f-ff8128ae1d4a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Waterproofing to Conduit Penetrations
0a6b4581-e85d-4e0d-a2eb-2ae8635308a2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 1 | Backfill and Compact to IL of Hydraulics
52958ee7-cf93-42a8-95f6-1b488a8bc40a |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2
1ec2fe28-305e-4a43-818c-aaa76514b251 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2 | Excavate Surface Water Drainage
451ac54b-7fda-4443-b840-514d0b30eea5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2 | Install Bare Earth Cable
d483d22e-6b17-40d7-bab1-dafddb50a1e7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2 | Suvey Setout
5b00d035-503b-4673-813a-fae2d9052a10 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2 | Install MH & CP
aa8b8ba9-997c-4d33-8b74-8b34d7728ba3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 1 - Laneway | Phase 2 | Backfill and Compact to underside of roadway
e041d33b-8653-4382-aa9d-e9f1c83f2b47 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road
72897b6b-33b7-49bd-b215-b7022188e71c |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester
5d43e2f8-d8fc-40c0-831c-e0801cb3e163 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Fence off
4ee9a787-c568-49d0-9a20-0bc91dd99a86 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Survey MH
f8a7f74b-f984-4312-b695-cd9e55574191 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Excavate & Install MH Chamber (SWMH-01.02) and break into Scruffy Dome
f3e57434-850c-4c95-af1c-80d39a675073 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Excavate Stormwater Lines (SWMH-01.02 to SWMH-01.03)
461ead20-5356-42da-8cd7-2079aa4b27fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Place and Backfill Stormwater (SWMH-01.02 to SWMH-01.03)
5994f1e9-3514-4d27-91da-477bed141d10 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Survey HV and Coms Pits (5 no.)
de077973-cb4c-4371-b834-63bfd44f9e9e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Excavate and Install Comms and HV Pits
751be540-ba4a-47ad-9a9b-578ba0b08d35 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Install HV Conduits (3no.)
f3735455-8b35-4a30-a9ea-eb423ef7159f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Backfill to Supgrade (GAP 65) and wrap with Geofabfric
af60d92c-660c-4d1e-aca7-f1fdda55a8b9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Place Sand Subgrade including Bidim
2291e538-6df1-4063-ab11-1f16125b9627 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Install Fibre Conduits (9no.)
b717b849-95f5-4d32-9c40-51c345dc7d48 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Install Fire Ring (including 3no. Hydrant Boxes)
e450119d-29b8-4d6b-98a7-c985ec2f5aeb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 2 - Carpark Compound, East/South Ring Road | Fibre Connection to Porchester | Install Geogrid and Place GAP65
c0c48e7e-8699-4642-857c-ce1fd5ab0e35 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team)
471b5a4e-5b6f-4d32-a3bf-2088f8e21880 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Decomission Stormwater Line + RL Dig
cbc1331b-6344-4e67-a496-d49fb5345b98 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Excavate Fibre Route 3 External
85322780-9c45-404d-9d0a-026958e0bd05 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Blinding and Install Conduits x3
9fab1664-920a-44be-a1e4-0d7a0608c5f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Excavate and Install Fibre Route 2
9d613766-1fdb-4b0b-a59d-de79cd1ac4f4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Blinding and Install Conduits x4 + Pit
53d34d97-d798-4acc-8446-99b0d5310e53 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Install Bare Earth Cable
1a32cc40-cf8e-44f0-a6f4-fb8ddf35f39b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Detail Excavation & Blinding
c0f212d8-67d0-4bdd-ba98-6b8b8a1f0b16 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Setout Waste
4da0840a-8cc0-4bd7-a90d-fc209965d2e5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Install Waste
365ad33e-c7da-4f4d-bb98-894a5a4468e9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Setout Stormwater
1dd108b5-14e9-4177-a9fb-c89d5852de23 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Install Stromwater Lines and MH
dc1c339a-5bea-4974-8cfe-c52ee583216c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Council Inspections
e6c94f02-1f92-44bd-ac16-db2b2e28b81a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Install Fire Main & DCW
24e4f4e7-abb7-4740-ad76-69436eb6ef9a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Council Inspection
4aa01676-64a7-4e14-ba7d-5d3f16994bc4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 3 - GL 1 Services Alginment (Confirm with cladding team) | Backfill
4e24fa4b-5d1f-4c62-b792-7d92c0760469 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2)
51260953-a48c-442c-8ec0-7c2f41cd4c3c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Excavate for Service Installation
80cef373-4308-42c5-8db1-3dea2c5d05ad |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install Stormwater from SWMH-01.03 to TP 10
2c74eb72-7603-493d-bf66-13dd8b07f15d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install TP10- Proprietry Item
b493d7e4-f9bf-4d5a-84b1-213b657b5808 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install Oil-Water Seperator
0bc00a1d-c0e1-48ce-b007-d92fa1ac65c8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Blinding and Install Electrical Conduits x9 (infront of Pod 3) (inc 3 pits)
c9861bce-10b7-4398-91b1-f122ff818495 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Excavate and Install Fibre (infront of Pod 3) (inc 1 pit)
a1b834dd-19de-444d-9a98-5343fdbee010 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Blinding and Install Electrical Conduits x9 (infront of Pod 2) (inc 3 pits)
ba70989d-a03c-4002-98fc-73301d3935d7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Excavate and Install Fibre (infront of Pod 2) (inc 1 pit)
8c1997fa-c575-4d39-8efd-22aeb281b80a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install Bare Earth Cable
d2ad4940-44eb-4382-8d2f-7dde4eec0189 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Setout Stormwater MH02.02 and Scruffy Dome
14d37106-ba9d-469d-a43d-19ee98a2d204 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install Stormwater Lines between MH and SD and Into service lane
e02a3dc2-243c-4626-8f21-a560e5851724 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Install Fire Main infront of Pod 3 and Pod 2
fbf71a7c-0b09-4404-b205-ec652325c0a1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 4 - Fuel Farm (from East Pod 3 to West Pod 2) | Backfill
aa3b6166-f196-4e0b-8f7f-c2610beae806 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring
df8f70cd-f445-4f81-9435-a251383d8443 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Bare Earth Cable
b23889ba-638f-48d1-8848-057be504423c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Survery Set Out Manhole
35b4a4c7-2290-4793-8b64-b68bcd400d1b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install MH & CP
7974815e-7bab-49ba-8bfd-595d58c2164d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Stormwater Pipework
3dc23936-b09a-46d2-b08a-e3d3991852eb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Council Inspection
192ce65f-b6fa-42ac-926c-de4bb7b8c0dc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Setout x2 HV Pits
3951ab6d-81f4-4018-a7bd-cce15d6ff439 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Pits
ef711b54-6816-4c29-95d8-44c1197af945 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Excavate Install Conduits Between Pits
bf7680f8-0402-4fd8-ad1f-384bf7fb5169 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Survey x3 Fibre Pits
58f5ea77-9564-4a4b-952f-914d33e0d7a0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Pits
c96a0ba2-f94a-44b8-a20d-95066a07e864 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Conduits Between Pits
9b6d4f54-b784-4a3a-9001-4e3a8d4ddfc1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Excavate for Fire Ring/Hydrant
6b209e5a-9e89-4a16-a9b0-0aa4c8619bc5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Install Fire Ring/Hydrant
dbd7a390-3dc1-4c37-930c-0ade854d0655 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Council Insepction
09b21b2b-1f2a-44a5-b21e-f9b0b34763d3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 5 - Western Ring | Backfill and Compact to road underside
98070da5-53c9-4fcb-98c3-cab4f0f2947b |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Civil Exterior | Zone 6 - Spark Side
2ca60a87-a498-4721-8330-1fb843f286fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 6 - Spark Side | Stage 1 Completed
3ded1041-d80d-45d0-ae09-d9862efb0b94 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Civil Exterior | Zone 6 - Spark Side | Vector Works Complete
0d81b480-5b4d-4bf1-b5c0-5df088230494 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Completion Phase One
5ce30088-aa70-448f-b1c6-b02bc62574dd |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase One | Client & Consultant Inspections Complete
6676984e-cc56-4a75-ba23-d93d686c46a7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase One | Defects Completed
5fc7a99a-6e6e-47f6-b906-293934bab3a4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase One | Interim Comissioning Complete
e14f1524-abae-4940-8757-213b0064d396 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase One | Interim Warranties and Certifications
2af7dea3-fe15-4e08-97d6-652696822349 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Hard Landscaping (Roads)
8e34465b-42e8-41ad-9e19-ad6c5626e3da |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1)
9317d98e-5d86-4958-975a-8cd84ec45ed8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | A29 GEO Fabric
f3ec67c1-ac83-46ef-890e-9d69972fc2c2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | 500mm Sand Blinding
67acce87-4ed6-4745-9e48-1d1e8113d278 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | A29 Geofabric
f14ddd94-d832-4aec-a55b-f9898a04ae68 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | Geogrid TX-170
06f6c1a2-2f74-45db-8cec-14901f246366 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | 170mm Gap65 Compacted Subbase
7eb04924-4d57-4d00-b6bd-941f22e1c5f7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | Install Kerb Raft And Kurbs
af5e5daf-ef8a-4546-981d-9b2fa6d78e9c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | 150 GAP40 Compacted Base Course
8b30833d-ced3-46bd-9ef3-595628fa022c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Ashphalt Ring Road - (East South Detail 1) | 35mm Asphalt - Metal
010b20b2-6172-4490-a56d-6081278c27a0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3)
82a740c1-d593-4d24-8b54-adfbc04af9f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | A29 Geofabric
83bc36c5-e843-4dbf-aeba-519f00b443f0 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | 500mm sand blinding
9cb8d775-ded1-4dfc-a51b-35cf9603cbeb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | A29 Geofabric
e80a77c0-c07a-4aff-bcaa-22d7f14cf2ba |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | Geogrid TX-170
512d8299-62a5-444f-bca8-bb12f765503a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | 170mm Gap65 compacted subbase
26b1b1ef-9715-4541-9bfe-013a8cf30041 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | Install Kerb rafts and kerbs
a2b6bb94-2daa-492c-aad1-4a0ee6889209 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | Install Stop end shuttering
c8a04a45-f80d-4b11-b27b-a3f0f635f3a2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | SE72 & 82 Mesh install
fb6e7962-b6af-471c-b36b-b97dc6e89f8e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Western Ring Road and Truck Dock (Detail 3) | Pour Concrete - 150mm 30mpa
43ff0b01-7125-4058-862e-21df527e78db |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6)
f2048397-c8c3-4f05-a9f3-3af17cc51d4f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | 150mm Gap65 compacted subbase
d1237a6f-192d-473f-8792-de0e5a364732 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | External Perimeter Shuttering
0a9e1fd3-e6d2-45c6-ad2a-a6741160f764 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | 50mm AP20 Subbase
1991721e-5a93-4bfa-8f8f-7b11790aa8e8 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | 10mm Chip
bac6db6e-5e40-45a0-bddd-7de8c1875931 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | 1 layer of 665 Mesh, Central
c96815ae-8aea-4e6c-a3df-0ce45c83bb0a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | 150mm thick 20mpa concrete
abae89e4-041e-4e5d-a715-42338c241c4d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Concrete Pad Walkway Between Pod1&2 (Detail 6) | Remove Reduntant Shuttering and make good
c28c7fff-14e1-4c62-af15-83357d3b683a |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad
33651331-e2e5-4e15-9f94-f08365452987 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | A29 Geofabric
ba32f2bd-bcd4-453c-a876-bc3669db16a9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | 500mm sand blinding
811d31d5-c9ea-4446-a61c-be008f8c220a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | A29 Geofabric
ad1ec18c-19b6-48ae-9175-0ccc25e43ad6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | Geogrid TX-170
544d98e1-bcf1-4b80-942b-4ea2123fad7c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | 170mm Gap65 compacted subbase
169c66be-5c07-470b-b893-b1d5cbde14f4 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | Install Kerb rafts and kerbs
c41f8af0-627d-46cf-a3a4-442b5221eb71 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | Install Stop end shuttering
69be9348-80ab-4d14-8023-6e6e4cb85a8b |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | SE72 & 82 Mesh install
0f450d0a-c882-4bbc-8709-482ec0846ac7 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Hard Landscaping (Roads) | Bin Store Concrete Pad | Pour Concrete - 150mm 30mpa
4ab172d1-f343-4298-9eaf-456e06445d31 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Soft Landscaping
f504c10a-9a57-4dab-ba19-68355f942070 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Soft Landscaping | Site Gates Install
51f2788a-e1cb-40b0-b013-81fbcba89fcc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Site Gates Install | Gate 1 - Eastern Chainlink
7b12d3b3-43c7-4633-be8f-7934d7bb434a |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Site Gates Install | Gate 2 - Westen Pallisade
95c79212-fdb4-4c3a-8dd1-7a736799ab77 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Site Gates Install | Gate 3 - Western Chainlink
c7fcdab4-734e-425d-9d32-a99d362091ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1)
d43b1315-b184-457c-af61-6f158e2ea4c5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Excavate to RL
c45de023-a7f9-47a4-86f7-40ec43b589d6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Place BIDIM A14 Filter Fabric
75b813cb-835c-4ed4-95e1-ee22c3b9a4ee |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Place 350mm Scoria
7f9201a0-cd0b-4479-8355-5f182ca929f1 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Install DN110 Slotted Drainage Pipes
a178b35f-a28b-4faa-a99a-55b39cb3566e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Place 350mm Scoria
42feece9-b635-41fd-ba5f-5dbffd3818c5 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Wrap and lap BIDIM A14 Filter Fabric
fe1d9856-8857-4ba9-9ad8-a21a1c81c81c |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Place 350mm of Free Draining Media in accordence with TP10
001aab97-521d-471c-ac67-6c03e62d2ba2 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Make Good and Complete Shaping to Swale (Batters and Base)
1e076630-c82a-4a07-ad55-118fcb39cdea |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | Western Swale structure (crew 1) | Planting
a76793d3-4f35-49c0-8072-8d1ca23c857d |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2)
281cd0cc-0951-4328-a0da-97258d4f76fb |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Excavate to RL
c4f29e9f-e2b6-4203-b2eb-b2c6132d82c6 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Place BIDIM A14 Filter Fabric
cb4fff8b-4762-492d-83be-fbf4316205b3 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Place 350mm Scoria
102e3863-3b8f-4d80-a6fb-a649ef9ba012 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Install DN110 Slotted Drainage Pipes
5cd16908-7a01-4ede-add4-f20f67cadeae |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Place 350mm Scoria
c831e034-5332-4891-a2a4-38d37f1c0970 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Wrap and lap BIDIM A14 Filter Fabric
5e52293d-29b3-4de6-a634-65b4a1474851 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Place 350mm of Free Draining Media in accordence with TP10
4b132d9f-e9a9-4565-8141-fa95398f4507 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Make Good and Complete Shaping to Swale (Batters and Base)
f331aeb9-44e9-496b-9f0a-1a267b42cc36 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Planting
aa7f4940-d04c-4fd7-9286-09e3461fd86d |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Soft Landscaping | South swale structure (crew 2) | Completed Civils
c8c56110-f35c-49d6-9a26-3b9da4d7bb56 |  | folder-normal | not-started |  | step | TRUE | FALSE | Project QA | Completion Phase Two
5f8d82b9-fc75-4ae6-802b-695d5a616b47 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | Comissioning Complete
613afc70-0d24-4fbe-995e-3eba81b13a5f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | Client & Consultant Inspections Complete
4b8c3fc0-aff4-492f-9e22-71d09df7ae7e |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | Defects Completed
a54e1b19-aaba-4360-8246-7a7f585e40bc |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | Warranties and Certifications
61659ca4-6780-4202-901b-8b0bcd6edab9 |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | O&M Manuals Issued
143f1d3f-fa65-4432-979c-17b64c25650f |  | checklist-flat | not-started | SYS - Project Fern Checklist (old version) | checklist-flat | FALSE | FALSE | Project QA | Completion Phase Two | CPU Granted
6bf8f186-112b-4177-83eb-57bfa0db9619 |  | folder-normal | no-status-not-started |  | step | FALSE | FALSE | Daily Site Reports
4c579482-cd0f-49b6-a0e4-718cbbfe4e9f |  | folder-normal | no-status-not-started |  | step | FALSE | FALSE | Council Inspections