## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - S - STO Poly Plaster |  |  |  |  | Yes | FC - S - STO Poly Plaster | 06b86352-d9fb-4548-a00a-22cb0e5daf15
checkpoint-status |  |  | checkpoint | Moisture Barrier installed with correct fixings & fixing pattern, checked and acceptable
checkpoint-status |  |  | checkpoint | All joints/penetrations/openings taped as per specs, checked and accurate
checkpoint-status |  |  | checkpoint | All windows installed, with air barrier sealant applied, checked and accurate
checkpoint-status |  |  | checkpoint | All head flashings are installed 3mm past end of window and acceptable
checkpoint-status |  |  | checkpoint | Foot tray, windows flashings and battens installed, checked and acceptable
checkpoint-status |  |  | checkpoint | Appropriate fixings used at correct centres for poly cladding, checked and acceptable
checkpoint-status |  |  | checkpoint | All cladding works completed and acceptable
checkpoint-status |  |  | checkpoint | Mesh Coat to plaster, banding installed, true and flat and acceptable
checkpoint-status |  |  | checkpoint | Topcoat and paint works completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Stopping QA |  |  |  |  | Yes | Stopping QA | 0956ce2d-1efd-442f-8d6a-6d2349e4f079
checkpoint-group |  |  | section | Stopping Prestart
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Bracing walls fixed correctly
checkpoint-status |  |  | checkpoint | No proud screws
checkpoint-status |  |  | checkpoint | No overdriven screws
checkpoint-status |  |  | checkpoint | Backblocking of joins as per Troake Backblocking guidelines
checkpoint-status |  |  | checkpoint | All areas of broken GIB dug out and ready for pre-filling
checkpoint-status |  |  | checkpoint | Sheets layout correct and in consideration of critical light
checkpoint-status |  |  | checkpoint | Grooved liners fitted correctly if present
checkpoint-status |  |  | checkpoint | All joins as per GIB site Guide above windows and doors etc
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area Ready for Stopping
checkpoint-group |  |  | section | Stopping Post Checks
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Screws adequately covered
checkpoint-status |  |  | checkpoint | Joints flat and level
checkpoint-status |  |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status |  |  | checkpoint | GIB® Cove joints acceptable
checkpoint-status |  |  | checkpoint | Floors scraped clean
checkpoint-status |  |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing completed plumb, level square and straight to the eye
checkpoint-status |  |  | checkpoint | Light check complete
checkpoint-status |  |  | checkpoint | Materials to be picked up from site
checkpoint-status |  |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Steel Stud QA |  |  |  |  | Yes | Steel Stud QA | 201156b4-1bbf-4a91-a813-6a952ce99585
checkpoint-group |  |  | section | Steel Stud Prestart
checkpoint-status |  |  | checkpoint | Is there a framing layout plan and does it have all necessary details and measurements
checkpoint-status |  |  | checkpoint | Is there a wall type plan and is it clear what walls are needing to be built
checkpoint-status |  |  | checkpoint | Do we have a door schedule/ door openings
checkpoint-status |  |  | checkpoint | Is there top connection detail
checkpoint-status |  |  | checkpoint | Are all services completed and finished
checkpoint-status |  |  | checkpoint | Is the floor clear
checkpoint-status |  |  | checkpoint | Do we have a clear run and is there anything stopping us from proceeding
checkpoint-status |  |  | checkpoint | Do we have enough DPC
holdpoint |  |  | signoff | Area OK to proceed
checkpoint-group |  |  | section | Steel Stud Post Checks
checkpoint-status |  |  | checkpoint | Have we done a check with a level and straight edge
checkpoint-status |  |  | checkpoint | Have we put building square in all internal corners
checkpoint-status |  |  | checkpoint | Have we checked all door openings are correct
checkpoint-status |  |  | checkpoint | Have we checked all walls are parallel
checkpoint-status |  |  | checkpoint | Have we installed DPC to all walls
checkpoint-status |  |  | checkpoint | Do all internal corner junctions have appropriate fixings for plasterboard
checkpoint-status |  |  | checkpoint | Have we left appropriate gap for deflection head
checkpoint-status |  |  | checkpoint | Are all materials removed from unit and rubbish taken to bin
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checks | 2b69c621-67a1-493c-8fc7-c6a8f988c5bc
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-sectioned |  |  | checklist | Insulation QA |  |  |  |  | Yes | Insulation QA | 2f4cfa7d-687f-4a14-ba68-6a07b63cc230
checkpoint-group |  |  | section | Insulation Prestart
checkpoint-status |  |  | checkpoint | Metal Ceiling Grid Completed
checkpoint-status |  |  | checkpoint | All nogs installed as required
checkpoint-status |  |  | checkpoint | Electrical wiring completed
checkpoint-status |  |  | checkpoint | Plumbing completed
checkpoint-status |  |  | checkpoint | Which walls and ceilings are to be insulated?
checkpoint-status |  |  | checkpoint | Garage included or excluded?
checkpoint-status |  |  | checkpoint | Any noise reduction batts to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | All left over materials and rubbish removed
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work completed as per spec
checkpoint-group |  |  | section | Insulation Post Checks
checkpoint-status |  |  | checkpoint | Ceiling Batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | Wall batts installed correctly and no gaps left
checkpoint-status |  |  | checkpoint | No proud insulation?
checkpoint-status |  |  | checkpoint | Insulation cut around (not over) pipes etc to prevent bulging of sheets
checkpoint-status |  |  | checkpoint | Noise reduction batts installed to walls or midfloors
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | All left over materials and rubbish removed?
checkpoint-status |  |  | checkpoint | Site clean and tidy ready for next trade?
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | PRE - S - Insulation |  |  |  |  | Yes | PRE - S - Insulation | 4b8ce1b7-9849-4362-b39c-cbe3cea0a7d9
checkpoint-status |  |  | checkpoint | All materials checked & aligning with consented design & specifications prior to install
checkpoint-status |  |  | checkpoint | Correct product & R value as per specification
checkpoint-status |  |  | checkpoint | All Insulation completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | B03 Defects |  |  |  |  | Yes | B03 Defects | 4fce2a5d-5221-41a8-9c89-00f8e8d0a26a
checkpoint-status |  |  | checkpoint | Living/Kitchen
checkpoint-status |  |  | checkpoint | Common Areas
checkpoint-status |  |  | checkpoint | Bedroom 1
checkpoint-status |  |  | checkpoint | Bedroom 2
checkpoint-status |  |  | checkpoint | Toilet
checkpoint-status |  |  | checkpoint | Bathroom
checklist-flat |  |  | checklist | B02 Remedial/Additional Work |  |  |  |  | Yes | B02 Remedial/Additional Work | 6db5af70-956e-49fa-8012-d1764501686f
checkpoint-no-status |  |  | checkpoint | B02 Remedial/Additional Work
boolean | 86dff885-f93d-5b44-bd82-2c49946b52fc |  | tickbox | Remedial
boolean | b8a21601-16d1-5677-b95e-adb0a8521ee0 |  | tickbox | Additional
checkpoint-no-status |  |  | checkpoint | 1
text | db7506db-a250-519c-b3a3-be5c5b395766 |  | textbox | 1.1 SI number:
text | a1747a83-f7d0-5d43-b1d2-ed0c9da243d0 |  | textbox | 1.2 Description of work:
button | 27f42eba-e31c-5747-b072-74763d96872f |  | button | 1.3 Troake | pass,fail
checkpoint-no-status |  |  | checkpoint | 2
text | 48be0e1e-9b1f-5a81-b1c2-7459a79b1274 |  | textbox | 2.1 Date:
label | 02a14135-957c-5ce6-8336-78a1c5baef8c |  | note | 2.2 Add photos – camera/upload
text | 9e948aec-76eb-5955-86a3-ebd7fec25e47 |  | textbox | 2.3 Troake Comments:
text | 485523bf-b4ea-561b-9bf4-9384f78b608d |  | textbox | 2.4 Ryman Comments:
button | a83ff0ba-cea1-51a1-8070-0bb29f6a60d3 |  | button | 2.5 Ryman | pass,fail
checkpoint-no-status |  |  | checkpoint | 3
text | e0424c16-7cd2-5375-92dd-3aa62f4715e7 |  | textbox | 3.1 Date:
text | 354e0d36-f76d-56d4-9866-ec6b932809fd |  | textbox | 3.2 Save/Edit:
checklist-sectioned |  |  | checklist | Fixing QA |  |  |  |  | Yes | Fixing QA | 6fb11ca0-a043-4181-b3d9-2d4da3f44942
checkpoint-group |  |  | section | Fixing Prestart
checkpoint-status |  |  | checkpoint | Exterior Cladding complete
checkpoint-status |  |  | checkpoint | Joinery installed
checkpoint-status |  |  | checkpoint | Doors liners installed including cavity sliders
checkpoint-status |  |  | checkpoint | Grooved jambs big enough (12mm for 10mm and 15mm for 13mm) on doors and windows
checkpoint-status |  |  | checkpoint | Walls checked to be level and planed if necessary with no protruding nogs
checkpoint-status |  |  | checkpoint | Metal ceiling battens running in the same direction and in consideration of critical light
checkpoint-status |  |  | checkpoint | No missing hangers or clips on Metal ceiling battens
checkpoint-status |  |  | checkpoint | No proud screws on any of the metal ceiling battens or wall strapping
checkpoint-status |  |  | checkpoint | Wall angle fixed off completely and corners fixed
checkpoint-status |  |  | checkpoint | All battens secure
checkpoint-status |  |  | checkpoint | Beam framing checked and acceptable
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Brace walls have brackets or straps at each end of the element
checkpoint-status |  |  | checkpoint | Services installed completely
checkpoint-status |  |  | checkpoint | Site clean and tidy of excess materials
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/ set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Work Completed as per Spec
checkpoint-group |  |  | section | Fixing Post Checks
checkpoint-status |  |  | checkpoint | All work completed to GIB® Site Guidelines
checkpoint-status |  |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status |  |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status |  |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per Troake Guidelines
checkpoint-status |  |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status |  |  | checkpoint | All plugs and penetrations have been marked on the floor and have been cut neatly and correctly
checkpoint-status |  |  | checkpoint | All plasterboard correctly fitted into rebated jambs
checkpoint-status |  |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status |  |  | checkpoint | Back block stick and centre screws removed
checkpoint-status |  |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status |  |  | checkpoint | Site Hazard Checklist Completed (attach photos)
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Report |  |  |  |  | Yes | Report | 9a647504-a40a-4ce0-8bf2-59bdb6bafeff
checkpoint-status |  |  | checkpoint | Engineer Inspection report
checkpoint-status |  |  | checkpoint | Inspection comments and Remedial items Actioned
holdpoint |  |  | signoff | Raise Remedial/Request Signoff
checklist-sectioned |  |  | checklist | Grid QA |  |  |  |  | Yes | Grid QA | a3984f8e-3258-4cab-889a-364cc51d84c7
checkpoint-group |  |  | section | Grid Prestart
checkpoint-status |  |  | checkpoint | Batten direction discussed and considered for critical light
checkpoint-status |  |  | checkpoint | Nogging requested from/by builders
checkpoint-status |  |  | checkpoint | Firewalls considered? i.e. Wall angle left off if IT Wall is full height
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | System considered and accounted for and all material ordered
checkpoint-status |  |  | checkpoint | Walls straight and true for wall angle
checkpoint-status |  |  | checkpoint | Bulkheads considered where required
checkpoint-status |  |  | checkpoint | All services in
checkpoint-status |  |  | checkpoint | All building work completed so work can begin
checkpoint-status |  |  | checkpoint | Site clean and tidy for start
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area OK to proceed
checkpoint-group |  |  | section | Grid Post Checks
checkpoint-status |  |  | checkpoint | Ceiling grid complete
checkpoint-status |  |  | checkpoint | Earth strapping
checkpoint-status |  |  | checkpoint | Bulkhead's formed where required and plumb, level & square
checkpoint-status |  |  | checkpoint | Tiling (Wall angle in shower)
checkpoint-status |  |  | checkpoint | Battens all running in the same direction and correct orientation for critical light/ sheet layout
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Joins Flush
checkpoint-status |  |  | checkpoint | No missing hangers or clips
checkpoint-status |  |  | checkpoint | Corners fixed correctly
checkpoint-status |  |  | checkpoint | Wall angle straight and true
checkpoint-status |  |  | checkpoint | Is angle the right way to supply top fixings for plasterboard?
checkpoint-status |  |  | checkpoint | Correct screw placing and clips screwed off properly
checkpoint-status |  |  | checkpoint | No proud screws or fixings
checkpoint-status |  |  | checkpoint | Site clean and tidy
checkpoint-status |  |  | checkpoint | Is there any gear that needs to be collected from Site? Can this be removed in the van? If not schedule pickup
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | POST - S - Internal Lining - Walls |  |  |  |  | Yes | POST - S - Internal Lining - Walls | b05d5492-d093-4d18-8013-2e74b0706ae8
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
text | e28caad6-8d8d-50e7-85cf-7c6c5d82c6ff |  | textbox | Specific products used (photos Required)
checkpoint-status |  |  | checkpoint | Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | POST - S - Internal Lining - Ceilings |  |  |  |  | Yes | POST - S - Internal Lining - Ceilings | b8903bd5-ed28-4f55-a1c6-14476bdb5c74
checkpoint-status |  |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status |  |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
checkpoint-status |  |  | checkpoint | Services/Penetrations, correctly formed & located (consider cutout tolerances and access hatches (location & size) where applicable)
checkpoint-status |  |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | PRE - S - Suspended ceiling grids |  |  |  |  | Yes | PRE - S - Suspended ceiling grids | bb219c35-7243-4e63-819c-7f05c875a474
checkpoint-status |  |  | checkpoint | Ceiling Height confirmed
checkpoint-status |  |  | checkpoint | Bulkheads plumb, level and square (if required)
checkpoint-status |  |  | checkpoint | Battens running in correct directions and orientation for critical light
checkpoint-status |  |  | checkpoint | Batten joins offset
checkpoint-status |  |  | checkpoint | Batten joins flush
checkpoint-status |  |  | checkpoint | All hangers and clips installed
checkpoint-status |  |  | checkpoint | Corners fixed correctly
checkpoint-status |  |  | checkpoint | Appropriate fixings used and installed as per required specification
checkpoint-status |  |  | checkpoint | Angles correct to fix plasterboard
checkpoint-status |  |  | checkpoint | Any seismic requirements and bracing elements installed
checkpoint-status |  |  | checkpoint | Suspended ceiling installation completed and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Interior Painting QA |  |  |  |  | Yes | Interior Painting QA | bd91414a-4c7b-4c6b-a6b2-fc9d1366d9cc
checkpoint-group |  |  | section | Interior Painting Prestart
checkpoint-status |  |  | checkpoint | Square stop
checkpoint-status |  |  | checkpoint | Internal returns
checkpoint-status |  |  | checkpoint | Behind cupboards
checkpoint-status |  |  | checkpoint | Behind Laundry tub
checkpoint-status |  |  | checkpoint | Dust in corner top and bottom
checkpoint-status |  |  | checkpoint | Wave in square stop
checkpoint-status |  |  | checkpoint | Around meters
checkpoint-status |  |  | checkpoint | Bathroom shower bottoms
checkpoint-status |  |  | checkpoint | Switches and plugs cut outs
checkpoint-status |  |  | checkpoint | Do we require mobile scaffold?
checkpoint-status |  |  | checkpoint | If yes, have we allowed for it?
checkpoint-status |  |  | checkpoint | If yes, has it been quoted or is it a variation?
checkpoint-status |  |  | checkpoint | Scaffold safe to use/set up safely
checkpoint-status |  |  | checkpoint | Lumps and bumps
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Area Ready to Begin
checkpoint-group |  |  | section | Interior Painting Post Checks
checkpoint-status |  |  | checkpoint | Walls
checkpoint-status |  |  | checkpoint | Ceilings
checkpoint-status |  |  | checkpoint | Doors
checkpoint-status |  |  | checkpoint | Trims
checkpoint-status |  |  | checkpoint | Skirting
checkpoint-status |  |  | checkpoint | Windows
checkpoint-status |  |  | checkpoint | Site left clean and tidy
checkpoint-status |  |  | checkpoint | Paint to be left on site
checkpoint-status |  |  | checkpoint | General Comments and Queries
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | B03 Defects (Common Areas) |  |  |  |  | Yes | B03 Defects (Common Areas) | d57b2d47-d6dc-46a8-98df-84ad434a9886
checkpoint-no-status |  |  | checkpoint | Add photos and comments as required
checklist-flat |  |  | checklist | B05 Remedial/Additional Work |  |  |  |  | Yes | B05 Remedial/Additional Work | dbb84b32-b0cf-41bc-8e81-70dee307024a
checkpoint-no-status |  |  | checkpoint | B05 Remedial/Additional Work
boolean | df1d5da2-2a64-5063-85d1-63b85b859818 |  | tickbox | Remedial
boolean | cad56666-e21e-5ed4-ac75-dcee1f4f7424 |  | tickbox | Additional
checkpoint-no-status |  |  | checkpoint | 1
text | 36556b4a-6087-5450-b8d7-8cafc88ee644 |  | textbox | 1.1 SI number:
text | 188ca46c-ca53-5966-8ca2-7542f15450f3 |  | textbox | 1.2 Description of work:
button | eb5b1930-37f3-5dfd-9347-e6c1bd608550 |  | button | 1.3 Troake | pass,fail
checkpoint-no-status |  |  | checkpoint | 2
text | fa3cf86e-9156-5e76-ad76-0b8ed5871ea2 |  | textbox | 2.1 Date:
label | 9bac8742-620d-5ac7-a832-44e9731434ae |  | note | 2.2 Add photos – camera/upload
text | 118b8939-edee-5bd5-928d-b098c10cb6e8 |  | textbox | 2.3 Troake Comments:
text | ad250d7f-77b4-5a78-ad22-7555b8ae00a7 |  | textbox | 2.4 Ryman Comments:
button | cbefded4-50b3-52c6-bb32-bc1e8ca8262a |  | button | 2.5 Ryman | pass,fail
checkpoint-no-status |  |  | checkpoint | 3
text | 378b2f5d-b702-5a7f-bf3a-5c2fc797e8e4 |  | textbox | 3.1 Date:
text | 2e3e58ab-ed1d-5ec1-969d-08621fc656f7 |  | textbox | 3.2 Save/Edit:
checklist-flat |  |  | checklist | B04 Remedial/Additional Work |  |  |  |  | Yes | B04 Remedial/Additional Work | dda6004d-2850-473d-a14f-33b84c9682f1
checkpoint-no-status |  |  | checkpoint | B04 Remedial/Additional Work
boolean | 79d867d1-f52b-50d2-b262-50ca8261c5c9 |  | tickbox | Remedial
boolean | 61804021-074a-5d5d-bc8e-d7b9d57a0899 |  | tickbox | Additional
checkpoint-no-status |  |  | checkpoint | 1
text | 3651313e-0867-5f5b-be46-214848e8db4b |  | textbox | 1.1 SI number:
text | 62c03160-248e-5c62-b8ae-7af8f767798e |  | textbox | 1.2 Description of work:
button | bef45b8a-b691-5d07-91f3-56403a76a7cf |  | button | 1.3 Troake | pass,fail
checkpoint-no-status |  |  | checkpoint | 2
text | 4900b910-8e7a-5cdd-a0c3-7b24e281e0ed |  | textbox | 2.1 Date:
label | f10a1da9-1ac7-5bed-b1ed-6d1b86f14074 |  | note | 2.2 Add photos – camera/upload
text | 26e41658-3af4-526c-b597-80f55ff57add |  | textbox | 2.3 Troake Comments:
text | f7d0c487-6b0a-5f0e-82e4-28cde007758b |  | textbox | 2.4 Ryman Comments:
button | 2a100bb1-143a-5098-a9d9-e4c030bb0a04 |  | button | 2.5 Ryman | pass,fail
checkpoint-no-status |  |  | checkpoint | 3
text | f0e206ee-b9eb-58df-b5bf-f60be834a2ed |  | textbox | 3.1 Date:
text | d834b65f-1459-539e-86de-38dc31d94bbd |  | textbox | 3.2 Save/Edit:
checklist-flat |  |  | checklist | POST - S - Painting |  |  |  |  | Yes | POST - S - Painting | ddc5a769-2ea1-4f3a-babc-50deb423d6e3
checkpoint-status |  |  | checkpoint | Any prep work & sealer coat completed
checkpoint-status |  |  | checkpoint | Light inspection completed and approved to continue
checkpoint-status |  |  | checkpoint | Any additional prep work completed (stopping, filling, sanding etc)
checkpoint-status |  |  | checkpoint | First top coat completed
checkpoint-status |  |  | checkpoint | Additional top coat applications completed
checkpoint-status |  |  | checkpoint | Final coat completed as per specifications
checkpoint-status |  |  | checkpoint | Painting work completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | B03 Remedial/Additional Work |  |  |  |  | Yes | B03 Remedial/Additional Work | e06fa095-c083-4033-b1e3-b337b4be6e59
checkpoint-no-status |  |  | checkpoint | B03 Remedial/Additional Work
boolean | de94370a-e7e2-5398-a713-558c1b082b47 |  | tickbox | Remedial
boolean | 9d5dcc13-8d6a-5572-b9db-287d57700c89 |  | tickbox | Additional
checkpoint-no-status |  |  | checkpoint | 1
text | 38b9d34e-b2b3-56fe-8f47-6dc86d890e43 |  | textbox | 1.1 SI number:
text | 956cb9c5-895c-51c8-9512-58bb3b9c8692 |  | textbox | 1.2 Description of work:
button | bfd83a74-4f60-558e-98ee-5dc7a032cea2 |  | button | 1.3 Troake | pass,fail
checkpoint-no-status |  |  | checkpoint | 2
text | a593f8c0-e88b-5389-9f21-40fe2edfb5df |  | textbox | 2.1 Date:
label | 3c25c24e-60eb-5b24-97ca-fb2f7335114d |  | note | 2.2 Add photos – camera/upload
text | 406b90ac-a050-52f7-85d3-f8574a56f0ab |  | textbox | 2.3 Troake Comments:
text | e7eec5f6-267c-53ff-8a89-dadcc49b214e |  | textbox | 2.4 Ryman Comments:
button | 3099311b-f2d7-5314-bf3b-b5d30ced3c78 |  | button | 2.5 Ryman | pass,fail
checkpoint-no-status |  |  | checkpoint | 3
text | c12c34e2-9fa7-59ba-939f-bf5aabbda15a |  | textbox | 3.1 Date:
text | 438f1c1c-ddba-537f-9993-267ef8523ae7 |  | textbox | 3.2 Save/Edit:
checklist-flat |  |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | e62d4eeb-e977-4ee0-bd37-581684ccacdb
checkpoint-status |  |  | checkpoint | PS3 Fire Protection - Interior Surface Finishes
checkpoint-status |  |  | checkpoint | PS3 Fire Stopping of the fire rated wall and Ceilings
checkpoint-status |  |  | checkpoint | PS3 Plasterboard
checkpoint-status |  |  | checkpoint | Material Schedule
checkpoint-status |  |  | checkpoint | Record of Building Work
checkpoint-status |  |  | checkpoint | Other documents
checklist-flat |  |  | checklist | PRE - S - Steel Stud Framing |  |  |  |  | Yes | PRE - S - Steel Stud Framing | eacaf87f-6c16-41ef-bf03-44b7eb698043
checkpoint-status |  |  | checkpoint | Steel Stud Dimensions / locations checked & accurate (openings considered where applicable)
checkpoint-status |  |  | checkpoint | Steel Studs have been installed square, straight and plumb
checkpoint-status |  |  | checkpoint | Fixings are correct to specification including any seismic/bracing requirements
checkpoint-status |  |  | checkpoint | All Nogs (Service/Specialty) & penetrations - installed, checked & correct (consider acoustic & fire rating requirements)
checkpoint-status |  |  | checkpoint | All Steel Stud framing completed correctly to specification & within tolerance in respective area(s)
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS