## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-004-STR-BRUNT-RSS Walls-Fill Placement | itp |  |  |  | Yes | CHK-004-STR-BRUNT-RSS Walls-Fill Placement
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-004-STR-BRUNT-RSS Walls-Fill Placement
label | Check list Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 12/07/2023
label | ITP created by: Jon De Castro
label | ITP approved for use by: Jon De Castro
checkpoint-status | 1 - Soil Reinforcement-Straps
label | Reference - VR682.08 IFC Drawings
label | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | Method - Visual
label | Frequency - Each strap
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 2 - Soil reinforcements-Connections
label | Reference - Installation Manual
label | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 3 - Soil reinforcements-Connections
label | Reference - IFC Drawings
label | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | – Bolts are to be snug tight.
label | Method - Each Fill Layer
label | Frequency - IP
label | Category - SE/PE
label | Responsibility - This Checklist Signed-off
label | Verifying Documents -
checkpoint-status | 4 - Soil reinforcements-Plan arrangement
label | Reference - IFC Drawings
label | Acceptance Criteria - Plan positions of Grid Strips are to be as per IFC Drawings.
label | – Grid Strips shall not overlapped
label | Method - Visual
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 5 - Soil reinforcements-Plan arrangement
label | Reference - IFC Drawings VR682.06
label | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
label | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 6 - Soil reinforcements-vertical deviation
label | Reference - IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1702
label | Acceptance Criteria - The vertical deviation of the soil reinforcement shall be within +1% (upwards) and -0.3% (downwards) of the soil reinforcement length, relative to the connection height.
label | ○ Avoid clash with drainage as directed in IFC Drawings.
label | Method - Measure, Survey
label | Frequency - Each fill Layer
label | Category - IP
label | Responsibility - Surveyor/SE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 7 - Fill-Pacement
label | Reference - VR204.10, VR682.16
label | Acceptance Criteria - Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
label | ○ All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps.
label | ○ Plant or vehicles shall not be allowed to traffic over or work on reinforcing elements until the reinforcement is protected by a minimum 150 mm layer of fill material.
label | Method - Measure, Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - PE/SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 8 - Select backfill-moisture content
label | Reference - IFC Drawings
label | Acceptance Criteria - Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within +0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry.
textbox | Attach Test Reults
label | Method - Document review
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 9 - Select backfil - placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | ○ Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with Temporary works design.
label | Method - Measure, Visual
label | Frequency - Each fill layer
label | Category - IP
label | Responsibility - PE/SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 10 - Test Roll / Proof Roll
label | Reference - Section 173.03, Section 204.12
label | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | Method - Visual Inspection
label | Frequency - Each fill layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This Checklist Signed-off, ConQA HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 11 - Compaction and Moisture Content Testing Frequency & Acceptance
label | Reference - IFC Drawings VR 204.14 Table 204.131 VR 682.16
label | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14 (Scale A)
label | ○ The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | Compaction Requirement to be Scale A:
label | ○ Characteristic Density Ratio 99%. (6 tests per lot)
label | Lot size:
label | ○ Type A Material - the lesser of one day's production or 5000sqm
label | Attach: Compaction & Moisture Content Test Results
label | Method - Review Document, Measure
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 12 - Post Compaction Material Property Testing
label | Reference - IFC Drawings
label | Acceptance Criteria - Material Properties Testing (Scale A)
label | ○ CBR ≥ 8% and Swell ≤ 1.5%
label | ○ LL ≤ 30%
label | ○ PI ≤ 12%
label | Grading:
label | ○ 150mm 100%
label | ○ 37.5mm 60-100%
label | ○ 9.5mm 25-100%
label | ○ 2.36mm 15-100%
label | ○ 0.60mm 10-100%
label | ○ 0.075mm 0-15%
label | Select backfill must meet the minimum requirements of VR Section 204 for Type A Filling.
label | Attach: Post Compaction Material Property Test Results
label | Method - Review Document, Measure
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 13 - As-built Conformance Survey
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | Attach: Survey As-built / Survey Report
label | Method - Document Review
label | Frequency - Each Fill Layer
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This Checklist Signed-off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP