## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation | itp |  |  |  | Yes | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation
label | ITP Description: RSS Walls-Precast Panel Installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 12/07/2023
label | ITP created by: Thilan Rathnayake
label | ITP approved for use by: Jon De Castro
checkpoint-status | 1 - Panels-survey set out-Tolerance
label | Reference - IFC Drawings VR 682.20
label | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | ○ Above must be checked with surveyor prior to backfill
label | Method - Measure
label | Frequency - Base course panels
label | Category - IP
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 2 - Mark-up panel for construction team
label | Reference - Construction Manual
label | Acceptance Criteria - Mark number of strips per row on the back of each panel.
label | – Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 3 - Panel installation
label | Reference - IFC Drawings
label | Acceptance Criteria - RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | – Check for correct architectural pattern
label | – Check for Weephole Locations
label | – Check the 19mm nominal gap to be maintained between panels
label | – Check the min 1:40 slope to be maintained (RSS Panels must lean backwards to this slope)
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | – the wall level shall not deviate from the specified level by more than ±20mm
label | – the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | Above must be checked with Surveyor prior to backfill
label | Method - Visual, Measure
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 4 - Panel installation- Corner Panels and Panels interfacing Abutment
label | Reference - IFC Drawings
label | Acceptance Criteria - 20mm nominal gap between panels and Abutment wall is to be mainatined
label | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
label | – 600mm wide BITAC tape installed
label | ○ Folded plates must be installed installed at coner panels and panels adjecent to abutments
label | ○ Above must be checked with Surveyor prior to backfill
label | Method - Measure
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 5 - Install Rubber Bearing Pads
label | Reference - IFC Drawings
label | Acceptance Criteria - 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
label | ○ Above must be checked with Surveyor prior to backfill
label | Method - Visual, Measure
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 6 - Filter fabric -Installation
label | Reference - IFC Drawings VR 682.11
label | Acceptance Criteria - Install Filter Fabric against all vertical and horizontal joints
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 7 - Drainage-Vertical Strip Drain
label | Reference - IFC Drawings VR 682.11
label | Acceptance Criteria - Install 300mm wide vertical strip drain as per IFC Drawings and in accordance with VR 682.11 at every vertical joint between panels in RSS wall.
label | ○ Ensure no gap is formed between strip drain and RSS panels
label | Method - Visual, Measure
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - SE/Supervisor
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 8 - Panel installation-Survey reference points
label | Reference - VR 682.21
label | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | Method - Visual
label | Frequency - Each course of panel installation
label | Category - IP
label | Responsibility - Surveyor/SE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 9 - Traceability of precast units and records
label | Reference - VR 620.09
label | Acceptance Criteria - Unique ID of precast panel is recorded.
label | ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | Method - Visual
label | Frequency - Each panel
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 10 - Panels installation - As-built Conformance Survey
label | Reference - IFC Drawings VR 682.06 VR 682.17 VR 682.20
label | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | The Contractor shall record the results of this checking together with details of any non–conformances and the associated corrective actions
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | – the wall level shall not deviate from the specified level by more than ±20mm
label | – the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | ○ Above must be checked with Surveyor prior to backfill
label | Attach: Conformance Survey Report
label | Method - Survey, Measure
label | Frequency - Each course of panel installation
label | Category - HP*
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist Signed-off
checkpoint-status | 11 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This Checklist Signed-off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP