## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-044-STR-Brunt-RSS Wall Main ITP | itp |  |  |  | Yes | ITP-044-STR-Brunt-RSS Wall Main ITP
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-044-STR-Brunt-RSS Wall Main
label | ITP Description: RSS Wall Main ITP
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 7/07/2023
label | ITP created by: Thilan Rathnayake
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Applicable Specs/Standards
label | Reference - VicRoads Section 682 Nov 2018
checkpoint | 1.2 - Applicable Specs/Standards
label | Reference - VicRoads Section 204 Dec 2015
checkpoint | 1.3 - Applicable Specs/Standards
label | Reference - VicRoads Section 610 Feb 2020
checkpoint | 1.4 - Applicable Specs/Standards
label | Reference - IFC drawings
checkpoint | 1.5 - Applicable Specs/Standards
label | Reference - BTN 009
checkpoint | 1.6 - Applicable Specs/Standards
label | Reference - AS5100-2007
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Concrete-Leveling Pad
note | Reference - IFC drawings
note | Acceptance Criteria - CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
textbox | Teambinder MA Ref Number:
note | Method - Document Review
note | Frequency - Each element
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Select Backfill
note | Reference - IFC Drawings
note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
note | ○ UNIT WEIGHT: 22 kN/m³
note | ○ INTERNAL FRICTION ANGLE ≥ 36.0°
note | ○ COHESION: 0 kPa
note | Gradation:
note | ○ 150mm : 100% PASSING
note | ○ 37.5mm : 60 TO 100% PASSING
note | ○ 9.5mm : 25 TO 100% PASSING
note | ○ 2.36mm : 15 TO 100% PASSING
note | ○ 0.6mm : 10 TO 100% PASSING
note | ○ 0.075mm : 0 TO 15% PASSING
note | Electrochemical Properties:
note | ○ RESISTIVITY >1000 Ω-cm
note | ○ CHLORIDES <200 mg/kg
note | ○ SULPHATES <200 mg/kg
note | ○ ORGANIC CONTENT 0%
note | Structural Properties:
note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
note | ○ LIQUID LIMIT ≤ 30%
note | ○ PLASTICITY INDEX ≤ 12
note | The select backfill must meet the minimum requirements of VicRoads Section 204 for Type A Filling.
textbox | TeamBinder MA Ref Number:
note | Method - Document Review
note | Frequency - Each material specification
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - General Backfill
note | Reference - IFC Drawings
note | Acceptance Criteria - Backfill behind the reinforced block shall have the properties specified in the IFC Drawings.
note | ○ Geotechnical Design Parameters for Embankment (Type A) Fill:
note | ○ Effective Friction Angle: ≥ 36.0°
note | ○ Effective Cohesion: 0-3 kPa
note | ○ Unit Weight: 22 kN/m³
textbox | TeamBinder MA Ref Number:
note | Method - Document Review
note | Frequency - Each material specification
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Perforated Pipe-material
note | Reference - IFC Drawings
note | Acceptance Criteria - Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
textbox | TeamBinder MA Ref Number:
note | Method - Document Review, Measure
note | Frequency - Each element
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Material Conformance - Folded plates
note | Reference - IFC Drawings
note | Acceptance Criteria - GRADE 250 D41
note | ○ 300x6MM FOLDED
note | ○ GALV. PLATE
textbox | TeamBinder MA Ref Number:
note | Method - Document Review
note | Frequency - Each raw
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Bearing Pads, Filter Fabric, Geotextile, Strip Drains & Chimney Drains
note | Reference - IFC Drawings
note | Acceptance Criteria - Refer to relevant IFC Drawings for details of these incidental materials.
textbox | TeamBinder MA Ref Number:
note | Method - Document Review
note | Frequency - Each material specification
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - RSS Precast Panels QA Documentations
note | Reference - Subcontractor Methodology and Procedures
note | Acceptance Criteria - RSS Precast Panel Supplier is required to provide the following Quality Assurance documentation prior to casting of precast panels.
note | – Quality Management Plan
note | – Works Procedures
note | – Concrete mix design
note | – Concrete crack repair procedure
note | – Concrete crack repair ITP
note | – Weld procedure qualification records
note | – Precast panel liftring design
note | – ACRS cert for steel reinforcement
note | – Concrete pre–pour records template
note | – Concrete pour records template
note | – Concrete post–pour records template
note | – Concrete cover check records template
note | – Record of dimensional measurements
note | Collate: Precast Quality Assurance Documentation so it can be uploaded into a Hold Point in Teambinder (don't attach here)
textbox | TeamBinder Hold Point Ref Number:
note | Method - Document Review
note | Frequency - Once for each type of panels
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - Conqa HP Release
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Levelling Pad-Survey Set out
note | Reference - IFC Drawings
note | Acceptance Criteria - Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the IFC Drawings and VicRoads Specification
note | Method - Measure, Visual
note | Frequency - Each retaining Wall
note | Category - IP
note | Responsibility - Surveyor, SE/PE
note | Verifying Documents - This ITP Signed Off
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Form Levelling pad
note | Reference - IFC Drawings
note | Acceptance Criteria - Form timber shutters to edge of levelling pad
note | ○ Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
note | ○ The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
note | ○ 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
note | Method - Measure, Visual
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Leveling Pad Concrete Pour
note | Reference - IFC Drawings
note | Acceptance Criteria - Concrete to be placed in accordance with VR Section Section 610.
note | ○ Leveling pad concrete strength shall be 25 MPa minimum.
textbox | TeamBinder MA Ref Number:
note | Attach: Concrete Delivery Docket & Pour Record
note | Method - Visual
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - SE/Site Supervisor
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Leveling Pad Concrete Testing
note | Reference - IFC Drawings
note | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
note | Attach: Concrete Compcressive Test Report
note | Method - Document Review
note | Frequency - Each Lot
note | Category - IP
note | Responsibility - PE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
note | Reference - IFC Drawings
note | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
note | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
note | Attach: As-built Survey Conformance
note | Method - Measure, Visual
note | Frequency - Each RSS Wall
note | Category - IP
note | Responsibility - PE/SE/Surveyor
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Precast RSS Wall Panels Installation
note | Reference - VR Section 682.17
note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
note | ○ The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
note | Attach: Lot map
note | Method - Visual Measure
note | Frequency - Each course of facing panel
note | Category - HP*
note | Responsibility - PE/SE
note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
checkpoint | 5.6 - Precast RSS Wall - Drainage
note | Reference - IFC Drawings
note | Acceptance Criteria - 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps.
note | ○ 100mm dia. perforated subsurface longitudinal draiange (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material.
note | ○ Chimney drain min 300mm wide comprising A5 or B2 filter material in accordance with VR Section 702. Perimiter of chimney drainage wrapped in BIDIM A24 (or approved equivalent) non-woven geotextile overlapped by 150mm min. at joints.
note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
note | Attach: Lot Maps
note | Method - Visual Measure
note | Frequency - Each course of facing panel
note | Category - HP*
note | Responsibility - PE/SE
note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
checkpoint | 5.7 - RSS Select Fill
note | Reference - IFC Drawings VR Section 682.16
note | Acceptance Criteria - The Contractor shall submit Compaction & Moisture Content Test Results (Scale A) for each layer of fill placement to the Superintendent for review and acceptance.
note | ○ No further fill placement shall be allowed if the total thickness of fill placement is greater than 1m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
note | ○ Refer to Fill Placement Checklist for each fill layer.
note | Attach: Lot Maps
note | Method - Visual, Test, Measure
note | Frequency - Each layer of fill
note | Category - HP*
note | Responsibility - PE/SE
note | Verifying Documents - CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As-built Conformance Survey
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
note | Attach: Survey As-built / Survey Report
note | Method - Document Review
note | Frequency - Each element
note | Category - IP
note | Responsibility - Surveyor, SE/PE/SPE
note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0, CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
checkpoint | 6.2 - Wall Post Construction Monitoring (This is part of the on-going monitoring of the RSS panels post installation)
note | Reference - VR Section 682.20, VR Section 682.21
note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in VR Section 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
note | (a) plan position shown on the drawings, at base of wall shall not exceed +/-15 mm;
note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
note | (e) the wall level shall not deviate from the specified level by more than +/-20 mm;
note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
note | Attach: Surveyor pick-ups / measurements.
note | Method - Measure, Survey
note | Frequency - In accordance with VR Section 682
note | Category - IP
note | Responsibility - Surveyor, Completions
note | Verifying Documents - Survey Monitoring Report (Refer back to CND)
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0, CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP