## 800 SL ITP
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | Project Number -
|  |  |  | Project: NZTA 5363 CIP SH30 Te Ngae Road Corridor-Iles Rd to Coulter Rd |  |  |  |  | Date submitted:
|  |  |  | Construction Process: Streetlight Installations |  |  |  |  | Prepared By: Downer New Zealand
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 800 - Streetlighting |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
900 | Setout, Materials and Preparation
900.1 | Method Statement Development / Job Safety & Environmental Analysis | Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed) | H | NA | NA | Method Statement and JSEA Completed and signed by relevant authority. | MS & JSEA | Contractor | Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
900.2 | Drawings and Specifications | Check drawings are for construction and latest revision. Check Specification is for construction and latest revision | H | Naa | NA | Drawings and Specification are the latest revision. | IFC Drawings and Specification | Contractor | Up to date drawings and specification to be reviewed before construction.
900.3 | Power Connection | Ensure power supply is organised and is undertaken by an experience and competent contractor. | M | Once | NA | Unison to supply power to streetlight bases, subcontractor connecting streetlights to the network to be "approved" by the local electricity network company. | Unison Documents | Sub-Contractor
900.4 | Survey Set Out | GPS Setout of the shared services trench location as per the construction drawings. | M | All shared trenches. | Visual Inspection | Streetlight set out locations do not clash with other features (i.e. existing/new services etc) | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works.
900.5 | Sediment Controls are in place for the particular section | Check ESCP and ensure any controls needed are in place before excavation. | M | once per section | Visual Inspection | Erosion and Sediment controls are in place prior to starting works. | Contractor's site diary and/or photos | Contractor
Construction and Finshing
900.6 | Pole | Assembly | M | each pole | Visual Inspection | Confirmation by contractor/installer of correct assembly per manufacturers instructions. | COC/QC Sheet | Sub-Contractor
900.7 |  | Installation | M | each pole | Visual Inspection | Installation to be 90 degrees to kerb and channel, pole tilt to be within 2o. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer. | COC/QC Sheet | Sub-Contractor
900.8 |  | Type | M | each pole | Visual Inspection | Ensure the correct pole type is installed per the latest IFC drawings. | COC/QC Sheet | Sub-Contractor
900.9 |  | Footings | M | each pole | Visual Inspection | Ensure poles are founded securely and have are adequatley backfilled to suit site conditions. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer. | COC/QC Sheet | Sub-Contractor
900.10 |  | Earthing | M | each pole | Visual Inspection | Confirmation by contractor/installer that all streetlights are earthed per installation requirements. | COC/QC Sheet | Sub-Contractor
900.11 | Luminaire | Type | M | each luminaire | Visual Inspection | Ensure the correct luminaire type is installed per the latest IFC drawings. | COC/QC Sheet | Sub-Contractor
900.12 |  | Tilt Angle | M | each luminaire | Visual Inspection | Ensure the correct luminaire tilt angle is installed per the latest IFC drawings. +/- 2O | COC/QC Sheet | Sub-Contractor
900.13 | Electrical Testing | Test relevant | H | each pole | Inspection / Audit | Confirmation by contractor/installer that streetlights and circuits have been satisfactorily tested in accordance with Electrical (Safety) Regulations 2010. | COC Sheet | Sub-Contractor
900.14 | Electrical certificate of compliance and electrical safety certificate | Complete COC | H | minimum once per Zone | Inspection / Audit | Submit COC. | COC Sheet | Sub-Contractor
Close Out
900.15 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor
900.16 | As-built drawings | Survey | H | At completion of construction | Asbuilts to be submitted at the completion of construction, information to be captured regularly. | Asbuilts reviewed and submitted (i.e. showing final location of all poles). | In Eight record | Contractor
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.