## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Streetlight Installations | itp |  |  |  | Yes | ITP - Streetlight Installations
section | Setout, Materials and Preparation
checkpoint | 900.1 - Method Statement Development / Job Safety & Environmental Analysis
label | Detail of Activity - Prepare shared services trench construction methodology and Job Safety & Environmental Analysis suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed)
label | H
label | Minimum Test Frequency - NA
label | Inspection / Test method - NA
label | Acceptance Criteria - Method Statement and JSEA Completed and signed by relevant authority.
label | Record documents - MS & JSEA
label | Responsibility - Contractor
label | Comments - Method Statement and Job Safety & Environmental Analysis to be provided to Engineer for review prior to commencing excavation on site.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 900.2 - Drawings and Specifications
label | Detail of Activity - Check drawings are for construction and latest revision. Check Specification is for construction and latest revision
label | H
label | Minimum Test Frequency - NA
label | Inspection / Test method - NA
label | Acceptance Criteria - Drawings and Specification are the latest revision.
label | Record documents - IFC Drawings and Specification
label | Responsibility - Contractor
label | Comments - Up to date drawings and specification to be reviewed before construction.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 900.3 - Power Connection
label | Detail of Activity - Ensure power supply is organised and is undertaken by an experience and competent contractor.
label | M
label | Minimum Test Frequency - Once
label | Inspection / Test method - NA
label | Acceptance Criteria - Unison to supply power to streetlight bases, subcontractor connecting streetlights to the network to be "approved" by the local electricity network company.
label | Record documents - Unison Documents
label | Responsibility - Sub-Contractor
checkpoint | 900.4 - Survey Set Out
label | Detail of Activity - GPS Setout of the shared services trench location as per the construction drawings.
label | M
label | Minimum Test Frequency - All shared trenches.
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Streetlight set out locations do not clash with other features (i.e. existing/new services etc)
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
label | Comments - Setout location prior to commencing works.
checkpoint | 900.5 - Sediment Controls are in place for the particular section
label | Detail of Activity - Check ESCP and ensure any controls needed are in place before excavation.
label | M
label | Minimum Test Frequency - once per section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Erosion and Sediment controls are in place prior to starting works.
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
section | Construction and Finshing
checkpoint | 900.6 - Pole
label | Detail of Activity - Assembly
label | M
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Confirmation by contractor/installer of correct assembly per manufacturers instructions.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.7 - Pole
label | Detail of Activity - Installation
label | M
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Installation to be 90 degrees to kerb and channel, pole tilt to be within 2o. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.8 - Pole
label | Detail of Activity - Type
label | M
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Ensure the correct pole type is installed per the latest IFC drawings.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.9 - Pole
label | Detail of Activity - Footings
label | M
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Ensure poles are founded securely and have are adequatley backfilled to suit site conditions. Confirmation by contractor/installer of correct installation to manufacturers specification by contractor/installer.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.10 - Pole
label | Detail of Activity - Earthing
label | M
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Confirmation by contractor/installer that all streetlights are earthed per installation requirements.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.11 - Luminaire
label | Detail of Activity - Type
label | M
label | Minimum Test Frequency - each luminaire
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Ensure the correct luminaire type is installed per the latest IFC drawings.
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.12 - Luminaire
label | Detail of Activity - Tilt Angle
label | M
label | Minimum Test Frequency - each luminaire
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Ensure the correct luminaire tilt angle is installed per the latest IFC drawings. +/- 2O
label | Record documents - COC/QC Sheet
label | Responsibility - Sub-Contractor
checkpoint | 900.13 - Electrical Testing
label | Detail of Activity - Test relevant
label | H
label | Minimum Test Frequency - each pole
label | Inspection / Test method - Inspection / Audit
label | Acceptance Criteria - Confirmation by contractor/installer that streetlights and circuits have been satisfactorily tested in accordance with Electrical (Safety) Regulations 2010.
label | Record documents - COC Sheet
label | Responsibility - Sub-Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 900.14 - Electrical certificate of compliance and electrical safety certificate
label | Detail of Activity - Complete COC
label | H
label | Minimum Test Frequency - minimum once per Zone
label | Inspection / Test method - Inspection / Audit
label | Acceptance Criteria - Submit COC.
label | Record documents - COC Sheet
label | Responsibility - Sub-Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Close Out
checkpoint | 900.15 - Collate above documentation
label | Detail of Activity - Document review
label | H
label | Minimum Test Frequency - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | Record documents - Review
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 900.16 - As-built drawings
label | Detail of Activity - Survey
label | H
label | Minimum Test Frequency - At completion of construction
label | Inspection / Test method - Asbuilts to be submitted at the completion of construction, information to be captured regularly.
label | Acceptance Criteria - Asbuilts reviewed and submitted (i.e. showing final location of all poles).
label | Record documents - In Eight record
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | Contractor's Rep Name:
holdpoint | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
label | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
text | BBO Engineers Rep Name:
holdpoint | Add Signature