## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | c564dea2-271d-4aae-86c3-b2e58d1acb78 |  | checklist | Second Fix Plumbing |  |  |  |  | Yes | Second Fix Plumbing | 0718e768-663c-42f3-8aab-4d87c634b35e
checkpoint-status | fc76d361-da70-419c-9005-3dd130c0de69 |  | checkpoint | All fit off fixtures match plan.
checkpoint-status | 057ae9ba-1207-485d-9496-7248b536868c |  | checkpoint | Water pipe work has maintained working pressure throughout.
checkpoint-status | c961c6db-a9f5-4f62-9794-157ec3e04266 |  | checkpoint | No debris in floor waste and drainage pipes.
checkpoint-status | 141d04b6-9183-492c-822b-7059462b9f61 |  | checkpoint | All hot water ring mains, TMValves and fixture outlets are set to the required temperature.
checkpoint-status | 98eca373-8ab4-43f7-b867-4f523a6cddba |  | checkpoint | Flanges installed on all pipe work.
checkpoint-status | 9cc420bc-2cc0-4ff3-982c-f265445431b6 |  | checkpoint | All drainage pipes are connected to the sanitary sewer.
checkpoint-status | 1954b365-c767-43cd-9983-91927700a809 |  | checkpoint | No cross overs, hot on the left cold on the right.
checkpoint-status | 243ce8e1-2d4c-4772-b374-0163815af44b |  | checkpoint | All fixtures are silicone down and splash sealed.
checkpoint-status | 4bde3cc9-321a-4e13-a561-42dbab017026 |  | checkpoint | All inspections and commissioning complete.
checkpoint-status | e7e87573-920a-450f-8879-dfca9a7d8d5f |  | checkpoint | Area is left clean and tidy.
checkpoint-status | eadd0e35-55a3-4f8c-b72d-cbb055b9164e |  | checkpoint | All QA photos taken.
checklist-flat | 1bed813f-e829-45b9-b8dc-d4ea41239009 |  | checklist | Plant Room / Hot and Cold Water Reticulation |  |  |  |  | Yes | Plant Room / Hot and Cold Water Reticulation | 32224f6c-acfb-4b99-8487-4fd59c5b9289
checkpoint-status | e1c5f875-7e3e-493f-941f-eb6d6926bb68 |  | checkpoint | Correct version of plans and revisions.
checkpoint-status | 3fcdb5e6-0bc0-49db-921d-434f7023bd04 |  | checkpoint | Correct pipe size, material, class, and joints as per specs.
checkpoint-status | 51e27e04-22ab-43c1-9bfc-e78fdbeebe34 |  | checkpoint | Correct valves installed as per plans and specs.
checkpoint-status | 27fccf0e-17e0-45cb-9e3a-b61dfb34167e |  | checkpoint | All seismic supports, insulation, and brackets installed.
checkpoint-status | 9b162455-d4f1-4176-9e83-f173f2f79609 |  | checkpoint | All testing, commissioning, and inspections complete.
checkpoint-status | d58172fd-f3da-404a-a7d5-ce7681b847a2 |  | checkpoint | Area left clean and tidy.
checkpoint-status | a1e6b0f4-bb5a-4f77-be43-73222262bc43 |  | checkpoint | All QA photos taken.
checklist-flat | 492d69da-53d5-4274-9d7c-7d1d71fe5ed4 |  | checklist | Drainage |  |  |  |  | Yes | Drainage | 3bf10371-7655-48b1-b39b-1132caca3716
checkpoint-status | edd7c424-f702-43e8-bc68-acd1f70a0c17 |  | checkpoint | All internal channel drains are installed to the correct heights and grade as per plans and specs.
checkpoint-status | 336b7cd6-c7d0-4eee-865c-7fdedd2fe4da |  | checkpoint | All threshold grates have been installed and connected to the storm water at the correct heights and grade.
checkpoint-status | 1e31f1ad-8e66-4114-9b6c-9ed81b42b5a9 |  | checkpoint | All external drainage is installed, connected the mains as per the plan, tested, inspected, back filled, and compacted.
checkpoint-status | 4c2ca0b1-1b88-4c8e-8cf9-5867e19ac260 |  | checkpoint | Area is left clean and tidy.
checkpoint-status | f36ec341-ca7b-4257-8b8d-f852d3384f03 |  | checkpoint | All QA photos taken.
checklist-flat | eb75b0d3-7e50-4079-8b3b-7daae405204d |  | checklist | Documents Checklist |  |  |  |  | Yes | Add Documents Checklist | 7fcc7265-9039-4a61-853b-9ae1cc4218fa
checkpoint-status | 194d0880-e9e5-4a01-9b85-39b53b16e238 |  | checkpoint | Council inspection sheet/report attached.
checkpoint-status | e234c617-6920-47f8-9398-ea047ad7ada4 |  | checkpoint | Naylor Love ITP completed.
checkpoint-status | 03f0d676-0f16-411c-8327-a51cbadd3c08 |  | checkpoint | Toyle inspection sheets complete.
checklist-flat | 7ac2b71b-6905-45b8-8f50-49c92dc495bd |  | checklist | First Fix Plumbing |  |  |  |  | Yes | First Fix Plumbing | b16990a1-fb72-4130-a593-24f713280256
checkpoint-status | 183e063e-2199-4fc2-81de-702a080072cd |  | checkpoint | Correct version of plans and revisions.
checkpoint-status | 6712c98c-6966-4261-9c02-581bab784046 |  | checkpoint | Check for correct fixtures and any client changes.
checkpoint-status | f9ce912a-5d13-4bd2-893a-08944bde36c8 |  | checkpoint | Correct pipe size, material, class, grade, and joints as per plans and specs.
checkpoint-status | 80ad5205-a6a8-439b-97e1-5fa812e37cae |  | checkpoint | Hot water pipes are run the shortest way possible and thermally lagged.
checkpoint-status | f22b3df1-bff0-4d7f-af01-bac7fc56f3de |  | checkpoint | All nogs and fixings are installed.
checkpoint-status | 9052fc02-6ae1-4fdd-a3b0-e80f5e891b13 |  | checkpoint | Check all wing back and waste pipe heights against the plan.
checkpoint-status | ebbb7650-1425-4073-b5d6-219a2b17d9ac |  | checkpoint | All pipe work is clipped neatly and silicone installed.
checkpoint-status | 04c06b4a-37f5-40e1-94dc-db411b0a7c95 |  | checkpoint | All inspections and tests are complete including water to 1500 kpa and waste pipes flood tested.
checkpoint-status | c6b543d1-a530-4942-85ec-4143e155763e |  | checkpoint | Water pipes are left under working pressure and test gauges have been removed.
checkpoint-status | 47aa97c8-3541-4d2f-b7bb-6743d37bc378 |  | checkpoint | Area is left clean and tidy.
checkpoint-status | e18c232f-5ac4-4da2-be95-1d0821f89e9d |  | checkpoint | All QA photos taken.
checklist-flat | b92ae5d3-8c1a-4fcd-a569-75bd68c8286b |  | checklist | Pre Floor Drainage |  |  |  |  | Yes | Pre Floor Drainage | e0f19962-c72b-44aa-acc7-73747cb6d16d
checkpoint-status | a3fff84b-0feb-461b-a39a-aa3d095c8d9e |  | checkpoint | Correct version of plans and revisions.
checkpoint-status | f97f6509-aa45-4ca6-8b09-697a8dd45ad8 |  | checkpoint | Drainage installed as per plans and specs.
checkpoint-status | a7756478-e57e-4692-9bb7-dda1f319a8c8 |  | checkpoint | Correct pipe and fittings used as per specs.
checkpoint-status | d9d66cb0-1073-4e97-b19b-2a45a82ba0a3 |  | checkpoint | Water test completed and passed.
checkpoint-status | 4e5b3a57-bc47-4255-a810-8b707cbff610 |  | checkpoint | Council inspection completed and passed.
checkpoint-status | 3254f25e-8ed3-4eca-8c5d-34b2698b57b0 |  | checkpoint | Back filling and compaction completed and area left clean and tidy.
checkpoint-status | c59ae978-4c43-4ae9-bc6f-1778814be1dc |  | checkpoint | All QA photos taken.