## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | N3-456 WSA SBT - ITP001 - Bulk & Detailed Excavation |  |  |  |  | Yes | N3-456 WSA SBT - ITP001 - Bulk & Detailed Excavation | 5b39e5b3-7d7f-4206-b8fc-e1f1227a04c3
checkpoint-group |  |  | section | Pre-Excavation
checkpoint-status |  |  | checkpoint | Structural & Architectural Drawings - Please attach
label | d93999ce-3b75-5003-b8ff-70946cdb4cc4 |  | note | Issued for Civil Drawings:
label | ce596789-ffd2-5d65-aaf4-58bad80b0ea9 |  | note | WSA10-CPBLLBE-010000-GT-SPC-380001
label | 5ba0df0d-3f28-5166-9e7f-33d93e77f798 |  | note | SMWSASBT-CPG-ATL-SN350-TU-DRG-050630
label | 4e103473-a5b7-528c-8d07-dc0dcb0aa9f8 |  | note | SMWSASBT-CPG-ATL-SN350-TU-DRG-050631
label | 0b8fa879-5a52-514d-b477-18e743e025f6 |  | note | SMWSASBT-CPG-ATL-SN350-TU-DRG-050632
label | 378a1c33-8e74-571e-9ec3-7b9deb56fc95 |  | note | SMWSASBT-CPG-ATL-SN350-TU-DRG-050633
label | 0e98ae78-5e70-5de8-b34a-807aec837cd5 |  | note | SMWSASBT-CPG-ATL-SN350-TU-DRG-050634
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-status |  |  | checkpoint | Surveyor set out in accordance with latest drawings above:
text | 05a34838-4036-5dd6-b805-152e736bbbcb |  | textbox | Existing RL
text | 2b2039a7-9eb6-529c-87d7-57df94ea17af |  | textbox | Established Control Points
checkpoint-status |  |  | checkpoint | Permit to Excavate - issued by head contractor prior to works commencement
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-group |  |  | section | Bulk Earthworks
checkpoint-status |  |  | checkpoint | Site supervisor to set-out of RL and dimensions per works planning
checkpoint-group |  |  | section | Wall Trimmings
checkpoint-status |  |  | checkpoint | Detailed excavation of foundation shall be completed to the depth and profile shown on the drawings.
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-status |  |  | checkpoint | All foundations excavations shall be free of loose water softened material and ponding water prior to placing concrete. Excess water to utilise temporary drainage systems or to be removed by other means.
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-group |  |  | section | Post Excavation
checkpoint-status |  |  | checkpoint | Surveyor to confirm construction tolerances are achieved (excluding areas where rock cleavage does not allow for):
label | f705e6ad-c9e3-595c-a0d0-5cdd6d7cd2ca |  | note | North facing wall: +25mm / -0mm
label | b29629b4-2bf6-564e-b31f-b5f946136b3a |  | note | South facing wall: +25mm / -0mm
label | 4255af96-27ef-54a4-82bd-e909289ef284 |  | note | Excavation cut-off level: +200mm / -0mm of MCO
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-status |  |  | checkpoint | Surveyor to provide As-Built survey of foundation upon completion of work area.
holdpoint |  |  | signoff | Signed off by Delta Group & CPB
checkpoint-group |  |  | section | Verification & Documents
checkpoint-status |  |  | checkpoint | This is to confirm Delta have carried out all necessary inspections and verifies that the work has been completed and conforms to the contract specification
checkpoint-status |  |  | checkpoint | Please attach copies / photos of the following documents ( Inspection Report, Product Details, Sample Material, Test Results / Certificates, Dockets & Other Certificates)
checklist-flat |  |  | checklist | Day Labour Authorisation |  |  |  |  | Yes | Day Labour Authorisation | a4f27cc0-4335-42fc-93f6-848dcd7259d4
checkpoint-status |  |  | checkpoint | Attach any relevant photos and documents
text | 744962eb-19cf-54a7-8ef4-5cbc36851d07 |  | textbox | Client
text | 9b882646-4cfc-5daf-adc1-586a2a24aae6 |  | textbox | Work Description
text | e2237f1c-f0d9-58f1-ae2c-7bf8c7061d0e |  | textbox | Labour
text | 751efefb-3c8c-5b62-b5b0-d086a4e44a8f |  | textbox | Materials / Plant Hire
checkpoint-status |  |  | checkpoint | Labour Signed Off
holdpoint |  |  | signoff | Signed of by Delta Group & CPB