## Block 1
Block 1 | [6 empty] | Checklists
Ground Floor
Mod A/0B-B(EX)
ITP# HEN/B1/L0/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/0B-L(ITS)
ITP# HEN/B1/L0/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
First Floor
Mod A/1B-B(EX)
ITP# HEN/B1/L1/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/1B-L(ITS)
ITP# HEN/B1/L1/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Second Floor
Mod A/2B-B(EX)
ITP# HEN/B1/L2/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/2B-L(ITS)
ITP# HEN/B1/L2/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment

## Block 2
Block 2 | [6 empty] | Checklists
Ground Floor
Mod A/0A-L(IT)
ITP# HEN/B2/L0/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/0A-B(IT)
ITP# HEN/B2/L0/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
First Floor
Mod A/1A-L(IT)
ITP# HEN/B2/L1/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/1A-B(IT)
ITP# HEN/B2/L1/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Second Floor
Mod A/2A-L(IT)
ITP# HEN/B2/L2/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/2A-B(IT)
ITP# HEN/B2/L2/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment

## Block 3
Block 3 | [6 empty] | Checklist to be Added
Ground Floor
Mod A/0A-L(IT)
ITP# HEN/B3/L0/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/0A-B(IT)
ITP# HEN/B3/L0/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
First Floor
Mod A/1A-L(IT)
ITP# HEN/B3/L1/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/1A-B(IT)
ITP# HEN/B3/L1/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Second Floor
Mod A/2A-L(IT)
ITP# HEN/B3/L2/01/A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/2A-B(IT)
ITP# HEN/B3/L2/01/B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Membrane Deck |  | Exterior Work - Membrane Deck
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
[5 empty] | Cavity Battens |  | Exterior Work - Cavity Battens
[5 empty] | Exterior Painting |  | Exterior Work - Exterior Painting
|  |  |  | Interior Work |  |  | Interior Work
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment

## Richardson Block 3
Block 3 | [6 empty] | Checklist to be Added
Ground Floor
Mod A/0A-L(KB_IT)
Mod A/0A-L(LB_IT)
ITP# RICH/B3/L0/1A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Insulation |  | Exterior Work - Insulation
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
Internal Work
[5 empty] | Internal Membrane |  | Interior Work - Membrane Waterproofing
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/0A-B(KB_IT)
Mod B/0A-B(LB_IT)
ITP# RICH/B3/L0/1B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Insulation |  | Exterior Work - Insulation Wall & Ceiling
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
Internal Work
[5 empty] | Internal Membrane |  | Interior Work - Membrane Waterproofing
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Block 3 | [6 empty] | Checklist to be Added
Ground Floor
Mod A/0A-L(KB_IT)
Mod A/0A-L(LB_IT)
ITP# RICH/B3/L0/2A
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | EW 3 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[6 empty] | IW 4 | Structure - Internal Wall
[6 empty] | IW 5 | Structure - Internal Wall
[6 empty] | IW 6 | Structure - Internal Wall
[6 empty] | IW 7 | Structure - Internal Wall
[6 empty] | IW 8 | Structure - Internal Wall
[6 empty] | IW 9 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Insulation |  | Exterior Work - Insulation Wall & Ceiling
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
Internal Work
[5 empty] | Internal Membrane |  | Interior Work - Membrane Waterproofing
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Mod B/0A-B(KB_IT)
Mod B/0A-B(LB_IT)
ITP# RICH/B3/L0/2B
Structure
[5 empty] | Floor Cassette |  | Structure - Floor Cassette
Wall Panels
[6 empty] | EW 1 | Structure - External Wall
[6 empty] | EW 2 | Structure - External Wall
[6 empty] | MW | Structure - Marriage Wall
[6 empty] | IT | Structure - Intertenancy Wall
[6 empty] | IW 1 | Structure - Internal Wall
[6 empty] | IW 2 | Structure - Internal Wall
[6 empty] | IW 3 | Structure - Internal Wall
[5 empty] | Ceiling Cassette |  | Structure - Ceiling Cassette
[5 empty] | Module Assembly |  | Structure - Module Assembly
[5 empty] | Roof Assembly |  | Structure - Roof Assembly
Exterior Work
[5 empty] | Insulation |  | Exterior Work - Insulation Wall & Ceiling
[5 empty] | Wraps / Penetration |  | Exterior Work - Wraps / Penetration
Internal Work
[5 empty] | Internal Membrane |  | Interior Work - Membrane Waterproofing
Electrical/Mechanical
First Fix
Wall Panel
E/M - External Wall/Marriage wall - Structural/Fire
E/M - Internal wall - Non structural
[6 empty] | Ceiling Cassette | E/M - Ceiling Cassette
[6 empty] | Module Assembly | E/M - Module Assembly
[5 empty] | Second Fix |  | E/M - Second Fix
Plumbing/Drainage
First Fix
[6 empty] | Floor cassette | P/D - Floor Cassette
Wall Panel
P/D - External Wall/Marriage wall
P/D - Internal wall
[6 empty] | Module Assembly | P/D - Module Assembly
[5 empty] | Second Fix |  | P/D- Second Fix
Passive Fire
[5 empty] | First Fix | External/Marriage wall | Passive Fire - External/Marriage wall
[6 empty] | Ceiling Cassette | Passive Fire - Ceiling Cassette
[6 empty] | Module Assembly | Passive Fire - Module Assembly
|  |  |  | Packaging and shipment |  |  | Packaging and Shipment
Nonconformity
Nonconformity - Form
Nonconformity - CAR

## Structure Checklists
checklist | Structure - Floor Cassette
section | Structural framing and Fixing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Joist: Sizes, spacings, treatment, grade as per fabrication plan
checkpoint | Install all floor framing elements as per fabrication plan.
checkpoint | Install all floor structural fixings as per fabrication plan.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to plumbing
section | Plumbing (Plumber to install plumbing as required)
checkpoint | Hold point: photo required and signed off by plumbing Team leader
checkpoint | Hold point: Signed off by Team leader before going to next step
section | Floor sheeting
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install temporary lifting straps
checkpoint | Apply floor sheeting as per fabrication plan
checkpoint | Floor fixed off as per fabrication plan
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Structure - External Wall
section | Structural Framing and Fixings
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Install all wall framing elements as per fabrication plan.
checkpoint | Install Portal frame and brace chord as per fabrication plan as required.
checkpoint | Install all structural fixings as per fabrication plan.
checkpoint | Transfer wall elements to upriser table.
text | Operator Name:
checkpoint | Check dimension: plus or minus 2mm
checkpoint | Check square and confirm 90 degree on four external corners
checkpoint | Check all structural fixings correct as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Structural Sheet Bracing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Correct Wall bracing Install sheet bracing as per fabrication plan
checkpoint | Fixings as per engineer design
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 1st Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 2nd Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 2 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements from upriser table to receiver table.
text | Operator Name:
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install as per fabrication plan.
checkpoint | Attach Insulation Certificate.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Wrap (RAB)
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install correct RAB as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements to wall storage area.
checklist | Structure - Marriage Wall
section | Structural Framing and Fixings
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Install all wall framing elements as per fabrication plan.
checkpoint | Install Portal frame and brace chord as per fabrication plan as required.
checkpoint | Install all structural fixings as per fabrication plan.
checkpoint | Transfer wall elements to upriser table.
text | Operator Name:
checkpoint | Check dimension: plus or minus 2mm
checkpoint | Check square and confirm 90 degree on four external corners
checkpoint | Check all structural fixings correct as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Structural Sheet Bracing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Correct Wall bracing Install sheet bracing as per fabrication plan
checkpoint | Fixings as per engineer design
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 1st Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 2nd Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 2 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements from upriser table to receiver table.
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Insulation
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install as per fabrication plan.
checkpoint | Attach Insulation Certificate.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Wrap (RAB)
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install correct RAB as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements to wall storage area.
checklist | Structure - Intertenancy Wall
section | Structural Framing and Fixings
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Install all wall framing elements as per fabrication plan.
checkpoint | Install Portal frame and brace chord as per fabrication plan as required.
checkpoint | Install all structural fixings as per fabrication plan.
checkpoint | Transfer wall elements to upriser table.
text | Operator Name:
checkpoint | Check dimension: plus or minus 2mm
checkpoint | Check square and confirm 90 degree on four external corners
checkpoint | Check all structural fixings correct as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Structural Sheet Bracing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Correct Wall bracing Install sheet bracing as per fabrication plan
checkpoint | Fixings as per engineer design
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 1st Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 2nd Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 2 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements from upriser table to receiver table.
text | Operator Name:
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Insulation
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install as per fabrication plan.
checkpoint | Attach Insulation Certificate.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Wrap (RAB)
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install correct RAB as per fabrication plan.
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements to wall storage area.
checklist | Structure - Ceiling Cassette
section | Structural framing and Fixing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Joist: Sizes, spacings, treatment, grade as per fabrication plan
checkpoint | Install all ceiling framing elements as per fabrication plan.
checkpoint | Install all ceiling structural fixings as per fabrication plan.
text | Operator Name:
checkpoint | Hold point: photo required an signed off by Team leader before before going to next step
section | Structural Sheet Bracing as required
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Correct Ceiling bracing Install sheet bracing as per fabrication plan
checkpoint | Fixings as per engineer design
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 1st Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Fire Lining 2nd Layer
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 2 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements from upriser table to receiver table.
text | Operator Name:
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Insulation
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install as per fabrication plan.
text | Operator Name:
checkpoint | Insulation Certificate.
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Structure - Internal Wall
section | Structural Framing and Fixings
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Install all wall framing elements as per fabrication plan.
checkpoint | Transfer wall elements to upriser table.
text | Operator Name:
checkpoint | Check dimension: plus or minus 2mm
checkpoint | Check square and confirm 90 degree on four external corners
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Standard/Single Layer Gib board
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
text | Operator Name:
checkpoint | Fixings as per fabrication plan
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements from upriser table to receiver table.
text | Operator Name:
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Standard/Single Layer Gib board
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Apply Layer 1 as per fabrication plan.
checkpoint | Fixings as per fabrication plan
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per fabrication plan.
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Transfer wall elements to wall storage area.
text | Operator Name:
checklist | Structure - Module Assembly
section | Module Assembly
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Select all relevant floors/ceiling cassettes and wall panels.
checkpoint | Apply the Gib fire sound for four edges of the first layer-For passive fire system.
checkpoint | Locate floor cassette on the podium.
checkpoint | Install three outer adjoining walls and fixed floor cassette as per fabrication plan.
checkpoint | Install all internal walls and fix to floor cassette and outer walls as per fabrication plan.
checkpoint | Install ceiling cassette and fix to outer walls and internal walls. Support/Prop necessary.
checkpoint | Install final outer wall and fix to floor/ceiling/walls as necessary. Remove Support/Prop.
text | Operator Name:
text | Operator Name:
checkpoint | Hold point: photo required an signed off by Team leader before going to next step
section | Services
checkpoint | Services installed as required
checkpoint | Hold point: photo required and signed off by plumbing/electrical/mechanical Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Insulation
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Install as per fabrication plan.
checkpoint | Attach Insulation Certificate.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Structure - Roof Assembly
section | Structural framing/trusses and Fixing
checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clarify shows page number
checkpoint | Check and ensure moisture content below 18%
checkpoint | Install all roof framing/trusses/purlins as per fabrication plan.
checkpoint | Install all structural fixings as per fabrication plan.
text | Operator Name:
holdpoint | Hold point: photo required an signed off by Team leader before going to plumbing

## Exterior Work Checklists
checklist | Exterior - Membrane Deck
section | Plumbing
checkpoint | Plumber to install outlet and overflow as required.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by plumbing Team leader
checkpoint | Hold point: signed off by Team leader before going to next step
section | Membrane
checkpoint | Subcontractor install membrane as per approved plans and specifications.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Subcontractor before going to next step
checkpoint | Hold point: signed off by Team leader before going to next step
section | Floating Deck
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install deck Jacks and deck Joists as per manufacture .
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Install timber decking.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Exterior - Wraps, penetrations, windows/doors and flashings
section | Wrap (RAB)
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install balance RAB.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Penetration
checkpoint | Locate and cut out all penetrations as per approved plans and specifications.
checkpoint | Install all penetrations.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Windows and doors
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all windows and doors as per approved plans and manufacture specifications.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Flashings and tapes
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all flashing tapes/Sealants to RAB joints, windows, doors, penetrations, etc., as required.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Install all flashings: Interstorey, Int/Ext corner, cavity closer.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Exterior - Cavity Battens
section | Cavity preparation/Batten
checkpoint | Check and review approved Plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | complete set out as per fabrication plan.
checkpoint | Install cavity battens.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist | Exterior Painting
checkpoint | Subcontractor to apply painting system as per approved plans and specifications. Operator name required.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Subcontractor before going to next step
checkpoint | Hold point: signed off by Team leader before going to next step
checklist | Packaging & Shipping
section | Internal Fixtures and Fittings Packaging
checkpoint | Toilet: Cistern fixed by using PET fridge tape
checkpoint | Shower: Shower head protected by wrapping it with EPE foam sheet membrane
checkpoint | Cabinets and Doors: All cabinet doors, mirror cabinet doors and drawers fixed using PET fridge tape.
checkpoint | Bathroom: Bathroom door and Shower door will be fixed with PET fridge tape.
checkpoint | Place Desiccant and Hygrometer inside the module.
text | Operator Name:
holdpoint | Hold point: photo required an signed off by Team leader before going to plumbing
section | External Protective Cover
checkpoint | Use protective film to cover a module completely
checkpoint | Use heat Gun to seal the protective film.
text | Operator Name:
checkpoint | Make sure there are no gaps in the film
holdpoint | Hold point: Photo required and signed off by Team leader before moving a Module to a Storage area.
section | Lifting and loading
checkpoint | 18-24T Forkhoist will be used to load a module onto a Specialised Transport Vehicle
checkpoint | Tie the module to the Transport Vehicle, using strops or with the equipment attached to the Vehicle
text | Operator Name:
checkpoint | Make sure the module is correctly sitting on the Transport vehicles
checkpoint | Make sure the Module has been secured with the correct ties
holdpoint | Hold point: Photo required and signed off by Team leader before going to next step.
section | Shipment
checkpoint | A Specialised Transportation Vehicle will be used to transport the module to Site
text | Operator Name:
checkpoint | Check if the Transport Company meet the approved transport criteria
holdpoint | Hold point: Photo required and signed off by Team leader before transporting a Module.

## Interior Checklists
checklist | Interior - Fitout
section | Plumber to confirm first fix plumbing complete
checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint | Hold point: signed off by Team leader before going to next step
section | Electrician to confirm first fix electrical complete
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: signed off by Team leader before going to next step
section | Complete internal wall lines
checkpoint | Complete all internal wall lines as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: Postline inspection photos required and signed off by Team leader before going to next step
section | Complete all passive fire requirements
checkpoint | Hold point: photo required and signed off by passive fire contractor
holdpoint | Hold point: signed off by Team leader before going to next step
section | Mechanical ducts and ventilation
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: signed off by Team leader before going to next step
section | False ceiling and bulkheads
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all false ceiling and bulkheads as per approved plans and specifications.
text | Operator Name:
holdpoint | Hold point: signed off by Team leader before going to next step
section | Gib stopping
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all internal Gib stopping as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Acoustic floor
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install acoustic floor as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Door and trims
holdpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
holdpoint | Install all internal floors and trims as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Painting
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all internal painting as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Kitchen and bathroom joinery install
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install kitchen and bathroom joinery as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Tiling and waterproofing: bathroom laundry Kitchen
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all waterproofing membrane to tile areas as per approved plans and manufacture specifications.
text | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Install tiles to bathroom, laundry and kitchen as per approved plans and specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Hardware
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all hardware as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step
section | Plumbing
checkpoint | Plumber to confirm second fix plumbing complete
checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint | Hold point: signed off by Team leader before going to next step
section | Electrical
checkpoint | Electrician to confirm second fix electrical complete
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: signed off by Team leader before going to next step
section | Floor Coverings
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all floor coverings as per approved plans and manufacture specifications.
text | Operator Name:
holdpoint | Hold point: photo required and signed off by Team leader before going to next step

## Electrical Checklists
checklist | External/IT/Marriage wall-Structural/Fire
section | First fix electrical
checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint | Install all flush boxes as per electrical services plan.
checkpoint | Install all electrical cablings as per electrical services plan.
checkpoint | Install all electrical conduit and draw wire as per electrical services plan.
text | Operator Name:
checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Internal wall-Non Structural
section | First fix electrical
checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint | Install all flush boxs as per electrical services plan.
checkpoint | Install all electrical cablings as per fabrication plans.
checkpoint | Install all electrical conduit and draw wire as per fabrication plans.
text | Operator Name:
checkpoint | Visual inspection: Cable protection/Support/fixing and damags
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
checkpoint | Hold point: Signed off by Team leader before going to next step
checklist | Ceiling Cassette-Structural/Fire
section | First fix electrical
checkpoint | Check and review as per electrical and mechanical services Plan
checkpoint | Install all electrical cablings as per electrical services plan.
text | Operator Name:
checkpoint | Visual inspection: Cable protection/Support/fixing and damags
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Module Assembly
section | First fix electrical
checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint | Connect all walls/ceiling electrical cables as per electrical services plan.
text | Operator Name:
checkpoint | Visual inspection: Cable protection/Support/fixing and damags
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Second fix electrical and mechanical
section | Second fix electrical
checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clarify shows page number
checkpoint | Install distribution board.
text | Operator Name:
checkpoint | Install all power points and light switches.
checkpoint | Install all lights.
checkpoint | Install heat pumps.
checkpoint | Install heat towel rail.
checkpoint | Install mechanical ventilation/Bathroom/Laundry/Kitchen.
checkpoint | Install oven/hob.
checkpoint | Install wall heaters.
checkpoint | Install smoke alarm.
text | Operator Name:
section | Electrical Testing(Inform electrician to carry out the required electrical testing for all above installation)
checkpoint | Electrical Testing-Earth Resistance and Continuity, Insulation Resistance, Polarity and Phase, Correct Circuit connection, etc.
checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Final functional inspection
section | Final Electrical Testing(Inform electrician to carry out final inspection for all fittings and installation)
checkpoint | Connect the power and check lights
checkpoint | Test and confirm the connection of all electrical fittings
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step

## PlumbingDrainage Checklists
checklist | P/D - Floor Cassette
section | First fix plumbing and drainage
checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint | Install pipes as per approved plans and manufacture instructions to above floor level.
text | Operator Name:
checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint | Complete air test to AS/NZS3500
checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | P/D - Wall panels
section | First fix plumbing and drainage
checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint | Install pipes as per approved plans and manufacture instructions.
text | Operator Name:
checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint | Hold point: photo required on digital level of all pipes' runs and signed off by Plumbing team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | P/D - Module Assembly
section | First fix plumbing and drainage before putting roof
checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint | Install pipes as per approved plumbing and drainage services Plan
checkpoint | Install connections as per approved plumbing and drainage services Plan
text | Operator Name:
checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint | Hot and Cold Water test for 30mins at 1550KPa as per AS/NZS 3500
checkpoint | Hold point: photo required of pressure gauge and signed off by Plumbing team leader before going to next step
checkpoint | Pressure gauge will be kept until second fix
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | P/D - Second Fix
section | Second fix electrical
checkpoint | Hold point: Check gauge pressure and make sure no press drop, take photos and signed off by
checkpoint | Remove gauge and start second fix.
checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint | Install connections as per approved plumbing and drainage services Plan.
checkpoint | Install toilet.
checkpoint | Install basin.
checkpoint | Install shower.
checkpoint | Install sink.
checkpoint | Install tub.
text | Operator Name:
checkpoint | Visual inspection to check Pipe lengths horizontal and vertical spacing as per approved plans
checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step

## Passive Fire Checklists
checklist | Passive fire Module Assembly
section | Module Assembly
checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint | Install fire dampers, collars and sealants as per manufacture specifications.
text | Operator Name:
checkpoint | Check fire rated linings; materials and passive fire protection measures as per GIB Fire rate system GWTLE 60A
checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Passive Fire - EW/MW/ITW
section | Passive Fire Wall
checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint | Install fire dampers, collars and sealants as per manufacture specifications.
text | Operator Name:
checkpoint | Check fire rated linings; materials and passive fire protection measures, as per GIB Fire rate system GWTLE 60A
checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step
checklist | Passive Fire - Ceiling
section | Passive Fire - Ceiling
checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clarify shows page number
checkpoint | Install fire dampers, collars and sealants as per manufacture specifications.
text | Operator Name:
checkpoint | Check fire rated linings; materials and passive fire protection measures, as per GIB Fire rate system GBUC 60
checkpoint | Visual inspection to check installation installed to match manufacture specifications and approved design
checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
holdpoint | Hold point: Signed off by Team leader before going to next step