## Fulton Hogan__Craigieburn Road
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
64cdf63b-8dcd-41b2-893b-76737829f774 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 1 ITP's
65cb4231-9be6-4944-a2ff-40074be0b6ab |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing
339eab72-ab97-4ab2-aba6-e7ba12f06b22 | Child 2 - Construction Works(bb9a11de-ebb3-55c8-b585-eae18ea6a8b7) -- 2.6 Clearing Process(98eeaa86-2fbb-5a6c-9fb1-e44ff1d99a19): Data not allowed on signoff Hold Point(6e02d527-6497-5155-9c90-09691cee8d3b): RESPONSIBILITY: Site Engineer(c99693dd-12b3-436f-b884-b479d9797789) Child 3 - Completion(c4f7ee1e-f3cc-550a-88da-82bf6789cf78) -- Final Inspection - Work Completed On(6e7fa3bd-551d-440c-b0c2-4e0225089cac): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | f4cdac93a9a6697e95d022449bc1204fed488476e914fd0f0e0895f834c46d91 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-001 - 11 Trees - Median Ch 24640 to Ch 25040
c0f0bfb6-1f72-4d91-a87f-acb167b0bad7 |  | checklist-flat | pass | 6c385c3c98c321e6987c49e6ca06223f93b991594499355dd4cdbe837b326da9 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-002 - Memorial park & Hume Hwy Center Median
a878acfc-41ec-403f-a279-37cd64d71380 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-003 - 9 Trees - Zone 3 - Westbound Ch 15000 to Ch 14700
24563494-83a6-482e-87dd-e55827c39a9f |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-004 - 64 Trees - Zone 4 - Westbound Ch 14400 to Ch 13880
14713e3b-0a44-44e8-adb6-56501c9dca57 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-005 - 1 Tree - Zone 1 - Hume Hwy South Center Median - Ch70139 - Ch70272
05964260-7468-4efa-a9c4-1f6ddb67d387 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-006 - 4Trees - Zone 4 - Golf Course - CH13800 - CH13600
3cdaab81-ef00-4a5e-bbef-215c47bba0d3 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-007 - 2 Trees - Zone 1 - Craigieburn - Hardy Ave - Ch16085 - Ch16110
720badad-3c5a-4848-ba96-e622e45997f0 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-008 - 3 Trees - Zone 2 - Craigieburn Road- West Bound - Ch16060 - Ch16080
e18755a3-0e56-4c40-8176-6c8a9a635812 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-010 - Topsoil Strip - Zone 4 - Westbound Ch13600 - Ch14400
76137e76-d08c-497b-9c40-7f673b60a4cc |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-011 - Clearing & Grubbing - eastbound zone 3 CH25370 -Dalys
9c8a90d3-08e4-4eb9-b075-2f4b172b84d1 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-012 - 24 Trees TBR & 1 trim - Zone 3- CH14760 - CH15080
746295d1-4d77-45d7-a18a-d0f6e2e1a649 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-013 - Z3 Topsoil Stripping - BTW Bridgewater Rd and the access to the sporting club - Ch14400 to Ch15080
7dd52405-c5d4-43d4-bd7d-cab451734a85 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-014 - Tree Removal - Rayfield trees
134fa2fb-10af-411d-929b-374517e44871 |  | checklist-flat | work-in-progress | dc296ee41af3a4e8c1455dcddf9d6e3530fd083a457f8bf7dab9db0b313ccae0 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-015 - Tree Removal B/W Newbold Ave to Bridgewater Rd
da5ba76d-6d2d-4340-95f7-0a9ed72cc90b |  | checklist-flat | pass | d870ed6d048ec6c26cefb41e8d0c4f25e66bab1c5a014d31dffa9b3cdc5934be | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-016- Trees Removal Zone 1,2 & 4 - 17 Trees
f30e969f-16a7-4e7a-8803-8a3357a66932 |  | checklist-flat | pass | 5e832e9b30807ac38c1698aa5e4c4523f42457acb0129ab827172e46b8b2502d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-017- Trees Removal -Memorial North Median - CH26330 to CH26270
2a4fa4c1-023e-481e-8e15-3be05bce91ab |  | checklist-flat | pass | 5e832e9b30807ac38c1698aa5e4c4523f42457acb0129ab827172e46b8b2502d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-018- Trees Removal - Walter St- CH70120 to CH70150
2ab47644-028b-458d-b8fb-54c24b7bf1c4 |  | checklist-flat | work-in-progress | 60bf39d1bea6a07f9ef4992b01c677254b3aae626db6020854fea251f937943f | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-019 - Balyang Golf course
b83cd995-df66-4e72-ae54-956a92be8d27 |  | checklist-flat | pass | 60bf39d1bea6a07f9ef4992b01c677254b3aae626db6020854fea251f937943f | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-020 - Trees Removal - Zone 2, 3, 4 and 7
56460cb4-78dc-4690-b507-43e261e4f288 |  | checklist-flat | pass | d2914bf86e85d5a68c145e12d39b8ed7677902c9a0173e05296d6839792e8dae | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-021 - Trees Removal - Vet Clinic
708a91da-4c86-4c54-9ce1-072b7e134041 |  | checklist-flat | pass | d2914bf86e85d5a68c145e12d39b8ed7677902c9a0173e05296d6839792e8dae | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-022 -Trees Removal - Hamilton St ( Left Turn to Hume Hwy) - CH16300 to CH16360
51034d40-1965-45e5-b8dc-a7c542b184fd |  | checklist-flat | not-started | ITP 0001 - Clearing & Grubbing | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-023 -Trees Removal - Balyang to Aitken - CH13270 to CH13570
0a96114f-49a3-4682-878f-9b913756e597 |  | checklist-flat | work-in-progress | 49baec836d560c3a123c6fcb141a5d56bcfbe7c1da293bd06bd00661b77e2216 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-024 - 1 Tree - Hardy East
b6697839-7d24-4991-801c-b56c3ecc1389 |  | checklist-flat | pass | d2914bf86e85d5a68c145e12d39b8ed7677902c9a0173e05296d6839792e8dae | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-025 - 18 Tree - Zone 3.2 and 3.3 outside project boundary
425de9ef-d610-4d48-a027-f0a9bc7c2efe |  | checklist-flat | work-in-progress | 49baec836d560c3a123c6fcb141a5d56bcfbe7c1da293bd06bd00661b77e2216 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-026 - Tree Removal - zone 3.2,4.4,6.1
23cdd9d1-10cb-4815-8f56-14551b3356bc |  | checklist-flat | work-in-progress | 49baec836d560c3a123c6fcb141a5d56bcfbe7c1da293bd06bd00661b77e2216 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A1-LOT-027 - grubbing 4.4
86b32aa2-c963-493f-b00f-b7ff25dc2a30 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep
d05d58a2-5b4a-4321-91b6-1e650cd75dbe | Child Final Inspection - Work Completed On(cdc9ada0-7bbf-4668-a4c1-4e5d292b2a5a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-001- Memorial Park East - CH26130 - CH26160 - NB
be817162-e0d1-4f33-ba27-0f4875b9cac4 | Child Final Inspection - Work Completed On(36eaacbd-79a1-400a-895a-d7efa7e34e37): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-002 - Memorial Park East - CH26130- CH26160 - NB
68407b01-ec0f-4d5d-8058-f39f10f3dfbe | Child Final Inspection - Work Completed On(4e5497fa-0796-49a1-9a23-501f86039161): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-003 - Memorial Park East - CH26180 - CH26220 - NB
413ada20-7c81-4571-af26-26e78a36d80f | Child Final Inspection - Work Completed On(8e6d86f7-14d8-4b7e-96ef-d835ac7ca0cc): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-004 - Hume Hwy North Median - CH70330 - CH70400 - NB
a415cad1-4399-43ef-9709-bd3a0dc787b1 | Child Final Inspection - Work Completed On(49ee59ae-285b-4f90-9dde-264f8f7cddfe): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-005 - Hume Hwy North Median - CH70330 - CH70400 - NB
97cbbe0c-b5c8-49bf-8908-724a781a889f | Child Final Inspection - Work Completed On(67a06a49-7edd-4bdc-92b0-6726dd300921): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-006 - Hume Hwy North Median - CH70400 - CH70445 - NB
472bd6ad-ce91-4d54-950d-fd8825f7051a | Child Final Inspection - Work Completed On(ad38b2c6-3996-4c2e-b399-9c75bb7ca2a1): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-007 - Hume Hwy North Median - CH70485- CH70506 - SB
0af0a9cc-01ba-411a-a827-3e9f30732942 | Child Final Inspection - Work Completed On(38a00098-daff-448a-9ab0-4934dc72a56c): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-008 - Hume Hwy South Median- NB - CH70190- CH70280 Cut Floor
6b804bd2-52e8-47de-b7f6-4488cc1caff4 | Child Final Inspection - Work Completed On(5f9fd2c0-2aa7-4b3d-afd3-2a24e19fb5d3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-009 - Hume Hwy South Median - NB - CH70190- CH70280 Layer 1
d0883fdd-1861-4184-ac89-81b66b38a3fb | Child Final Inspection - Work Completed On(05db91a0-846c-403d-8ede-da5ae2a762c9): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-010 - Hume Hwy South Median- NB - CH70190- CH70280 Layer 2
a45524c8-2a9d-4a72-91c3-edb0ce719526 | Child Final Inspection - Work Completed On(747ae6f4-9d59-499c-9400-60712b42f407): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090
b2758db6-0732-45e6-8f62-6b8012e221d2 | Child Final Inspection - Work Completed On(e8a1d0c3-9f6a-40e6-997c-33210bc7932f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-012 - Hume Hwy North Median - CH70330 - CH70400 - NB- 400mm below Subgrade
89baf978-6c82-4dea-b9e0-fa3912757325 | Child Final Inspection - Work Completed On(20c0aee9-8117-4766-8901-79cc45be7eb2): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-013 - Hume Hwy North Median - CH70330 - CH70400 - NB - 400 below subgrade
34ff2c39-5979-4f59-b33b-09eaa00e877b | Child Final Inspection - Work Completed On(dfc42886-2f8a-44b2-879f-91cd7ee2daec): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-014 - Golf Course West - WB - CH13860-CH13700
38a94752-cafb-40d5-8c5e-57d408b8788e | Child Final Inspection - Work Completed On(80686a75-2c1d-47b4-932d-854a5e514c4f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-015- Hume Hwy North Median - CH70310 - CH70400 - SB - Bottom of Subgrade
f9157049-210d-4e9a-8bc7-a2437bce42e9 | Child Final Inspection - Work Completed On(4ba02e70-e61b-4b98-863a-8c4d6b6be2db): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-016 - Golf Course East - WB - CH14040-CH14090
3041c38f-fa6c-4eec-a971-96fd6f3f8aec | Child Final Inspection - Work Completed On(c9f25111-cc6e-47e8-a8a5-5a02d0b45d06): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-017 - Golf Course East - WB - CH14250-CH14306
10417479-ba84-4d1a-99c4-d1eee9d866f5 | Child Final Inspection - Work Completed On(289d3cd0-0ccf-4ae4-b234-5217fbcbf5bb): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-018- Hume Hwy North Median - CH70330 - CH70400 - NB - Subgrade
28ad749f-784a-4e08-a148-31b891531376 | Child Final Inspection - Work Completed On(ec3cf6a5-364d-4dd7-acad-7cfdb0937d5b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-019 - Golf Course East - WB - CH14040-CH14090 - lift 1
792976e4-4a20-4062-98b7-2296f2794720 | Child Final Inspection - Work Completed On(49f53c16-bb52-4822-b510-fc79cc5f2f5d): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-020 - Golf Course East - WB - CH14040-CH14090 - lift 2
9a8021c7-9265-4eea-9b0b-114c71ea2149 | Child Final Inspection - Work Completed On(35024e23-e814-44fd-aa77-fd83b4cf4f3b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-021 - Hume Hwy North Median - CH70310 - CH70330 - NB - 200 below Subgrade
354ad5de-fe2b-46c9-9895-517508c2bcd9 | Child Final Inspection - Work Completed On(0e2ba93f-83fa-4065-b59a-b6c2784002ba): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Subgrade
5ea20c97-5c08-49fe-9598-d520a407dba6 | Child Final Inspection - Work Completed On(3f41135c-a38d-4547-87a7-68a2c30a169b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-023- Hume Hwy North Median - CH70310 - CH70326 - SB - Subgrade
348a2123-12d5-468d-9d36-f84c83e60b08 | Child Final Inspection - Work Completed On(14dd8fa9-d6e7-4a8d-81d3-33274b1fd132): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-024- Hume Hwy North Median - CH70400 - CH70460 - SB - Bottom of Subgrade
eddadc9a-be18-4020-9f23-c387bb4cd1ca | Child Final Inspection - Work Completed On(ad237c37-7075-4582-a2c0-06edd976477b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-025- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep
c661fc6e-1d1e-43aa-9f3e-350a7c07bfdf | Child Final Inspection - Work Completed On(fafaf617-db45-44fc-8f99-417ad4ecf2de): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-026- Hume Hwy North Median - CH70326 - CH70460 - SB - Subgrade
e1ac58b3-2b4b-4810-9703-08344de3a178 |  | checklist-sectioned | pass | 6b8913c19e28a45cbf767a536d58c084746f3008975200810426b570c2af4986 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-027- Golf Course East- Ch 13960 to Ch 14040 - 400 below subgrade
8a6210fe-1cb7-4f39-99e7-a850ec11a6d9 |  | checklist-sectioned | pass | 6b8913c19e28a45cbf767a536d58c084746f3008975200810426b570c2af4986 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-028- Golf Course East- Ch 13960 to Ch 14040 - 200 below subgrade
8eee8312-4212-4adf-8a22-62ccc36ae072 |  | checklist-sectioned | pass | 7d6a3c5f08a1392859076a49b0c25fd8d99e32f5eb3cf714c8a7c5fa7c4fde86 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-029- Golf Course West- Ch 13865 to Ch 13900 - Subgrade prep
8a2b8404-9a54-4734-8a68-85076fc565de |  | checklist-sectioned | pass | 7d6a3c5f08a1392859076a49b0c25fd8d99e32f5eb3cf714c8a7c5fa7c4fde86 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-030- Golf Course West- Ch 13940 to Ch 14040 - Subgrade prep
e3af3918-093d-43d6-bdd3-f73accf424ef |  | checklist-flat | pass | 82f3624d603331351e6994a61b7a396403ad02f98cf61e740760736d197d45f1 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-032- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Bottom Of Subgrade
d7ffbd68-fba4-47fe-9095-9a9ab1b44577 | Child Final Inspection - Work Completed On(da929674-5fd4-4a3f-8af4-54f5569ba25e): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-033- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - 400 below subgrade
d6101e7a-cdf4-45e4-aed3-bac147d97ace | Child Final Inspection - Work Completed On(908f3b10-58f5-4832-8f9f-af0d9614711c): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-034- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - 200mm below Subgrade/ Cut floor
00b6292e-7a50-4899-9452-ca03c3f8cad4 | Child Final Inspection - Work Completed On(8dc49f26-02c3-41b2-a709-9258f10df421): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-035- Hume Hwy North Median - CH70460- CH70490 - SB- Entry - Subgrade
47036334-2855-41f6-87d7-bba5fb728589 |  | checklist-sectioned | pass | e2dcc809c63b7ab5906e1e0b3f49d6cf583a57c70fed3faf072f05569f76d641 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-036 - Hume Hwy North Median - CH70400 - CH70435 - NB - Type Pavement 6 - Egress- Subgrade
ab4bb385-94a3-4d23-9e82-ba933b2566cb |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-038- Memorial Park East - CH26145 - CH26220 - 600mm below cut floor
d6265a00-679c-4615-987f-88f4e1f0ce0c |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-039- Hume Hwy North- Bullnose - CH16366 - CH16380 - 200mm below Subgrade
0188c156-6b37-4d2b-a36d-fbc36b8d10bf |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-040- Hume Hwy South - Bullnose - CH16366 - CH16380 - 200mm below Subgrade
6739ea5e-1a11-4d5a-8efb-ce9665442c36 |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-041- Memorial Park East - CH26145 - CH26220 - 300mm below Subgrade
197b9ac0-7d47-4a88-9d50-99847c3f5385 |  | checklist-sectioned | pass | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-042- Memorial Park East - CH26145 - CH26220 - 600mm below Subgrade
36c891fc-a9fc-40f5-8100-8f07a9375ed3 |  | checklist-sectioned | pass | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-045 - Hardy St - West Bound - CH16068 - CH16105 - 100 mm below Subgrade
bac3a1f6-47d0-4305-a3f9-acea3411d0b2 |  | checklist-sectioned | pass | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-046 - Memorial Park - CH16266 to CH16345 - WB - Subgrade
08990d1f-f6a5-43ad-af55-643cb8d7308d |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-047 - Memorial Park - CH16148 to CH16266 - WB - Subgrade
fbe6993c-30be-46ba-9e4c-476164775562 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-048- Memorial Park - CH26135 to CH26255 - EB - Subgrade
1f5f1149-f9ca-4657-8147-74d3c70a743f |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-049- Hume Hwy West Slither - CH70075 to CH70200 - Subgrade
f5ab721e-f617-4be7-898c-2b61c64c55c9 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-050 - Zone 3.1 - CH 15080 - 14860
997c82a6-1266-4719-849b-638fa582c979 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-051 - Zone 3.1 - CH 14860 - 14760
624f9618-93f2-4007-8707-db7be47b4b99 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-052 Bridgewater Road Northern Median - CH25090 - CH25100 - Subgrade
de25b7af-6104-4f40-a770-d7791c5ed8b4 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-053 - Bridgewater Road Southern Median - CH25090 - CH25100 - Subgrade
7208a685-b3bc-49db-92fe-8c40aeb33026 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-054 - Bridgewater Road South East Corner - CH25115 - CH25120 - Subgrade
81dd176a-369f-4110-9bb6-173a55dff9bc |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-055 - Bridgewater Road - CH25080 - CH25115 - Subgrade
92a06920-622f-447e-b912-9fa50a0da654 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-056 - Craigieburn Plaza Eastbound - CH25900 - CH26060 - Subgrade
b21a7ec8-d388-4279-87b4-b9d757e49219 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-057- Memorial Park - CH26330 to CH26350 - EB - Subgrade
93c21b3b-d2da-4350-b644-776bff5a08f1 |  | checklist-sectioned | not-started | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-058- Memorial Park - CH26290 to CH26350 - WB - Subgrade
9e7e5148-0de9-411b-9c06-b8489ae2366f |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-059- Zone 3.1 - Between Bridgewater Rd and Gate 3.1 - CH15070 to CH 15080 - WB - Subgrade
7e452824-a4fd-4d0b-9028-d762739ba48e |  | checklist-sectioned | not-started | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-060 - Craigieburn Rd Westbound CH15780 TO CH16020 - Type 6 Pavement
3500e5e2-1593-45c0-a9b1-afe504185a71 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-061 - Craigieburn Rd Westbound - CH16015 to CH16080
4f8aa80c-8df1-4693-be33-234b5973f2cd |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-062 - Zone 3.1 - Pavement type 7 - CH15040 to CH15060
a0b6c7d2-a6c7-4dab-9ae8-1e62352dde28 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-063 - Zone 3.2 - Clovelly west - CH14500 to CH14690
16e9c5be-fb33-4cab-947a-cf47faf8a0e2 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-064 - Zone 3.2 - Clovelly west 2nd layer - CH14500 to CH14690
d8327888-90c7-43e6-8ea7-14561ecf09e0 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-065 - Zone 4.4 - Zone 4 West - CH13570 - CH13400
128e31bb-9852-4283-938d-57704d8bbd51 |  | checklist-sectioned | not-started | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-066 - Zone 3.2 - Batter Works (Type C) - 900mm Below - CH14520 to CH14620
b46d2c3b-e9ad-4d24-b585-8bb423598e58 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-067 - Zone 3.1E CH15120 to CH15186
958be2c4-0aca-4acc-9166-3cb9154b69d7 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-068
254e7b50-7124-4940-996a-a1e6ac4d6e6c |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-069 - Zone 3.3 - Pavement Type 1 - CH14420 to CH14500
3a8825f4-27b5-4827-b23b-fa14febb61af |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-006 - Excavation, Fill with Type B and Subgrade Prep | ITP-006-A1-LOT-070 - 3.1 E Subgrade Prep - Craigieburn Rd CH15187 to CH15217 WEST BOUND
ea36fe5c-97a3-4351-892c-8c63abc8544b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A
79fc3246-35d2-46bc-8cef-334ed8f8e18a | Child Final Inspection - Work Completed On(61582bf7-7aad-4704-b7f5-35a44e0c1b50): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-001 - Memorial Park - CH26130- CH26225 - NB
37a5993f-8c27-4abe-9dcb-c6c19c0fb9b3 | Child Final Inspection - Work Completed On(4901efb6-1270-43da-8e4f-b736029ad4b5): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-002 - Hume Hwy North Median - CH70330 - CH70400 - NB
3e9f604e-b2d1-4514-8afe-e1573d19dec4 | Child Final Inspection - Work Completed On(f4d9f409-66af-46c4-a674-850da28c7f20): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-003 - Hume Hwy North Median - CH70330 - CH70400 - NB
71af21ee-0bec-4414-b638-b7706563828c | Child Final Inspection - Work Completed On(a8647733-1353-402f-9b4c-cfa3339fd2c8): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-004 - Hume Hwy North Median - CH70400 - CH70445 - NB
73f8b372-ce4b-4469-ae35-0da8e43246fa | Child Final Inspection - Work Completed On(ec7df61a-1cd3-4632-9a38-a44d86387c3e): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-005 - Hume Hwy North Median - CH70400 - CH70445 - NB
3027bb7f-4e92-4c48-873a-2c7f9f38eca2 | Child Final Inspection - Work Completed On(9844f0c7-a0e4-439f-8493-634670ddafb1): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-006 - Hume Hwy North Median - CH70485 - CH70506 - SB - Layer 1
a68f099e-8d1f-4a64-9dda-2d438f767fdf | Child Final Inspection - Work Completed On(d47d6db6-582a-49c8-b398-9251351c6c16): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5ecb629e2113860d82bc9b6dc05d5a174f69dffac82bc4bd537ba083d7125c1d | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-007 - Hume Hwy North Median - CH70485 - CH70506 - SB
cec557bb-c684-4bf3-bd9f-7d0e11c90c2a |  | checklist-flat | pass | 884b47b805edf30c7e4bf94c5164b986431b487ef3a142e7e60946c9501f8407 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-008 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 1
f14d2997-7626-45ed-ac57-4d96499370a0 |  | checklist-flat | pass | 884b47b805edf30c7e4bf94c5164b986431b487ef3a142e7e60946c9501f8407 | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-009 - Hume Hwy South Median - CH70190 - CH70280 - NB - Layer 2
fa6ba67e-baf9-4377-aa50-13081f1c9e85 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-010 - Golf Course East - WB - CH14250-CH14090 - Lift 1
563d7f25-40f8-483c-b24d-ab7e759d2b6d |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-011 - Golf Course East - WB - CH14250-CH14090 - Lift 2
da5e00d8-9820-41f6-aae5-aa8386e80a91 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-015 - Hume Hwy North Median - CH70330 - CH70400 - NB - Layer 2
69046c61-18cc-4a6a-bc44-149b9f1d251e |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-022 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 1
56202291-008c-44ff-9378-c0fdb08bd002 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-023 - Hume Hwy North Median - CH70310 - CH70330 - NB - Layer 2
66f45cd1-7be9-4f1d-9e33-9d8c04a5abde |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-024 - Golf Course West - Ch13865 to Ch13900 - 1st lift Capping
c838b7d6-4bc7-4ce6-ad94-c392e4f8d22d |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-025 - Hume Hwy North Median - CH70400 - CH70460 - SB - Type A Layer 1
18e2289a-85de-4027-8eb4-1503bdd6263e |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-026 - Hume Hwy North Median - CH70326 - CH70400 - SB - Type A Layer 1
ea84f861-6130-4744-922d-0347c0fd4ebf |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-027- Hume Hwy North Median - CH70460 - CH70490 - SB- Entry - Type A Layer 1
dced0c07-1375-440a-aaa5-51ef32f55170 |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-028- Hume Hwy North- Bullnose - CH16366 - CH16380 - Type A - Layer 1
371e32ec-cb3d-42c8-9f20-4497bcd48e9a |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-029- Hume Hwy South - Bullnose - CH16366 - CH16380 - Type A -Layer 1
173da6f9-07e9-45a7-9e92-0cb0e5fc5af7 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-030- Memorial Park North - CH16266 to CH16350 - WB - Type A Capping (260mm)
e23515b6-53dd-4a83-ab58-44a92cf17577 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-031 - Memorial Park - CH16148 to CH16266 - WB - Type A Capping (260mm)
772d7cb1-6a58-4900-afdc-50a315ed1bfc |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-032 - Memorial Park - CH26135 to CH26255 - EB - Type A Capping (260mm)
2ebacd36-7864-4529-8ba7-6215606b6e72 |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-033- Hume Hwy West Slither - CH70075 to CH70200 - Type A (260mm)
edb34f3d-23d7-41dd-90d5-919df881af0e |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-034- Hume Hwy West Slither - CH70075 to CH70200 - Type A (260mm)
eb6c8ae5-f7e4-4e23-9480-57b75b9a6bf0 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-035 - Bridgewater Road - CH25080 - CH25115
516a4e0f-ccdf-4082-b811-e578e9be447c |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-036 - Zone 2 - Craigieburn Plaza Eastbound - CH25900 - CH26060
d52fc933-aeed-4592-94b3-f7606058638a |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-037 - Zone 1 - Craigieburn Walters Intersection - CH26060 to 26140 - Lime Stab
0817e556-25bc-4ca7-98d6-ae813f18e861 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-038 - Memorial Park - CH26280 to CH26350 - EB - Type A Capping
c4eb1354-62db-40b1-bbec-952c052244e1 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-040 - Craigieburn Rd Westbound - CH16015 to CH16080
a80b1e52-f5f2-4eec-8c4c-92716691fc48 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-041 - Zone 3.1 - Pavement Type 7 - CH15040 to CH15060
8d3a66a3-85b7-496c-864b-858cca25447c |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-042 - Craigieburn Rd WB CH15253 - CH15286 - Zone 3.2E
ff363749-5ac6-4a0b-a579-99134c5beaf2 |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-043 - Zone 3.3 - Pavement Type 1 - CH14420 to CH14500
1485c66c-6455-42c7-90fc-abeffeca128e |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-044- Zone 3.1E 1st Layer Capping CH15121- CH15216
881b5bfc-d057-4bc6-9ddd-dd8ffa114bb7 |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-045 - Zone 3.2E - Craigieburn Rd CH1512-CH15217 capping
49b253bb-69c2-4784-9382-9e9e087920ea |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-047 - Zone 4
fe788566-5e1b-4772-91b0-dd8245a10cf2 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A1-LOT-046 - Zone 4.4 - Zone 4 West - CH13570 - CH13400
7e7eef9d-8e40-4ff4-85ea-70be4ae5f141 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement
0c186d51-d41c-46bf-9da8-702d6ec60085 |  | checklist-sectioned | work-in-progress | 74d34924f1a68c5a46eecc4d895681eca60bdad5a33036e8243b9afcf6500d52 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-003 - Golf Course East - CH14250-CH14165 - WB
a1fa6eb4-0f7f-4d17-88fc-0ad0ed18c4a0 |  | checklist-sectioned | work-in-progress | 74d34924f1a68c5a46eecc4d895681eca60bdad5a33036e8243b9afcf6500d52 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-004 - Golf Course East - CH14165-CH14090 - WB
19ea8ee6-5472-4f31-b250-74e289507f99 |  | checklist-sectioned | pass | c996cd00a6a5d54baade046be30ae615c349183bb7dc26cf870a14551602796c | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-005 - Hume Hwy North Median - CH70310 - CH70450 - NB - CL4
3a6646df-21e9-40fb-ac3c-8b0ad00692e2 |  | checklist-sectioned | pass | c996cd00a6a5d54baade046be30ae615c349183bb7dc26cf870a14551602796c | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-006 - Hume Hwy North Median - CH70310 - CH70490 - SB - CL4
8a1fd0cb-52eb-40b9-b4cd-f880e7674c21 |  | checklist-sectioned | pass | 22dd6cae9b52c342a62880b4924a4876f1b524085030c9379d5ada068e6b317e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-008 - Hume Hwy South Median - CH70194 - CH70280 - NB - Pavement Type 3
eea46838-926a-4dc4-83a5-85bf50f74781 |  | checklist-sectioned | pass | 77fc70ecb022a104a72515ce3e81440e128324c92045f9307f8256755e95e636 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-009- Hume Hwy South Median - CH70142 - CH70194 - NB - Pavement Type 6
b6a9f134-9a22-4b71-9151-629631e6efd1 |  | checklist-sectioned | pass | 85d5cce5bcf0cfce046b8100e63efdbe642a82734184e1fdcf78a63c0ead0d04 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-010- Hume Hwy North- Bullnose - CH16366 - CH16380
1d9c1a3a-8109-4679-b274-26d808d57051 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-012 - Memorial Park - CH16266 to CH16350 - WB
a35aee7d-1de1-4b61-863a-841a27d68648 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-013- Memorial Park - CH16148 to CH16266 - WB
98cd3c43-5204-4d4a-9afd-9a99fa6f1727 |  | checklist-sectioned | pass | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-014- Memorial Park - CH26148 to CH26266 - EB
eb82595e-c6c2-4744-8bec-49b6a934860e |  | checklist-sectioned | pass | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-015 - Hume Hwy West Slither - CH70075 to CH70200
84074944-7f94-420a-a06b-e4ea49c6b004 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-016 - Zone 3 West - CH15078 - 14900 (Layer 1)
a3951c16-d8a3-463a-ba2a-4f023bf5afc8 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-017 - Bridgewater Road Northern Median - CH25090 - CH25100
defbb239-ef00-4c0b-b321-7d5171549196 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-018 - Bridgewater Road Southern Median - CH25090 - CH25100
be654ec8-3d93-4e32-bfcc-c95d66fa6608 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-019 - Bridgewater Road South East Corner - CH25115 - CH25120
a648d452-b158-4967-b719-e30f68d45e5e |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-020 - Bridgewater Road - CH25080 - CH25115
9ed8e6dd-9cc4-4fb8-88f6-8085d322b444 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-021 - Zone 3 West - CH14880 - 14900 (Layer 1)
a416ea38-e311-43ff-acab-37b52fee5bea |  | checklist-sectioned | work-in-progress | 4701d6c87b1ab9100bdf50fa62d119b554f1391b366a6508a6e92871997f473b | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-022 - Zone 2 - Craigieburn Plaza Eastbound - CH25900 - CH26060
1095c87a-d51b-4c8c-8d78-66035633a58f |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-023 - Zone 3 West - CH14880 - 15078 (Layer 2)
7c789023-9b99-4502-847a-a6f3b7a910f2 |  | checklist-sectioned | pass | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-024- Memorial Park - CH26266 - CH26330 - EB
b3f276ac-6932-4a05-8046-eee4bd325023 |  | checklist-sectioned | pass | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-025- Hardy RD - CH26060 - CH26140 - EB & WB
7ecdc266-e11a-4c70-8e7a-35c78046a5c2 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-026- Zone3.1 - CH14770- CH14880 - WB- 1st layer
94dd5e97-a9b3-46f9-b0a9-e0747cf2b959 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-027 - Craigieburn Rd Westbound - CH26260 - CH26330
f0b86082-4780-4b2c-b72f-30a82e9ccc26 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-028- Zone3.1 - CH14770- CH14880 - WB- 2nd layer
0211e5f0-3faf-4884-bf05-29668f4f69aa |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-029- Memorial Park - CH26330 - CH26360 - EB
6e29fd23-d27e-416f-bbee-784dbbce3e73 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-030 - Memorial Park - CH26280 to CH26350 - EB
550ca964-c612-4328-a5aa-14843343164c |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-031 - Zone3.1 BTW Bridgewater and Gate 3.1- CH15070 to CH15080- 1st layer
95b544b0-1d82-4b82-bee6-16e0be653453 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-032 - Zone3.1 BTW Bridgewater and Gate 3.1- CH15070 to CH15080- 2nd layer
00ab8d23-5d62-4838-8606-e02b659377d6 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-033 - Craigieburn Rd Westbound CH15780 TO CH16020 - Type 6 Pavement
8a6a7d8f-7bc1-4fe1-abe6-778b9a8ba500 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-034 - Craigieburn Rd Westbound CH16015 TO CH16080 - Type 3 Pavement
bdd90e94-adb0-456d-a619-eb12016b446e |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-035 - Zone 3.1 -Type7 pavement - CH15040 to CH15060-Cl3
72bb9093-9123-4575-8d70-fcf1ad27161d |  | checklist-sectioned | fail | 4701d6c87b1ab9100bdf50fa62d119b554f1391b366a6508a6e92871997f473b | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-037 - Zone 3.2 -Clovelly West - CH14500 to CH14745 - 1st layer
96132024-2aaa-4916-9c1f-b01be5cad466 |  | checklist-sectioned | work-in-progress | db37239a3a127632512492488f14503c99c817d0e4cd151a198c97236c028eec | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-038 - Zone 3.2 -Clovelly West - CH14500 to CH14745 - 2nd layer
c9d10012-1263-4bd9-a008-0296fc49bed0 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-036 - Zone 3.1 -Type7 pavement - CH15040 to CH15060-Cl2
59af2642-0d0c-498f-813e-c3369df5d7f5 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-009 - Unbound Pavement | ITP-009-A1-LOT-039 - Zone 3.3 - Pavement Type 1 - CH14420 to CH14500
d0de1d29-d5a1-4dd7-b9fd-d3a4ff9fa8a8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage
5d13bdf4-42e0-4e6a-98fd-48873b539eda |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-001 - Hume Hwy North - Ch 70320 - Ch 70460- SB - Double Sides
6e9a4a34-382e-427f-ba62-5dad3c454e05 |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-002 - Hume Hwy South - Ch 70140 - Ch 70204 - NB - Double sides
3517dd44-322d-4e6c-8a7b-a6d864df833a |  | checklist-sectioned | pass | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-003 - Hume Hwy North - Ch 70315 - Ch 70386 - NB -Double sides
10e90aec-9074-4004-95f8-3aa10bc20dcb |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-005- Hume Hwy North - Ch70460- Ch70490 - SB- Entry
b7d1aa44-33e0-47a1-a3cb-c083205af523 |  | checklist-sectioned | work-in-progress | 31441229c4d7ccc22762648add154d895de5c8ba3d08b303668609990e885e80 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-006- Hume Hwy North - Ch70306 - Ch70322 - Bullnose
0b82b990-c2cb-40f2-ab2d-75190c09bfcf |  | checklist-sectioned | work-in-progress | 5a023bd0fe0c05cba8ae226130dc910af6a7f39ac4cec25de77709ae83460ad8 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-007 - Hume Hwy South - Ch 70204 - Ch 70280 - NB - Double sides
50997ea9-2f24-4fee-947c-4929f731055a |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-008 - Hume STH Bullnose
4430fd1d-36e0-4a8f-92f5-43d33221543e |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-009 - Memorial Park WB CH16150 - CH16355 (Both Sides + Islands)
522a671f-6882-41da-8d4c-e00ed6091cf7 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-010 - Memorial Park EB - CH26132 - CH26350 (Both Sides)
ce4a35ed-e133-419d-9ee4-718799a324f4 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-011 - Hume Hwy West Slither - CH70075 to CH70220
15de2490-f50b-4b6d-8197-ec02992f6cbd |  | checklist-sectioned | pass | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-012 - Bridgewater Road Northern Median - CH25090 - CH25100
caf6c855-3685-4ed9-99f5-7712240606bc |  | checklist-sectioned | pass | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-013 - Bridgewater Road Southern Median -CH25090 - CH25100
4f83ae58-8d01-4a8e-9f3f-2535cd9bb3cc |  | checklist-sectioned | pass | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-014 - Bridgewater Road South East Corner - CH25105 - CH25120
77a0a9b5-a7e6-4d70-8bb1-2f0cfaa6cd2f |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-015 - Bridgewater Road centre crossing- CH25080 - CH25115
5abfa4f2-300a-4281-9d7d-f247964b31f4 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-016 - zone 3.1 - CH14930 - CH15070 - Nth side
892eebb0-7e24-4f5a-9212-ec13d999a743 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-017 - Craigieburn Rd EB - CH25980 - CH26140 (Both Sides)
7e756a66-9614-4146-9532-3b5f61219e2c |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-018 - Craigieburn Rd WB - CH26225 - CH26300 (Both Sides)
a763a56c-2dd9-40ae-bd66-6ec249221cc2 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-019 - zone 3.1 - CH14990 - CH15040 - Sth side - pit 346 to pit 090
e3321a90-7468-4f83-8bb0-62305f31aefc |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-020 - zone 3.1 - CH14920 - CH14990 - Sth side - pit 090 to pit 092
8bbff870-11bc-494d-96aa-cbbedfc877ae |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-021 - zone 3.1 - CH149990 - CH14780 - Sth & Nth sides
30e7f667-b87b-4828-a341-1c38e01164be |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-022 - Zone 3.1 - CH14780 - CH14840 - Sth & Nth sides
0563201c-1256-4ad1-92d1-3991aec4373e |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-023 - Zone 3.1 - BTW Bridgewater West and Gate 3.1 - Sth & Nth sides
bb0d0cb1-3d08-4f79-b2e8-28c16724b716 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-024 - Plaza Median
a68e490a-2978-4228-ae26-2e100fd29dc4 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-025 - Slip lane zone 3.1- CH15040 to CH15060
29b686db-e3b8-4cb9-a722-def844302ec7 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A1-LOT-026 - P040 - P039 - Coffee Shop Z2
f6eb6436-064c-4ea6-a830-b8171d33e35e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock
524d6b13-68cc-4ee1-b32a-76e1a027d88b |  | checklist-sectioned | pass | 1d392233850777c1cf96f8bc01c98df02e5f1f72003286bfd2108fb3150ed8fb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-001 - Hume Hwy North Median - CH70310 - CH70400 - NB
6226d3f7-8a5e-4206-93ba-b6e0c206306b |  | checklist-sectioned | pass | 1d392233850777c1cf96f8bc01c98df02e5f1f72003286bfd2108fb3150ed8fb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-002 - Hume Hwy North Median - CH70310 - CH70460 - SB
371c3cad-c8db-4da1-90d1-b080add1ea93 |  | checklist-sectioned | pass | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-003 - Hume Hwy South Median - CH70194 - CH70280 - NB - Pavement Type 3
d1ac07f5-7b0f-4cad-b650-55a9789d8fba |  | checklist-sectioned | pass | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-004 - Hume Hwy South Median - Bull-nose - CH16366 - CH16380
8baa6f21-2e0c-49cd-ae3a-f42c18101961 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-005 - Hume Hwy West Slither - CH70075 to CH70200
0abd8dd9-c00b-46dc-a6d5-b75ac28f81c1 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-006 - Bridgewater Road - CH25080 - CH25115
177fab87-c188-4d85-9c4b-c25632f58efe |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-007 - Memorial Park - CH16148 to CH16266 - WB - CTCC
0829a3d2-cbc2-4bc7-ae9f-fcdfad09d5bd |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-008- Memorial Park - CH26148 to CH26240 - EB - CTCC
a9130421-fbb4-434a-944a-0568f85d4898 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-009- Zone3.1 - Between Bridgewater to Clovelly - CH14940 to CH15040 - WB - CTCC
b4d0a042-2d0b-4a5a-bf69-743e929d9a79 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-010- Memorial Park - CH261240 to CH26300 - EB - CTCC
223019b7-782a-4eb3-88bc-6b285f4f1c23 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-011- Walters Intersection - CH26060 - CH26180 - EB & WB
0ea0ad3c-1423-49ce-8d09-b8886086ffd3 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-012- bus stop -Zone3.1 - Between Bridgewater to Clovelly - WB - CTCC
e4f647ac-5843-471d-9297-889e781ede31 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-013 - Zone 2 - Craigieburn Plaza Eastbound - CH25900 - CH26060
3f4b8898-980a-4919-802a-b33e074db833 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-014 - Craigieburn Rd Westbound - CH26270 - CH26330
fba5f3d6-d987-40be-9db6-45c2e731c227 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-015 - Memorial Park - CH26280 to CH26350 - EB - CTCC
89601aaf-9154-4e8d-8b76-29ae50e0ce33 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-016 -Z3.1 Middle to Clovelly - CH14770 to CH14900 - WB - CTCC
0d4151b6-101f-4e00-b832-7e4e15e3344c |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-017 -Z3.1 Bridgewater to Gate 3.1- CH15040 to CH15080 - WB - CTCC
aac97d56-cbed-4681-b496-0fcae97f5e86 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-018 - Craigieburn Road Eastbound - CH15900 to CH15990
c0c038e7-840d-466d-bb55-f048d5b4a87c |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A1-LOT-019 - Craigieburn Rd Westbound CH16020 to CH16080
27bd3213-eb95-4c34-abaf-23019d36b2d0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel
52d0e7b3-46c8-4d8b-8983-16fca5063428 |  | checklist-sectioned | pass | b7e51bd93029ed359dbd2e96bec2c58186dfaafef7c0e9ecf8791fd491f5ee8f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-001 - Hume Hwy North (CH70450 - CH70315)
f621e1c4-3616-4f45-82d8-cadaac0afcde |  | checklist-sectioned | pass | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-002 - Hume Hwy South
152e3db9-bf53-4e7c-abde-34e5fae8cbe3 |  | checklist-sectioned | pass | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-003 - Hume Hwy North(CH 70450 - CH 70480)
b3621130-d2d6-4fca-9714-80fca65604c3 |  | checklist-sectioned | pass | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-004 - Hume Hwy South (Bullnose)
a67816b8-a3c2-4760-90c6-54fc29f293d5 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-005 - Bridgewater Road Northern Median - CH25090 - CH25100
53f2fe28-c61f-4498-acae-61c629c67421 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-006 - Bridgewater Road Southern Median - CH25090 - CH25100
3f7c8916-34b2-4faa-8b29-59a017f3b1f9 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-007 - Bridgewater Road South East Corner - CH25105 - CH25120
7669ca2b-ad6f-48d5-8275-68e36cd349c5 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-008 - Bridgewater Road SW Traffic Island - CH25080 - CH25085
8b417f56-2b45-4d76-89e9-d9850983744d |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-009 - Memorial Park - Craigieburn Rd Eastbound CH26140 to CH26300
a586be3f-f20d-4750-90bc-a50b3cd8013c |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-010 - Memorial Park - Craigieburn Rd Westbound CH16150 to CH16270
75069ec8-d649-49df-9398-0e8ca11e7581 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-011 - Hume Hwy Northbound - CH70075 to CH70220
6e012cd2-0730-4891-bef2-9662cdd4c94a |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-012 - Craigieburn Rd Eastbound - CH26000 to CH26160
7b40477e-91be-4d45-bbd8-fd93df7234c6 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-013 - Craigieburn Road Westbound - CH16140 to CH16180
782eaf00-e37b-472f-a187-3043bd812269 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-014 - Craigieburn Rd Eastbound and Westbound - CH26260 to CH26360
1b844a30-8f53-4003-8a2d-5616f693a753 |  | checklist-sectioned | not-started | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-015 - Zone 3.1 Westbound - CH14770 to CH15080
f257fb19-ee82-4711-958e-5ebe4166bccc |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-016 - Zone 2 - Craigieburn Rd Westbound CH15950 to CH16020
23f088d4-3696-434d-98d6-a3a1bf708c48 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-017 - 25 Craigieburn Rd - CH25960 to CH26000
4daa10a6-6b30-4bba-80b4-c3ddf6377b63 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-018 - 27 Craigieburn Rd - CH25960 to CH26000
d82d40be-0b88-409e-a91b-06d010ac2c4a |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-019 - CRAIGIEBURN RD WESTBOUND CH15900 to CH16000
d8b616ae-3994-49d5-a61c-dbbb10dc6356 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-020 - Hardy East Island (South Side) - 16120 to 16200
3953567f-e258-4f00-8af1-83ea8266f5e3 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-021 - Craigieburn Rd Westbound CH16260 to CH16280
57326d9d-84f1-49db-b627-bc41ced1b152 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-022 - Hume Hwy Left Slip Lane
f3363a7d-9b7e-4472-979d-abe95a3bca08 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-023 - Craigieburn Rd Westbound Medians CH15920 to CH16080
0d640348-53b4-4f74-be74-5f076f51b0f2 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-024 Zone 3.1
e48f74db-9808-4a4e-b1e2-2ec7f71a8ac3 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-012 - Kerb and Channel | ITP-012-A1-LOT-025 - Craigieburn Rd EB - CH15880 to CH15940
1e166968-d1c5-4bd5-b3e9-2e0e2defc426 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-013 - Structural Concrete
0c92621c-d065-457f-b78c-290b82e78490 |  | checklist-sectioned | pass | fae5cf31f0e4d05eaace3a9ee5478d16e865cfc3a9ae0e7cb5b43ee78bba0825 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-013 - Structural Concrete | ITP-013-A1-LOT-001 - Hume Hwy South - Headwall 1011 - BASE
0b03f792-9f3c-41e4-bc12-57ddb050d275 |  | checklist-sectioned | pass | d04619e6cf2b1626eb9a1bf67ddc2799299d79968c27e54e3e062f0104a45177 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-013 - Structural Concrete | ITP-013-A1-LOT-002 - Hume Hwy South - Headwall 1011 - WALLS
0cf4eb1e-43fd-4db2-89ce-eb5b487198b3 |  | checklist-sectioned | not-started | ITP 0013 - Structural Concrete | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-013 - Structural Concrete | ITP-013-A1-LOT-003 - Maintenance Strip Ground Beam from Pit 304 to Pit 305
861160d9-095c-40fd-8da9-cb91a884b8ad |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-016 - Bored Pile Construction
6b05bfb7-fece-4da7-8a20-3335e1f2c51f |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage
c8aec1c5-4a09-4e57-a4f2-da9353e160f1 | Child Lot Verification(91dba596-71ad-5d8a-bfa6-55a8d6e2e91c) -- Lot Verification.(69a1685a-3318-5677-811c-26beb26f94b8): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(91dba596-71ad-5d8a-bfa6-55a8d6e2e91c) -- Lot Verification.(69a1685a-3318-5677-811c-26beb26f94b8): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(91dba596-71ad-5d8a-bfa6-55a8d6e2e91c) -- Lot Verification.(69a1685a-3318-5677-811c-26beb26f94b8): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(91dba596-71ad-5d8a-bfa6-55a8d6e2e91c) -- Lot Verification.(69a1685a-3318-5677-811c-26beb26f94b8): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(91dba596-71ad-5d8a-bfa6-55a8d6e2e91c) -- Lot Verification.(69a1685a-3318-5677-811c-26beb26f94b8): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | fbab148c1ee0edbc6633c617eb9bea2d948916700b898128282095ab6227ff68 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-001 - Stormwater Drainage - Pit 1002 to Pit 1001 - Hume Hwy southbound Xing - Z1
a49b3fe4-96d2-467a-8e4b-94c59ce36df3 | Child Lot Verification(2b2cd7e3-e5d0-5474-90d1-b10413df41f2) -- Lot Verification.(63d389a7-b4c8-5573-b961-9d981c2d82d7): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(2b2cd7e3-e5d0-5474-90d1-b10413df41f2) -- Lot Verification.(63d389a7-b4c8-5573-b961-9d981c2d82d7): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(2b2cd7e3-e5d0-5474-90d1-b10413df41f2) -- Lot Verification.(63d389a7-b4c8-5573-b961-9d981c2d82d7): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(2b2cd7e3-e5d0-5474-90d1-b10413df41f2) -- Lot Verification.(63d389a7-b4c8-5573-b961-9d981c2d82d7): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(2b2cd7e3-e5d0-5474-90d1-b10413df41f2) -- Lot Verification.(63d389a7-b4c8-5573-b961-9d981c2d82d7): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 90e1853179248dc124399413909b23617d8c4f1775e0005ce14ae434bdf49f93 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-002 - Stormwater Drainage - Pit 1014 to Pit 1015
0cb6d1a9-c0da-4acf-8b1d-fcbdce0f6a3c | Child Lot Verification(4bb42656-3a5b-55f2-976c-8ea9d3cf3c42) -- Lot Verification.(717d94ca-18e0-59c0-8bc9-574c39c5812d): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(4bb42656-3a5b-55f2-976c-8ea9d3cf3c42) -- Lot Verification.(717d94ca-18e0-59c0-8bc9-574c39c5812d): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(4bb42656-3a5b-55f2-976c-8ea9d3cf3c42) -- Lot Verification.(717d94ca-18e0-59c0-8bc9-574c39c5812d): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(4bb42656-3a5b-55f2-976c-8ea9d3cf3c42) -- Lot Verification.(717d94ca-18e0-59c0-8bc9-574c39c5812d): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(4bb42656-3a5b-55f2-976c-8ea9d3cf3c42) -- Lot Verification.(717d94ca-18e0-59c0-8bc9-574c39c5812d): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 90e1853179248dc124399413909b23617d8c4f1775e0005ce14ae434bdf49f93 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-003 - Stormwater Drainage - Pit 1015 to Pit 1016
d544bfbd-0703-4a67-969b-5b871fe3b6ef | Child Lot Verification(b25480b7-f1bf-5fdb-b2ae-ae1c84d23160) -- Lot Verification.(fbf9d9e2-d650-51c4-9ddf-8bcb229a5759): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(b25480b7-f1bf-5fdb-b2ae-ae1c84d23160) -- Lot Verification.(fbf9d9e2-d650-51c4-9ddf-8bcb229a5759): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(b25480b7-f1bf-5fdb-b2ae-ae1c84d23160) -- Lot Verification.(fbf9d9e2-d650-51c4-9ddf-8bcb229a5759): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(b25480b7-f1bf-5fdb-b2ae-ae1c84d23160) -- Lot Verification.(fbf9d9e2-d650-51c4-9ddf-8bcb229a5759): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(b25480b7-f1bf-5fdb-b2ae-ae1c84d23160) -- Lot Verification.(fbf9d9e2-d650-51c4-9ddf-8bcb229a5759): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 90e1853179248dc124399413909b23617d8c4f1775e0005ce14ae434bdf49f93 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-004 - Stormwater Drainage - Pit 1016 to Pit 1017
ced98aa3-2b58-474b-af50-f1348f234f12 | Child Lot Verification(1762875f-bee4-5892-a08e-131c16a8b0af) -- Lot Verification.(770f3138-1386-5ad5-965b-3d585bffa776): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(1762875f-bee4-5892-a08e-131c16a8b0af) -- Lot Verification.(770f3138-1386-5ad5-965b-3d585bffa776): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(1762875f-bee4-5892-a08e-131c16a8b0af) -- Lot Verification.(770f3138-1386-5ad5-965b-3d585bffa776): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(1762875f-bee4-5892-a08e-131c16a8b0af) -- Lot Verification.(770f3138-1386-5ad5-965b-3d585bffa776): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(1762875f-bee4-5892-a08e-131c16a8b0af) -- Lot Verification.(770f3138-1386-5ad5-965b-3d585bffa776): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 90e1853179248dc124399413909b23617d8c4f1775e0005ce14ae434bdf49f93 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-005 - Stormwater Drainage - Pit 1017 to Pit 1018
8388b1e3-a433-4d2e-9191-b5ea08daa031 | Child Lot Verification(261dab13-87cf-5999-81be-510ec71f4599) -- Lot Verification.(5e7b6da3-4b47-57cb-b03f-cdd5df969782): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(261dab13-87cf-5999-81be-510ec71f4599) -- Lot Verification.(5e7b6da3-4b47-57cb-b03f-cdd5df969782): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(261dab13-87cf-5999-81be-510ec71f4599) -- Lot Verification.(5e7b6da3-4b47-57cb-b03f-cdd5df969782): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(261dab13-87cf-5999-81be-510ec71f4599) -- Lot Verification.(5e7b6da3-4b47-57cb-b03f-cdd5df969782): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(261dab13-87cf-5999-81be-510ec71f4599) -- Lot Verification.(5e7b6da3-4b47-57cb-b03f-cdd5df969782): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 90e1853179248dc124399413909b23617d8c4f1775e0005ce14ae434bdf49f93 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-006 - Stormwater Drainage - Pit 1018 to Pit 1019
3e9af6b7-b023-4cea-9d80-8d65129e43d0 | Child Lot Verification(db7fa8ce-56d5-5a78-afd1-a7bb00658da8) -- Lot Verification.(c712f703-52e1-5182-94b2-19afd34c27e9): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(db7fa8ce-56d5-5a78-afd1-a7bb00658da8) -- Lot Verification.(c712f703-52e1-5182-94b2-19afd34c27e9): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(db7fa8ce-56d5-5a78-afd1-a7bb00658da8) -- Lot Verification.(c712f703-52e1-5182-94b2-19afd34c27e9): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(db7fa8ce-56d5-5a78-afd1-a7bb00658da8) -- Lot Verification.(c712f703-52e1-5182-94b2-19afd34c27e9): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(db7fa8ce-56d5-5a78-afd1-a7bb00658da8) -- Lot Verification.(c712f703-52e1-5182-94b2-19afd34c27e9): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 94fa3d7bba6e334fd0bf687735c23b2beb02b34d4c18db4205b1c6757d1a5921 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-007 - Stormwater Drainage - Pit 1019 to Pit 1020
5ce61b85-6f43-4022-a0c5-289ada61ec00 | Child Lot Verification(299862fe-e08d-5d0d-b422-ad44c19c574c) -- Lot Verification.(4c0b46af-82ea-57a1-92fd-b8c8d9332efd): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(299862fe-e08d-5d0d-b422-ad44c19c574c) -- Lot Verification.(4c0b46af-82ea-57a1-92fd-b8c8d9332efd): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(299862fe-e08d-5d0d-b422-ad44c19c574c) -- Lot Verification.(4c0b46af-82ea-57a1-92fd-b8c8d9332efd): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(299862fe-e08d-5d0d-b422-ad44c19c574c) -- Lot Verification.(4c0b46af-82ea-57a1-92fd-b8c8d9332efd): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(299862fe-e08d-5d0d-b422-ad44c19c574c) -- Lot Verification.(4c0b46af-82ea-57a1-92fd-b8c8d9332efd): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 94fa3d7bba6e334fd0bf687735c23b2beb02b34d4c18db4205b1c6757d1a5921 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-008 - Stormwater Drainage - Pit 1020 to Pit 1021
c2b88c4c-de49-4bec-9627-a052c9b0bf32 | Child Lot Verification(9c62e0af-30e1-5278-a48f-ecfe4c8cc457) -- Lot Verification.(7c02278e-641c-5e27-94bf-588cf04365fa): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(9c62e0af-30e1-5278-a48f-ecfe4c8cc457) -- Lot Verification.(7c02278e-641c-5e27-94bf-588cf04365fa): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(9c62e0af-30e1-5278-a48f-ecfe4c8cc457) -- Lot Verification.(7c02278e-641c-5e27-94bf-588cf04365fa): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(9c62e0af-30e1-5278-a48f-ecfe4c8cc457) -- Lot Verification.(7c02278e-641c-5e27-94bf-588cf04365fa): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(9c62e0af-30e1-5278-a48f-ecfe4c8cc457) -- Lot Verification.(7c02278e-641c-5e27-94bf-588cf04365fa): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 94fa3d7bba6e334fd0bf687735c23b2beb02b34d4c18db4205b1c6757d1a5921 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-009 - Stormwater Drainage - Pit 1021 to Pit 1022
931accf8-298a-417d-ba51-8dfc67e7f491 | Child Lot Verification(ced1ac83-1ca1-40cd-9e11-2d9d8a38d3d7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 280a4a6b614c24c1142cdf3f06c29e7aca2acf5552bb68d1c6ff2e3036bd7dfd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-010 - Stormwater Drainage - Pit 1002 to Pit 1003
0b19d393-a624-4f47-90a5-9d8a38209fa4 | Child Lot Verification(0696a294-5bf7-4bb9-bf37-055f8faed0be): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 37b1352f46dffecacfc013c709b42f616d7f9df3823199aa1ffab95c331eede3 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-011 - Stormwater Drainage - Pit 1002 to Pit 1007
aba593f6-a5b4-4f90-822e-3fa39f0fa859 | Child Lot Verification(8a5e32d5-4584-51d8-8f4a-ff4eef784b65) -- Lot Verification.(d0d358d5-d47e-5f8e-985d-3f5dc62d6fb4): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(8a5e32d5-4584-51d8-8f4a-ff4eef784b65) -- Lot Verification.(d0d358d5-d47e-5f8e-985d-3f5dc62d6fb4): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(8a5e32d5-4584-51d8-8f4a-ff4eef784b65) -- Lot Verification.(d0d358d5-d47e-5f8e-985d-3f5dc62d6fb4): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(8a5e32d5-4584-51d8-8f4a-ff4eef784b65) -- Lot Verification.(d0d358d5-d47e-5f8e-985d-3f5dc62d6fb4): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(8a5e32d5-4584-51d8-8f4a-ff4eef784b65) -- Lot Verification.(d0d358d5-d47e-5f8e-985d-3f5dc62d6fb4): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 5ff292025b4b0fe8e47acceae7841db55847642eb1db2498891f8acec1c51800 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-012 - Stormwater Drainage - Pit 1003 to Pit 1004
ec0951ce-d0ec-4069-b587-75a437cff786 |  | checklist-sectioned | work-in-progress | f261acd619c350c4a0e97b5603b42159ac5d1255e77a467a7f2cba7f7ae27a46 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-013 - Stormwater Drainage - Pit 1003 to Pit 1006
081d3d25-a683-4238-892a-7d53ff583f8c | Child Lot Verification(8f7ec7d9-f240-4863-b050-5ee2e912e98a): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 37b1352f46dffecacfc013c709b42f616d7f9df3823199aa1ffab95c331eede3 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-014 - Stormwater Drainage - Pit 1004 to Pit 1005
e542018a-bd2e-4e02-98ec-66d1e2dc1c6b | Child Lot Verification(39205bff-5152-435e-9d4b-8a6d4ed72649): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 37b1352f46dffecacfc013c709b42f616d7f9df3823199aa1ffab95c331eede3 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-015 - Stormwater Drainage - Pit 1007 to Pit 1008
eddacc99-d4b5-4b5e-a9e6-1c99b3437240 | Child Lot Verification(6308bc16-f558-45f9-836e-2a7789183baf): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 37b1352f46dffecacfc013c709b42f616d7f9df3823199aa1ffab95c331eede3 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-016 - Stormwater Drainage - Pit 1007 to Pit 1009
617c662e-1ed7-43e8-994e-19553c6ddf9b | Child Lot Verification(e3c48555-4e66-444a-8ad4-d2441500f9d5): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 37b1352f46dffecacfc013c709b42f616d7f9df3823199aa1ffab95c331eede3 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-017 - Stormwater Drainage - Pit 1009 to Pit 1010
40dda952-483b-4582-b510-9ef78fe634fa | Child Lot Verification(a321b568-c542-4ef2-b3e8-2c011489bdf0): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 29424f1dbb96c576c326cb48ee5154397f0f98a0a30d93811853f0b6bbdaef74 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-018 - Stormwater Drainage - Head wall 1000 to Pit 1001
c5590ed6-d5a0-45b5-ae1c-e6f5dd004343 | Child Lot Verification(131b9980-90d9-4d9b-90ef-5fd3b1ed8fc7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 113466792846d670483824cb1b4393c0367065ffbdc5d8642ceb0e34d4d63079 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-019 - Stormwater Drainage - Pit 226 to Pit 227
22b555ec-f75d-44f8-bdd4-09c777850010 | Child Lot Verification(258279b6-4a76-42ae-83d9-3201c3990861): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 6973298eb560f4ff9373532c96dd7d864a5eb71747eb986e261c68cecf29a6cd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-020 - Stormwater Drainage - Pit 227 to Pit 228
f357e360-c253-46a7-ab94-50d877b221b8 | Child Lot Verification(67c6a5c5-0a75-4bdf-974d-c03930e3bcc7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 6973298eb560f4ff9373532c96dd7d864a5eb71747eb986e261c68cecf29a6cd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-021 - Stormwater Drainage - Pit 228 to Pit 230
4c26ba9b-3480-47e3-82bd-0744e50579ec | Child Lot Verification(352cf3d9-73e4-45fe-bb00-548215352f00): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 6973298eb560f4ff9373532c96dd7d864a5eb71747eb986e261c68cecf29a6cd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-022 - Stormwater Drainage - Pit 230 to Pit 231
43fe2333-f62e-4c12-a631-3b92d27a42bf | Child Lot Verification(46473ddb-ae7c-4d3b-b0b3-9dc33842beec): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 6973298eb560f4ff9373532c96dd7d864a5eb71747eb986e261c68cecf29a6cd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-023 - Stormwater Drainage - Pit 231 to Pit 232
b7b79c12-5cf1-44b9-aa52-d8dfdbe1189a | Child Lot Verification(ec499785-bbef-4f90-980d-2c6af072eaba): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | 6973298eb560f4ff9373532c96dd7d864a5eb71747eb986e261c68cecf29a6cd | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-024 - Stormwater Drainage - Pit 232 to Pit 233
5c9a0d09-2413-4dbc-85ac-65f765388144 | Child Lot Verification(b5cca31a-9814-4e9b-b343-2538dd9fe2ab): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-025 - Stormwater Drainage - Pit 233 to Pit 234
bfdd43ad-26bd-49aa-87fd-4d5b34ea24d6 |  | checklist-sectioned | work-in-progress | 8b7f4b8402b9a02aa43c416c6da1989036aaa09b19e10d881d7e0972865d828b | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-026 - RCBC - Hume South Median - Pit 1011 to Pit 1012
f4701a11-813c-4851-bfcd-afd2effaf92f |  | checklist-sectioned | pass | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-027 - Stormwater Drainage - Pit 090 to Pit 167 - BTW Bridgewater Rd to Clovelly Dr
2a78d068-6897-41c1-b29b-3e683d217eba |  | checklist-sectioned | pass | ed4ed9b63c48a7fff281821b61d97094167c1ed2de475ea5b5385c807f73a69f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-028 - Stormwater Drainage - Pit 167 to Pit 091 - BTW Bridgewater Rd to Clovelly Dr
24d0157b-5737-41cd-8de9-4bfcd6cdb41c |  | checklist-sectioned | pass | ed4ed9b63c48a7fff281821b61d97094167c1ed2de475ea5b5385c807f73a69f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-029 - Stormwater Drainage - Pit 091 to Pit 092 - BTW Bridgewater Rd to Clovelly Dr
0641e706-b116-45e4-9da2-00d52c0a44a3 |  | checklist-sectioned | work-in-progress | a5f8f56991ea5e3e923b308761a0e60d36fadac7342eccb12da3df00e17cde95 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-030 - Stormwater Drainage - Pit 092 to Pit 192 - BTW Bridgewater Rd to Clovelly Dr
19662a28-2542-4904-8a76-0de2b1babe25 |  | checklist-sectioned | work-in-progress | ed4ed9b63c48a7fff281821b61d97094167c1ed2de475ea5b5385c807f73a69f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-031 - Stormwater Drainage - Pit 192 to Pit 192-1 - BTW Bridgewater Rd to Clovelly Dr
54f589c0-3f8e-4662-9d36-bed5536673d4 |  | checklist-sectioned | fail | ed4ed9b63c48a7fff281821b61d97094167c1ed2de475ea5b5385c807f73a69f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-032 - Stormwater Drainage - Pit 305 to Pit 305a - BTW Bridgewater Rd to Clovelly Dr
1e16a688-4e62-48f4-aaec-19255990d49e |  | checklist-sectioned | pass | ed4ed9b63c48a7fff281821b61d97094167c1ed2de475ea5b5385c807f73a69f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-033 - Stormwater Drainage - Pit 305a to Pit 304 - BTW Bridgewater Rd to Clovelly Dr
c7f0dfa0-4c61-467c-ae41-35a661ad3199 |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-034 - RCP (525mm) Drainage - Pit 063 to Pit 063 -1 - Hardy West St
a6da25a3-d809-462d-93ab-ef0ba92e6f1c |  | checklist-sectioned | pass | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-035 - Stormwater Drainage - Pit 090 to Pit 346 - BTW Bridgewater Rd to Clovelly Dr
cecde716-7bef-4cff-aeb7-9e84fc3b32e2 |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-036 - RCP (450mm) Drainage - Pit 199 to Pit 331 - Hardy East St
eccc1cf4-a228-4c93-9180-10733a1e512b |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-037 - RCP (900mm) Drainage - Pit 094 to Pit 017-1 to Pit 017 - BTW Selwyn Ave and Bridgewater Rd
e39b0c09-05e9-4ef5-a1d9-739284f68f5e |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-038 - RCP (375mm) Drainage - Pit 118 to Pit 328 - Bridgewater Rd
1749a2db-ea58-4c1e-ad91-8cebcd2da829 |  | checklist-sectioned | pass | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-039 - RCP (900mm) Drainage - Pit 302 to Pit 259-1 to Pit 259 - Rayfield AVE
43975ca9-7e61-4e7a-9357-f10c2f28415a |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-040 - RCP (300mm) Drainage - Pit 328 to Pit 133 - Bridgewater Rd
0aa74c76-c29d-4a91-aedf-1fe096340785 |  | checklist-sectioned | work-in-progress | 7d0161420adf6f3a06070eb8d907d908af8a6ea45ed3baba6e70698f3fbd00e5 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-041 - RCP (300mm) Drainage - Pit 133 to Pit 337 - Bridgewater Rd
a2d68da9-0df9-4039-8bc1-23fec9dd09bf |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-042 - RCP (900mm) Drainage - Pit 259 - Pit 259-1 - Rayfield AVE
99849fc2-5649-49b8-bf6e-26ef53a7e27c |  | checklist-sectioned | pass | 7d0161420adf6f3a06070eb8d907d908af8a6ea45ed3baba6e70698f3fbd00e5 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-043 - Stormwater Drainage - Pit 346 to Pit 114 - BTW Bridgewater Rd to Clovelly Dr
6f3973d8-c17a-4b4d-a593-5060b4af1b24 |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-044 - RCP (375mm) Drainage - Pit 142 to Pit 299 - Plumpton Ave
ee26c1c4-5c93-4145-be7a-6d03836e930b |  | checklist-sectioned | pass | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-045 - RCP (450mm) Drainage - Pit 255 to Pit 088 - Bridgewater Rd
be413268-3984-4eab-b763-d361e73bf806 |  | checklist-sectioned | pass | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-046 - RCP (375mm) Drainage - Pit 113 to Pit 255 - Bridgewater Rd
0bc21a6f-6263-4e10-8f01-3aa4d8cc65bb |  | checklist-sectioned | pass | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-047 - RCP (300mm) Drainage - Pit 117 to Pit 337 - Bridgewater Rd
25304276-bdda-4ca1-a16c-a9828a6f3d90 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-048 - RCP (1200mm) Drainage - Pit 250 to Pit 270 - Z4 Craigieburn Rd-EB-Occu.
f838d5d2-29ee-4885-bac1-c6d31fca8c32 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-049 - RCP (1200mm) Drainage - Pit 270 to Pit 274 - Z4 Craigieburn Rd-EB-Occu.
f8fdfcae-aa68-4e7a-98b5-01ad005ab339 |  | checklist-sectioned | pass | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-050 - RCP (1200mm) Drainage - Pit 274 to Pit 266 - Z4 Craigieburn Rd-EB-Occu.
37899f86-5be8-40ea-833e-31f83f0fca39 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-051 - RCP (1200mm) Drainage - Pit 266 to Pit 261 - Z4 Craigieburn Rd-EB-Occu.
deb9d316-168b-432e-b88d-f09a3dd29c49 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-052 - SP (375mm) Drainage - Pit 001 - Pit 166 - Memorial Park - WB
a12685c4-ffb7-4f20-acd6-d6c2788e429d |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-053 - RCP (300mm) Drainage - Pit 166 - Pit 271 - Memorial Park - WB
f617e42a-1331-441d-8bed-16d77b74b021 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-054 - SP (375mm) Drainage - Pit 166 - Pit 166-1 - Memorial Park - WB
30344ce8-6e66-4a55-badc-f4e4dc23c38b |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-055 - SP (375mm) Drainage - Pit 166-1 - Pit 166-2 - Memorial Park - WB
32e1e3eb-431d-4bfe-a417-2efa5d8482fd |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-056 - SP (375mm) Drainage - Pit 166-2 - Pit 166-3 - Memorial Park - WB
1ec9e6c2-d441-4ee6-90be-4236f4532f76 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-057 - SP (375mm) Drainage - Pit 166-3 - Pit 070 - Memorial Park - WB
a8b161a1-fc91-4a5c-990c-ccbe673a4adf |  | checklist-sectioned | pass | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-058 - SP (375MM) DRAINAGE -pit 113 to pit 114
2e4b18fe-0f48-41f1-984b-0b6610d410c7 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-059 - RCP (375MM) DRAINAGE - pit 113 to pit 297
fa0acc71-91a1-441e-905d-77e8f2932383 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-060 - RCP (300MM) DRAINAGE - Pit 053 to Pit 053-1
7977025e-65ae-424b-9b6f-c077f342b928 |  | checklist-sectioned | pass | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-061 - RCP (300mm) DRAINAGE - Pit 113 to Pit 120
fde1e6de-ccfe-481f-8383-a2fb2d76a000 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-062 - RCP (375mm) DRAINAGE - Pit 037 to Pit 326
b2be0290-21ef-4c95-b84a-9ae3e5d3eca1 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-063 - RCP (375mm) DRAINAGE - Pit 037 to Pit 037a
78d8e4b3-afec-40be-8e03-fe21481eec56 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-064 - RCP (750mm) - P359 - P001 - Memorial Park WB
c9b19b42-5a18-4ee9-9ea5-77d24c0ed56c |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-065 - RCP (600mm) - P064 - P384-3 - Hanson Rd Intersection CM
e4f45acd-1c04-466e-aa17-c42238783bc0 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-066 - (300mm) RCP Cl3 - Drainage line P342 to P120-1 - Z3
87b4665b-ff85-4531-a62a-ef5e18c35a72 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-067 - Stormwater Drainage - Pit 090 to Pit 135 - BTW Bridgewater Rd to Clovelly Dr
1e38111e-1578-4297-bd37-9be0db37e973 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-068 - SP (750mm) Drainage - Pit 001 - Pit 007 - Memorial Park - Bullnose
742482a6-b511-4879-9f8c-0ca269d17e64 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-069 - SP (375mm) Drainage - Pit 007 - Pit 008 - Memorial Park _ Center Median
f631ebca-6e84-4211-9fbe-487c453c1403 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-070 - SP (750mm) Drainage - Pit 007- Pit 182 - Memorial Park _ Center Median
e81f07c0-bd1f-4af8-8c80-0ca38df4e1db |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-071 - SP (375mm) Drainage - Pit 182 -1 - Pit 004 - Memorial Park _ Center Median
41797699-b9a3-447c-99f7-4083c3731aca |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-072 - SP (375mm) Drainage - Pit 004 - Pit 006 - Memorial Park _ Center Median
a0de8e95-e293-46f1-927e-290014250e1c |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-073 - SP (375mm) Drainage - Pit 006 - Pit 006-1 - Memorial Park _ Center Median
2d7b3afa-e12c-48e6-9100-fe92e4a14c9f |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-074- SP (375mm) Drainage - Pit 006-1 - Pit 349 - Memorial Park _ Center Median
390cc3bb-6150-488a-8f2c-36796295030d |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-075 - SP (375mm) Drainage - Pit 349- Pit 009 - Memorial Park _ Center Median
aa3665fc-28a1-417f-b4cb-99abc4f55976 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-076 - Stormwater Drainage - Pit 088 to Pit 194 - BTW Bridgewater Rd to Belsay Pl
6cf0a7fe-66b7-4c79-9e56-49ee6bc9bd60 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-077 - 450mm Stormwater Drainage - Pit 194 to Pit 086 - BTW Bridgewater Rd to Belsay Pl
ffe56b62-dcc6-4b29-9161-2775defd95d0 |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-078 - 900mm RCP pipe - Pit 086 to Pit 052 - BTW Bridgewater Rd to Belsay Pl
2302d6f0-f189-4e90-9b8b-b3f8f394d2fd |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-079 - 900mm RCP pipe - Pit 052 to Pit 084 - BTW Bridgewater Rd to Belsay Pl
0f61fee2-0bc1-480f-a588-927e0c18f88c |  | checklist-sectioned | work-in-progress | b32adc139c942d678d49d964d50951bcc5e0c7690ceefc962b5959e89767053e | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-080 - 900mm RCP pipe - Pit 084 to Pit 017 - BTW Bridgewater Rd to Belsay Pl
900a5f27-e5e9-48c9-bda6-161d32c497ae |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-081 - 525 RCP - P035 - P384 - Hanston St x Craigieburn Rd Xing
23ac74d8-fcce-4b17-8b92-d4dced663ccb |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-082 - 375RCP - P261 - P261-1 - 005 - Walter St Xing (Walter St Occo)
42e2cd70-e4a1-466b-96f0-48d090d520fc |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-083 - 450RCP - P199 - P282 - Walter St Xing (Walter St Occo)
8998b466-4a9b-4032-b6d7-7bf3fa1af44b |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-084 - SP (375mm) Drainage - Pit 009- Pit 009 -1 - Memorial Park _ Center Median
256cde56-63c8-49c0-b3ff-3fea9ed74aa5 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-085 -SP (525mm) Drainage - Pit 257- Pit 389 - Memorial Park North
3cac5a62-344b-45ec-a35f-1a708e6079d1 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-086 -RCP (525mm) Drainage - Pit 389- Pit 249 - Memorial Park North
78e15b77-d6dd-49cd-8c2b-8c66d21bcbbd |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-087- SP (375mm) Drainage - Pit 249- Pit 018 - Memorial Park North
a241cff7-b963-4b13-86e5-c75dbfa8bc40 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-088- RCBC(450x300) - HW 256- Pit 188 - Memorial Park North
00462b33-8ffd-4f1b-ba7d-da0ec0f6e97b |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-089- SP (1050mm) Drainage - Pit 54 - Pit 321 - HARDY St
f6f61cee-88ac-4edc-bb48-4a7f9855ec56 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-090 - SP (450mm) Drainage - Pit 54 - Pit 331 - HARDY St
43a6681f-fbe8-47a4-a16a-480797a8f430 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-091- SP (375mm) Drainage - Pit 321- Pit 321- 3 - HARDY St
9dcdb30e-e86e-4aec-a1e6-29b165b8fd2e |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-092 - SP (375mm) Drainage - Pit 331- Pit 331 -1- HARDY St
8fe809bf-cba3-4fff-b38e-beb4b7eb3cc7 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-093- SP (375mm) Drainage - Pit 321- Pit 321- 1 - HARDY St
610cbc34-1d38-4c83-ae43-3bf0eb96e51d |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-094- SP (900mm) Drainage - Pit 182- Pit 386 - Memorial Park
457cada5-415d-40e8-bce0-c210c4ff5221 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-095 SP (375mm) Drainage - Pit 386 - Pit 366-1- Memorial Park
976947ba-d1e5-4bad-a8d6-287d13e3fb9f |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-096 RCP (600mm) Drainage - Pit 151 - Pit 150-1
edc4da15-fcd3-48ca-9b14-7469da63b218 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-097- RCP (750mm) Drainage - Pit 54 - Pit 063 - HARDY St
bc277ae6-a2dd-4659-b270-201d55c6a312 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-098- RCP (525mm) Drainage - Pit 063-1 - Pit 030 - Pit 030-1 - HARDY St
a1564ce0-a762-4997-a34b-d66a329e2bed |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-099- SP (375mm) Drainage - Pit 11-1 - Pit 023 - Plaza
e82ac084-3601-4380-af17-e548793756d5 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-100- SP (375mm) Drainage - Pit 023 - Pit 024 - Plaza
2a37692f-a9f9-4ca0-9757-8f0225ba1c5a |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-101- SP (375mm) Drainage - Pit 024 - Pit 032 - Plaza
4d4517a3-b90b-431c-8dee-f1e6bc4dad23 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-102- 1050RCP - Drainage - P321 - P11-2
dce63f7e-93b1-4a56-aaf8-81be3f95cfa9 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-103- 750RCP - Drainage - P011-1 - P011 - Intersection North
52676416-e664-49c2-bb03-2107d1307a06 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-104- 375RCP - Drainage - P011 - P010 - Intersection North
6f33bc13-766c-4d0d-bfbe-22dc99ea5c40 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-105- 900RCP - Drainage - P011 - P011-2
e8d79cfb-e8fa-41fa-9509-d89d23d07fd4 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-106- 900RCP - Drainage - P002 - P275 - Intersection North
aebf3677-13c3-4bd2-b2e4-38ac73680d33 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-107- 900RCP - Drainage - P275 - P386
3b03d673-c2d0-4159-b36d-8c138a91c7a9 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-108- 375RCP - Drainage - P321-2 - P321-1
4622ba09-ccd5-4990-9c9f-2c29a8546ef3 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-109- 375mm StormPro - Drainage - P329 - P025
e99535a9-707f-43c5-b333-0846ac581c78 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-110- 375RCP - Drainage - P025 - P032
4f5c524e-339c-42d2-8396-b4108ad85161 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-111- 375RCP - Drainage - P043 - P366
353f5aa6-38c9-4542-bf6e-d4f97ba6a270 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-112- 375 StormPro - Drainage - P366 - P042
3ceeebd7-31bc-43f5-aee3-f9d04b3862be |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-113- 375RCP - Drainage - P042 - P040
c4f60762-bfea-4b3e-a261-501e3c38ed39 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-114- 375 StormPro - Drainage - P040 - P364
b334de38-7e42-4936-bdc0-a2417527d3f1 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-115- 375 StormPro - Drainage - P364 - P039
d700bdeb-e688-42dd-8aa5-e55b3e7b0a72 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-116- 450 StormPro - Drainage - P039 - P385
ecbba20b-eab4-47ee-8b84-8c05702a7d77 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-117- 600RCP - Drainage - P054 - P054-1
77aacdad-ef49-4da1-84fe-99ab02f5972f |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-118- 600RCP - Drainage - P054-1 - P054-2
e568e149-8f67-4707-90d7-40b4bc92e78a |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-119- 600RCP - Drainage - P054-2 - P054-3
8b630e54-26a1-47be-a164-296dc772abf2 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-120- 375RCP - Drainage - P041 - P046
578f5017-b9c2-4faf-806b-d474ba4eb33b |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-121- 375mm stormpro Pit 009-1- Pit 009-2
7f1f99bd-d2fb-4f98-a8d1-d90bd2429fe7 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-122- 375mm stormpro Pit 009-2- Pit 009-3
29f85db8-a844-42c9-92fd-fc4719dc556f |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-123- 375RCP - Drainage - P321-1 - P321-2
48cb2caa-b87c-4515-8ad0-31f1f42c1d70 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-124- 375 StormPro - Drainage - P192-1 - P192-2 - Zone 3.1
0ea91054-ffce-4919-99c5-31a9e2c09da8 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-125- 375 StormPro - Drainage - P192-2 - P093 - Zone 3.1
136836b0-6b75-4330-be92-903256a4dc20 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-126- 375mm stormpro Pit 009-3- Pit 009-4
363af4a7-a45d-4fd1-b536-0b5fd143012a |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-127- 375mm stormpro Pit 009-4- Pit 012
8502146d-81b6-4630-8370-3219e8e279d7 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-128- 375mm RCP Pit 012- Pit 012-1
c5586abe-a893-42de-a864-3cbb99cd1607 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-129- 375mm Stormpro Pit 012-1 - Pit 357
a37a3d62-fb44-4107-a0cb-8dce73a2ce80 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-130- 525mm stormpro Pit 257- Pit 391
29e4a6fe-f253-41fd-8dfd-87789e1e5ec3 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-131- 450mm RCP Pit 391 - Pit 263
851b1949-6607-47e5-bc3b-1c1eb55aa141 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-132- 450mm RCP Pit 263- Pit 016
f929a550-ab60-4c7f-b990-bb56b63c450b |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-133- 375mm Stormpro Pit 237 to Pit 031
ba6f1684-9b10-4e7f-8eab-34b19f28a8a7 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-134- RCP 1200mm - Pit 190 to Pit 260
98297946-010c-4530-a5e7-a26541d4e532 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-135 - RCP375 - Pit 237 to Pit 237-1
583e946f-3c2c-4bf8-9793-00200292f38a |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-136 - RCP375 - Pit 043 to Pit 366
78cc9640-ee8e-47e2-b968-aabe012110da |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-137 - RCP1200 - Pit 260 to Pit 261
561e9bf4-0940-434a-8b45-2cb725a32a3e |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-138 - RCP1200 - Pit 261 to Pit 266
41054239-2421-4982-b087-e023c62ad985 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-139 - RCP1200 - Pit 190 to Pit 187
126a3f74-4c82-4501-9ef9-ea5f5369f340 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-140 - RCP525 - Pit 215 to Pit 214
c6bd35c2-febb-47d3-b7cd-671a60eb9dea |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-141 - RCP525 - Pit 187 to Pit 207
862d32fd-9d3c-4fd0-af5b-59880f8389ab |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-142 - RCP375 - Pit 043 to Pit366
55e813d4-1431-439f-a68b-89c8d7d2dce0 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-143 - Storm Pro 375 - Pit 366 to Pit 042
ed0252d9-3bc2-4e5e-b735-ad5d84886e81 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-144 - RCP375 - Pit 042 to Pit 372
56b73e7d-0d90-4c06-adf5-4e46ee80f244 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-145 - RCP525 - Pit 207 to Pit 106
7f530a84-5daa-4e2d-a647-9715f7e839ab |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-146 - RCP450 - Pit 215 to Pit 216
8f2be43e-188e-45a6-a194-fbd536773701 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-147 - RCP375 - Pit 234 to Pit 235
2e5d1d87-1e18-4a70-a59b-09d9c1e3289d |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-148 - RCP525 - Pit 106 to Pit 211
e6c8110f-bfd7-4452-883e-cb36fce8a932 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-149 - RCP525 - Pit 211 to Pit 212
fbaa7bd9-5852-4ddd-b8cd-e0216ccab0a3 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-150 - RCP375 - Pit 235 to Pit 154
33520c87-77fa-41fc-bbec-6658622b2b5f |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-151 - RCP375 - Pit 154 to Pit 236
de75dcae-44b2-4a88-924f-ea6bf3ef6f4c |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-152 - Stormpro 525 - Pit 212 to Pit 214
cb87c970-721c-4b6f-a3ae-903b99e20a82 |  | checklist-sectioned | pass | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-153 - RCP450 - Pit 216 to Pit 217
ae955ace-a29b-4412-94d8-7c795bff5315 |  | checklist-sectioned | pass | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-154 - RCP450 - Pit 217 to Pit 218
ef1c2d09-45e6-4be7-a658-97a16552b0cb |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-155 - RCP450 - Pit 218 to Pit 219
9dd9acec-31a1-4b70-aa5e-e5e4ee60ec9f |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-156 - Stormpro450 - Pit 238 to Pit 239
aacc03f7-7d5c-4321-9a2b-4cd177380132 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-157 - Pit 040 to Pit 039
5978c4c9-850a-48a6-b94f-5c66172088f0 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP 0017 - Underground Stormwater Drainage
f59663f5-d80f-4d9a-8e93-137956095119 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-158 - RCP450 - Pit 239 to Pit 240
2a9d6820-a86b-4bd2-a2d3-d3bd50440f2d |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-159 - RCP375 - Pit 196 to Pit 197
3ff4c444-7539-4f67-9332-c16949fbb859 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-160 - StormPro 375 - Pit 197 to Pit 198
7a4e8713-946a-480b-9ef4-cc81e30b7bc1 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-161 - StormPro 375 - Pit 198 to Pit 200
50fbe818-5958-4212-b89f-207f976d0706 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-162- Craigieburn Rd - Pit 364 to Pit 039
21f60c14-db69-40d4-80d7-66473944d30e |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-163- Craigieburn Rd - Pit 384 to Pit 384-1 - Hanson Intersection - CM
d708f594-cea0-4c22-a3c8-21446a56b5b8 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-164 - RCP 900 - Pit 187 to Pit 399,264,204
6988996e-4e31-4219-8576-d341a2b0598a |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-165 - RCP450 - Pit 240 to Pit 241
c01fee0d-4b69-4dad-8f45-f29434008fe4 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-166 - Stormpro 375 - Pit 241 to Pit 085
390b46ab-0f75-4343-af7d-561833992e53 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-167 - RCP 375 - Pit 205 to Pit 247
7b44ab59-8559-449d-ab31-44cdc7d5a134 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-168 - Stormpro 375 - Pit 085 to Pit 242
94f6da1f-4a22-4618-8837-a6e177330b2a |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-169 - RCP 375 - Pit 173 to Pit 175
81bcaefe-2425-4aa0-aa9c-c0af3eba7174 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-170 - RCP 375 - Pit 176 to Pit 175
aab9466c-3ce6-4d32-9606-dcb305e18a53 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-171 - RCP 375 - Pit 176 to Pit 195
c26138e4-6813-4bef-90d1-3a63ee851421 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-172 - P384-2 - P384-3 - 900 RCP - Shell CM
fda67774-1b04-498f-ba72-624bb9dd99f4 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-173 - RCP450 - Pit 219 to Pit 220
29872098-1821-40a8-8669-6ee8dded5fac |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-174 - StormPro 600 - Pit 204 to Pit 203
19b1d4a3-42e2-46dd-86fe-4d45a06466cc |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-175 - RCP 600 - Pit 203 to Pit 286
619f1f01-97c2-40ef-9919-23e257ec8833 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-176 - StormPro 450 - Pit 220 to Pit 221
bfa84ae9-9982-45f7-a3a7-7983c90e29be |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-177 - RCBC 450x300 - Pit 307 to Pit 280
38a3c93a-e574-4c21-b2b6-51ce25076268 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-178 - RCP 375 - Pit 280 to Pit 173
a35d04b3-c19b-4f14-93c3-0ed1e257202b |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-179 - StormPro 450 - Pit 221 to Pit 222
b31f648f-1ae5-4b08-8b95-5ef25ca54251 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-180 - RCP375 - Pit 195 to Pit 196
dbb91f31-a314-4acd-94a2-41a2eac8323b |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-181 - RCP375 - Pit 173 to Pit 279
344b381c-0f7c-46f1-af6a-d45d31c5642a |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-182 - RCP375 - Pit 287 to 172
8a24a4e3-3edf-4227-ace9-571f8ec3862e |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-183 - RCP375 - Pit 172 to 301
4e8e8787-b8fc-4877-b265-3523f124cf93 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-184 - RCP375 - Pit 381 to 380
b185e0c8-6165-4531-978c-26fbb0db1c16 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-185 - StormPro 375 - Pit 380 to 303
9e213b99-b9e0-4dbc-b33f-70a854579d07 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-186 - StormPro 375 - Pit 304 to 303
d1914fb3-b098-4d73-9dff-13a9ac5134d8 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-187 - RCP 450 - Pit 222 to Pit 223
c0e88835-1f58-4dc0-99de-3c4c52eaeb3d |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-188 - RCP 450 - Pit 223 to Pit 398
173f440d-0035-497f-9435-31911d8111ff |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A1-LOT-189 - RCP 450 - Pit 398 to Pit 224
76e5444d-84cc-4a75-8685-d7ea76cc90c3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation
99174aa2-1c01-46d8-bf87-ecd17943ea16 |  | checklist-sectioned | pass | c70a993d562759889bd11e16bd05f35ef401a60f4a761608c00518d2cbeeb8bb | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-002 - Hume Hwy North Island (Nth/Sth Bound)
7cf0a8d6-953a-41b5-b3ad-90300e1da9c1 |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-001 - Hume Hwy South Island (Sth Bound)
853db03c-12b1-43ca-b1f9-972e3312b4c4 |  | checklist-sectioned | pass | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-003 - Hume Hwy South Island (Nth Bound)
e2874bc9-838d-4cbb-b5bf-fb17a4e4c336 |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-004 - Memorial Park Median Guardrails
fb9289f3-d473-46dd-b2a0-012334092646 |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-005 - Ramshield installation - Z3.1- West of Brigewater and South of the Bus stop
a9985d56-f08f-492a-9b5c-eee5df46aa3c |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-006 - Memorial EB/WB Both Sides - CH26146 - CH26344
b63e6815-2e90-45da-bd9f-169b79a22eb3 |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-026 - Guardrail Installation | ITP-026-A1-LOT-007 - Hume Hwy NB - CH70088 - CH70250
905c09b3-51ec-41ca-867a-4740dee5b371 |  | folder-normal | pass |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-049 - Topsoil Placement and Landscaping
49023852-647b-491b-812a-2ed466295eac |  | checklist-sectioned | pass | e040ab70a3bb56b0457209394fde7c5c84581a7f4890b4c4f1b05d842f306689 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A1-LOT-001 - Hume Hwy North
bc54faa6-c98f-4ee0-9c05-eccef05f04dc |  | checklist-sectioned | pass | e040ab70a3bb56b0457209394fde7c5c84581a7f4890b4c4f1b05d842f306689 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A1-LOT-002 - Hume Hwy South
ea2fda00-592a-406f-927e-88c0e4374df0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways
07b9998e-2f56-4424-933a-a28e22933bc8 |  | checklist-sectioned | pass | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-001 - Hume Hwy North Bullnose
7ed09116-6f94-414d-ad83-c66d153f5790 |  | checklist-sectioned | pass | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-002 - Hume Hwy North (Sth Bound) Maintenance Strip
dd4be924-39e4-4eb4-92e4-1f4f1f24407d |  | checklist-sectioned | pass | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-003 - Hume Hwy South (Nth Bound) - Maintenance Strip CH70265 - 70220
cc98d7bc-b43d-4c4b-9a21-cbbf6f3001ce |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-004 - Hume Hwy South (Nth Bound) - Maintenance Strip CH70220 - 70110
e80f413f-f486-41e9-870d-3bc18a984ff6 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-005 Hume Hwy North (Sth Bound) - Maintenance Strip CH70506 - 70485
d13c7415-69e0-4b4a-8401-011e8b5c8cbe |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-006 Hume Hwy North (Nth Bound) - Maintenance Strip CH70334 - 70360
b0177f1e-ea90-45aa-8551-4b42302f2188 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-007 - Hume Hwy North (Nth Bound) - Maintenance Strip CH70360 - 70435
8c914d47-afb9-4ad4-8f4d-bfeaf82cbae6 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-008 - Hume Hwy South (Sth Bound) - Maintenance Strip CH70267 - CH70100
721f39f3-c42a-4b99-b0ec-3ddc9bd73ac4 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-009 - Bridgewater Rd to Clovelly Dr - WB - SUP CH14900 to CH15000
cc6abb6f-4db6-424e-969c-c96f47be9b91 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-010 - Bridgewater Rd South East Corner - CH25100 - CH25120 - SUP
d501faed-2169-400b-b7af-c6c32425c767 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-011 - Bridgewater Rd NB Bullnose - CH25090 - CH25100
73904f36-0d98-4cca-bcee-6f636123285b |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-012 - Memorial South Bullnose Infill
04e3e22d-eac8-4455-be33-e37f8636a20b |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-013 - SUP - Plaza Corner - CRG Rd EB - CH25960 - CH26123
eac4604c-2317-4e15-aaa8-07845ab29b59 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-014 - Craigieburn Rd Eastbound SUP - CH16040 to CH16130
b089bc98-68ad-401e-8ea7-576a2eeba76f |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-015 - Walters Intersection North Eastern Island
6513fad8-d6f9-4ea1-8d61-65b122b5e8c1 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-016 - Zone 2 - Shell Driveway Western Driveway
3700ad33-7e94-4453-9b08-991213935a4a |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-017 - Zone 2 - Shell Driveway Eastern Driveway
61e8d29f-158e-4ed5-b3b9-c2e78837c93c |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-018 - Zone 1 - Memorial Park - WB / EB - Maintenance Strip
5e2f8160-71ad-4985-9596-b1ed9f1056d4 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-019 - Zone 1 - Memorial Park - WB - Southern Island Infill
a3c05b3a-157a-491f-ab21-64d621fba4cd |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-020 - Zone 1 - Intersection Southern Island Infill - Hardy Slip Lane - CH16121 - CH16137
e9f862f7-122f-4123-be31-38d6947da3c3 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-021 - Zone 3.1- Bus bay CH14990 to 15040
57b66247-3e41-4b98-918c-0633fd79cee4 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-022- Plaza West of Ampol Driveway - CH26993 - CH26000
502d9f97-258b-4e81-a5b0-5dd3e5d5e7d1 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-023- Plaza East of Ampol Driveway - CH26008 - CH26016
4a190eac-f642-461f-9bea-a55f9915fc60 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-024 - Hume Slip Lane x CRG Rd WB Bullnose
6e842451-97c6-42bc-9693-93bf289b811e |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-025 - Vet to Benston Crossover - CRG Rd WB
f1bdb63f-e137-4e15-af14-9d65b934f375 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-026 - Chinnock Ct Driveway
c2a9b8d6-dba1-4dd7-9040-4c5ce281f080 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-027 - Craigieburn Hume Intersection Southern Islan - CH70280
53b102de-4adf-43f1-9454-6be1d046ed10 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-028 - Maintenance Strip Ground Beam from Pit 304 to Pit 305
2922f859-53f3-4a66-9c37-ad03481f4d63 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A1-LOT-029 - SUP - Craigieburn Rd Westbound - Zone 3 CH14760 to CH15080
18b80b1e-9618-4c17-a556-1ef0ff4ace2d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-065 - Wire Rope Safety Barrier (WRSB)
c5bcc917-b792-4e31-bdf4-ec9bffa27f0c |  | checklist-sectioned | work-in-progress | 5c9779f7e9594d08b24c7fcb5e01fd6a443799219c62ca3cb5b9f1c40f616a62 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-065 - Wire Rope Safety Barrier (WRSB) | ITP-065-A1-LOT-001 - WRSB Anchor Block Pour - Hume Hwy North median - Northbound and Southbound
a5fa2b26-3269-4531-9dc2-4bfff5b3683b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-074 - Installation of Fencing
0144a2ba-888f-4be2-b8ef-e79e3b34e87f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement
80ae39d3-e578-48e6-a91a-769232d3c6ca |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-001 - Hume Hwy North (Sth Bound) - Base Course
0669a6fe-7755-4800-88f1-c8152ab01db1 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-002 - Hume Hwy North (Nth bound) - Base Course
48771162-ea38-46c1-b667-bb1bf8284162 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-003 - Hume Hwy North (Nth Bound) - Intermediate Course
3f19de63-d2d4-47e9-8aad-fe974e2f0408 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-004 - Hume Hwy South - Base Course
7800cdfd-7a06-41bc-9a87-885342c53a0a |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-005 - Hume Hwy South - Intermediate Course
22e4e574-505e-41dd-b701-0a005521b271 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-006 - Hume Hwy North (Sth Bound) - Intermediate Course
01f931b1-9d9f-40f0-b40f-b7c0a50cf70b |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-007 - Hume Hwy North (Sth Bound) - Base Course CH70462 - CH70430
21c7a63b-76a3-4b7d-9825-f2c4cdcdfd04 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-008 - Hume Hwy North (Sth Bound) - Intermediate Course CH70462 - CH70430
edd03dfa-6221-4162-99ae-61decee6ee83 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-009 - Bridgewater Road PT3 - Base - CH25080 - CH25120
746ff3fc-f288-43f6-938b-03fa1282ee97 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-010 - Bridgewater Road PT3 - Intermediate - CH25080 - CH25120
1bfc5032-85a3-409a-9dd0-7ba999768caf |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-011 - Bridgewater Road PT6 - Base - CH25090 CH25100
e745fab7-6c8b-4418-b31d-ae7ebb45b118 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-012 - Bridgewater Road PT6 - Intermediate - CH25090 - CH25100
f8428d73-6ae6-42a1-985f-748b93e6812d |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-013 - Bridgewater Road PT10 - Patching 1 - CH25080 - CH25105
5b312a20-2c93-4de5-87bb-45f64a6f6eb5 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-014 - Bridgewater Road PT10 - Patching 2- CH25080 - CH25105
61071324-87c0-41c4-9e84-3cf2f51e187f |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-015 - Craigieburn Rd Eastbound - CH16010 to CH16300 - Layer 1
c9922c07-e3da-45c6-aae7-aafa6e66cc7a |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-016 - Craigieburn Rd Westbound CH16080 to CH16260 - Layer 1
91f1b3fc-61b2-427a-9fd3-31dfcc2c6838 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-017 - Craigieburn Rd WB - CH26160 to CH26360 Including Hume Slip Lane
7561895e-6d21-4199-af0e-0095a9a42213 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-018 - Craigieburn Rd EB CH16290 to CH16360 (Layer 1)
30adfae1-25c2-4449-922c-e73884a6c2e2 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-019 - Craigieburn Rd EB CH16290 to CH16360 (Layer 2)
3b2aeb77-be6b-4246-aa69-05ac44547f78 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-020 - Hume Slip Lane CH70070 to CH70200 - Base Course
fe42c1f0-c5c5-415b-89d8-d8c5ed1e6828 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-021 - Craigieburn Rd Eastbound CH25910 to CH26020 - Base Course - Type 11
ab42f3d3-0f02-4c30-97bf-8ad61f1a2b59 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-022 - Craigieburn Rd Westbound CH16020 to CH16150 - Base Course
e3feafd7-e66c-49be-8a7f-b176fde8ce0a |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-023 - Craigieburn Rd Eastbound CH25910 to CH26020 - Intermediate Course - Type 11
e985f0e4-a632-44a7-8b71-f0ffb8280a73 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-024 - Craigieburn Rd Westbound CH16020 to CH16150 - Intermediate Course
0b733608-3c6d-4db4-80ed-02a798bc0f55 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-025 - Zone 3.1 Westbound CH14780 to CH15030 - SF layer
d3d2ffc2-cb24-4c67-bdb3-9524f13bd88a |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-026 - Zone 3.1 Westbound CH14780 to CH15030 - SS layer
9dfed113-acce-4194-9940-1cab4bbc69cc |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-027 - Zone 3.1 Westbound CH15040 to CH15070 - SF layer
cf0d3f90-4ee6-44a5-a2bd-fde629c8de87 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-028 - Zone 3.1 Westbound CH15040 to CH15070 - SS layer
de71fd36-e0e3-41dd-9e9c-ae9f6c26e227 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-029 - WC - Hume HWY STH BND 2 right turning lane & middle through lane
bd0d7041-24ef-4777-9b29-6e9df953ae16 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-030 - WC - Hume Sth Bnd to CRG Intersection shoulder and 2 through lanes
9f9e68fe-2e1e-476c-a919-73fb7189eb0d |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-031- pt3 Walter/hardy intersection base course
ce874653-ffee-4ba3-8414-d365f2df09e2 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-032-Craigieburn to hume right turn & left turn slip to hume
56a84cdf-c7aa-4541-8511-dfc9d5bf74ff |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-033 - Zone 3.1-Slip lane-Type N-layer1
5c9d9ff8-0eb6-4b99-82a9-c9e6574d3b84 |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-034 - Zone 3.1-Slip lane-Type N- layer 1
5f0bff11-d2c8-4271-b7f2-670d24a5731d |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-035 - SF Base course shell subway slip lane up to plaza west driveway
61e499da-1ee6-4bf4-88ca-92a685b75d56 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-075 - Asphalt Placement | ITP-075-A1-LOT-036 -SI intermediate course shell subway slip lane up to plaza west driveway
53a6547e-e12e-440a-bd54-b24d8e593d14 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage
58ce27c6-97f9-429a-a4df-8acc64d5f3bb |  | checklist-sectioned | pass | 46504b4475f1a51f81242ee3138dc0dad40acae67ca84b16785bcbc230e02f20 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A1-LOT-001- Hume Hwy South Island - CH70100 to CH70280
141dee06-4b25-46bb-b365-98cf34c17b26 |  | checklist-sectioned | pass | 46504b4475f1a51f81242ee3138dc0dad40acae67ca84b16785bcbc230e02f20 | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A1-LOT-002 - Hume Hwy North Island CH70290 - CH540
287f3f73-fe17-48a9-a882-bfd4eac641f5 |  | checklist-sectioned | work-in-progress | ITP 0076 - Permanent Roadside Signage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A1-LOT-003- Bridgewater Occu
24ca4f80-bce3-411e-99ee-2212aa4a137d |  | checklist-sectioned | pass | ITP 0076 - Permanent Roadside Signage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A1-LOT-004 - Z1 Occupation
79218e5e-769d-4052-923b-d866a4ffbafa |  | checklist-sectioned | pass | ITP 0076 - Permanent Roadside Signage | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A1-LOT-005 - Z2 Occupation - Shell - Hume
97e4bf6b-4bcb-4d7c-8dcd-7bf733102922 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-078 - Insitu Pit Construction
32f56fa5-ab75-4ea5-ad37-7f2a492c1cbb |  | checklist-sectioned | pass | ITP 0078 - Insitu Pit Construction | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A1-LOT-001 - Pit 194 Base - Zone 3 East
87ac721b-ee5c-4b37-a4f8-3b37571e7faa |  | checklist-sectioned | pass | ITP 0078 - Insitu Pit Construction | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A1-LOT-002 - Pit 194 - Wall Lift 1 - Zone 3 East
7f111ad3-0fdc-491a-b2e9-1b8eff86fc5d |  | checklist-sectioned | pass | ITP 0078 - Insitu Pit Construction | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A1-LOT-003 - Pit 194 - Wall Lift 2 - Zone 3 East
83b74e16-c620-4d0f-b3f2-67203cb4f70d |  | checklist-sectioned | work-in-progress | ITP 0078 - Insitu Pit Construction | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A1-LOT-004 - Pit 282 - Walter St Corner
e8f979fe-1b4f-48c7-acf3-497380e223d8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-081 - Structural Crack Repair
87981670-dd76-4f6e-9337-0d65c14e5c65 |  | folder-normal | not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-082 - Structural Patch Repair
3cc87952-a6b1-49c6-9e74-39d8735f4462 |  | checklist-sectioned | not-started | ITP 0082 - Structural Patch Repair | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-082 - Structural Patch Repair | ITP-082-AX-LOT-XXX - Desc
079b7b35-4554-4db0-9b07-f80dca9efb58 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-083 - Precast Concrete Install
624b37b0-ba1c-4474-b188-644397b6b388 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials
9dca3327-3fee-433f-a332-dbdfac7ba11b |  | checklist-sectioned | work-in-progress | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-003 - Zone 4.4 - Between Aitken & Balyang
c017b50e-19e8-46a0-a98f-d15b8efc22fd |  | checklist-sectioned | pass | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-001- Zone 1 - Craigieburrn Roundabout - CH26060 to CH26150
7a0c01ae-a2ab-4f9c-803a-50720418399e |  | checklist-sectioned | work-in-progress | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-002- Zone 1 - Memorial Park East Bound - CH26260 to CH26340
bddad34c-1174-4158-8051-b7a9a4589b1c |  | checklist-sectioned | work-in-progress | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-004 - Zone 4 - CH14000 - CH14110
1817f281-0d65-409d-96cd-bb3693ba0bff |  | checklist-sectioned | not-started | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-005 - Zone 4 - CH14110 - CH14250
6f1c2dac-12a2-49ca-b800-a29f5ffdca2b |  | checklist-sectioned | not-started | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-006 - Zone 4 - CH13560 - CH14000
7f75ea87-d26b-449c-bf7d-49cb563629c0 |  | checklist-sectioned | not-started | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 1 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A1-LOT-007 - Zone 4 - CH14250 - CH14360
7fb27518-a1b5-4e1e-a978-cc98b6b39bc8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-085 - SUP Installation (HCC)
9257fea7-b526-47e6-aec2-38bfa947e77f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 1 ITP's | ITP-086 - Welding Carbon Reinforcement
69f77ca4-416b-40dd-89f1-fab9a29ca28f |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 2 ITP's
d0a560c5-8e01-4523-a7c2-71e402368e19 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing
92142673-77bf-4eb0-82db-19635e1b4715 | Data not allowed on checklist-sectioned: label(3b7aa0bd-ed14-4718-81ea-1079e4f80218) Child 2 - Construction Works(9e54b564-aab9-51a1-92d1-84dbc28a5084) -- 2.6 Clearing Process(57b9648a-c85c-561f-8a4d-2084ef24aa18): Data not allowed on signoff Hold Point(34a4f1f8-214f-5373-b056-0121e473520d): RESPONSIBILITY: Site Engineer(c99693dd-12b3-436f-b884-b479d9797789) Child 3 - Completion(94f469cb-8835-5fa6-8aa0-2f7f205bab00) -- Final Inspection - Work Completed On(22bf60d2-d477-4a44-9fe0-2038315d7e4d): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 178562f898084fa1c1c64bf36f32f129d299344bd7bae1c16e6449fc8f9ebe53 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-001 - 9 Trees WB CH10780-CH10940
befee931-1911-406c-b1c2-becc8f0cf158 | Data not allowed on checklist-sectioned: label(3b7aa0bd-ed14-4718-81ea-1079e4f80218) Child 2 - Construction Works(f8407966-1cbd-5be1-91e7-493063d4763c) -- 2.6 Clearing Process(303522d8-8b92-507d-a9e9-c6e7e21a1995): Data not allowed on signoff Hold Point(ad09c3cc-ffd1-59db-9b27-6ba890512cee): RESPONSIBILITY: Site Engineer(c99693dd-12b3-436f-b884-b479d9797789) Child 3 - Completion(2a411f4b-94ff-5432-8f20-7ad339a5ea83) -- Final Inspection - Work Completed On(4c50528b-cc7b-4b92-9333-59b853c2f662): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 178562f898084fa1c1c64bf36f32f129d299344bd7bae1c16e6449fc8f9ebe53 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-002 - 34 Trees WB CH10800-CH11050
5a0a9421-c9b2-437c-b8ab-63d5ff707bf0 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-003 - WB CH10900-CH11300 Stripping
f2181dce-e0b1-48cb-9e43-9d45f5ae55fd | Data not allowed on checklist-sectioned: label(3b7aa0bd-ed14-4718-81ea-1079e4f80218) Child 2 - Construction Works(bf29e8ca-628f-5560-a03f-06985535e440) -- 2.6 Clearing Process(eb46c89d-9b2c-5a5b-8c4a-ee08d2b18662): Data not allowed on signoff Hold Point(f9a5cbd3-21fa-57f3-b7a8-571244822cf8): RESPONSIBILITY: Site Engineer(c99693dd-12b3-436f-b884-b479d9797789) Child 3 - Completion(af8e2b30-6c84-5d54-80c0-02de060017d9) -- Final Inspection - Work Completed On(1d85705d-c3a9-4954-8e17-406a4e373a5f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 178562f898084fa1c1c64bf36f32f129d299344bd7bae1c16e6449fc8f9ebe53 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-004 - WB CH10500-CH10880 Stripping
a0fe3162-b400-4b72-b818-44694ecf3521 |  | checklist-flat | pass | 6c385c3c98c321e6987c49e6ca06223f93b991594499355dd4cdbe837b326da9 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-005 - 29 trees CH11500-CH11300
4fab7057-d818-4b8f-8356-b0e87b73e4f0 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-006 - Mickleham North CH40350 - CH40700
801f6a48-b8ad-4c17-87aa-ad34b0de9d44 |  | checklist-flat | pass | 6c385c3c98c321e6987c49e6ca06223f93b991594499355dd4cdbe837b326da9 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-007 - Debonair - Vantage Stripping
e9ca5eeb-02d5-4e30-b17b-d7e15acca90e |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-008 - 48 trees CH10100-CH10240
88f9ccc4-d4d2-44c8-b427-e232f06965b2 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-009 - CH60140-CH60310 Stripping
ed691adb-74a5-4a29-a890-95c254c40656 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-010 - 129 trees CH10235-CH10500
73ffff78-c2cf-486f-ab08-fdfca768e054 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-011 - 9 Trees NB and SB CH40200-CH40600
e4b5fc30-f98d-41d1-9173-2a2b2aefda64 |  | checklist-flat | pass | da953bf2274ef8dd4ce9a68f34850397b09a933c7a56309d09ea324716eb6eaa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-012 - WB CH10650-CH10500 Stripping
02ab4ebb-7125-4dae-a6d9-819492ba7cc4 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-013 - WB CH10100 - CH10290 Stripping
1eae3be8-4c2f-4129-9a1d-9e2b719bed21 |  | checklist-flat | pass | 8392dc980c91917d26de7facc052e8be8810f5a385ad924224dd0fe66d9c6b77 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-014 - WB CH10370 - CH10490 Stripping
5f8d9059-d05c-415b-9cf6-1306b55ae199 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-016 - Mickleham South 30000-30200
8527679b-3af1-48d4-acc7-beeea71b5ea8 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-017 - Mickleham South CH30200 - CH30400
71c9afb8-57c8-4e26-94f1-b2ddc03ee08e |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-019 - 2 trees CH11050 - CH11100
e0c8bc62-64f6-43ec-a002-1703af3a0797 |  | checklist-flat | pass | 23fc73ef97d6dd27505b9ae25afc41e8557ba95cc0f0ec8de3aedcb4c6820365 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-021 - Zone 5 – Aitken Blvd - SB - CH60540-CH60340
c194c2f0-8b0b-4078-a162-be5735b305ee |  | checklist-flat | pass | d870ed6d048ec6c26cefb41e8d0c4f25e66bab1c5a014d31dffa9b3cdc5934be | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-024 - Zone 6 & 7 - Champion, Debonair & Mickleham Rd.
9dbcd686-2e80-4f2e-a4a0-375ac71cb1f8 |  | checklist-flat | work-in-progress | a688f0da9a3bd8d727341ef77560066defbab2d69a561834b9ee42ab734bf133 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-025 - Aitken Blvd to waterview blvd & Aitken creek bridge
4dda2183-e7a4-481f-b488-4e295017f45f |  | checklist-flat | pass | a688f0da9a3bd8d727341ef77560066defbab2d69a561834b9ee42ab734bf133 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-026 - Zone 5 – Aitken North - North Section Stage 1 - SB - CH60930-CH60740
a1fa146e-e225-42b9-a74d-c6a0837882ab |  | checklist-flat | work-in-progress | 60bf39d1bea6a07f9ef4992b01c677254b3aae626db6020854fea251f937943f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-027 - Zone 5 – Aitken North - South Section Stage 1 - SB - CH60740-CH60590
65de4ee4-9188-41ce-ad86-5ea2edb1cbbe |  | checklist-flat | work-in-progress | 3455b537d1ff1c363194ebbe3b07956225111fbc0a5c0718a7ed2f9a8d4ac0b6 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-028 - Zone 7 Vantage - CH11680 to CH12140
799e63e9-da2c-419a-a112-196283558a2a |  | checklist-flat | pass | d2914bf86e85d5a68c145e12d39b8ed7677902c9a0173e05296d6839792e8dae | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-A2-LOT-029 - Zone 6- CH11980-12300
b31f6592-ea96-4978-af60-d43c3beb4ee9 |  | checklist-flat | work-in-progress | 60bf39d1bea6a07f9ef4992b01c677254b3aae626db6020854fea251f937943f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-AX-LOT-XXX - Utilities gas and power tree removal
cdac45b2-a78e-4246-bb6b-2853ff1d7a08 |  | checklist-flat | not-started | ITP 0001 - Clearing & Grubbing | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-001 - Stripping Topsoil Clearing & Grubbing | ITP-001-AX-LOT-XXX - Desc
83d5888a-8236-4008-a3a9-36345594d583 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep
3989ad36-6be8-4f57-b1b7-d5e8a6ca1d42 | Child Final Inspection - Work Completed On(97d4c811-7bae-4a92-85b5-348c8d7039af): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-001 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB
ea54e5f6-82b2-4521-8563-75bc7b0b7f9a | Child Final Inspection - Work Completed On(125dbb41-8b58-4df1-b03b-e351aa1579e6): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-002 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB
4a79adf6-e99c-4eaa-917d-025a1e7809b2 | Child Final Inspection - Work Completed On(e24174cc-45f3-47df-b436-c00e43b3a265): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-003 - Zone 7 East Gate 7.4 - CH11680-CH11480-WB
b5dadc89-9a61-4e52-9aa5-92dc1d746180 | Child Final Inspection - Work Completed On(e47d0f4d-e428-45c5-b281-9f34e8e28c7e): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-004 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB
677b8344-6f0d-45a5-9ce1-c29a0f99a2ce | Child Final Inspection - Work Completed On(1673adf1-6f5c-421d-a72f-b32b59448d34): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-005 - Mickleham North CH30520 - CH30750
ebcf0d62-a4c4-465b-a49d-b030fef8673d | Child Final Inspection - Work Completed On(841f4b67-fd09-405e-a9b8-8bfb8ffbdd15): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-006 - Mickleham South CH30120-CH30234 Cut
8f3c974d-9005-4397-b303-2c55afcee8fc | Child Final Inspection - Work Completed On(c5273e03-1a57-438d-8e7d-0517ed5b2298): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-007 - Mickleham South CH30120-CH30234 Lift 1
c88a9d58-58a9-4d9f-b63d-5db84d1dd358 | Child Final Inspection - Work Completed On(5ec24db9-a7c8-4e53-bafe-57b1fded47aa): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-008 - Mickleham South CH30120-CH30234 Lift 2
e8b2304e-5fc2-4f14-aada-90e27eab0f6b | Child Final Inspection - Work Completed On(209425c3-49a9-4514-82de-a8ead2b096fc): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-009 - Mickleham South CH30020 - CH30316
9b7077dc-92d0-4652-8c25-6147ae9f310f | Child Final Inspection - Work Completed On(88688f5b-8fe0-4908-b0c5-f8e0a91eab8f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-013 - Mickleham South CH30020 - CH30120
0eb6d859-00ff-4ba6-b3a1-f394f9801a65 | Child Final Inspection - Work Completed On(131d4352-3d4a-4fcb-b897-0287acb654fd): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-015 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10650-WB
81931f44-e5e4-4963-9f04-27f6be3c32b1 | Child Final Inspection - Work Completed On(12e6e02a-25d2-45cd-80b4-8ade46aa1ecb): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-017 - Mickleham South CH30152 - CH30316
69d912b2-e288-4448-a642-71e99b833a06 | Child Final Inspection - Work Completed On(db02d1b5-097a-429f-a29d-022fee3fb5db): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-018 - Mickleham North CH30520 - CH30665
770ee4a0-efab-407d-9567-04d4ceb150be | Child Final Inspection - Work Completed On(992142b8-ef6d-411c-9c8d-03a4c343ba71): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-019 - Mickleham North (NB) CH30520 - CH30800
5594c4fb-7de3-446c-a38e-9ab0584a9866 | Child Final Inspection - Work Completed On(0cabbddb-0903-4684-bcc7-621cb7554e46): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-020 - Zone 7 East Gate 7.2-7.3 - CH10580-CH10850-WB
d2df9a47-c923-48b4-a7fa-5b588bfc9167 | Child Final Inspection - Work Completed On(5711df3f-a460-4a7d-8f39-b9da4cdc4638): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-023 - Mickleham North CH10520 - CH10550
5d647e92-e254-4ae1-b8e9-d68dc0e2bdd5 | Child Final Inspection - Work Completed On(f67bbdf1-9a31-42af-bb90-d93a79909f46): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-024 - Mickleham North CH10520 - CH10550
28d3cd8e-2f16-485b-8bd4-44d500496e8b |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-025 - Mickleham North CH10520 - CH10550 L5 SG
d28c6ecb-a64d-4dca-892b-aa0e3cd23117 | Child Final Inspection - Work Completed On(6f847ee2-6b2a-41a0-9e20-c6baaf45005b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-027 - Zone 7 West Craigieburn Rd - CH10035-CH10185-EB
f2fb118e-d993-4505-beb0-2a97c3bfd8da | Child Final Inspection - Work Completed On(8ffd835d-c0b2-4c9b-a09a-87f43ef05416): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700-WB
d8aa210c-4554-4c2a-9ce9-c7adf48f0678 | Child Final Inspection - Work Completed On(d17c6a56-76f1-444d-874b-fd94cb4e1560): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-029 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 1
ce9d344f-9377-442a-8f3f-b2cad05c2b78 | Child Final Inspection - Work Completed On(87673f94-dc12-4c92-ae88-ed3e378a7151): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-030 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2
4711ae27-0a38-4804-933e-fd2b612abc2a | Child Final Inspection - Work Completed On(4335d4ea-c318-4afc-8633-08106f599b99): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-031 - Mickleham South (NB) CH30316 - CH30400
dc334938-02fc-4517-a59f-dff878d78675 | Child Final Inspection - Work Completed On(1424eb30-1ec5-4b1d-9da2-99777a37e707): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-032 - Mickleham North NB CH30470 - CH30500 Cut floor
81171910-bc10-4e38-9e6e-fdfbcc89445d |  | checklist-sectioned | pass | bc0230acd1a341230e33cd9fbe5e8c38fa06efaada029aa66a38043b9339f8e5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-033 - Mickleham North NB CH30470 - CH30500 Layer 1
835ae462-7205-4ab9-8127-6aaaf407b977 | Child Final Inspection - Work Completed On(cf253be7-5ff0-4e0c-b666-e57731f1e394): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-034 - Mickleham South CH30316 - CH30400
65f5e903-3641-4272-b9bd-adb9d7008b1b |  | checklist-sectioned | pass | 4103ce72895d114ad5e8a524b2df5c1517d0af0c8c814333020e908f859397b7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-035 - Mickleham Intersection CH30400 - CH30420
6a10a7d1-d11e-47e2-86a3-3d9c3c7f1f20 | Child Final Inspection - Work Completed On(899f9cc5-6fd7-46ce-a509-5adb0ad1223a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-036 - Mickleham Intersection CH30400 - CH30420
b338ad66-37e5-4bd6-aa17-98e3f6cee776 |  | checklist-sectioned | pass | 4103ce72895d114ad5e8a524b2df5c1517d0af0c8c814333020e908f859397b7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-037 - Mickleham Intersection CH30400 - CH30420
7df17777-08a6-42ad-9f95-2a8154bdfe1a | Child Final Inspection - Work Completed On(29991aae-53ff-4f6b-aacf-880c0e80cdf9): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-038 - Mickleham Intersection CH30400 - CH30420
77cafe36-4f2a-4ebc-8e25-72aa1d651a3f | Child Final Inspection - Work Completed On(7f676811-70cf-438e-98f3-7ecab51efd1f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-039 - Mickleham Intersection CH30400 - CH30420
c0d37486-2fb0-426e-b777-edc90cc8ca3d | Child Final Inspection - Work Completed On(47935e3a-da54-4e33-a083-5c45e17d08b3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-040 - Mickleham North (SB) CH30420 - CH30520
bcb7f745-8535-4f51-bfbe-97db5dfbd204 | Child Final Inspection - Work Completed On(2eec6b8d-cccb-47ff-84a5-4f272be6e2ec): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-042 - Mickleham North (NB) CH30450 - CH30520
a0221b04-931e-4123-8d3d-a8b26754ceda | Child Final Inspection - Work Completed On(a9f430ee-4cdb-49c6-97ca-75ed7cc5679e): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-043 - Mickleham Intersection CH30400 - CH30430
770bb5fe-a48d-4ec1-baca-5114433c5a85 | Child Final Inspection - Work Completed On(e81d98e2-3051-4bee-91b4-4477ff2be29f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-045 - Mickleham Intersection NE CH20500 - CH20550
6125992f-1d44-462f-82c3-5e18c3ad05fb | Child Final Inspection - Work Completed On(bb9a902d-0131-45f7-865e-73b503d9c3ab): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-046 - Mickleham North CH40750 - CH40780
bbe16f00-0251-4e27-b83c-fcc1108be9ec | Child Final Inspection - Work Completed On(478cfc8d-6244-446c-81c2-c523bafcb79f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-047 - Mickleham South CH29980 - CH30015
4b74180c-94bc-406c-ada5-2f2529a13b59 | Child Final Inspection - Work Completed On(97d09e0d-b53f-4b27-b0ef-ed71d16dc0c4): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-048 - Mickleham Intersection CH10520 - CH10600
fbf0e1f6-dbd2-4205-a92f-279bd31c5c2b | Child Final Inspection - Work Completed On(2a5619d5-8410-44fa-9f43-cb958224563c): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-050 - Zone 7 West Dam - CH10300 to 10350 - Layer 1
369e0c73-093f-4117-8d5e-b3d389005a50 | Child Final Inspection - Work Completed On(fb103647-2687-455d-81a7-d493b66c17f4): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-052 - Zone 7 West Dam - CH10300 to 10350 - Layer 2
9007cca1-7dff-4965-ad3b-f523b219eb36 | Child Final Inspection - Work Completed On(465d6145-95a6-4297-bd3b-f37ce280cae8): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-053 - Zone 7 West Dam - CH10300 to 10350 - Layer 3
5aac1993-732f-40a7-b9aa-8bb4a3ca42da | Child Final Inspection - Work Completed On(505acad6-c558-47f5-8fa1-716c275bca42): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-054 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140-WB
979dbaa5-7710-4b11-acef-76c5db75abfc | Child Final Inspection - Work Completed On(894bd8b2-fab0-438c-960e-fd02487e2518): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-055 - Zone 7 West Dam - CH10300 to 10350 - 400mm Below Subgrade (Top of Layer 4)
30078d49-0033-46bd-ac12-e92705b31604 | Child Final Inspection - Work Completed On(6d36044a-b63d-4aab-8bd8-f7d955b80fb1): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-057 - Zone 7 East (GSM Capping Shift) - CH10780-CH10850-WB
9cacb86b-8ad0-492f-96fe-f0ae856fb81b | Child Final Inspection - Work Completed On(4f76b8a9-25ba-412b-b269-034cbcce1a35): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-058 - Zone 7 East SUP - CH10850 to CH10730
79273849-2ac6-4305-b200-1d060b28a61a | Child Final Inspection - Work Completed On(85ee4db9-8f5a-4baf-8a32-77b699fd176e): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-059 - Zone 7 East SUP - CH10730 to CH10680
fcda3d33-c922-4481-b02b-61d01d04e672 | Child Final Inspection - Work Completed On(000690c3-fa9e-46c4-8541-4e5de6fa9926): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-060 - Zone 7 East SUP - CH10600 to CH10630
f5154923-7cde-4e33-94c3-d845a90513b6 | Child Final Inspection - Work Completed On(1d84e4ab-c77d-4d22-bbbc-ab66fd8289f5): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-061 - Zone 7 East SUP - CH10600 to CH10730
aa7156d8-8557-47f8-94c0-f9255f9301b0 |  | checklist-sectioned | pass | 4103ce72895d114ad5e8a524b2df5c1517d0af0c8c814333020e908f859397b7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-062 - Zone 7 West Dam to Tennis Court - CH10290 to CH10460 - Subgrade Level
474955f8-a08a-4723-a17d-da99853629a4 | Child Final Inspection - Work Completed On(45af1530-0fb3-4d9f-8d32-d4c02272a4c8): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 5af564752deedfef178df53ed70a9cf5cc0d24ef84e765dd841edf0e290c4eb7 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-063 - Zone 7 West Dam - CH10300 to 10350 - 200mm Below Subgrade
c89706c2-03be-443e-b6fa-6d3d87287f3f | Child Final Inspection - Work Completed On(927be36f-46fa-4d27-af54-1d0001692bad): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | work-in-progress | 03c1083005aa453cd8bc8b6c537d4cc5b79f36ce2d99d48ecd30f491a3773d71 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-064 - Zone 7 East Nobility Rd to Gate 7.5 - CH11360 to CH11490 - WB
eeebc86c-2c44-4404-986c-3ab5b58af541 | Child Final Inspection - Work Completed On(595e6fe3-60a1-4965-b8b5-b898d992d607): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-065 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (400mm Below Subgrade)
a774188d-6e34-4928-8a82-4f7a9643a5c6 | Child Final Inspection - Work Completed On(404641d7-48a9-4f50-ac47-23006380e351): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | eece2b99e115d2a5aecedae1de1ef135d40a6c9fe019c8893e2bbe90c2370f10 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-066 - Zone 7 West Tennis Court - CH10350-10410 - Cut Fill (200mm Below Subgrade)
662e546b-bd19-4abd-8c34-30333d5a7f50 |  | checklist-sectioned | pass | bc0230acd1a341230e33cd9fbe5e8c38fa06efaada029aa66a38043b9339f8e5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-068 - Zone 7 West - CH10420-10470 - Rectification Works @ 200mm below Subgrade
2375291e-e046-485c-be55-1bd3e3b52d45 |  | checklist-sectioned | pass | bc0230acd1a341230e33cd9fbe5e8c38fa06efaada029aa66a38043b9339f8e5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-069 - Zone 7 West - CH10420-10470 - Rectification Works @ 400mm below Subgrade
63aef433-257b-4db7-915b-7e5a80b9c97f |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-072 - Zone 7 SUP - CH10550 to CH10650 - Subgrade Level
8dedf032-f79d-45bb-ae57-be041a42c49d |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-073 - SUP Subgrade Prep - NW Mickleham Intersection
02cb95d4-a7e4-42d7-8779-9e49e1219f25 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-074 - SUP Cut Floor Level - NE Mickleham Intersection
8999462a-1eeb-4318-a8da-f0115de09adc |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-075 - SUP subgrade Layer 2 - 200mm installation - Mick NE
a380165f-c75b-4e1c-97de-e4d545eb5bca |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-076 - SUP subgrade Layer 3 - 200mm installation - Mick NE
aae6a1dc-b79e-49d0-9eae-0ea67febeed8 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-079 - SUP subgrade Layer 4 - 200mm installation - Mick NE
b428f99a-1e25-49f9-a5b1-c8acb2e7407d |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-080 - Type B layer 800m below FSL
63687d1d-4a54-4425-9250-fa8c3868cc26 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-081 - SUP subgrade Layer 5 - 200mm installation - Mick NE
f1e1d24a-0bda-4db8-a46d-2d6361eb1321 |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-082 - Zone 7 West CH 10180 - CH 10300
d9ec4029-951e-4475-b86f-4908064140fc |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-083 - Zone 7 West SW CH 10450 - CH 10490 Cut + 200
61873fe4-7885-49ef-937a-950bf30caa25 |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-084 - Zone 7 West SW CH 10450 - CH 10490 SG top
ce707958-1a10-4eb4-8745-95a1622fc1bd |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-085 - SUP subgrade Layer 6 - 200mm installation - Mick NE
31504925-b313-4391-a1a9-d2d2f06a70c7 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-086 - Type B layer 600m below FSL dam
e5e5f8f5-5d3d-4284-b0f2-8da92d50a8f5 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-087 - SUP subgrade Layer 7 - 200mm installation - Mick NE
a6a62942-420e-4d90-bd77-1ba4a0dd77de |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-088 - Zone 7 East - Debonair Cut Floor and Layer 1 - CH11220 to CH11300
494c0b04-4672-4898-af51-c34ec9118614 |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-089 - Zone 7 West SW - Slip Lane Tie In - CH 30370 - 30390
9292c500-79f7-435a-b099-539572e3a028 |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-090 - Mickleham Rd North (Northbound) SUP Subgrade - CH30465-30695
f631ab68-cb91-46cd-b485-99ce9c7f550e |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-091 - Zone 7 East - Layer 2 - CH11220 to CH11300
949db9e4-6e4f-427b-8d84-d7a9376f9ced |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-093 - Type B Layer 400mm below FSL Dam - Zone 7 West (CH10300-10350)
a9338605-6d15-41c6-ad83-bc7dc47afb60 |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-094 - Type B Layer 200mm below FSL Dam - Zone 7 West (CH10300-10350)
4df2332b-b166-4829-a3de-ce24eb3b1443 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-095 - Zone 7 East - Layer 3 - CH11220 to CH11300
67f7b07a-5a64-410a-acdc-57389c1d3789 |  | checklist-sectioned | pass | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-097 - Zone 7 East Debonair - Cut Floor & Layer 1 - CH11300 to CH11320
833417c5-dc78-4fba-b00c-225079cd54cd |  | checklist-sectioned | pass | f8eae16faecadd5670aba034cfc776eaa51746bf3f7fd05230af96df4225e98a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-104 - Zone 7 West - 755 Driveway Wedge - CH10135-CH10180 - Subgrade Level
37e18799-75d9-4230-8832-6c7b9e2fe628 |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-105 - Zone 5 Aitken South - North Section to Healesville Loop - CH60520 to CH60410 - SB
38166d82-cca7-44f2-9374-2e81d8dc9933 |  | checklist-sectioned | work-in-progress | 50212f19c4f6a0188ed7611658eba50f03d6b1944b3b4c20c57389b434a0585a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-106 - Subgrade Layer - Mickleham Intersection NW - Type 16 Pavement (CH30439-30473)
baf9b4e7-dcd1-4043-9e94-f328350468e4 |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-107 - Zone 7 East - Subgrade L1- CH11300 to CH11330
28007781-b26d-4f1f-95aa-694907b3ae03 |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-108 - Zone 7 East - Subgrade L2- CH11300 to CH11330
fa8bc9b9-bc98-424e-8d93-875ba8d2eb0b |  | checklist-sectioned | pass | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-109 - Zone 7 East - Debonair Pde CT- CH11300 to CH11320
1c7d61a3-105c-4fe0-9081-d9715f849590 |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-110 - Zone 7 East - sub grade CH11320 to CH11360
74792d5c-9ba2-4ded-8e1c-ed56e5d86d2d |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-112- Zone 7 East - Debonair Pde Subgrade layer 0 - CH11300 to CH11320
c05c1a21-d99b-41eb-b1c6-bc52e2522bfc |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-113- Zone 7 East - Debonair Pde Type A (Subgrade) - CH11300 to CH11320 (canceled)
d79f05ff-f95c-4c15-a6ba-f61932a92cd2 |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-114 - Zone 5 Aitken South - Southern Section - CH60410 to CH60280 - SB
cf6dcdc6-7d94-4a14-9c9d-c3e586a220ce |  | checklist-sectioned | fail | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-115 - Zone 7 East Deb-Van 11113-11128
5bf53954-fdfd-46ca-b580-5d78fe84da6f |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-116 - Zone 7 East Gate 7.4 - CH11350-11480
a7138ce5-9d74-4280-9da4-31f6671e59c2 |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-117 - Zone 5 Aitken North - Lower Half - SB - CH60800 to CH60860
91b35b75-9712-44ad-8591-61869d7f464f |  | checklist-sectioned | work-in-progress | efb06602b4cc49af5f93fc42534a81b1a9fe52d07b356e4058c478f5596f06db | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-118 - Zone 5 Aitken North - Upper Half - SB - CH60860 to CH60940
65214cb1-a084-46b9-a3d0-c2b3c770f92c |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-119 - Zone 7 East Vantage CH11790-11850
5239c9a1-7760-41d3-bedc-9e4aff95f4d2 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-120 - Zone 7 East Stage 2 - Mickleham to Debonair (CH20545-20770)
f988efd5-4f89-4b05-8488-ed0f489e8671 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-121 - Zone 7 East Vantage CH11880-11970
0eeeb726-dfe1-4328-a947-576a1e8445ea |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-122 - Zone 7 Vantage Intersection - CH11840-CH11860
b772c723-7433-4c2a-8141-ad42f1df3c95 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-123 - Zone 7 Vantage Intersection - CH11870-CH11880
7ebaf14b-e4b0-4155-8a41-abdccb3c9844 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-124 - Zone 5 Aitken North - South Section - SB - CH60600 to CH60740
017cf454-e5e7-49c4-a053-16127f444c63 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-125 - Zone 7 West Stage 2 - Subgrade Level (CH20360-20470)
4f1c39ec-0877-4fb5-a544-654899312fad |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-126 - Zone 7 Vantage CH11870-CH11900
57df79ce-6b6c-4cb7-a667-15b8d40db064 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-127 - Zone 5 Aitken South - SE Intersection - SB - CH60508 to CH60631
60e466f5-057d-4767-9703-defe91c32837 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-128 - Zone 7 West Stage 2 - Subgrade Cut Floor Level (CH20240-20470)
ce9165c1-b6d0-47d3-9bdf-fd83177fe1b1 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-129 - Zone 7 East Stage 2 Gate 7.14 (CH20720-20760) Rework
9acf85f8-2786-4d9c-8c5e-64f2d29e0927 |  | checklist-sectioned | pass | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-130 - Zone 5 Aitken North Southbound S1 - Mid-Section (CH60740-CH60860)
08a4eed5-0fd6-489d-94d7-9275873afdd0 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-131 - Zone 7 West Stage 2 - 750-760 Craigieburn Rd (CH20170-20230)
705975d8-d622-4bf8-b7d7-eb8dd8e7bb30 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-132 - Zone 5 Aitken South Stage 2 - Northbound Turning Lanes North of Ajana (CH60370-60500)
caf45c1b-6095-4dd7-bc91-25a3b63e7254 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-133 - Zone 5 Aitken South Stage 2 - Southbound Lane South of Ajana (CH60130-60370)
2258006f-ac01-4f30-b36e-b91d43981833 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-135 - Zone 5 Aitken South Stage 2 - Ajana Tie-In (CH60354-60344)
6d1adc0b-2755-4575-a5ab-e0bcc6f88cd1 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-134 - Zone 5 Aitken South Stage 2 - Southeast Corner (CH60540-CH60550)
3fbf7b31-f24a-4810-9507-807872fa121a |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-136 - Zone 5 Aitken South Stage 2 - PT6 Tie-In (CH60050-60130)
53576c77-05fa-4555-b656-cbb131fa88e2 |  | checklist-sectioned | not-started | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-137 - Zone 7 West Vantage slip lane 11825-11845
d594fb77-d4bb-457a-91d2-18fa79ead670 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-138 - Zone 5 Aitken North East Intersection - SB - (CH60580-CH60700)
f1e64e3d-e5ca-4b05-802b-c97ed060c370 |  | checklist-sectioned | not-started | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-139 - Zone 5 Aitken Southwest Extension - CH50370 to CH50550
47d6da08-4532-42ed-b7cc-d031b612fbc5 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-141 - Zone 6 Champion Intersection 12300-12320
9ae3b3cc-c2b9-436d-a38e-8b072d850e36 |  | checklist-sectioned | work-in-progress | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-006 - Excavation, Fill with Type B & Subgrade Prep | ITP-006-A2-LOT-142 - Zone 5 Aitken South East Corner - CH13280 to CH13320 - WB
9738caa8-6cb8-4124-9deb-fa2f9b3237ca |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A
f602301a-1008-4c2f-b6cf-72299a555bad |  | checklist-flat | work-in-progress | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-001 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 1
ccd487eb-b335-4c8e-9b57-43f6e271c01b |  | checklist-flat | pass | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-002 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 1
17bbc18b-64e6-45d6-bde9-b44f460e060f |  | checklist-flat | work-in-progress | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-003 - Zone 7 East Gate 7.1-7.2 - CH10900-CH11220-WB Layer 2
e70c5153-18f0-4fcc-8342-e08cc90051aa |  | checklist-flat | work-in-progress | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-004 - Zone 7 East Gate 7.2-7.3 - CH10660-CH10850-WB Layer 2
28aa3ea3-eb78-4357-8902-ed0d7fb3e8ee |  | checklist-flat | work-in-progress | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-005 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 1
98b10c5b-99b4-4e3e-b2cb-ef62c64afa11 |  | checklist-flat | work-in-progress | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-006 - Zone 7 East Gate 7.2 - CH10850-CH10900-WB - Layer 2
a280df96-ba23-43c4-a41a-e25163a7612c | Child Final Inspection - Work Completed On(dff50462-4abf-4136-9c66-e0e0f52c725b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 8bd3078d87847443bbfa2534be0cee98dc02a5e9965c9d1953eec8560cc064fa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-008 - Mickleham South CH30000 - CH30234 L1
08bea5d9-753e-4f59-be37-01f89f4fcd25 |  | checklist-flat | pass | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-009 - Zone 7 East Gate 7.4-Nobility Rd - CH11680-CH11480-WB - Layer 1
1d5ebba7-fc1a-4c1c-9053-b7b6bc11cf57 |  | checklist-flat | pass | db13a81ccb70765f405f26bd6d263ca7cd36d7e670877e1dd59c5e7fa34c0c80 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-010 - Zone 7 East Gate 7.4-Nobility Rd - CH11510-CH11480-WB - Layer 2
53cd0720-cdb3-4cf6-a500-722f28bac002 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-011 - Mickleham South CH30000 - CH30234 Layer 2
81646338-4ce0-46bd-b2c3-4518486780e8 | Child Final Inspection - Work Completed On(091882cf-522c-43d0-a80a-431944953a21): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 8bd3078d87847443bbfa2534be0cee98dc02a5e9965c9d1953eec8560cc064fa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-012 - Mickleham South CH30000- CH30152 Layer 1
fd431083-0b6e-4ae3-a740-bc64141d8489 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-013 - Mickleham South CH30234 - CH30316 Layer 2
cc6a868f-8526-4817-ad8d-80ac2161e5f7 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-014 - Mickleham South CH30234 - CH30316 Layer 1
05c80be9-a040-418b-8078-13a1fa69885e |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-015 - Mickleham South CH30152 - CH30316 Layer 1
983d80b3-cf30-459a-8dfe-640d92dbe47f |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-016 - Mickleham South CH30152 - CH30316 Layer 2
1d0c2363-b5e4-45f1-a5aa-9e6271b19ba7 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-017 - Mickleham North (SB) CH30520 - CH30665 Layer 1
48e2ef6b-0b4e-440f-894c-6aae6ebb450c |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-018 - Mickleham North (SB) CH30520 - CH30665 Layer 2
9b3a2e8f-96a1-4128-b843-fa6f21c69e04 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-019 - Zone 7 East Gate 7.3 to Mickleham - CH10550-CH10850-WB - Layer 1
e84b67fe-4554-4b0c-a94e-30113b49f81f |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-020 - Mickleham North (NB) CH30520 - CH30665 Layer 1
5e29801e-1345-4685-96df-77e3667225a2 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-022 - Mickleham North (NB) CH30520 - CH30665 Layer 2
9ce5b4b3-4b1a-42e5-a73c-618710b88226 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-023 - Mickleham North (NB) CH30665 - CH30800 Layer 1
9aa8fd7b-2ec6-44a6-8157-38ee675907e8 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-024 - Mickleham North (NB) CH30665 - CH30800 Layer 2
4e04907f-26c8-4a43-affc-d881a9702895 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-025 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 1
6e866b65-b027-4ff1-be8e-c630f565bc98 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-026 - Zone 7 West Occo Works - CH10035-CH10185-EB - Layer 2
5e4c2c1c-6da6-4ab9-b5b9-398458b6d611 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-027 - Zone 7 East Gate 7.3 to Mickleham - CH10650-CH10850-WB - Layer 2
09cd2567-6db6-46c6-a9a2-b86681f1a8ca |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-028 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 1
46c2a99e-006f-4f07-b281-ff3bdfb9a808 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-029 - Zone 7 East (North Half GSM) - CH10610-CH10700 - Layer 2
09267ff3-9389-4c46-b22e-9bd2b6c1e361 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-030 - Zone 7 West (Slither) - CH10000-CH10135 - Layer 1
eba88c05-c6e9-4491-997c-7c39673788eb |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-031 - Zone 7 West (Slither) - CH10035-CH10135 - Layer 2
f98ae1cc-fd8e-4510-bfdd-1e8af83e93f4 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-032 - Mickleham South (SB) CH30316 - CH30400 Layer 1
f9b1a488-3a35-453f-acdb-9e2a0e355302 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-033 - Mickleham South (SB) CH30316 - CH30400 Layer 2
9d6ce962-b047-4c6f-9609-7bd0608b1fec |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-034 - Mickleham South (NB) CH30316 - CH30400 Layer 1
2c72652b-bbcb-446a-9d46-5ed40f5817d6 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-035 - Mickleham South (NB) CH30316 - CH30400 Layer 2
d93bd52f-e338-455f-a534-23ae2f134f62 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-036 - Mickleham North (NB) CH30450 - CH30520 Layer 1
0a8e29c3-8b1d-4978-80c0-019a0fcbf2da |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-037 - Mickleham North (NB) CH30450 - CH30520 Layer 2
62cedbc5-170b-4808-929b-ea10fa79fa02 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-040 - Mickleham North (SB) CH30470 - CH30520 Layer 1
f51ae852-ddfe-4654-a12a-2a6b0fa5b563 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-041 - Mickleham North (SB) CH30470 - CH30520 Layer 2
acb6fe93-9557-4a2a-a0e5-9d3f90465589 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-044 - Mickleham North (SB) CH30430 - CH30470 Layer 1
93c42e29-3c7e-40ed-8f6c-2dfdb33db074 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-045 - Mickleham North (SB) CH30430 - CH30470 Layer 2
c413d76d-4ebd-4e3e-998e-f928a269838e |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-046 - Mickleham Intersection CH30400 - CH30430 Layer 1
cdbfd604-7771-4cdc-bd65-8cb1229885b8 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-047 - Mickleham Intersection CH30400 - CH30430 Layer 2
5ef93447-8d62-4c43-9146-2cc0ff95b35c | Child Final Inspection - Work Completed On(f533c84e-6e43-4adb-bbc6-9189ebde165a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 8bd3078d87847443bbfa2534be0cee98dc02a5e9965c9d1953eec8560cc064fa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-048 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 1
a5fce3db-e731-40a3-8f49-ac5968f3d759 |  | checklist-flat | pass | 58cdaca09e4386ead161c9ead49fe1b5e6ae7813ea74392a904e0a2a95ae0dbb | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-049 - Mickleham Intersection (Eastern Tie End) CH10550 - CH10600 Layer 2
7d0887de-7abd-4575-a3c9-c98f43c6240d | Child Final Inspection - Work Completed On(56457509-9c71-4da8-b157-c3c72254ed80): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 8bd3078d87847443bbfa2534be0cee98dc02a5e9965c9d1953eec8560cc064fa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-050 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 2
2af4284b-c247-4695-8cc7-b32de305907e | Child Final Inspection - Work Completed On(a1c0a375-25ee-4b70-9d94-9e0cb6c3bb99): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-flat | pass | 8bd3078d87847443bbfa2534be0cee98dc02a5e9965c9d1953eec8560cc064fa | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-051 - Mickleham North NW Slip Lane CH10470 - CH10490 Layer 1
e1949e48-afdb-4c2a-9c86-abdec276d044 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-052 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10840-CH11140 - Layer 1 - WB
720bd921-5fdf-4264-85df-6fe1726ed1c6 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-053 - Zone 7 East Gate 7.1-7.2 (Post ACM) - CH10900-CH11190 - Layer 2 - WB
05f1dcf2-83e8-4728-9782-022bf9e34c9a |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-055 - Zone 7 East (Post Drainage Install) - CH10550-CH10750 - Layer 2
16c72dc2-296b-421f-a8e0-84bf3fb19f68 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-056 - Zone 7 East - CH10780-CH10850 - Layer 1
8a7e056c-ef79-4c9b-afa6-75474596c870 |  | checklist-flat | work-in-progress | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-057 - Zone 7 East - CH10780-CH10850 - Layer 2
b93cb4c0-2089-4fac-9967-6a81fcf28164 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-058 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 1
58d425f4-4893-418c-9d02-52379161f7d2 |  | checklist-flat | pass | 9e01650e3064fa0f428333580d9589419eb77604a44a79a3cf02f74b7c9d398f | checklist-flat | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-059 - Zone 7 East - Nobility Rd to Gate 7.5 - CH11480-CH11400 - WB - Layer 2
901fe1e2-289e-4c16-88de-1f53ab6d4cf0 |  | checklist-sectioned | pass | c1d421ad426b6c55ac46c6b7ba50cdea4ddea516cea675e0a59acb354a4f7a6f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-060 - Zone 7 West CH10290 to CH10460 - WB - Layer 1
da6782b8-707e-4d87-b838-0017c3de9f51 |  | checklist-sectioned | pass | c1d421ad426b6c55ac46c6b7ba50cdea4ddea516cea675e0a59acb354a4f7a6f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-061 - Zone 7 West CH 10350 to CH 10460 - WB - Layer 2
2c2cfbd5-37da-4cf1-a31e-ef5fd56ca066 |  | checklist-sectioned | work-in-progress | f62f1a80071bab01463fbc476161c4db9eb526d38eb4f1da44634f6547da8df5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-062 - Zone 7 East - 7.1-7.2 - CH10920-CH10850 - WB - Layer 2
d28aa965-48a3-4646-a50b-5f4c4e46108e |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-063 - Zone 7 West CH 10180 to CH 10290 - WB - Layer 1
1df59fb7-8cd5-4581-97b7-f2a58e5a790c |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-064 - Zone 7 West - CH 10450 to CH 10490 - WB - Layer 1
572ac80a-eae5-465e-b997-72534f41e343 |  | checklist-sectioned | work-in-progress | cb9a6ef3ad882583dc83de53b67f4db88818dd3dec8c5c4be8c6325f13262b80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-065 - Zone 7 West, Dam SUP - CH10300 to CH10350 - WB - Layer 1
e4bb2fc1-0bbc-467b-adee-47fbe1dade24 |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-066 - Zone 7 West, SW Slip Lane - CH 30370 to CH 30395 - NB - Layer 1
9605391a-2056-4341-80c5-c245b2c9f41b |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-067 - Zone 7 West CH 10180 to CH 10350 - WB - Layer 2
c88892eb-308b-439a-9774-d3cf6207505b |  | checklist-sectioned | pass | 22bdb7f68495772b2a052b2b005866ac05d8830ba2c2ce3f4348b2d3e585471c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-068 - Zone 7 West, SW Intersection - CH10450 to CH10495 - WB - Layer 2
98a0559c-0075-44dd-82ea-3dc308b38642 |  | checklist-sectioned | pass | cb9a6ef3ad882583dc83de53b67f4db88818dd3dec8c5c4be8c6325f13262b80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-070 - Zone 7 East - Layer 1 Capping - CH11220 to CH11300
54128504-2813-451e-9b26-0c8d8f9d2e08 |  | checklist-sectioned | work-in-progress | cb9a6ef3ad882583dc83de53b67f4db88818dd3dec8c5c4be8c6325f13262b80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-071 - Zone 7 East - Layer 2 Capping - CH11220 to CH11300
62f95e96-88db-43ad-a893-6a87f5bcf72d |  | checklist-sectioned | work-in-progress | cb9a6ef3ad882583dc83de53b67f4db88818dd3dec8c5c4be8c6325f13262b80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-072 - Capping Layer - Mickleham Intersection NW - Type 16 Pavement (CH30439-30473)
6bcf65db-8dcf-4341-9ce2-f7af8f736c5c |  | checklist-sectioned | pass | 910fc6b34ef14733d938511facd89565278351d811ae38d91301989b918c0378 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-073 - Zone 7 West SW Slip Lane Layer 2
9898a845-991f-4265-8762-751cca9a1491 |  | checklist-sectioned | pass | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-074 - Zone 7 East - Layer 1 Capping - CH11300 to CH11360
ce49e10c-adb2-4c80-a786-1af8b5766b20 |  | checklist-sectioned | pass | 910fc6b34ef14733d938511facd89565278351d811ae38d91301989b918c0378 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-076 - Zone 7 West - Jo's property wedge + U-turn Lane Layer 1
0a0403e2-1f1f-43ed-87ab-fac1c9310f50 |  | checklist-sectioned | pass | 910fc6b34ef14733d938511facd89565278351d811ae38d91301989b918c0378 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-077 - Zone 7 West - CH 10120 to CH 10180
8410a8f8-ad55-4585-adb7-040211eef571 |  | checklist-sectioned | pass | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-079 - Zone 7 East - Layer 2 Capping - CH11220 to CH11360
6a319c22-7ed9-49d8-b226-83dc4eb79676 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-080 - Zone 7 East - Capping 1 - CH11300-CH11320
272e86f9-3b24-498d-b592-1da89c3fcb08 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-082 - Zone 5 Aitken South - North Section - 1 Layer 240mm - CH60520-CH60410 - SB
15e7b08e-33dc-45f7-b789-c9cf7ad9dc5a |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-083 - Zone 5 Aitken South - South Section - 1 Layer 240mm - CH60410-CH60280 - SB
bcb33345-5aa7-4893-9d70-d53512559ce9 |  | checklist-sectioned | pass | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-085 - Zone 7 East Capping 2 Deb-Van 11360-11480
2480cc2d-c6f8-4395-ab86-689f5f2214b3 |  | checklist-sectioned | pass | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-086 - Zone 7 East Capping 1- Deb-Van 11360-11480
25a385d0-3903-4c25-9a3a-efca49fcf741 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-087 - Zone 7 East Capping 1- Deb-Van 11112-11130
d8c8f8fc-9806-46f0-a52b-a6a7878c373e |  | checklist-sectioned | not-started | b7cb0cf9efc509c90d83237c1d1cea20b778a590f459a87adac2d20b5ccea60e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-088 - Zone 6 Temp pavement Capping 1- 12730-12790
dc8cb1e4-6106-4da9-bb2d-5beac9b38054 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-091 - Zone 5 Aitken North - Upper Half - Layer 1 - CH60860-CH60940 - SB
90d68727-9bd3-4cdf-86e9-ea3f28859578 |  | checklist-sectioned | work-in-progress | 9a2b0bc1a77eefa7d12dd417df9d1af343c63ade557e4d348705d734c0900866 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-092 - Zone 5 Aitken North - Upper Half - Layer 2 - CH60860-CH60940 - SB
f43afab4-976e-4a37-956e-db6a78cef5b8 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-093 - Zone 7 East Vantage CH11650-11820 - Layer 1
f1bdf10f-5e89-4d2c-909d-5d0740123a7f |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-095 - Zone 7 East Stage 2 - Mickleham to Debonair CH20545-20770 - Layer 1
fef6196a-b15f-4b2d-a6c1-4255e6963002 |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-096 - Zone 7 East Stage 2 - Mickleham to Debonair CH20545-20770 - Layer 2
6a359714-b88b-42f1-8273-68ce32e98877 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-097 - Zone 7 East Vantage CH11880-11970
d019b5ff-9e55-412c-b194-31638da3420a |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-098 - Zone 7 East Vantage CH11750-11840 - Layer 2
bfd3cdb2-7845-4b23-8650-32e57790fe68 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-100 - Zone 5 Aitken North - South Section - Layer 1 - CH60600-CH60740 - SB
a78c486e-4993-40ea-b903-7b9b17aa8669 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-101 - Zone 5 Aitken South - SE Corner - Layer 1 - CH60508-CH60531 - SB
4e76567e-b1d4-4fb5-8787-2d5bf28547c1 |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-102 - Zone 7 West Stage 2, including Bridging Layer (CH20390-20470) - Layer 1
329d54c7-9e20-4c77-bd62-9d5807ea9f3f |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-103 - Zone 7 West Stage 2, Narrow Section (CH20240-20390) - Layer 1
9ab9df7f-94cf-4bff-aa9b-5e13227ac6d6 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-104 - Zone 7 West Stage 2 CH20240-20470 - Layer 2
c05ffc45-51a3-4c70-8be4-df381aa1d521 |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-105 - Zone 7 East Stage 2 Gate 7.14 Layer 1 (CH20720-20760)
8881198e-7931-4d00-a9c6-f4c6a04d2f03 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-106 - Zone 7 East Stage 2 Gate 7.14 Layer 2 (CH20720-20760)
4598edcc-cdb4-42ae-b0b2-809ba94f9653 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-107 - Zone 6 Lime stabilization CH11875-12190
ad2d68c7-1972-4909-967f-b8dcbc59c2be |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-108 - Zone 7 West Stage 2 (CH20240-20380)
4172c71e-c75f-4d3e-8a17-37599caffb60 |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-109 - Zone 5 Aitken North - Mid Section - Layer 1 - CH60740-CH60860 - SB
75c40988-3d8b-4012-a8fd-927ed33d0457 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-110 - Zone 7 West Stage 2 - Far End Layer 2 (CH20170-20230)
7b4c8bdb-7a5b-41ac-ae53-88f2253bbc2d |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-111 - Zone 7 West Stage 2 - Far End Layer 1 (CH20170-20230)
e61afb37-d9bc-4247-8871-1f43739ae17b |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-112 - Zone 5 Aitken South Stage 2 - Northbound Turning Lanes North of Ajana (CH60370-60500)
0babf245-211c-4012-baa2-2c079144afbd |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-113 - Zone 5 Aitken South Stage 2 - Southbound Lane South of Ajana (CH60130-60370)
b65329c3-f447-457a-a77c-db9bf497c04a |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-114 - Zone 7 West Vantage - CH11805-11690
953a0c8e-743a-4655-8df9-1a5dc2a349f2 |  | checklist-sectioned | not-started | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-116 - Zone 5 Aitken South Stage 2 - Ajana Tie-In (CH60354-60344)
27dfd770-044d-4fd7-877e-221294eb3ec2 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-117 - Vantage to champion Centre median
bdef1395-5b48-463a-a6f7-7ea8f95842be |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-115 - West Champion - lime stabilized capping 12300-12180 layer 2
093be6e6-dec3-400f-83df-7111a1689e5e |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-119 - East champion layer 1 - 12320 - 12390
bdee6fb8-e1b9-48fd-a2b5-a8e1d32feda1 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-120 - East champion layer 2 - 12320 - 12390
0bb1955c-7543-454a-8d18-3c669934a514 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-118 - Zone 7 East Stage 2 - Top of Capping Layer CH 20780 to CH 21280
9d499197-6195-44b6-b44e-be2ee57fa462 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-121 - Aitken South Stage 2 - Southeast Corner (CH60500-60550)
0d83f932-0028-4c5b-bdea-a0ce312df1e6 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-122 - West Champion - Lime stabilized CH12400-12450
94f8253d-cd56-4c5b-9a31-d4753dc8da9c |  | checklist-sectioned | pass | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-123 - East Champion - Lime stabilized CH12570-12750
a61cd587-2344-443b-93d1-c4f8fa2f442b |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-124 rev01 - Champion intersection - lime stabilized capping 12300-12320
790a6ed1-b1a0-474a-a26c-8a4aa980915a |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-129 - West Vantage slip lane capping layer 1 11825-11845
33cc3edb-a789-45c0-8924-1823beb4e130 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-126 - capping layer 2 west vantage slip lane 11825-11845
c67019e9-cf85-4149-859a-72cce67d87da |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-125 - Zone 7 East Stage 2 - Top of Capping CH 21280 - CH 21360
99bcd85f-450b-4c18-b58e-2522f3a27bf4 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-127 - Zone 6 Aitken bridge Capping layer 12430-12590
e493d6fb-56a7-4082-ab42-d129db4ca830 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-128 - Zone 5 Aitken North East Intersection - SB - (CH60580-CH60700)
32ba63bb-14ce-4dcb-bc1b-aa2b967f2890 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-133 - Zone 6 Champion intersection CH12300-12320
351a2f1c-bab8-45c7-93de-ae9cedfd3b43 |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-132 - Zone 7 East Stage 2 - Top of Capping CH 20760 - CH 20780
00f96863-be23-4ca0-91c9-3ad5b8218b6e |  | checklist-sectioned | work-in-progress | ITP 0007 - Fill With Material Type A | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-007 - Fill with Material Type A | ITP-007-A2-LOT-134 - Zone 5 Aitken South East Corner - CH13280 to CH13320 - WB
b9368fdf-6672-4116-a126-19062c6330aa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements
1de7bcb6-f55c-4866-ac41-507f444d378a | Child 3 - Testing and Inspection(d9ce69fa-7f4a-5d0b-a12e-7dfa8099ab63) -- Final Inspection - Work Completed On(8263d454-3923-475f-9d2b-0afa53c1b188): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-002 - Mickleham South (NB) CH30020-30234
7152f254-1b58-4a7a-8fd7-674c99d9c29b | Child 3 - Testing and Inspection(7a5ca205-ced1-5b18-a3a7-c08987deeefb) -- Final Inspection - Work Completed On(e818221a-6133-45f1-8927-df866bf0cd1a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-003 - Mickleham South (SB) CH30020-CH30152
6aee3028-e050-42e7-91ad-ba4cc0a87e57 | Child 3 - Testing and Inspection(b03d4b01-44c1-51fd-896e-634611dbf39d) -- Final Inspection - Work Completed On(ac3ddda9-4234-43d6-8ee8-a5d2d02e7115): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-004 - Mickleham South (NB) CH30234-Ch30316
08a95298-5719-4e60-bb1c-6157ce159943 | Child 3 - Testing and Inspection(e784dedc-9076-525f-aed4-615db9ddde1b) -- Final Inspection - Work Completed On(ebecc599-bf4d-4c49-856a-f5830d562cbf): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-005 - Mickleham South (SB) CH30152-CH30316
a33506e5-9ba1-4ab6-8de0-157a730edbb7 | Child 3 - Testing and Inspection(f2a6eaf3-9c7e-579a-9fdc-8a3e36996e73) -- Final Inspection - Work Completed On(c9dfc0a1-cf0f-4658-bd45-ef840ae65fff): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-006 - Mickleham North (NB) CH30520-CH30665
a69f8ecf-8ee7-445e-b468-188d8653e329 | Child 3 - Testing and Inspection(1c3724a2-3a50-5800-8da8-247de1c1572a) -- Final Inspection - Work Completed On(b9e682ed-0089-4d8e-a44d-c9c95d81a44c): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-007 - Mickleham North (SB) CH30520-CH30665
c2c601ed-50e2-4fe6-9d44-4a207c51556e | Child 3 - Testing and Inspection(0c60e5d8-60be-5335-a528-ee38d7885b9a) -- Final Inspection - Work Completed On(f6b916d5-9830-4afd-83ab-90dfe320ef6f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-008 - Mickleham North (SB+NB) CH30665-CH30800
a5734bf4-a36c-4965-8e2a-4398cb67ebd5 | Child 3 - Testing and Inspection(b52c3b7a-f319-5d46-b62e-7a40590669b8) -- Final Inspection - Work Completed On(ec83462e-7d03-4fef-82e6-d359f001d6ef): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | b758f319a16b17d89ae935a1304a0349ad1413449367c1c714b710861a21589b | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-009 - Zone 7 West - Occo Works (CH20040 - 20170)
0e2023d5-cde8-457f-9c0f-8b4acf008201 | Child 3 - Testing and Inspection(e6ccecb7-5bf5-5693-b92d-e6c3c600758f) -- Final Inspection - Work Completed On(a4e3ab6c-ac49-4fc8-850c-4687dcfed3bf): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-010 - Mickleham South (NB+SB) CH30316-CH30400
4d488fec-7c1f-4ee5-900c-4807ae5ddd07 | Child 3 - Testing and Inspection(482c546d-9450-532c-b287-fb6ec6b6bc5d) -- Final Inspection - Work Completed On(21942de8-cab4-4f57-9dac-cd986a632f7d): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-011 - Mickleham North (NB) CH30430-CH30520
8e75b99d-5e08-41fd-b112-2332bd17184e | Child 3 - Testing and Inspection(417427d1-08ed-573d-8b23-cc256406c213) -- Final Inspection - Work Completed On(d2c04d44-007b-41e5-b5a1-c8d5c2f83662): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 136525aea3da0b5f9d4c3cffea917dc27e35a5cb2a46b3f71c4449a6d6ac0a8e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-013 - Zone 7 East (Gate 7.3-CH10650) (Class 4 Placement)
ee893eb0-4225-4bf5-8468-3dfd9b3dad1b | Child 3 - Testing and Inspection(e99bc3e4-f591-5d02-890b-585a5baf3035) -- Final Inspection - Work Completed On(1d22696f-6072-49b1-bfd0-35938a101031): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-015 - Mickleham North (SB) CH30435-CH30455
10e8972e-7dbf-4c83-afe2-325122c91607 | Child 3 - Testing and Inspection(3d62152e-324f-5135-a3a1-fe4c2b601bcd) -- Final Inspection - Work Completed On(c89a9689-e631-40d8-8d89-e5b99cc09ca3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-017 - Mickleham North (Type 6) CH30785-CH30820
dc9b832d-8438-4c87-9d06-c45f8fa28334 | Child 3 - Testing and Inspection(7a14a532-7fe1-504a-85c5-9629fb5b6972) -- Final Inspection - Work Completed On(ebc39bd3-2fb0-4d87-87b8-6168804e47fe): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-018 - Mickleham South (Type 6) CH29980-CH30030
382d627d-b78a-4984-b99c-3d832b05639c | Child 3 - Testing and Inspection(e5c452c2-abc9-5720-a004-0a3322828987) -- Final Inspection - Work Completed On(369f4758-e63f-4937-85ce-04a33e3c79c4): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-021 - Mickleham North (SB) CH30450-CH30520
a80f8521-4032-43a1-9b66-4c0a66e3d793 | Child 3 - Testing and Inspection(5a4485b8-5a62-59c4-a5f3-ce14910356b8) -- Final Inspection - Work Completed On(b4f47f02-bdd1-431a-98a5-b2e471865fd9): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-022 - Mickleham Rd Intersection (EB) CH30400-CH30430
e7d500ac-bf48-4dee-8c82-9346ed3a4abc | Child 3 - Testing and Inspection(5ee9a16d-fdb4-5f80-8de5-154197a0d6d4) -- Final Inspection - Work Completed On(4f4b368a-342e-4a28-bf9a-cdac22c8c2bf): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-024 - Mickleham Intersection (SE Lane +Slip Lane) CH10550-CH10600
419cfb84-4892-4f67-9c62-a998e1bfdaaa | Child 3 - Testing and Inspection(bedc665f-66e5-5c49-87d4-76b2b363940f) -- Final Inspection - Work Completed On(06123ee9-1683-4c1a-b6d3-d7e42df0d2f1): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-025 - Mickleham Intersection NE (North- Eastern Slip Lane) CH20540-CH20560
f58a8d06-7cce-4b83-b74d-15c6e26e4771 | Child 3 - Testing and Inspection(0bd15582-3cfc-5fc2-b6fa-3152ea5e94fa) -- Final Inspection - Work Completed On(d241d022-0e33-4862-bc58-21d7a7b4ca63): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | bcd724515c44012b129261981080ad0c1529fd88c9af44adec1055af610abec1 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-026 - Mickleham Intersection NW (North-Western Slip Lane) CH20470-CH20490
6baf2970-9345-4dee-9a02-1213865f2be0 | Child 3 - Testing and Inspection(748c3189-203e-5063-a25a-e9403e748a21) -- Final Inspection - Work Completed On(b3a8f86d-530c-42f1-b69a-8afe4866007b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 0603a3910982b4c8534f7b48b97157a31cce01cf6ed486b7827948460f9f5c92 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-027 - Zone 7 East - Occo Works (CH10580 - CH10650)
263fe0dc-6709-472a-a2e2-347938cfe5a2 | Child 3 - Testing and Inspection(9ee12367-95a7-5c11-9701-17c61f06183f) -- Final Inspection - Work Completed On(356d2f64-311a-4076-b085-47862344d771): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 74b9bccd580909645594f86ee247f0eef544e43ced71ad13845292e1a9e54b75 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-028 - Zone 7 East - Occo Works (CH10650 - CH10870)
34857904-8cf1-4f7c-bc39-c7c37dd51aab | Child 3 - Testing and Inspection(14bfb588-c92f-5fb0-a79f-ff755c8c8736) -- Final Inspection - Work Completed On(df6bd7c2-cdd5-40b4-991d-08c4716ecd39): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 136525aea3da0b5f9d4c3cffea917dc27e35a5cb2a46b3f71c4449a6d6ac0a8e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-029 - Zone 7 West - Occo Works (CH10035 - 10050)
8efbc116-baae-49ac-863d-7361e84c6c73 | Child 3 - Testing and Inspection(dc403952-5998-5650-8ac4-106c7f620884) -- Final Inspection - Work Completed On(17a64d0a-68ca-4cec-8e19-413b44a68d9f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 136525aea3da0b5f9d4c3cffea917dc27e35a5cb2a46b3f71c4449a6d6ac0a8e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-030 - Zone 7 West - Occo Works (CH10000 - 10035)
213b18d0-753e-4b7d-b940-b623bc1973d2 | Child 3 - Testing and Inspection(08213583-3eb5-56cc-86f1-d3fdfa419998) -- Final Inspection - Work Completed On(45495fdf-d4ed-404a-874c-d010f6552a26): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 136525aea3da0b5f9d4c3cffea917dc27e35a5cb2a46b3f71c4449a6d6ac0a8e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-031 - Zone 7 West - Occo Works (CH10000 - 10040)
0035dff9-9b03-4233-85ba-74849c614b00 |  | checklist-sectioned | work-in-progress | 147515011a107572911271f8cc1b7a519dbc96a4ab646a5a86edc2b71f208aec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-032 - Zone 7 East CH10950-CH11190
f89eb352-5c6f-4b16-8ed2-8df6a99b0dd7 |  | checklist-sectioned | work-in-progress | 147515011a107572911271f8cc1b7a519dbc96a4ab646a5a86edc2b71f208aec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-033 - Zone 7 East CH10920-CH10950
c2e0e7a8-ba37-4da4-a216-11c285d6a1b6 |  | checklist-sectioned | work-in-progress | 147515011a107572911271f8cc1b7a519dbc96a4ab646a5a86edc2b71f208aec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-034 - Zone 7 East CH10920-CH10850
ca100d9e-ac4c-46e0-a684-1788520f95af |  | checklist-sectioned | pass | db4e340540cfdb954492ced657deb448fcbb5ac7243d473ec81c6604efeb92a9 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-035 - Zone 7 West CH10250-10400
fe0acb97-2610-4def-b465-7bb81f7ff508 |  | checklist-sectioned | work-in-progress | 366ab13a67d5eabb4c7479773b24464b3873ca3805496f91621b89b715ac3dbf | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-037 - Crushed Rock Layer 1 - Mickleham Intersection NW - Type 16 Pavement (CH30439-30473)
5fda42f0-bc0d-43fa-829d-94f369fa6504 |  | checklist-sectioned | work-in-progress | 366ab13a67d5eabb4c7479773b24464b3873ca3805496f91621b89b715ac3dbf | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-038 - Crushed Rock Layer 2 - Mickleham Intersection NW - Type 16 Pavement (CH30439-30473)
e081ba6f-2dec-4d63-bfe5-bfd6be9f6343 |  | checklist-sectioned | pass | 77fc70ecb022a104a72515ce3e81440e128324c92045f9307f8256755e95e636 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-040 - Zone 7 West - Wedge + U-turn Lane
82b51209-e566-4046-b7d1-6038c1c24113 |  | checklist-sectioned | work-in-progress | 2c4311c3d7cb32cd86be0e317e3419f4e533bf00bab41db1237d57f07c7305a5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-041 - Zone 7 East Capping 1 CH11300-CH11360
1e5c4372-6e5a-4148-aa81-e1344ad618b4 |  | checklist-sectioned | pass | 77fc70ecb022a104a72515ce3e81440e128324c92045f9307f8256755e95e636 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-039 - Zone 7 West SW intersection + Slip lane
85f8ca6a-2eae-4367-b391-912327cc9798 |  | checklist-sectioned | pass | 85d5cce5bcf0cfce046b8100e63efdbe642a82734184e1fdcf78a63c0ead0d04 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-042 - Zone 7 East Class 4 1% Cement L1 CH11250-CH11360
97dd8a07-ea28-45e2-b3d7-db807bcb707f |  | checklist-sectioned | pass | 85d5cce5bcf0cfce046b8100e63efdbe642a82734184e1fdcf78a63c0ead0d04 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-044 - Zone 7 East Class 4 1% Cement L1 - CH11210-CH11250
7e089888-5e15-44dd-aa77-0b62de76dd8f |  | checklist-sectioned | work-in-progress | 2c4311c3d7cb32cd86be0e317e3419f4e533bf00bab41db1237d57f07c7305a5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-046 - Zone 5 Aitken South - North Section - Class 4 L1 - CH60520-CH60410
678fa5b9-2602-4b77-b5d9-1c0b716c07dd |  | checklist-sectioned | work-in-progress | 2c4311c3d7cb32cd86be0e317e3419f4e533bf00bab41db1237d57f07c7305a5 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-047 - Zone 5 Aitken South - South Section - Class 4 1% CT L1 - CH60410-CH60280
deeb6f4d-ece7-496f-b08c-5ccf04798eba |  | checklist-sectioned | work-in-progress | 85d5cce5bcf0cfce046b8100e63efdbe642a82734184e1fdcf78a63c0ead0d04 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-045 - Zone 7 East CH10780-CH10840
ecf319c1-3123-4f5b-9a3f-644a43a1d089 |  | checklist-sectioned | pass | 85d5cce5bcf0cfce046b8100e63efdbe642a82734184e1fdcf78a63c0ead0d04 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-049 - Zone 7 East (WB) -Type 15 - CH11112-11130
c5231fb9-5100-4a47-88be-2102afe7c479 |  | checklist-sectioned | work-in-progress | a415c53b3e26cb5f755b32dffaac6400570a9d4597568e83d60f1bd1ed2ea104 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-050 - Zone 5 Aitken North - Upper Half - Layer 1 - CH60860-CH60940 - SB
aec1de78-269a-4611-9609-51feee2741b7 |  | checklist-sectioned | pass | b63377c694fee8e52f7aa5b055e102df3a7dce22a453af5a198165d0c3111969 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-051 - Zone 7 East (WB) -Class 4 CH11360-CH11700
ffbebaab-8335-4448-ad97-af8ceda9864f |  | checklist-sectioned | pass | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-052 - Zone 7 Vantage -Class 4 CH11750-11970
3eaa9b14-ead9-49d5-b3c8-7cfa4a62d704 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-053 - Zone 7 East Stage 2 (CH20545-20750)
bd76570f-a696-427f-b670-4432c5a18bca |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-054 - Zone 7 East Stage 2 Rework (CH20720-20760)
f06bbb93-c069-4041-9933-285c3125680c |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-055 - Zone 7 West Stage 2 (CH20360-20480)
4cccdab7-ef35-45bf-9222-17dcd5800228 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-056 - Zone 5 Aitken North - Mid Section - CH60740-CH60860 - SB
c58095c0-fb75-4d82-8164-ed9263497e9a |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-057 - Zone 5 Aitken North - South Section - CH60600-CH60740 - SB
1a72f1c1-ebb2-4261-a8c5-45ffca482f22 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-058 - Zone 7 West - Stage 2 - Mid-Section - CH20230-CH20360 - EB
ee64b108-655f-4a92-b7b1-f7339c752c9a |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-059 - Zone 6 - Vantage East - CH11900-CH12180
8c4d9d0d-3808-4aa1-9f8f-892cc7677361 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-060 - Zone 7 West Stage 2 - 750-760 Craigieburn Rd (CH20170-20230)
6af8ef2a-87b9-4381-a005-853cc0f594f9 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-063 - Zone 5 Aitken South Stage 2 - Southbound Lane South of Ajana (CH60130-60370)
1d408f7e-740c-4c9e-9150-2dc096aa507e |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-065 - Zone 5 Aitken South Stage 2 - Ajana Tie-In (CH60354-60344)
f7591544-a465-4afb-960e-864c933a6963 |  | checklist-sectioned | not-started | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-061 - Zone 5 Aitken South Stage 2 - Northbound Turning Lanes North of Ajana (CH60330-60510)
5796022c-df63-4b03-98dd-ef07d9c073a7 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-064 - Zone 6 S1 Champion to Vantage - 12170-12290
14270b88-7de9-4442-81ef-051772914310 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-066 - Zone 7 West Vantage 11630-11820
b9ac44b7-b7ad-40d6-8284-4cfdb3146f46 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-067 - Zone 5 Aitken South Stage 2 - Southeast Corner (CH60500-60550)
0e096bc6-297e-458d-8139-cc10762f0af9 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-068 - Zone 5 Aitken South Stage 2 - SW Corner Island
3236eaf7-8081-4422-b1ba-9b032aea7aa5 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-069 - Zone 7 East Stage 2 (CH20890-21200)
2a052808-01fd-4a70-b7bb-8ee8326b0d75 |  | checklist-sectioned | work-in-progress | 4672bc8bddaa4f84f56a140ea93452542c901c9033b72f687574c09d1f204404 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-070 - Zone 5 Aitken South Stage 2 - SE Corner atop Drainage (CH60530-60545)
4451859d-766a-4aed-ac37-1cf1c65bcb5b |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-071 - Zone 6 Champion Parade CH12290-CH12350
404b299b-4842-422d-a550-f297452335a6 |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-073 - Zone 6 Champion Parade CH12500-12750
34aa47db-95f1-4924-8137-20e13a603b8c |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-074 - Zone 6 Champion Parade CH12350-12440
19082282-2d3e-4c18-8b9a-f37b1a31788b |  | checklist-sectioned | work-in-progress | 24d60fed06d600ed17880bb45e05099c15ada50f3fc4f4ffb22144e84a3b572e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-075 west vantage slip lane 11830-11870
2531490b-6343-476f-8acb-a67e16cceaec |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-076 Zone 6 CL4 Bridge CH12440-12490
38ef73d8-6b14-40c8-9556-7d948baf0ff6 |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-077 Zone 6 CL4 Bridge CH12490-12590
ccaaa353-d5b4-4a15-9fdc-1adf431129c0 |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-072 - Zone 7 East Stage 2 (CH21200-21300)
a577dfe3-e2c7-435a-84f6-f27ce670ef39 |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-078 - Zone 7 East Stage 2 (CH20760-20890)
e7047450-a250-4f1e-89a0-358d5ac63a81 |  | checklist-sectioned | work-in-progress | ITP 0009 - Unbound Pavements | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-009 - Unbound Pavements | ITP-009-A2-LOT-079 - Zone 6 Champion intersection
2427bb70-6993-4367-b393-5f919d1b3f28 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage
938472d8-0c6c-42bf-9259-6eb67cc9119d |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-001 - Mickleham South CH30070-CH30234
ff49d6c1-8721-480e-88b2-c69ef75ecb33 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-002 - Mickleham South CH30234-CH30316
856d772e-0e29-4726-8a3d-b48b85b18005 |  | checklist-sectioned | work-in-progress | ea1f0a0371d2ca4159a2698a042aa65be9aa98e8c8dbf24f615175c88b9aa989 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-003 - Mickleham North Southbound ( CH 30520- 30785)
d3eef4cb-98b0-4f8e-a99e-ce61b3f63ef2 |  | checklist-sectioned | work-in-progress | ea1f0a0371d2ca4159a2698a042aa65be9aa98e8c8dbf24f615175c88b9aa989 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-004 - Mickleham North ( CH 30520- CH 30785 ) NB
fd27ee46-4b0b-48df-a25f-daf5a20be809 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-005 - Mickleham South CH30316-CH30370
bfd39949-6ffb-46cc-b21f-008cac14a6a6 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-006 - Mickleham South (CH30316-CH30370)
3122fd78-dd83-4ad0-860f-fa8cbc24de5c |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-007 - Zone 7 West of mick Rd ( CH 20070- CH 20175 )
1cbbcb98-ba74-46da-919d-aec95a237aad |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-009 - Zone 7 East (CH 10600- CH 10780)
b00df914-ab59-48d6-9890-1471bb51030e |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-011 - Zone 7 East (CH 10780 - 10850)
62c1b922-1515-41b2-9e8d-ae100c55e91c |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-012 - Mickleham North - Pavement 6 (CH30785-CH30845)
17ae9214-f1d1-44e8-9aac-43e6ad67aedc |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-013 - Mickleham Intersection - SE Traffic Island (CH10550 - CH10560)
48592111-7497-4882-ba4c-5764a2a07259 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-014 - Zone 7 West CH10000-CH10180
ee25dd65-c1d9-412d-88a0-12f125b28e52 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-015 - Mickleham North (SB) + NE Traffic Island (CH40500-CH40360)
b0036973-8ef6-44c6-800b-2a81699904a1 |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-016 - Mickleham South CH29980-CH30070
44b2cae4-6de8-4dcd-b762-411239c255fe |  | checklist-sectioned | work-in-progress | 794c74779a411f55111d500e159ba31cfce37048b907bac2840511c6da010dfd | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-017 - Mickleham North CH30430-CH30520 NB
fd597ddb-15d3-43e3-b3a2-16d4d119811a |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-018 - Mickleham Intersection CH20475-CH20500 NW Island
f401f92d-6ab6-439e-b74c-cbd65d1c6286 |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-019 - Zone 7 East WB - CH10850 to CH10950
f80f75f1-e802-4e9a-8eef-1bd6e9b5e13e |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-020 - Zone 7 East WB - CH10920 to CH11020
a03efad1-d8de-47b4-8855-959be633bd9e |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-021 - Zone 7 East WB - CH11070 to CH11140
5f99fbb7-7e1d-44ca-ac79-2d70fa19e3e3 |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-022 - Zone 7 East WB - CH10880 to 11020
ee256847-5e3f-4682-bfa6-2b2d10fd4def |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-023 - Zone 7 East WB - CH11020 to 11110
69985a63-c178-49f7-b35c-e504c2c3ad86 |  | checklist-sectioned | work-in-progress | ac5443a868c29a599af7024ef2f306e1f141558a0b9e0f031312037cf66242cb | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-024 - Craigieburn Rd WB - CH 10840 - CH 10910
888b2665-5196-4bb0-bda0-cde8886b7961 |  | checklist-sectioned | work-in-progress | 31441229c4d7ccc22762648add154d895de5c8ba3d08b303668609990e885e80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-025 - Zone 7 West WB Verge CH10220 - CH10280
d60cdc82-5379-4395-ae96-477bc743e3c4 |  | checklist-sectioned | work-in-progress | 31441229c4d7ccc22762648add154d895de5c8ba3d08b303668609990e885e80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-026 - Zone 7 West WB Verge CH10280 - CH10380
e43020ab-fc63-4d9b-a78c-cc25eb48b267 |  | checklist-sectioned | work-in-progress | 31441229c4d7ccc22762648add154d895de5c8ba3d08b303668609990e885e80 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-027 - Zone 7 West WB Median CH10220 - CH10380
c42ee120-d1a8-49ee-a6f3-1e81622c5ba0 |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-028 - Zone 7 West Verge +Median CH 10380 - CH 10470
9c3027e3-2849-47f1-8c5e-76898f8d0bda |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-029 - Zone 7 West - SW Slip Lane
c813500c-bb50-488c-96f7-51fc699ab699 |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-030 - Zone 7 West - WB Verge + median
03402785-4bd0-49ec-ba32-1a8da4f9cc02 |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-031 - Zone 7 East - Subsoil drainage
7ad2a0f6-9b8f-4fc2-83de-2f0193b2f854 |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-032 - Zone 7 East - Subsoil drainage CH11250 to CH11100
b723bc5d-4da3-44ac-926e-8b9209df5011 |  | checklist-sectioned | work-in-progress | 7a173f71e9a2845c0e8d6d3bf42810b5110aacb90fccc33c55d9096871834422 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-033 - Zone 5 Aitken North Verge + Median - CH60830-60940
4b8011fd-ce62-4050-b875-1ac6ee7908c6 |  | checklist-sectioned | work-in-progress | adeacda5b483d9474dd4dce42a03aa9f2372eabe8ebe108346f8058b0a4aa5fe | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-034 - Zone 7 East Deb to Vant Stage 1 - Install SSD (Verge + Median)
781f2ef0-041b-4491-8f21-2cf581e5fe7f |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-035 - Zone 7 East Deb to Vant Stage 1 - Install SSD (Verge + Median) 11560-11670
e428f888-add8-4f47-8058-886607e86961 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-036 Zone 7 Vantage Install SSD 11850-11950
632c3d9b-9805-4b07-902f-3820fac8cc0e |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-037 Zone 7 Vantage Install SSD 11750-11840
24826f20-ba2e-44a8-b14e-ef3f83405827 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-038 Zone 7 Vantage Install SSD 11870-11900
39b0f99c-75c5-44be-9c89-ed11813e56c2 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-039 Zone 7 Vantage Install SSD 11825-11850 western median design change
f72f8d5b-1bc2-44e0-8a78-9a3f53537fee |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-040 - Vantage intersection
b894c194-d506-4cf5-a7c6-9b0cf682d9de |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-041 - Zone 7 East Stage 2 (CH20655-20725)
99496667-1e0d-4d7f-97d0-782504fadabb |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-042 - Zone 7 East Stage 2 (CH20545-20750) Median + North Side
a8967660-e534-499d-b58d-3cb8e78bda3f |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-043 - Zone 5 South - Southbound Carriageway (CH60522-60354)
27a7d29b-b45c-41c7-b397-5d602158dbf0 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-044 - Zone 7 East Stage 2 (CH20720-20760) Median + North Side
2a625179-2524-457b-a16c-cab287f1702d |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-045 - Zone 7 West Stage 2 (CH20403-20474) North Side
5f3b8219-e18b-4f09-bc03-d03565128cce |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-046 - Zone 7 West Stage 2 (CH20377-CH20427)
ac1525c3-2faf-4d15-a058-2ba7a49d8223 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-047 - Zone 5 Aitken North Middle Section (60840 - 60760)
30373e67-0915-42c9-8d89-7fd841b1f8ae |  | checklist-sectioned | not-started | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-048 - Zone 7 West Stage 2 (CH20230-CH20380)
42c998fb-4f81-49dd-a7da-dd7705a477a2 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-049 - Zone 6 Vantage East (12110 (S) and 12080 (M) - CH12180)
4560e04a-3151-4cd1-b1b2-267e0cb2eb78 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-050 - Zone 6 East Vantage (12110 (S) and 12080 (M) - 11880 part 2
a2cb371a-d991-41ad-8815-6f65e9724751 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-051 - Zone 7 West Stage 2 - 750-760 Craigieburn Rd (CH20170-20230) - North + Median
a83b0d37-4171-4aab-a489-3a8d7596dff5 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-052-West champion ssd 12030-11950(pit 606)
9778d9b3-4a57-4394-b83c-009a7d821b48 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-053 - Zone 6 west champion (11900-11950(pit606))
e4ae1819-090f-4dcb-8018-79fa13b64902 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-054 - Zone 5 Aitken South - Pavement Interface North of Ajana - CH50340 to CH50500
58261db6-dd16-4da7-8286-c914708a90b3 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-055 - Zone 5 Aitken South - South of Ajana - CH60320 to CH60200
ea1b3ae6-fa2f-4801-bee2-811f0fcbe6f1 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-056 - Zone 5 Aitken South - South of Ajana and Median - CH60320 to CH60200
d82378e7-7b7a-480d-af00-a5a8a53c9cb5 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-057 - Zone 5 Aitken South Stage 2 - Ajana Tie-In - CH60354 to CH60344
2489d859-143f-4abd-85ba-7eaf12376ba4 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-058 - Zone 6 West champion 12145 - 12295
b285eec8-0399-4401-ad83-42d97a099c96 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-059 - Zone 5 Aitken South Stage 2 - SE Corner Interface (CH60500-CH60540)
eaeb428a-fd31-4c7e-b887-73ed09689290 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-060 - Zone 7 West Vantage 11650-11820
f48a5fd1-5838-4be6-bc67-c7502561f672 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-061 - Zone 5 Aitken South Stage 2 - PT6, SE Corner
b567f92f-1499-4b95-9357-8e19d9e32c48 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-062 - Zone 7 East Stage 2 - Median (CH20780-CH20900)
285c88f4-39de-4f0e-89b1-d66557226386 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-063 - Zone 7 East Stage 2 - Median (CH20900-21020)
02ba3a31-af08-4fde-bd44-b7afb369ed21 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-064 - Subsoil Drainage West champion SSD near slip lane 11800-11850
1fbe906b-0cf8-4b5a-a704-28c07e85f8df |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-065 - Zone 7 East Stage 2 - Median (CH21020-21140)
3516707c-b59c-443e-9032-a785d14b2372 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-066 - Zone 6 Median - CH12530-12750
c9ccb288-9871-4909-8a69-8ba96272cee0 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-067 - Zone 7 East Stage 2 Median (CH21140-21270)
18bf37b1-2b46-4ed8-b5b4-ea4c175f28df |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-068 - Zone 6 Champion intersection - CH12290-12450
b80d6309-64e5-49bd-bec4-476b45e07eb7 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-069 - Zone 7 East Stage 2 - North Verge (CH21120-21255)
0dd54d58-fc50-4900-a3f3-9b775f28d8b6 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-070 - Zone 7 East Stage 2 - North Verge (CH21020-21120)
4efe370e-502c-45d9-91a7-7f91e74979bd |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-071 - Zone 7 East Stage 2 - North Verge + Crossings (CH20780-21020)
d58f1a27-1804-4745-8162-6af9cc9cd1d9 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-072 - Zone 7 West Vantage - Traffic island (CH11832-11844)
595ca9a7-acd6-46c5-b777-04d4469a71c2 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-073 - Zone 6 Road crossing CH12350
cd85f6d5-20d8-4700-aa7c-81a6eb2a3580 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-075 - Zone 7 East Stage 2 - North Verge + Median (CH20760-20800)
baa6c794-801a-4bd1-84af-5caba0651da9 |  | checklist-sectioned | not-started | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-074 - Zone 6 Aitken bridge 12430-12540
f4be6bdc-7bf3-4b00-840e-f3fa9cbe4055 |  | checklist-sectioned | work-in-progress | ITP 0010 - Subsoil Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-010 - Subsoil Drainage | ITP-010-A2-LOT-076 - Zone 6 Champion intersection CH12250-12330
89f2fc9b-14e6-423d-8641-423f10775195 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock
f6912197-b1cb-43b2-b712-7ebce6cb06d0 | Child 3 - Testing Requirements(83964288-eece-5116-82c4-61e694372d72) -- Final Inspection - Work Completed On(11876eba-85b6-4131-829b-78202f1f5cc8): checkpoint-no-status has incorrect meta.stepType checkpoint-status Child 3 - Testing Requirements(83964288-eece-5116-82c4-61e694372d72) -- Final Inspection - Work Completed On(9cfe455d-cfd0-4fc6-b03d-152108e22c0a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | e4b8c847746288a710b8cca7dd24241890291a2202938528d9ad7b7fe8f3c5de | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-001 - Mickleham South CH30070 - CH30234
1a43e680-28c7-4bbc-9acb-a08ac18f98e3 | Child 3 - Testing Requirements(8e668f06-5f84-5af4-b3e8-ca03aa4c64c5) -- Final Inspection - Work Completed On(bbe6d648-5546-4103-b83f-6707dbb88af7): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-002 - Mickleham South CH30000 - CH30200
22f02519-a451-42ae-9fd7-718eb9bb10f7 | Child 3 - Testing Requirements(34d446b2-abe8-595d-9ab7-f8b47d1c3d66) -- Final Inspection - Work Completed On(fdf1481a-a09f-41bf-a655-7a752158a356): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-003 - Mickleham South CH30234 - CH30316
0de5757d-3a59-49da-a175-89020b53f3ae | Child 3 - Testing Requirements(19f08ac7-d198-59c1-abf6-a54728a04c69) -- Final Inspection - Work Completed On(5290ad48-acfe-41ac-8023-94a33c5373ff): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-004 - Mickleham North (Northbound) CH30520 - CH30665
a176bfb1-a82a-4a02-9198-34b120e5d5cb | Child 3 - Testing Requirements(a62450ab-005b-5f6f-84be-77d5f59c16fb) -- Final Inspection - Work Completed On(f82452b3-43e9-490b-911e-b7234ddadd05): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-005 - Mickleham North (Southbound) CH30520 - CH30575
a36cff26-e6e2-4e68-b82d-649f5cd32ea1 | Child 3 - Testing Requirements(e5252fd1-df6a-591b-9743-23cd034e39bc) -- Final Inspection - Work Completed On(89f142e8-2821-4aea-86d3-ae4008dbc605): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | dac60c7c1c459af65250c1a3522d4f6ecdca414d5ec5a99594c65843155aeafe | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-006 - Mickleham North CH30665 - CH30820
bc23f36b-f339-4b15-a1bc-ef4e1d1e2227 | Child 3 - Testing Requirements(eb9e0fe2-b14e-5314-8fb5-440104a9293d) -- Final Inspection - Work Completed On(e67273ef-4eed-4dbc-bd49-95b91d828ba9): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-007 - Mickleham North CH30575 - CH30665
fbbbe0d5-6785-4fbc-a084-e37e6af38c79 | Child 3 - Testing Requirements(74e26afa-6c77-5222-8c03-455a118a3243) -- Final Inspection - Work Completed On(60f2df03-5bc5-4d74-bfd6-337ecbb3857f): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-008 - Mickleham South (NB) CH30316 - CH30400
8eefe6e2-bb9b-41a8-a012-bccac796165f | Child 3 - Testing Requirements(d7b4867b-ca86-5419-9f59-8f5a6d887ef1) -- Final Inspection - Work Completed On(8ff63efc-d597-4e94-9c35-d12afd3c5589): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-012 - Mickleham South CH30316 - CH30375
9b41e6ff-d2b8-4481-b06e-5185da54823a | Child 3 - Testing Requirements(96f29dc7-dd30-5fae-8b88-6221d4226483) -- Final Inspection - Work Completed On(a9ad3da8-d992-48db-abb1-3e7fc8495de3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-013 - Mickleham North (Northbound) CH30430 - CH30470
e58d879d-3663-4664-b241-7502b778c520 | Child 3 - Testing Requirements(a685d723-ec43-509a-8504-95d411d7be71) -- Final Inspection - Work Completed On(96c521d5-2aaf-4c3a-abc3-4eea157891f3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-014 - Mickleham North (Southbound) CH30400 - CH30520
ea191adb-8ab7-449a-b9a9-60acf582271a | Child 3 - Testing Requirements(86a5c7ee-73d3-5e02-b565-b211ac1780bd) -- Final Inspection - Work Completed On(202d53e1-61c9-4b2f-a781-02819357a0d5): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-015 - Mickleham North (Northbound) CH30470 - CH30520
71ac7024-5110-4e32-94f7-07e5ec52eb02 | Child 3 - Testing Requirements(86fac040-9d97-5f94-95ca-d578e6995f1f) -- Final Inspection - Work Completed On(2a25be73-d91d-41ab-a970-2879922b9331): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-016 - Mickleham Intersection CH30400 - CH30430
61a9581f-ddff-41ea-a468-66b9d98103d0 | Child 3 - Testing Requirements(6b97a37d-a117-5df7-ab19-bed5f7a2458f) -- Final Inspection - Work Completed On(d867f1b7-aaaa-4eb7-be00-4b4a86e1bfe6): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-017 - Zone 7 East (WB) CH10590 - CH10620
8b1001cb-4167-486a-8772-d025b7ae3ea4 | Child 3 - Testing Requirements(58e061a2-8ce9-5892-9fa5-5c579ab43539) -- Final Inspection - Work Completed On(d092bfff-65e5-4641-a934-34b80c77c2be): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-018 - Mickleham Intersection (SE SLIP LANE + WB CARRIAGEWAY) CH10550 - CH10590
ddb3ed7a-a2dc-43d2-9ab8-eec4d712f8b8 | Child 3 - Testing Requirements(be00c9e6-9bdb-5a2f-96e8-4f64023e1f81) -- Final Inspection - Work Completed On(e94bb4c0-27ce-4258-b8ed-878236dacd45): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | ddb5f79eff5bd98b88c9deb1fd1ce1b756304827d9b679ff67176ec7309fb192 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-019 - Mickleham Intersection (NE Slip Lane + East Bound Carriageway) CH20520 - CH20570
8b819354-1522-4d77-8117-ba68bd3deacc | Child 3 - Requirements(a6e933f5-0a34-5166-bfb6-df4f99f20c6a) -- Final Inspection - Work Completed On(f1e1a743-f6bf-45f1-b7c5-cfc671e3f8a3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 177c17df581a968cc2df194630211b7907613ba6f3635e33cfa3f493b6b5c66e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-020 - Mickleham Rd Intersection NW Slip Lane CH20470 - CH20490
9ab162a6-75f2-4f2f-8184-06ac330a67ff |  | checklist-sectioned | pass | 0f9b196fb823ee9afab79a2f52826568f364d3e7abb89b7d6871d617df217a1c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-021 - Mickleham to Debonair CH10940-CH11110
d90babad-009b-4024-bfc8-280158665510 |  | checklist-sectioned | work-in-progress | a9b59d2763cb2f9b7a2c55cf540f21e637938ed492c65349281305733904918e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-022 - Mickleham to Debonair CH10830-CH10940
46cbe2be-34c2-44a8-8ae6-52238d20a0de |  | checklist-sectioned | pass | 39eeea93f5f5d2b9778e8e4d78b3bbacc2593d2d675944c98960361165294c20 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-023 - Zone 7 West - WB lane CH 10250 - CH 10400
8038e1eb-5ace-4056-be4e-724be622ee19 |  | checklist-sectioned | pass | 39eeea93f5f5d2b9778e8e4d78b3bbacc2593d2d675944c98960361165294c20 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-024 - Zone 7 West - WB lane+ Slip Lane CH10400 -CH 10500
2da6e683-1d1d-4fbb-b583-ab1b26a90907 |  | checklist-sectioned | pass | 39eeea93f5f5d2b9778e8e4d78b3bbacc2593d2d675944c98960361165294c20 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-025 - Zone 7 West CH 10170 to CH 10250
488912c2-dc78-4ef2-b8a7-0f0e7172bada |  | checklist-sectioned | work-in-progress | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-026 - TBC
d2a02d7d-94f6-47bd-bde7-f86f140271da |  | checklist-sectioned | work-in-progress | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-027 - TBC
675dc514-0fdb-4319-99ba-469c66b59d34 |  | checklist-sectioned | work-in-progress | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-028 - Zone 6 Temp pavement- 12730-12790
7f66b157-184b-4668-a674-570e7e35438f |  | checklist-sectioned | work-in-progress | c70354eee1908637e562114274b56494550b319135133514e8ab1d26966f1b7f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-029 - Zone 5 Aitken North - Upper Half - CH60860 to CH60940
6eff4e13-2978-4b8a-a78e-2e829a4664c6 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-030 - Zone 7 East CH11500-11660
3a9cc667-628e-42cb-80d7-faf26c02527f |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-031 - Zone 7 East CH11360-CH11500
eefe2787-f407-491e-beb1-cec8f2b7542b |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-032 - Zone 7 Vantage CH11870-11970
80cebe83-cf72-4663-8901-65abc12ff2e1 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-033 - Zone 7 Vantage CH11750-11840
f62981a6-85a5-460f-841b-c7144263e27e |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-034 - Zone 7 Vantage CH11870-11890
909291af-fa4b-487b-8842-60e4413fd5c0 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-035 - Zone 7 Vantage CH11825-CH11850
f43f132d-11d9-4ea8-8435-cb052f0549c2 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-036 - Zone 7 Vantage CH11870-11890 Layer 2
31cd5a5d-5da3-49f8-b745-27456c681c15 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-037 - Zone 7 East Stage 2 (CH20545-20750)
124ff8aa-dc2e-45b9-ab24-4d0e29413baa |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-038 - Zone 5 Aitken South - North Section - CH60520 to CH60410 - SB
93c99b1c-4e02-4893-a2b9-6cde821bf2f1 |  | checklist-sectioned | pass | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-039 - Zone 5 Aitken South - South Section - CH60410 to CH60360 - SB
2db82f5c-8b93-455f-b36e-fc5faa2758e6 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-040 - Zone 5 Aitken North - Mid Section - CH60840 to CH60620 - SB
478d8a03-45f9-4e09-ace8-5117345e88da |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-041 - Zone 7 West Stage 2 (CH20360-20480)
10754ef5-e2f1-49eb-a7d9-95229d8727d8 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-042 - Zone 7 West Stage 2 (CH20230-20360)
90b33d77-a79f-467e-b459-db2e50134457 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-046 - Zone 7 West Stage 2 - 750-760 Craigieburn Rd (CH20170-20230)
5ab068f0-d15e-4742-b72e-09c982ac5614 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-043 - Zone 5 Aitken North - Mid Section - CH60780 to CH60650 - SB
6e653eda-67fb-48a7-a5cf-c2a7543f5b0a |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-044 - Zone 5 Aitken North - Mid Section - CH60650 to CH60620 - SB
87cb7e3f-9917-4429-9bca-6f2566cf12c8 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-045 - Zone 6 Vantage to champion S1 - CH11900 to CH12180 - EB
f11bc950-7e03-425c-b85e-c3ade684cfee |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-056 - Zone 7 West Vantage 11660-11820
55cbe590-6f4a-4d2a-9fd1-bde3a80774e8 |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-057 - Zone 7 West Vantage slip lane 11835-11870
9ce18404-8e5f-4655-a37a-195b294b84fe |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-058 - Zone 6 - CH12600-12750
dfe383f3-4095-433b-ae04-59a8cc54896d |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-059 - Zone 6 - CH12550-CH12600
6bca2799-55e5-4561-8b9d-04378013706f |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-060 - Zone 7 East Stage 2 - West of Ambulance Bay (CH20890-21000)
80766e86-2a98-4653-85c3-832836542868 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-061 - Zone 7 East Stage 2 - East of Ambulance Bay (CH21120-21200)
05a85f43-742d-45b5-8d23-cebebb0c9fd4 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-062 - Zone 7 East Stage 2 - West of Ambulance Bay (CH21000-21120)
4d68a41b-8d2d-4581-9d2c-1fbda8ab801e |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-063 - Zone 7 East Stage 2 - East of Ambulance Bay (CH21200-21330)
2e104201-e499-4e48-99ab-67d01308c47f |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-064 - Zone 7 East Stage 2 - Gate 7.14 to Site Sheds (CH20760-20890)
9db09ffe-9e73-434f-a033-bcfcc18b4b44 |  | checklist-sectioned | not-started | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-065 - Zone 6 - CH12440-12490
ba138021-871b-4202-9ed7-cc8b7bea9dbd |  | checklist-sectioned | work-in-progress | ITP 0011 - Cement Treated Crushed Rock | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-011 - Cement Treated Crushed Rock | ITP-011-A2-LOT-066 - Zone 6 - CH12345-12440
fa9159ec-507e-489e-ba6f-8a808e5bed15 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install
1af1ed26-a0df-44d9-80f6-f47563ed9e4f |  | checklist-sectioned | pass | 900767607d68dcf1ca2b6e0fc8930456ee06da8ce5fcb4cb35dc99363425ffa8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-001 - Zone 7 West (CH 10050 - 10098)
2c43e1ec-81bb-4cdb-882b-5cd2c539fb44 |  | checklist-sectioned | work-in-progress | 900767607d68dcf1ca2b6e0fc8930456ee06da8ce5fcb4cb35dc99363425ffa8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-002 - Zone 7 East (CH 10600 - 10850)
9c24d83b-734f-4298-9baf-079cd2479f63 |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-003 - Mickleham South (NB+SB) CH30105-CH30234
09e72413-68af-4cd6-9633-223552c6dd4b |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-004 - Mickleham North (Media) CH30510-CH30700
72b1b46b-2394-4b36-96b0-27102486c824 |  | checklist-sectioned | pass | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-005 - Mickleham North (SB + Verge) CH30510-CH30785
b6900243-767e-4133-bcf2-bd93d0e4965e |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-006 - Mickleham North (NB) CH30510-CH30665
e433534c-72bb-44e5-b503-9f68b9253c18 |  | checklist-sectioned | pass | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-007 - Mickleham South (NB) CH30234-CH30365
c165fb57-00d2-4624-bac1-ae5129bc9550 |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-008 - Mickleham South (Median) CH30285-CH30365
0ca3b1a3-f65a-431d-b3bd-fb00a5679a9f |  | checklist-sectioned | pass | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-009 - Mickleham North (SB + Verge) CH40190-CH40300
46851c22-599d-4247-be89-1a648c753584 |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-010 - Mickleham North (NB) CH30455-CH30510
2f722906-2901-4341-a9e4-38769742908a |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-011 - Mickleham North (SB) CH30455-CH30510
ff0e821e-2f17-4103-9137-2f2f10b0e402 |  | checklist-sectioned | fail | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-012 - Mickleham South(Bullnose) CH30375-CH30385
7644b0b0-778d-4545-a1b9-570c67363b70 |  | checklist-sectioned | pass | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-013 - Mickleham Intersection (NB+SB+EB) Traffic Islands - CH10490-CH10550
96550978-1bf7-4c89-b97f-84d06c6283b2 |  | checklist-sectioned | work-in-progress | 900767607d68dcf1ca2b6e0fc8930456ee06da8ce5fcb4cb35dc99363425ffa8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-014 - Mickleham Intersection (SE Verge) - CH10540-CH10600
24c2c4db-2648-4fb3-9f14-180448471f4b |  | checklist-sectioned | pass | 8a60189befe30537265a1d78229d8416cffc1d6ed460aefd18c5c2f9ef732e49 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-015 - Mickleham North (NB + SB) - CH40330-CH40470
e603eb56-d081-44b2-b146-1053074f7410 |  | checklist-sectioned | work-in-progress | fd16c419bd12ca9f60be2d04f203af7269732bbb6bf6f12c26caeeb7f278ece7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-016 - Mickleham Rd NE Island - CH40341 to CH40352
4b0530a7-96d6-436f-ab6e-00d5f4dde9b6 |  | checklist-sectioned | work-in-progress | fd16c419bd12ca9f60be2d04f203af7269732bbb6bf6f12c26caeeb7f278ece7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-017 - Mickleham Rd NW - CH30471 to CH30478
f403c486-a58a-4c14-8295-f24edd1534e4 |  | checklist-sectioned | work-in-progress | fd16c419bd12ca9f60be2d04f203af7269732bbb6bf6f12c26caeeb7f278ece7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-018 - Zone 7 East Mick-Deb - CH10890-CH11000
f9977f90-e573-4e8f-9fed-738b609a8307 |  | checklist-sectioned | work-in-progress | fd16c419bd12ca9f60be2d04f203af7269732bbb6bf6f12c26caeeb7f278ece7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-019 - Zone 7 East Mick-Deb - CH11000-CH1110, CH10830 to CH10890
9f34829f-e05c-4224-bd41-48a8d064fffb |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-020 - Zone 7 East Mick-Deb - CH10880-CH11110
ed74d2c9-a1c3-481e-a780-9723a6b4bdb1 |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-021 - Zone 7 West Median + Verge - CH10260-CH10380
ee2639d2-b07b-444e-9da2-d954f9bb49c0 |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-022 - Zone 7 Debonair - CH11270 to CH11350
d5082b99-4fa2-4f88-b4e1-360ea375aaea |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-023 - Zone 7 West - WB lane Wedge + Median CH 10100 - CH 10260
e47c0327-f6d6-4e67-8aaf-551ec0d72d8e |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-025 - Zone 7 West - Wb lane (Verge + Median) CH10380 - CH10490
955c7eca-fba6-4e02-a295-7b39bbe1d048 |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-024 - Zone 7 Debonair - CH11100 to CH11250
37dbb66d-b8e6-4a86-8fdb-e2746eea2def |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-026 - Slip lane + Traffic island
0f1d1145-d1d9-4434-9213-2009df225a14 |  | checklist-sectioned | work-in-progress | 7f9c209a224d254c4c9651ba030610d435c8a20de1239603181265bf8b43c1e7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-027 - Zone 7 East - Ch10820 to ch10880
e563aaee-accd-4157-a603-6c2a08032abd |  | checklist-sectioned | work-in-progress | d2a5234a02b6df823e035bda026291ea4bd642ff33e2964de2f5c88e441e2764 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-028 - Zone 5 Aitken North - Upper Half - CH60860 to CH60940 - SB
6bf96e66-c99f-45e1-8886-b00ecf09dfa3 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-029 - Zone 7 Mickleham Rd North East Driveway Island
481fed0c-78c8-4fb3-bbae-6d7679634582 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-030 - Zone 7 - Vantage to Debonair - CH11340 to CH11650 - WB
28bd1977-4b88-4b40-8ef4-a792cde5f974 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-031 - Zone 7 - Vantage to Debonair - CH11860to CH11910 - bullnose
e72e72d0-968e-456f-a4da-82071fc84ead |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-032 - Vantage Intersection -
0ce64ed4-a337-4607-bfe0-657c91c431cb |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-037 - Vantage
11f57116-a213-4a4e-9a80-2cbfbdaeb866 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-033 - Zone 7 East Stage 2 - North Side + Median (CH20545-20720)
d56eba9a-cb0f-4520-ab21-2f7f5f548c83 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-034 - Zone 7 Mickleham to Debonair Median + Bullnose (CH10535-10605)
7a76f4d1-24ab-4a66-9eda-b88b12ca3557 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-035 - Zone 7 Mickleham Rd Intersection NE (CH40335-40370)
b2db645d-bed0-4f06-aa6e-33c9be9fe685 |  | checklist-sectioned | pass | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-036 - Zone 5 Aitken South - Southbound Stage 1 (CH60520-60360)
635b34b1-b05a-4cef-bc87-0c0cc3aa3a43 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-038 - Zone 7 East Stage 2 - Median + North Side (CH20720-20760)
71820738-daf4-4bc9-956d-6ab6eaf7c22e |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-039 - Zone 7 West Stage 2 - Median + North Side (CH20380-20480)
86c54bfc-79cd-4025-9700-18ca53753281 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-040 - Zone 7 West Stage 2 - Median + North Side (CH20280-20380)
c0cfd779-7e2d-475b-b373-3767495ef543 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-042 - Zone 7 East Stage 2 - Median + North Side (CH20230-20280)
906aec26-f2a9-4c26-ad87-d5fdbf8f9de1 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-041 - Zone 5 Aitken North - SB and Median Mid Section
5e497942-27c2-49ae-ad23-8429b0f14413 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-043 - Zone 6 vantage to champion S1 both runs (11900-12180)
f4f3e296-4251-4196-9e4c-0a67e1f12609 |  | checklist-sectioned | not-started | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-044 - West CH 20170 - CH 20230
fffdfbfb-1e6e-4534-84f1-a43b2f4dd160 |  | checklist-sectioned | not-started | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-045 - Zone 5 South Stage 2A - Southbound (CH60050-CH60370)
153d846b-bcc0-4736-abf6-d5401cc97a96 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-046 - Zone 6 Champion West S1 both runs (12170 - 12290)
9dc0a8ab-fcca-4a3f-b107-352ed42e9484 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-048 - Zone 7 West Vantage 11650-11820
81a567c2-d89b-4401-88a3-555bd201865b |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-049 West vantage slip lane 11820-11840
a4848da7-c29f-4d18-a414-37db037368b0 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-050 - Zone 7 East Stage 2 - Median (CH20890-21120)
1426d962-3a7b-4c50-8d76-d46473836384 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-051 - Zone 7 East Stage 2 - North Verge (CH20890-21200) + Median (CH21120-21200)
3dc60d4c-7ff5-4141-8689-5511b1037618 |  | checklist-sectioned | work-in-progress | ITP 0012 - Kerb and Channel | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-012 - Kerb & Channel Install | ITP-012-A2-LOT-052 - Zone 7 East Stage 2 - Median + Verge (CH21200-21300)
d7ca991c-2df2-46a5-8180-f762135c105c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete
fd977767-1f02-436c-88c9-25c959c7abf8 |  | checklist-sectioned | work-in-progress | d04619e6cf2b1626eb9a1bf67ddc2799299d79968c27e54e3e062f0104a45177 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-001 - Ex450 Pit Raising
5d8fbe83-b37f-44e1-8d20-cfef3aaf9cce |  | checklist-sectioned | work-in-progress | d04619e6cf2b1626eb9a1bf67ddc2799299d79968c27e54e3e062f0104a45177 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-002 - Zone 7 East CH10830-10860
4786a74b-9232-48cf-96df-98cd708ffd74 |  | checklist-sectioned | work-in-progress | ITP 0013 - Structural Concrete | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-003 - Zone 6 - Aitken Bridge -
c27d5b46-0611-4109-a332-2bce36f99129 |  | checklist-sectioned | work-in-progress | ITP 0013 - Structural Concrete | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-004 - Zone 6 - Aitken Bridge - Insitu barriers CH12500-12510
b40dd47b-ce8c-4318-a93d-17457709572e |  | checklist-sectioned | work-in-progress | ITP 0013 - Structural Concrete | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-005 - Zone 6 - Aitken Bridge - Insitu barriers CH12460-12490
d9fba6d0-2d39-4799-803f-f0c45b70b7fd |  | checklist-sectioned | work-in-progress | ITP 0013 - Structural Concrete | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-013 - Structural Concrete | ITP-013-A2-LOT-006 - Zone 6 - Aitken Bridge - Pile caps 8&9
f18087f3-0b03-4b3a-8340-8a4262cdc42d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-016 - Bored Pile Construction
05f74d42-7b03-44b1-bd09-c4193b97e8c1 |  | checklist-sectioned | work-in-progress | ITP 0016 - Bored Pile Construction | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-016 - Bored Pile Construction | ITP-016-A2-LOT-001 - Bored Piles WB - BP09&03
63664c34-b734-41f4-b2d9-b4fd1c64bb89 |  | checklist-sectioned | work-in-progress | ITP 0016 - Bored Pile Construction | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-016 - Bored Pile Construction | ITP-016-A2-LOT-002 - Bored Piles WB - BP08,07
d2efd469-7e3a-460f-aff0-f3050ad2d8c4 |  | checklist-sectioned | work-in-progress | ITP 0016 - Bored Pile Construction | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-016 - Bored Pile Construction | ITP-016-A2-LOT-003 - Bored Piles WB - BP01,2,4,5&6
0ce98b2d-3ed1-4b58-8cdd-1f3c02c25774 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage
3587fb99-4a3f-4ae3-91b0-100dce29224a | Child Lot Verification(8af674e9-127a-4cdd-88b0-85875c1d81f4): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-001 - Stormwater Drainage - Pit 582 to Pit 583 - Zone 7 East Mickleham to Debonair (Westbound)
e086ca8d-1b0c-4889-a1ca-230089600dfb | Child Lot Verification(b289b02e-24c2-4545-88f6-b7aeb17f62fb): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-002 - Stormwater Drainage - Pit 578 to Pit 579 - Zone 7 East Mickleham to Debonair (Westbound)
d2cddb18-ee6d-429d-8e6c-ead01f305d78 | Child Lot Verification(b6aae5ee-b192-4cd8-bc29-3d3ec6154380): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-003 - Stormwater Drainage - Pit 579 to Pit 580 - Zone 7 East Mickleham to Debonair (Westbound)
d317022f-6162-4ac1-813f-f4cea1782296 | Child Lot Verification(f5834bca-7c75-4dff-ae72-03083faa5b03): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-004 - Stormwater Drainage - Pit 580 to Pit 581A - Zone 7 East Mickleham to Debonair (Westbound)
9f25ca1e-c4e0-42e0-8301-dad8653481b5 | Child Lot Verification(db38c1cc-9e76-42ee-b4a7-816ece4f7b02): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-005 - Stormwater Drainage - Pit 581A to Pit 581 - Zone 7 East Mickleham to Debonair (Westbound)
969d239f-3b30-4cac-b6fb-0befe8b2b723 | Child Lot Verification(5b6c4393-aae0-4e6a-bdde-83be9e1860df): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-006 - Stormwater Drainage - Pit 581 to Pit 582 - Zone 7 East Mickleham to Debonair (Westbound)
ad7fd7c1-d729-4398-800b-51789e31f346 | Child Lot Verification(d4eb3152-4e0d-4cdf-b1ca-c4cbcff38e15): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-007 - Stormwater Drainage - Pit 577 to Pit 578 - Zone 7 East Mickleham to Debonair (Westbound)
9581b076-500d-44cc-80de-ce1827604f18 | Child Lot Verification(23786d8d-8d91-4c6f-96bf-5383d0ffe2af): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-008 - Stormwater Drainage - Pit 583 to Pit 584 - Zone 7 East Mickleham to Debonair (Westbound)
cd9fff25-dcbb-4b13-b08f-fc33ac154d06 | Child Lot Verification(7a26eb9f-bf19-4979-859e-30e671b0a3ef): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-009 - Stormwater Drainage - Pit 584 to Pit 585 - Zone 7 East Mickleham to Debonair (Westbound)
9498f2ba-d3b2-4ad8-b5e8-abe41949c90d | Child Lot Verification(17e23111-def2-46dd-a6ca-5f32a3572f67): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-010 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound)
4bf17a34-cebf-4920-9799-7abde20ca124 | Child Lot Verification(208410a8-a7cf-47f3-bcf1-36262eed736e): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-011 - Stormwater Drainage - Pit 575 to Pit 576 - Zone 7 East Mickleham to Debonair (Westbound)
17470f73-f1cd-44ef-a130-dfd45ce9766e | Child Lot Verification(fe28d675-b485-4fcf-b51e-c1e1046850da): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-012 - Stormwater Drainage - Pit 576 to Pit 577 - Zone 7 East Mickleham to Debonair (Westbound)
482cd140-6b2f-49e9-a069-22e9ccd2f456 | Child Lot Verification(cf729ba4-0f2a-4ea3-a821-8b99c5249ac8): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-013 - Stormwater Drainage - Pit 999 to Pit 1000 - Zone 7 West Stage 1 (Westbound)
d2f3a181-62d4-4ad8-b1e6-898f27730f8c | Child Lot Verification(03956729-6b88-42b5-90e4-936ae8d4b7d8): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-014 - Mickleham North. ( Pit 1042-1041)
b1967441-49db-4027-94bb-9aa0a7f7274f | Child Lot Verification(fe207cb5-2055-5253-93de-ddc7bbe8d2de) -- Lot Verification.(3a45762b-e85c-5cac-a63c-ca0211c8a6bc): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(fe207cb5-2055-5253-93de-ddc7bbe8d2de) -- Lot Verification.(3a45762b-e85c-5cac-a63c-ca0211c8a6bc): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(fe207cb5-2055-5253-93de-ddc7bbe8d2de) -- Lot Verification.(3a45762b-e85c-5cac-a63c-ca0211c8a6bc): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(fe207cb5-2055-5253-93de-ddc7bbe8d2de) -- Lot Verification.(3a45762b-e85c-5cac-a63c-ca0211c8a6bc): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(fe207cb5-2055-5253-93de-ddc7bbe8d2de) -- Lot Verification.(3a45762b-e85c-5cac-a63c-ca0211c8a6bc): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-015 - Mickleham North (Pit 1041-1040)
1463126a-1d49-49db-bdbf-1935ec74e516 | Child Lot Verification(5ae49b03-6319-4910-b4b9-df10cc8e11ab): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-016 - Mickleham North (Pit 1040-1039)
9e33f978-589b-4368-9f1f-e70a3fc3140a | Child Lot Verification(ee3d28ac-1802-4344-ae60-7e2d26b3738a): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-017 - Mickleham North ( Pit 1039-1038)
d81e8d97-6073-495b-973a-9d5d2c84bf64 | Child Lot Verification(86e86cb7-41b5-5cf4-819c-fa270b14c753) -- Lot Verification.(f68e80e3-2add-5a6e-9990-ae9eb45037df): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(86e86cb7-41b5-5cf4-819c-fa270b14c753) -- Lot Verification.(f68e80e3-2add-5a6e-9990-ae9eb45037df): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(86e86cb7-41b5-5cf4-819c-fa270b14c753) -- Lot Verification.(f68e80e3-2add-5a6e-9990-ae9eb45037df): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(86e86cb7-41b5-5cf4-819c-fa270b14c753) -- Lot Verification.(f68e80e3-2add-5a6e-9990-ae9eb45037df): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(86e86cb7-41b5-5cf4-819c-fa270b14c753) -- Lot Verification.(f68e80e3-2add-5a6e-9990-ae9eb45037df): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-018 - Mickleham North (Pit 1038-1037)
fbc0a206-2a41-4b17-81d5-c6ede9eaed67 | Child Lot Verification(456c1e4d-3153-57d5-9df7-40d8bfc90153) -- Lot Verification.(3f7272c7-c3d9-58ce-948f-d531fa8340d5): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(456c1e4d-3153-57d5-9df7-40d8bfc90153) -- Lot Verification.(3f7272c7-c3d9-58ce-948f-d531fa8340d5): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(456c1e4d-3153-57d5-9df7-40d8bfc90153) -- Lot Verification.(3f7272c7-c3d9-58ce-948f-d531fa8340d5): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(456c1e4d-3153-57d5-9df7-40d8bfc90153) -- Lot Verification.(3f7272c7-c3d9-58ce-948f-d531fa8340d5): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(456c1e4d-3153-57d5-9df7-40d8bfc90153) -- Lot Verification.(3f7272c7-c3d9-58ce-948f-d531fa8340d5): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-019 - Mickleham North (Pit 1037-1036)
f0e2def9-d6ea-421c-b23c-fdb11c210e30 | Child Lot Verification(e533db72-85cd-465a-b989-c0ec6aa0155c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-020 - Mickleham North (Pit 1036-1035)
d155e0b0-c595-4bd8-8bea-f0faa176b91f | Child Lot Verification(cf6c79e2-7fc4-4064-bf08-6fa9acf47122): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-021 - Mickleham North (Pit 1035-1034)
96bda989-b26b-41c9-a219-8ccefd202029 | Child Lot Verification(93171003-366c-4b04-9a56-f4f69490c17a): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-022 - Mickleham North (Pit 1034-1033)
66a7b2ca-6806-4fa6-94c1-f4458dde0222 | Child Lot Verification(c405cd6e-3c35-470b-abb4-e9d997676ace): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | pass | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-023 - Mickleham Intersection ( Pit 1048-1047)
afcd4b01-4ee7-4597-a8c4-e1da3aa65918 | Child Lot Verification(8f462834-3642-4c5b-8424-d7805b3babdb): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | d0423870a398edf354d71c5fb292f67e42193fa83dca2dbad9f594b94f4f62a7 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-024 - Mickleham Intersection ( Pit 1047-1046)
db9dbecf-5b36-46f1-a846-e358303f056d | Child Lot Verification(eb33c0ed-1a3e-479d-9712-5dd2c84cfd37): checkpoint-group has incorrect meta.stepType checklist-flat Child Lot Verification(c7a1d750-1fe3-5f78-b819-48f66a0cac09) -- Lot Verification.(25317920-adf6-599b-9890-df4e75647daa): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(c7a1d750-1fe3-5f78-b819-48f66a0cac09) -- Lot Verification.(25317920-adf6-599b-9890-df4e75647daa): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(c7a1d750-1fe3-5f78-b819-48f66a0cac09) -- Lot Verification.(25317920-adf6-599b-9890-df4e75647daa): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(c7a1d750-1fe3-5f78-b819-48f66a0cac09) -- Lot Verification.(25317920-adf6-599b-9890-df4e75647daa): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(c7a1d750-1fe3-5f78-b819-48f66a0cac09) -- Lot Verification.(25317920-adf6-599b-9890-df4e75647daa): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | work-in-progress | 60b0a06454b3bbc0e664ef83b66783ac7fdb3deddc612f3cd5fa5a0a29392349 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-025 - Mickleham Intersection ( Pit 1046-1045)
045597e9-6a3a-4cd4-b268-22fddbcca93b | Child Lot Verification(760a2150-c7ef-5d23-9240-d8f962015ae8) -- Lot Verification.(42f43651-0ead-5cb6-993d-9dc0143f3161): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(760a2150-c7ef-5d23-9240-d8f962015ae8) -- Lot Verification.(42f43651-0ead-5cb6-993d-9dc0143f3161): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(760a2150-c7ef-5d23-9240-d8f962015ae8) -- Lot Verification.(42f43651-0ead-5cb6-993d-9dc0143f3161): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(760a2150-c7ef-5d23-9240-d8f962015ae8) -- Lot Verification.(42f43651-0ead-5cb6-993d-9dc0143f3161): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(760a2150-c7ef-5d23-9240-d8f962015ae8) -- Lot Verification.(42f43651-0ead-5cb6-993d-9dc0143f3161): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-026 - Mickleham Intersection ( Pit 1045-1044 )
a6779fa1-1277-4783-ba4f-171662901f96 | Child Lot Verification(22e82ad9-cb39-5eb3-a424-5d06e356dd33) -- Lot Verification.(dd8d0719-0f13-5d64-b83f-8659a6eee615): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(22e82ad9-cb39-5eb3-a424-5d06e356dd33) -- Lot Verification.(dd8d0719-0f13-5d64-b83f-8659a6eee615): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(22e82ad9-cb39-5eb3-a424-5d06e356dd33) -- Lot Verification.(dd8d0719-0f13-5d64-b83f-8659a6eee615): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(22e82ad9-cb39-5eb3-a424-5d06e356dd33) -- Lot Verification.(dd8d0719-0f13-5d64-b83f-8659a6eee615): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(22e82ad9-cb39-5eb3-a424-5d06e356dd33) -- Lot Verification.(dd8d0719-0f13-5d64-b83f-8659a6eee615): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-027 - Mickleham Intersection ( Pit 1044-1043)
8c6b79c7-9c16-4913-8c7f-f5bc1eb0e8d9 | Child Lot Verification(7fac6dd4-e43a-4544-82fb-6cb56585122d): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-028 - Mickleham Intersection ( M1-M2)
435c8cd9-6264-4169-bb1d-9700eef7dea9 | Child Lot Verification(4e8bd5ab-c6e2-5d72-a9c5-35b9318746f3) -- Lot Verification.(9e4d1a0a-7105-5974-a305-8f77e71708c8): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(4e8bd5ab-c6e2-5d72-a9c5-35b9318746f3) -- Lot Verification.(9e4d1a0a-7105-5974-a305-8f77e71708c8): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(4e8bd5ab-c6e2-5d72-a9c5-35b9318746f3) -- Lot Verification.(9e4d1a0a-7105-5974-a305-8f77e71708c8): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(4e8bd5ab-c6e2-5d72-a9c5-35b9318746f3) -- Lot Verification.(9e4d1a0a-7105-5974-a305-8f77e71708c8): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(4e8bd5ab-c6e2-5d72-a9c5-35b9318746f3) -- Lot Verification.(9e4d1a0a-7105-5974-a305-8f77e71708c8): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-029 - Mickleham Intersection ( 1049-1048)
36cc9c6b-9ea6-486b-bce1-9e1b1c7820b1 | Child Lot Verification(4ab4cf87-6a65-5492-8470-834ec936ffd4) -- Lot Verification.(6689a147-a828-5c64-8da2-9820a56840bb): DataPoint Is the relevant RFI attached to the Lot?(4daafa34-b6fe-578e-bc8f-06c9be9611f6) is missing 'select' values Child Lot Verification(4ab4cf87-6a65-5492-8470-834ec936ffd4) -- Lot Verification.(6689a147-a828-5c64-8da2-9820a56840bb): DataPoint Is the relevant NCR attached to the Lot?(55c74180-aa48-5d36-be50-754058170faa) is missing 'select' values Child Lot Verification(4ab4cf87-6a65-5492-8470-834ec936ffd4) -- Lot Verification.(6689a147-a828-5c64-8da2-9820a56840bb): DataPoint Are any relevant Mails/ Transmittals attached to the Lot?(d85bfd15-27c8-55b4-ba0b-e00ee57faf5a) is missing 'select' values Child Lot Verification(4ab4cf87-6a65-5492-8470-834ec936ffd4) -- Lot Verification.(6689a147-a828-5c64-8da2-9820a56840bb): DataPoint Lot verified By(03cd4fd9-edd2-5aea-bc9c-c745c76aa385) is missing 'select' values Child Lot Verification(4ab4cf87-6a65-5492-8470-834ec936ffd4) -- Lot Verification.(6689a147-a828-5c64-8da2-9820a56840bb): DataPoint Lot Status(2674fabd-18b3-5be9-b7ff-d4b8a51cadcb) is missing 'select' values | checklist-sectioned | pass | f3ec5edbc6503aa5802ef28ec9275790d0d65454c7a7b6ed201764206a4200d2 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-030 - Mickleham Intersection (1049-1050)
0e5131e7-6221-463b-965d-862dc78d6c0e | Child Lot Verification(2c900316-1b6c-4da2-9c36-b824265fa8fd): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-031 - Mickleham Intersection (1191-1192)
be074f69-76b1-411a-94fe-b47809913cad | Child Lot Verification(0a41e8e9-1ce0-4cd3-88b0-8f9e5a468b55): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-032 - Mickleham Intersection (1192-1193)
087140fe-043b-4cba-aef8-034d3fc286aa | Child Lot Verification(d340ebe4-0cfc-4473-851d-33d8daaa1252): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-033 - Mickleham Intersection (997-998)
fa4b66f1-578d-4fe0-b6b7-fd8f60dade81 | Child Lot Verification(c35218ff-8308-4f47-9765-3fca0e633819): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-034 - Mickleham Intersection (996-997)
99540034-0f93-43cb-b7ea-3525f526d12c | Child Lot Verification(8d66d284-d1ef-40d9-9c15-dfd68c48d311): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 3bc96fed2b3c6c2deffe73d1aa6b18a087473e3c9635f16cdaffddb5e52c61c6 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-037 - Mickleham Intersection SE (1193-998)
c5245717-6c78-43dc-b43c-3509f34bafc0 | Child Lot Verification(fd6694ce-ffae-407d-bdc3-349ded36ec5c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 3bc96fed2b3c6c2deffe73d1aa6b18a087473e3c9635f16cdaffddb5e52c61c6 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-038 - Mickleham Intersection NE (1050-994)
26102694-55cf-47cf-8c68-9b50cc0c6f1a | Child Lot Verification(4072d4dd-821a-499b-9f17-3ff520774873): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-039 - Mickleham Intersection (993-1088)
ab518f98-89ab-4e24-8339-1ff431893011 | Child Lot Verification(6b537fed-b350-44d6-91e4-9aacd4371d09): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-040 - Mickleham Intersection (Pit 1013 - pit 1014)
16d20013-8511-421a-a4e4-87f16bf47c42 | Child Lot Verification(8ae2b22a-d670-4634-ab47-99f68f89ad52): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 3bc96fed2b3c6c2deffe73d1aa6b18a087473e3c9635f16cdaffddb5e52c61c6 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-041 - Mickleham Intersection NW (1014-1015)
343610d7-e874-4f4b-b542-206edde7218e | Child Lot Verification(7823b4bf-0834-42dc-ad71-94c19b92135a): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-042 - Mickleham Intersection SE (1178-1178a)
894c844e-52a8-4cb1-89fd-139a5a23e40f | Child Lot Verification(5ccfe566-ca8c-4a4b-84ca-9f31cdc42e9e): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-043 - Mickleham Intersection (1178-1177)
b17db5f4-84b5-425a-9edc-34338113e543 | Child Lot Verification(825c0cb8-d1d4-41a9-ba54-85621aab2cfe): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-044 - Mickleham Intersection (1177-1066)
b4a2f616-37de-436e-bf28-a5dd9f095bcd | Child Lot Verification(61956535-8732-49f0-b3b4-bceff53af6d9): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-045 - Mickleham Intersection (1177-1176)
03dadae4-55f4-42d4-80a0-98a56cf79100 | Child Lot Verification(a7287eee-5b20-44f5-b0df-47928c6b7877): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-046 - Mickleham Intersection (1176-1015)
588e228b-5f2d-44b8-9c6f-0632b440cbf6 | Child Lot Verification(27bc606e-c932-49b6-99ac-058b033a6692): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-047 - Mickleham North NB (1069-1116)
9d731b67-7f88-423d-8b9c-cb4788b895c1 | Child Lot Verification(d5fa6641-0ac7-49e2-aee0-d0f3dc6496ef): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-048 - Mickleham North (1096-1097)
21cc115d-b7de-4437-baea-27a0ea17d9c7 | Child Lot Verification(7a6855c3-b116-4de7-8b02-dddd95d4b741): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-049 - Mickleham North (1079-1080)
7c2a0b70-bee2-47c4-8fa9-f3948f63b03c | Child Lot Verification(1bc1b58f-8056-4522-84e4-dd77d23348fd): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-050 - Mickleham North (1092-1093)
99df8ee4-5bcb-4f3a-8c05-faa7369e8488 | Child Lot Verification(f949c6ec-7573-42c7-a566-8e6c732189cf): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-051 - Mickleham North NB (1161-1162)
b7c8892d-33d6-4a2a-a62a-085e9a754688 | Child Lot Verification(11fc81d5-200b-4bb5-b4d0-8593e6805536): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-052 - Mickleham Intersection (Pit 1014 - pit 1159)
a1025661-ad3b-4d2e-b3d2-fc43f6925d1c |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-053 - Mickleham North NB (1114-1115)
1b86fd02-b39e-4ed7-9f93-aafa7239d83a | Child Lot Verification(50572550-b8d5-4bf6-b626-4ea5432a9419): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 4a8b6b8fc4722a9100f85b0474efc0934a739a1c8721348ba449c84d46397d12 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-054 - Stormwater Drainage - Pit 573 to Pit 573a - Zone 7 East Mickleham to Debonair (Westbound)
1c515344-eea5-48d1-b3d3-17592ed59b88 | Child Lot Verification(45ef0951-ae80-4984-b56c-f0a0aa550a1d): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-055 - Stormwater Drainage - Pit 573a to Pit 573b - Zone 7 East Mickleham to Debonair (Westbound)
bb09d0da-e48a-4754-9164-ea037e077b68 | Child Lot Verification(b6468a9c-46e9-4026-bb4c-f7a34175be1e): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 73e428b6965b30fe285ac47407e8274a7f48e3765818ee0c3a3ebb38720ce626 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-056 - Stormwater Drainage - Pit 573b to Pit 573c - Zone 7 East Mickleham to Debonair (Westbound)
c50a90db-59fe-45de-ba7e-ff4296fdbdb1 | Child Lot Verification(a79fa7c7-6b40-41fe-9ee2-6c73cd8b93bd): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-057 - Stormwater Drainage - Pit 573b to Pit 572a - Zone 7 East Mickleham to Debonair (Westbound)
22a7701c-ab14-4508-bc5e-2d65064a5115 | Child Lot Verification(fea9a495-2fb0-418f-a82e-05f7c12d7b3d): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-058 - Stormwater Drainage - Pit 572a to Pit 572 - Zone 7 East Mickleham to Debonair (Westbound)
4176bcb4-d242-4729-8af1-0a9caf47ebd3 | Child Lot Verification(74b317f9-ebc2-475c-acd3-6a92650202d3): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-059 - Stormwater Drainage - Pit 572 to Pit 571 - Zone 7 East Mickleham to Debonair (Westbound)
612095fd-1ddf-4074-a6f0-666cf805a556 | Child Lot Verification(90973196-a551-43a5-b313-0f6845e03b6c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-060 - Stormwater Drainage - Pit 571 to Pit 569 - Zone 7 East Mickleham to Debonair (Westbound)
6a4de109-02fc-43dd-ba3b-e2d3501a59ae | Child Lot Verification(fcc08c09-c718-45ac-b5cf-29db83220c5c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-061 - Stormwater Drainage - Pit 569 to Pit 568 - Zone 7 East Mickleham to Debonair (Westbound)
6e7ed13e-3bf6-4ea7-8adc-b9989c844e25 | Child Lot Verification(56d7886b-6e10-4248-98f1-bede86a9a53c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-062 - Stormwater Drainage - Pit 568 to Pit 567 - Zone 7 East Mickleham to Debonair (Westbound)
7fa80175-b214-4f41-8415-ea382624b1fd | Child Lot Verification(ba6420ff-fe8b-4356-a358-6e962eeb2fba): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | ead557fbae69f3189690fd9ad3f06f0685f42a56a847280e157ecd7293dd2c44 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-063 - Stormwater Drainage - Pit 567 to Pit 587a - Zone 7 East Mickleham to Debonair (Westbound)
830c3b48-93bf-4f2a-8122-4908ebf226af | Child Lot Verification(7a47d863-8767-41f8-ac26-72cd955dbd0c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-064 - Stormwater Drainage - Pit 567 to Pit 567a - Zone 7 East Mickleham to Debonair (Westbound)
7c2307ca-f0ee-4f09-963c-fb2596d39fa9 | Child Lot Verification(b5a59510-a558-43ea-97e0-0613c82f1d83): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-065 - Stormwater Drainage - Pit 567a to Pit 567b - Zone 7 East Mickleham to Debonair (Westbound)
a14f2942-630a-46f7-a6ee-1d66d8acbb10 | Child Lot Verification(671ff3e3-2d7a-41d7-a8cc-50174f564758): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-066 - Stormwater Drainage - Pit 567b to Pit 567c - Zone 7 East Mickleham to Debonair (Westbound)
49f72592-74b2-4561-99b6-efaf55813e42 | Child Lot Verification(9935ff9a-28b5-4ea9-8bbd-ae74969c4bd5): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-067 - Stormwater Drainage - Pit 567b to Pit 566a - Zone 7 East Mickleham to Debonair (Westbound)
3e6afd72-7bee-4a3f-ac65-61a7d5a2ec1d | Child Lot Verification(b3a2a498-97db-4737-90bb-36f3b61c39bc): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-068 - Stormwater Drainage - Pit 566a to Pit 565 - Zone 7 East Mickleham to Debonair (Westbound)
533402ef-f82e-4ef5-95de-bfd11a47b962 | Child Lot Verification(ee1bb082-51bc-42a4-ae21-8b9433e53df5): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-069 - Stormwater Drainage - Pit 565 to Pit 564 - Zone 7 East Mickleham to Debonair (Westbound)
a83578c6-534a-4145-9bf8-bbf280739959 | Child Lot Verification(454f77b7-7dba-4ee6-8211-92c80dfde000): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-070 - Stormwater Drainage - Pit 564 to Pit 563 - Zone 7 East Mickleham to Debonair (Westbound)
fd48c004-124b-42e4-beba-4ae266551d28 | Child Lot Verification(052c9c66-580b-46fe-8a59-2a42a2e9dbbf): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-071 - Stormwater Drainage - Pit 563 to Pit 562 - Zone 7 East Mickleham to Debonair (Westbound)
ce86f475-7ba2-4c61-a16a-47cad24b87fd | Child Lot Verification(2f80b805-c48a-4d7d-a913-582484bce327): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 8fe33c2c9bccd9abeaac9da50daf3d1cfab740639a55633903dd6372e184f308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-072 - Stormwater Drainage - Pit 562 to Pit 561 - Zone 7 East Mickleham to Debonair (Westbound)
986952c4-d4a7-4db2-b5c2-73345775c530 | Child Lot Verification(454b38c7-f4ec-4d40-b279-9039030b4eb7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 70c207b0c712970a3e25313d26904c8bbe052c02b866e67e2d8119f9020d8580 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-073 - Mickleham Intersection (Pit 994- pit 995)
9c9449e9-15d1-4a68-ab7f-d6fedb496085 | Child Lot Verification(ffe81f9b-09ad-4016-b76f-6c80a662ed34): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-074 - Stormwater Drainage - Pit 557A to Pit 556 - Zone 7 East Debonair to Vantage (Westbound)
ce98aa16-2df5-43e1-8693-29c07c2bab34 | Child Lot Verification(926772b5-6f32-47be-862e-872ea4dac6ed): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 9c68f30da80bd9c7d503a919e9aacb313ab292344aca828119723d78720d37ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-075 - Stormwater Drainage - Pit 556 to Pit 556A - Zone 7 East Debonair to Vantage (Westbound)
5afafa2a-78ac-4f94-a2db-f6e58336c41f | Child Lot Verification(d3d40c6c-0986-4897-bc3f-7ae569fe47c2): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-076 - Stormwater Drainage - Pit 556A to Pit 555 - Zone 7 East Debonair to Vantage (Westbound)
e016c052-d175-4662-b11c-e6af65f55e47 | Child Lot Verification(6aede666-2e5a-427a-b01b-afab4cb0f4dd): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-077 - Stormwater Drainage - Pit 555 to Pit 554 - Zone 7 East Debonair to Vantage (Westbound)
fabb5068-f1d2-4e7a-83c3-31be1b37660a | Child Lot Verification(95b37d6d-562b-4c38-bcf3-1a9216aa71b1): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-078 - Stormwater Drainage - Pit 554 to Pit 553 - Zone 7 East Debonair to Vantage (Westbound)
93a082a9-2ddc-4008-8a78-cd89186106ff | Child Lot Verification(04f9ba82-9550-4206-8470-bb4cad199150): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-079 - Stormwater Drainage - Pit 553 to Pit 552 - Zone 7 East Debonair to Vantage (Westbound)
beced918-886a-49a3-9b82-115b446508df | Child Lot Verification(20679bef-5691-43f0-ba90-d12a69b3fdc8): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-080 - Stormwater Drainage - Pit 552 to Pit 551 - Zone 7 East Debonair to Vantage (Westbound)
c5f2cf51-0509-4384-9b87-99bf7ef2a76e | Child Lot Verification(8e947044-cbf7-4528-b00b-cee4cc2c6d62): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-081 - Stormwater Drainage - Pit 551 to Pit 550 - Zone 7 East Debonair to Vantage (Westbound)
28972c9d-353a-45ff-bc76-5a3e7cf96e27 | Child Lot Verification(2236d43d-34cd-44e4-845b-0fee5135d8ee): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-082 - Stormwater Drainage - Pit 550 to Pit 549 - Zone 7 East Debonair to Vantage (Westbound)
93f827c6-9866-4d26-9f43-c3bc9dad7a54 | Child Lot Verification(016340d4-b30f-4fde-a63c-1a811ae7ecbf): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-083 - Stormwater Drainage - Pit 549 to Pit 548 - Zone 7 East Debonair to Vantage (Westbound)
c21785a5-2bbc-4c03-8e8e-f4340973b3f0 | Child Lot Verification(67217aab-39cb-427e-b549-ea19dd3ca2d7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-084 - Stormwater Drainage - Pit 548 to Pit 547 - Zone 7 East Debonair to Vantage (Westbound)
381f55a1-d0b7-49ab-89fe-70186ca416e5 | Child Lot Verification(9e2a03af-963e-45bd-9721-d450518067f6): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-085 - Stormwater Drainage - Pit 547 to Pit 546 - Zone 7 East Debonair to Vantage (Westbound)
8c2f204b-43e9-4c1d-87ef-0b9e4100f55d | Child Lot Verification(04f44b8f-47dc-4eff-a7a7-278922b471f6): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-086 - Stormwater Drainage - Pit 546 to Pit 545 - Zone 7 East Debonair to Vantage (Westbound)
b28d832e-2735-465b-b8d9-7b8370fdecc6 | Child Lot Verification(81db3ddd-1fd5-4447-a1b5-ed83224f8abd): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-087 - Stormwater Drainage - Pit 545 to Pit 545A - Zone 7 East Debonair to Vantage (Westbound)
367daabb-bbae-4675-ac9c-2ee09a1c0521 | Child Lot Verification(55e22e03-7e55-49b2-9d87-37d7158b4cd2): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-088 - Stormwater Drainage - Pit 545A to Pit 544 - Zone 7 East Debonair to Vantage (Westbound)
61c49fcf-bc61-4030-8a11-66d515020198 | Child Lot Verification(c291beab-cace-4e75-855a-910e31e23c13): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 00682c1049ba35b00909778f66cc4fae40ea5e88128521af0dc3a7fa258dc2c8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-089 - Mickleham North East ( Pit 992-993)
364e69cd-2963-4349-8862-179794983413 | Child Lot Verification(f0a10088-3fcb-419a-8f77-8c5202082cef): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 00682c1049ba35b00909778f66cc4fae40ea5e88128521af0dc3a7fa258dc2c8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-090 - Mickleham North East ( Pit 993-1088)
d83eae81-b7df-4017-b203-0331f2b5d3e2 | Child Lot Verification(1fe809ef-7a26-4e85-80e1-fb08cca173ca): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 00682c1049ba35b00909778f66cc4fae40ea5e88128521af0dc3a7fa258dc2c8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-091 - Mickleham North East ( Pit 1088-1087)
f13067f5-a2d5-4e87-9820-ffe13fc13547 | Child Lot Verification(4e06f27e-9e6b-4aff-b571-5336f790dbbf): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | ead557fbae69f3189690fd9ad3f06f0685f42a56a847280e157ecd7293dd2c44 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-092 - Mickleham North East ( Pit 1087-1086)
3ce34951-9af6-407b-a3d2-753bd24905ea | Child Lot Verification(9bbbfcc9-f907-4986-8554-4dea4845c782): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-093 - Stormwater Drainage - Pit 1210 to Pit 1165 - Zone 7 West Stage 1 (Westbound)
d406c953-7077-4b15-96b8-087f73525fdb | Child Lot Verification(c1e8f1ec-efab-45b1-a48f-fd913ed3e0b5): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-094 - Stormwater Drainage - Pit 1165 to Pit 1166 - Zone 7 West Stage 1 (Westbound)
a2b12d69-b526-49ea-b80b-4af42fbd93bf | Child Lot Verification(ee54e3b1-6485-403e-8d5e-25c5cadc60cc): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-095 - Stormwater Drainage - Pit 1166 to Pit 1167 - Zone 7 West Stage 1 (Westbound)
c30012ce-9060-476d-a6ee-f2c58e501657 | Child Lot Verification(aaeda5bc-81e3-4a14-9941-8a3676b7c3ba): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-096 - Stormwater Drainage - Pit 1167 to Pit 1168 - Zone 7 West Stage 1 (Westbound)
13d7dd82-4af6-40f9-bd5e-28215ed40d48 | Child Lot Verification(54ca8d88-d56b-46b2-a0a4-4a10dae59c3c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-097 - Stormwater Drainage - Pit 1168 to Pit 1169 - Zone 7 West Stage 1 (Westbound)
5067b7ab-a9dd-437c-83b3-55d9aa40a12c | Child Lot Verification(f0be1217-4b32-4946-8e58-885fded44273): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-098 - Stormwater Drainage - Pit 1169 to Pit 1170 - Zone 7 West Stage 1 (Westbound)
a7417cd4-752c-4f0e-b55a-7dc30e058f0f | Child Lot Verification(2b4ca716-1023-4aa5-beb1-01af1298d2aa): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-099 - Stormwater Drainage - Pit 1170 to Pit 1171 - Zone 7 West Stage 1 (Westbound)
37219ea9-e6a3-4272-81ca-52817fa7126c | Child Lot Verification(f914e55f-8b5f-4e75-8787-b1092d6b5e3b): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-100 - Stormwater Drainage - Pit 1171 to Pit 1172 - Zone 7 West Stage 1 (Westbound)
594b00a8-b848-4f1a-832f-6d809852fd3a | Child Lot Verification(e78d7c42-6bb7-48f2-aefb-9df693f7430f): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-101 - Stormwater Drainage - Pit 1172 to Pit 1173 - Zone 7 West Stage 1 (Westbound)
5f53c0fb-9b2e-4670-a948-5227ca46e3f1 | Child Lot Verification(24edad2e-e9a8-47a8-9b3d-40974c6e497c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-102 - Stormwater Drainage - Pit 1173 to Pit 1174 - Zone 7 West Stage 1 (Westbound)
56475a47-8aeb-4084-b7b8-d7e9eb79004b | Child Lot Verification(6175737b-cdbb-4512-a756-c668228a2f4f): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-103 - Stormwater Drainage - Pit 1174 to Pit 1175 - Zone 7 West Stage 1 (Westbound)
347ba5ea-5fc8-4879-8bf0-2ac63fe27802 | Child Lot Verification(ab0d8cdf-f4d7-4bc3-9429-4c411804a51b): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 9c68f30da80bd9c7d503a919e9aacb313ab292344aca828119723d78720d37ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-104 - Stormwater Drainage - Pit 1175 to Pit 1176 - Zone 7 West Stage 1 (Westbound)
d84e8591-c5fd-4de7-a4f6-103bad917971 | Child Lot Verification(769a7762-ff3d-45f7-8f09-4011ff2af1c9): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-105 - Mickleham South East ( Pit 998-688ac)
59d0dcd8-f2a2-4783-a355-416e6dc2e69b | Child Lot Verification(8ac96253-f3f6-4cd0-a151-49429af23ea0): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-106 - Mickleham South East ( Pit 688ac-688ad)
9ff98495-58c3-4cff-8872-6d8036b366cf | Child Lot Verification(5399569f-d6f4-4768-958d-5e992177f3d3): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | a5fea64ab792918f19065c3b7365c33da461c908d483b0a607d06e0405467f1e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-107 - Mickleham Intersection (NE) ( Pit 995-996)
0cbece09-478f-4f95-881d-283a354eef3f | Child Lot Verification(887ca901-75d5-49db-a3fb-9181af1c0d07): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-108 - Mickleham North ( Pit 1042-1043)
a79817d1-fe58-4c6f-b1de-af394695e2b3 | Child Lot Verification(bf3be8b4-ff6a-4228-8a11-287f8c4efd22): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-109 - Mickleham South ( Pit 1180-1181)
cbe55731-fdce-4ff1-a46b-640a076dfe79 | Child Lot Verification(fb74e62e-ac0a-48a5-bdcc-98ffe5bd4824): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-110 - Mickleham South ( Pit 1184-1185)
c99008ca-c7c6-4080-9cab-65bd56c93306 | Child Lot Verification(df811052-4f58-46f7-85ae-6156dc5da4e2): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-111 - Mickleham South ( Pit 1186-1187)
cb8b1acf-d0dd-4800-8489-f320f0f5edae | Child Lot Verification(a92782c8-4da6-4041-9e07-c178821f5d39): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-112 - Mickleham South ( Pit 1188-1189)
04ed15ce-d5a5-449a-a18d-565aa7c5f421 | Child Lot Verification(d36165e6-8c71-42c7-9bf8-85846cd8c6b7): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-113 - Mickleham Intersection (NE) ( Pit 994-1190)
c7bca1e7-82bf-4f20-a838-15d6f08be8da | Child Lot Verification(022570ae-205f-406e-8751-5180d61a429b): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-114 - Mickleham North ( Pit 1117-1118)
f6502e47-7989-469c-9d2e-cb1ff344511b | Child Lot Verification(5df6acf0-f9da-417f-ac42-7930b8a4d8f3): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-115 - Zone 7 East - Mickleham to Debonair WB - Pit 561 to 560
8c61f9ee-e967-44e9-a60a-49fafc322f05 | Child Lot Verification(e7188c06-4d5e-4a53-b5a9-60a245ba09b6): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-116 - Zone 7 East - Mickleham to Debonair WB - Pit 560 to 559
d506e05e-a552-40e6-84d5-e2479d18d681 | Child Lot Verification(b5c55311-c5ed-4fec-bc99-a362482e0a4e): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-117 - Zone 7 East - Mickleham to Debonair WB - Pit 559 to 558
314313fa-c7ef-4156-936d-3358bb58de63 | Child Lot Verification(8914d9c4-50dd-4f2f-b3a8-0647a73d987e): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-118 - Debonair Intersection WB - Pit 558 to 558b *Cancelled*
4a0d5c16-b2c6-4b48-8214-119ba7c30bee | Child Lot Verification(c6a097b8-eedd-464e-b109-97c0f1b80d6b): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-119 - Debonair Intersection WB - Pit 558b to 557a
bba35eba-3cc9-4e61-9ddc-e0317b4ea6cc | Child Lot Verification(630a34b4-f731-4dbb-ac5f-e89b8d9b680c): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 3bc96fed2b3c6c2deffe73d1aa6b18a087473e3c9635f16cdaffddb5e52c61c6 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-120 - Zone 7 East - Mickleham to Debonair WB - Pit 558a to 558
2ab1ee7a-97f9-4aad-ad11-7a60a1cd86d3 | Child Lot Verification(90fad255-44eb-44bf-80b4-b1d8532f3700): checkpoint-group has incorrect meta.stepType checklist-flat | checklist-sectioned | work-in-progress | 148dcf43fa45fa86e6fec847c919f94dcf9801ee293f6138de7cd7ca62968308 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-121 - Debonair Intersection WB - Pit 450 to 450a
b7f50e9a-f406-4107-86aa-6bb97cbdc8e3 |  | checklist-sectioned | work-in-progress | 0d565480695df7c335e579125810526806b5b04e1c41eabc057fc9dc8f5af101 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-122 - Stormwater Drainage - Pit 1176 to Pit 1177 - Zone 7 West Stage 1 (SW Intersection)
e0ec8ec3-09a8-45bd-835e-933fb5865a41 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-123 - Stormwater Drainage - Pit 1177 to Pit 1178 - Zone 7 West Stage 1 (SW Intersection)
bb590258-11f5-49a6-8e00-77ab23b3f1b0 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-124 - Stormwater Drainage - Pit 1177 to Pit 1066 - Zone 7 West Stage 1 (SW Intersection)
e6dea5ab-963b-4e82-bef0-a59011eb1928 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-125 - Stormwater Drainage - Pit 1176 to Pit 1015 - Zone 7 West Stage 1 (SW Intersection)
09f8d6a7-8579-4798-bbd5-58acd7ca2a2d |  | checklist-sectioned | work-in-progress | 0d565480695df7c335e579125810526806b5b04e1c41eabc057fc9dc8f5af101 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-126 - Stormwater Drainage - Pit 1049 to Pit 688ab - Zone 7 Mickleham Rd North (Southbound)
af40421e-2a56-4947-b9f8-bf5617396f20 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-127 - Stormwater Drainage - Pit 1047 to Pit 1047a - Zone 7 Mickleham Rd North (Southbound)
4a9a1397-2534-4ec4-8673-bbd1ab278e3d |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-128 - Stormwater Drainage - Pit 1045 to Pit 1163 - Zone 7 Mickleham Rd North (Southbound)
34fefcb9-aaf7-4374-a7d8-0461138bb3ba |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-129 - Stormwater Drainage - Pit 1043 to Pit 1160 - Zone 7 Mickleham Rd North (Southbound)
d2e72b42-92a0-48ab-aaef-8a3868d33f10 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-130 - Stormwater Drainage - Pit 1041 to Pit 688aa - Zone 7 Mickleham Rd North (Southbound)
dc1e9182-9ccf-487c-ba1c-49be58cd5558 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-131 - Stormwater Drainage - Pit 1037 to Pit 688a - Zone 7 Mickleham Rd North (Southbound)
ab23d5a8-202a-4042-90ae-d9c94a908f2a |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-132 - Stormwater Drainage - Pit 1035 to Pit 1059 - Zone 7 Mickleham Rd North (Southbound)
22f67d29-7ae0-449f-a48b-17a65ee89c1a |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-133 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to Vantage (Westbound) (Superseded by 136)
fb82202f-9b7b-4564-8b2b-41b11b8b508f |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-135 - Stormwater Drainage - Pit 558 to Pit 558C - Zone 7 East Mickleham to Debonair
994d54b6-2118-4c1b-b235-e1fec607de8c |  | checklist-sectioned | work-in-progress | 0d565480695df7c335e579125810526806b5b04e1c41eabc057fc9dc8f5af101 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-136 - Stormwater Drainage - Pit 847 to Pit 846 - Zone 7 East Debonair to vantage
f5a5f86c-0fae-431d-9986-43d7bb988c53 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-137 - Stormwater Drainage - Pit 846 to Pit 845A - Zone 7 East Debonair to vantage
06ac54d9-7725-408f-8899-9f5bebf20fbe |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-138 - Stormwater Drainage - Pit 845A to Pit 845 - Zone 7 East Debonair to vantage
090e1f72-7975-4b7b-b49e-e959812ba42e |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-139 - Stormwater Drainage - Pit 845 to Pit 844A - Zone 7 East Debonair to vantage
708bd5e5-b36f-40be-b36b-9cbe6a7380a8 |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-140 - Stormwater Drainage - Pit 844A to Pit 844 - Zone 7 East Debonair to vantage
fd94a289-a09a-4330-90ce-9a1b60bb3c9b |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-141 - Debonair Intersection WB - Pit 558C to 558b
5a1d1216-6c60-416b-bfb3-382dd3e4d4ee |  | checklist-sectioned | work-in-progress | e2b737d9a817b30d25b23684ca768609dcc946ba537b43baf0708b558848317a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-142 - Debonair Intersection WB - Pit 558B to 557A
b84eaebc-4797-4c75-91f1-273946145aa0 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-143 - Zone 7 East Deb-Vantage Pits 545A-544
f6fcc2ed-f6c4-46c8-85a8-2869fe1326a5 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-145 - Zone 7 East Deb-Vantage Pits 544-543
f0f58b3f-074c-4aeb-9d89-ac89ed767207 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-146 - Zone 7 East Deb-Vantage Pits 543-542
6b99915a-c327-46a9-9171-dcf519ed565b |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-147 - Z7 East S2 Mick to Deb - Pit 873 to Pit 872
4c48b571-5671-4f64-a01a-b0cba1d630c0 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-148 - Z7 East S2 Mick to Deb - Pit 872 to Pit 871
a3ec7e46-564a-40c0-af12-6b4d83a8019e |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-149 - Z7 East S2 Mick to Deb - Pit 871 to Pit 870
dd31e96e-56b8-415d-84cb-bd73723edf07 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-150 - Z7 East S2 Mick to Deb - Pit 870 to Pit 869
ba672d27-c738-4468-b569-cb91eeabb431 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-151 - Z7 East S2 Mick to Deb - Pit 869 to Pit 868
cb7a024c-5fff-4e2b-afa2-fc34b0c6af8c |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-153 - Zone 5 Aitken South SB - Pit 1090 to 1091
a186e723-bbd7-4335-847c-3e178cf2401a |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-154 - Zone 5 Aitken South SB - Pit 1091 to Ex.1092
93bb4b95-96ad-4011-a63a-cba5347d64c4 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-155 - Zone 5 Aitken South SB - Pit 1091 to 1091a
3ec119f0-a90d-4b14-ab44-86d0838b60ab |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-156 - Zone 5 Aitken South SB - Pit 1091a to 1091b
cba3768d-4f7b-4ea4-a2d5-61035e803b6a |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-157 - Zone 5 Aitken South SB - Pit 1091b to 1091c
17ddee2f-44cb-4fd9-9d15-a3b8c69701f3 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-158 - Zone 5 Aitken South SB - Pit 1091c to 1094
a84c0908-8611-4a92-a388-74653bddcb8e |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-159 - Zone 5 Aitken South SB - Pit 1091c to 1091d
a4c785d8-c45c-453f-a8f9-fb79127ae54b |  | checklist-sectioned | pass | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-160 - Zone 5 Aitken South SB - Pit 1091d to 1091e
9216b9ad-0710-44db-ae11-2d28afe787e7 |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-161 - Zone 5 Aitken North SB - Pit 1057 to 1133
170fde39-db77-497d-99e7-0d9fcf6be87b |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-162 - Zone 5 Aitken North SB - Pit 1133 to 1137
3cc95bbf-82d5-45d8-8bbb-187675c7d9e2 |  | checklist-sectioned | work-in-progress | 6119dbc948e9efa5baefa324c00558cd7bcbbf9ac276c5fa49398eb83bc0d11f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-163 - Zone 5 Aitken North SB - Pit 1137 to 1139
639dcc82-1bfa-4399-a0e2-8c590a4f30af |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-164 - Zone 5 Aitken North SB - Pit 1139 to 1136
8313c76a-33a0-4cc7-aaea-d19fae2a2822 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-166 - Zone 5 Aitken South SB - Pit 1098 to 1300
574460f5-9343-4ed8-84b2-e5096fed67d2 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-167 - Zone 5 Aitken South SB - Pit 1300 to 1031
e4ecff23-427e-4f25-8fa4-98e5e43a2fdd |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-168 - Zone 5 Aitken South SB - Pit 1031 to 1064
94ee6360-5f16-4d44-bfdf-f2485e650a8e |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-169 - Zone 5 Aitken South SB - Pit 1064 to EX. 1142
f568be05-1281-4721-8806-fb353f3ac783 |  | checklist-sectioned | work-in-progress | 4973fb75b67d8d15dcb6254be2afad252b07b794f4e47f9359863a411f131b5e | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-170 - Zone 5 Aitken South SB - Pit 1031 to 1030
fdfbe256-efee-480b-9cfa-6092bd258029 |  | checklist-sectioned | work-in-progress | 7be58703b2b9121b1ed0d0c034407ffefcbbd11561fc75dbe0af296831ce6910 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-171 - Zone 5 Aitken South SB - Pit EX. 653 to 991
88d9db9b-28ba-4c96-b045-911436c92759 |  | checklist-sectioned | work-in-progress | f87f8d96218e2552a74d0b1c1c76370fe92a0e24a41d947776312a839c5e8d2a | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-172 - Zone 7 Vantage - Pit 910 to 707
7edb8da1-ac30-4d1b-9bc7-9ea2921b1b47 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-173 - Zone 7 Vantage - Pit 707A-705B
5b7ac6ff-18c2-4d84-a94a-67c47a8c0ade |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-174 - Zone 7 Vantage - Pit 705-705B
1bccd679-71ae-47d6-a36d-6090745180a4 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-175 - Zone 7 Vantage - Pit 705B-705A
306a7976-28a6-4da2-910c-74a2152d2803 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-176 - Zone 7 Vantage - Pit 705A-536A
84fb6ebd-6fcc-4fda-8b70-65a647d6e6d5 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-177 - Zone 7 Vantage - Pit 536A-537B
8eaf78d5-dc37-4235-9da2-225ccec3f65a |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-178 - Zone 7 Vantage - Pit 537B-537
f0802f78-0a75-4a0e-aad5-8445caca27f5 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-179 - Zone 7 Vantage - Pit 537-537A
9eac0c53-1fb9-4f87-9f48-5fa72a23e0d3 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-180 - Zone 7 Vantage - Pit 537A-538
9c7d7da1-8b34-468a-b7e7-f11073a57c65 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-181 - Zone 7 Vantage - Pit 538-539
3bee9d36-03be-4120-81f8-385d72295757 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-182 - Zone 7 Vantage - Pit 539-540
e0561639-91a1-4294-b1ad-7ffc8698a39a |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-183 - Zone 7 Vantage - Pit 540-541
a0fcfee4-a9c7-4726-a60a-b75afb2a9d6b |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-184 - Zone 7 Vantage - Pit 541-542
865ae42e-ae58-41dc-b7e7-ee66d720d746 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-185 - Zone 6 Pit 609.1-609
4828dcfa-b690-4608-8c23-bb2c923924d5 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-186 - Zone 6 Pit 609-608
a128804c-c768-4798-8cfb-c2ac41721848 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-187 - Zone 6 Pit 608-607
f85241b7-5f2d-43d8-9d40-c2915455567b |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-188 - Zone 6 Pit 607-606
4b8282fe-b5fe-4db4-b7b0-6a90b08497fd |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-189 - Zone 6 Pit 606-605
e39c4636-ce68-4d64-a72b-eae893d64421 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-190 - Zone 6 Pit 605-604
dd0fff3a-dc52-46ad-bc89-5fd304f19666 |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-191 - Zone 6 Pit 604-603
a5c52f65-d5f6-4142-acae-dd8d77c97fd5 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-192 - Zone 6 Pit 603-602
2865a1a4-acaf-437e-b1dc-474859bc5f4a |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-193 - Zone 7 Pit 705B-705
5099cacd-9333-4758-a7e1-cca9d7267202 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-194 - Zone 7 Pit 705B-707A
b05c929c-6b62-4aa0-b47e-8b7bb6d2b85a |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-195 - Mickleham South NB (1178A-1179)
e5998131-aa26-406e-8828-0bc29d78571c |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-196 - Mickleham South ( Pit 1125-1126)
571bd320-2732-46e9-b72b-d2295ac1ef1b |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-197 - Zone 5 Aitken South SB - Pit 986 to 1024
c5aade99-1408-4468-bdcf-8ff905ff7fc5 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-198 - Zone 5 Aitken South SB - Pit 1024 to Existing Pit
ab3c0d61-3c77-4caf-a7e1-07b05488e181 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-199 - Z7 East S2 Mick to Deb - Pit 868 to Pit 868A
89b95ada-656c-4b2f-b7ee-3a2ea7a73a51 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-200 - Z7 East S2 Mick to Deb - Pit 868A to Pit 867
c0bcd11e-d722-4d2b-a242-45e5e07217ee |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-201 - Z7 East S2 Mick to Deb - Pit 867 to Pit 867A
0af65c09-9633-450c-8965-8b051a4e191c |  | checklist-sectioned | work-in-progress | cab51d2f4b24dfe76b891e2065659c3c4a02b4a5bf6430269c6f2bc6ea8f0e79 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-202 - Zone 5 Aitken North SB - Pit 1119 to Existing Pipe
78b7177d-b4c2-41dc-8f14-913d320572f6 |  | checklist-sectioned | work-in-progress | 0c240fa586f3be42a163c909edbcbeccec31d1a3ebc86dc0fb315b32ed088960 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-203 - Z6 595A-602
3de3e0cd-ff40-4328-b8cb-ed76bf0e9221 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-204 - Zone 5 Aitken North SB - Pits 1127 to 1123
3965eb1e-aa55-4624-9e1a-116bb770f4b6 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-241 - Zone 6 594A-594
e7751315-fc3b-4eb9-81e6-edb9cb298c0c |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-242 - Zone 6 594-595A
9fea9279-e41d-401b-a2ca-10c302f500ce |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-243 - Zone 6 619C-619B
4f065b9d-a2fc-4e0b-84d8-ce61554a2892 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-246 - Zone 6 - 619B-619A
1c97e088-6015-4781-b385-2efbdf498988 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-247 - Zone 6 - 619A - 619
b2134c39-586a-4a3f-8789-e8daf3314090 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-248 - Zone 6 - 619 - 320
c831645b-6de7-4187-9e32-269cd457b3ae |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-249 - Zone 6 - 320 - 620A
3ac502f3-2914-4b9e-ae7a-8983c92ebea1 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-251 - Zone 6 - 822B-623
67ea335e-05bb-4311-a389-093486674621 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-252 - Zone 6 - 623-624
ee9310f9-0264-416f-8890-4f140b5cdd11 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-253 - Zone 6 - 626-627
42ab29fa-0044-47b2-8b6c-bf940f53d1ac |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-254 - Zone 6 - 627-628
7c768bb5-a5c2-456a-9db9-f085b4374861 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-255 - Zone 6 - 628-629
c15803dd-b9d5-46b8-ace3-b371e87245b0 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-256 - Zone 6 - 629-630
0763007d-c5fe-424f-b2ad-edd6b2c3ad07 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-257 - Zone 6 - 625a-623
0490fa2c-1c09-4c24-aac1-7aaaf2b97b34 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-258 - Zone 6 - 630-631
179f867c-8938-45b1-afe3-c687cb1221b8 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-259 - Zone 6 - 631-632
bcbedac6-efc1-430d-bab2-2d78dd537154 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-260 - Zone 6 - 592A-591
64d6ff76-954c-4580-8051-e58a29a23334 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-261 - Zone 6 - 624-625
d291c372-3a4a-4d47-9c4d-581ced7441d1 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-262 - Zone 6 - 631-632
732881ab-41e5-4de4-9765-a0e267ff1d0a |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-263 - Zone 6 - 625-625A
c2a24493-83e6-4ab4-ae5b-d4accfe70cab |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-334 - Zone 6 - 776-777a
4989a91e-6c88-46f0-9582-764cbb8416bd |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-328 - Zone 5 Aitken North East Corner - SB - Pit EX.893 to 1301
c5bacabf-1891-4989-8ebb-a2b845b89851 |  | checklist-sectioned | work-in-progress | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-335 - Zone 5 Aitken North East Corner - SB - Pit EX.893 to 1078
933ce988-5d9c-4987-85b3-f42331b48da2 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-336 - Zone 5 Aitken North East Corner - SB - Pit 1076.1 to 1078
e1df5ebc-9124-4839-b1db-9643cbdbd13b |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-337 - Zone 5 Aitken North East Corner - SB - Pit 1077 to 1078
5906192d-122b-4bb5-9ea5-d0e29dea6184 |  | checklist-sectioned | not-started | ITP 0017 - Underground Stormwater Drainage | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-017 - Underground Stormwater Drainage | ITP-017-A2-LOT-338 - Zone 5 Aitken North East Corner - SB - Pit 1060 to 1078
99cf921c-19e4-4ba7-b6e2-36f7ce9e96fa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation
225455cb-7159-4ee9-afb2-65bf4a8b94de |  | checklist-sectioned | pass | 0ad47b0d976d97ce792d427372694243f3e7fba1e7cf097eb9b7fcb50408e44b | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-001- Mickleham South (NB) CH30000 - CH30234
541122a1-b9f1-43d4-abe1-5249b5808cb5 |  | checklist-sectioned | work-in-progress | fb65e9e01f355121e42fc2f0668eb91e53bcddb7b6cd1581f437da704fde8435 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-002 - Mickleham South (Median) CH30120 - CH30360
aff0d553-8a71-420c-ad84-9d773cfb18b4 |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-003 - Mickleham South (SB) CH40050 - CH40280
509ccd5f-e1d2-4d71-823a-aa7993c98c4b |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-004 - Mickleham South (NB) CH30234 - CH30365
a4073707-3b55-4930-86e6-881aa18b1a3f |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-005 - Mickleham North (SB) CH40640 - CH40720
ad9a38da-526d-4274-8769-496f67236b00 |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-006 - Mickleham North (NB) CH30615 - CH30700
05d52d26-f6d7-4211-ba08-50cfe99859bf |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-007 - Mickleham North (Median) CH30433 - CH30680
334af3cd-8c73-4844-ae60-d9f47ec5d6be |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-008 - Mickleham North (NB) CH30450 - CH30605
b3207a12-9af6-491b-88f1-6b63a09a4b43 |  | checklist-sectioned | pass | 844c41c7d659e50b28fe9a95959dfb7b10cf3e09671fa7755fd96b2c471cda90 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-009 - Mickleham North (SB) CH40490 - CH40560
02cc0d5c-943a-48c3-813f-f29b0f340c6e |  | checklist-sectioned | work-in-progress | fb65e9e01f355121e42fc2f0668eb91e53bcddb7b6cd1581f437da704fde8435 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-010 - Zone 7 West CH 10080 to CH 10170
c8e3a334-a786-4d44-99c2-c52ddba5a01e |  | checklist-sectioned | work-in-progress | fb65e9e01f355121e42fc2f0668eb91e53bcddb7b6cd1581f437da704fde8435 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-011 - Zone 7 East - CH10600-10820
8abfb783-786f-4525-9a3f-471c2d1e5531 |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-014 - Zone 7 East - ch10875-ch11110
9e974774-978d-479e-af98-ab9ff08d7833 |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-016 - Zone 7 East - CH11150-CH11300
2e9b757c-18ca-411c-ac6c-0a2f0887af1c |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-017 - Zone 7 West Verge CH 10160 to CH 10470
90bcafba-89e4-4d56-8c3e-84b77f555968 |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-018- Zone 7 West median WB CH 10234 to CH 10380
d5ed6ced-9054-40d1-a555-e8c0d4ae10cf |  | checklist-sectioned | work-in-progress | 9b1e41d6c809b32ef4f9fdbaa173d57b887ac2db2c262db70947aa03258e3469 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-019 - Zone 7 West WB Verge - CH10100 to CH10144
c603caa5-69d7-4d12-a175-da74af64e11c |  | checklist-sectioned | not-started | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-020 - Zone 7 East Mick to Deb - CH10825 to CH10965
74104133-db53-4446-824d-36a86a730f6f |  | checklist-sectioned | work-in-progress | ab687ef11fa4494c83d9e987c49b41b505c58c882cb0668480834e8fd593f83f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-021 - Zone 7 Debonair to Vantage - CH11330 to CH11670
07934a6f-bb78-4920-a2b6-4bf38d83d72a |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-022 - Zone 7 East Stage 2 - CH20550 to CH20750
8c26a492-8a17-4467-bfd7-6be664ae0254 |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-023 - Zone 7 Mickleham Intersection - NE (CH40357-40407)
3a5e4a46-243d-4819-ba59-11713d70dece |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-024 - Zone 7 East Stage 2 - Median (CH20537-20751)
58e8dd6a-7520-470a-b044-7a80d62dbc4b |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-025 - Zone 7 West Stage 2 - Median + Verge (CH20178-20455)
e72b7f28-77e7-4ad7-a4d5-96d3a6192321 |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-026 - Zone 5 South Stage 1 - Southbound (CH60360 to CH60515)
53852bd9-5824-4a48-b7c2-afced84930cb |  | checklist-sectioned | work-in-progress | ITP 0026 - Guardrail Installation | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-026 - Guardrail Installation | ITP-026-A2-LOT-027 - Zone 6 Champion to Vantage - Westbound (CH11900 to CH12280)
e9acce40-c3bf-4fb6-9115-d738d1a21c9a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-049 - Topsoil Placement and Landscaping
902d80f4-9460-4a02-82ee-02f8f09ea1bf |  | checklist-sectioned | not-started | a39837f6bddd2459481a4b0889cbeb114af99d4166e00ad19bdb02d3cded3945 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A2-LOT-001 - Zone 7 East Debonair Pde CH11280-11350
557d78a9-1eb6-4b00-8067-44635648c38d |  | checklist-sectioned | work-in-progress | e040ab70a3bb56b0457209394fde7c5c84581a7f4890b4c4f1b05d842f306689 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A2-LOT-002 - Zone 7 West CH 10100 to CH 10500 WB Lane Verge
0ab74a99-6953-44d6-8424-cbb34f841a5b |  | checklist-sectioned | work-in-progress | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A2-LOT-003 - Zone 7 East Mickleham to Debonair - Stage 1 (CH10825-11300)
6def1d45-32a7-4c2b-9ddb-2c57c4629c52 |  | checklist-sectioned | not-started | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-049 - Topsoil Placement and Landscaping | ITP-049-A2-LOT-004 - Zone 7 Mickleham Road - South West (30000-30375)
6c913bcf-ce4f-46af-912f-b47342106345 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways
6f4f9cdf-3402-4856-af89-e1eb6356241f |  | checklist-sectioned | work-in-progress | 0f1c99b67408a3eefde097425d123a3cd62f4e2ad030add57f23458a38bec562 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-011 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40640-40685
3593c5b3-3176-45f5-98c2-78b4ee79dcb7 |  | checklist-sectioned | work-in-progress | 0f1c99b67408a3eefde097425d123a3cd62f4e2ad030add57f23458a38bec562 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-012 - Maintenance Strip Install - Mickleham Road North, S/Bound CH40685-40715
8b836968-29e3-4d30-a373-6fd80635c296 |  | checklist-sectioned | work-in-progress | 0f1c99b67408a3eefde097425d123a3cd62f4e2ad030add57f23458a38bec562 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-013 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10545-10620)
6fce2ab4-a8fb-42ab-af02-0e103f9c8ce4 |  | checklist-sectioned | work-in-progress | 0f1c99b67408a3eefde097425d123a3cd62f4e2ad030add57f23458a38bec562 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-014 - SUP - Zone 7 East, SE Corner of Mickleham Intersection (CH10543-10551)
b82b3107-f2c4-41aa-95f3-505904b79f8e |  | checklist-sectioned | work-in-progress | 0f1c99b67408a3eefde097425d123a3cd62f4e2ad030add57f23458a38bec562 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-015 - Maintenance Strip Install - Mickleham Road North, N/Bound CH30480-30605
abff7df2-f284-4735-9d24-39e83334ffa2 |  | checklist-sectioned | work-in-progress | 913e9f7b9ca68ba65ce168cf4a1166325989a16b56ee19de250bfff4f266b433 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-018 - SUP - Mickleham Intersection Northbound (CH30621-30688)
6fff6418-bc8e-453b-a87d-4b73b7feece9 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-016 - Mickleham Road North (S/Bound) - Concrete Driveway (CH40616-40643)
63e82f81-8d5a-4cce-8474-18965043b1b4 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-017 - Zone 7 East SUP prep CH10830-CH11230
006f07f7-f430-48a6-8e51-9205a5e4f33e |  | checklist-sectioned | fail | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-019 - Zone 7 Debonair - Traffic Island CH11315
9ee12d05-6ec0-4809-97f5-ef6b823768ee |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-020 - Zone 7 Debonair - SUP
13681aa6-732a-4368-884e-eeee80e4c2bd |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-021 - Zone 7 East - SUP 10980-11100
5b14a5f3-7410-4c99-a986-a9c4b2a5bab5 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-022 - Zone 7 East - Driveway
c7efb98e-c83e-48f0-a683-38735b44e0e1 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-023 - Zone 7 West SUP CH 10300 to 10470
0d6245eb-3aa4-44ec-a9b0-ffd57f767760 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-025 - Zone 7 West Property 755 Driveway, x2 driveways for 1505
beb9e50c-2dd5-44e8-8550-79b1e452003f |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-026 - Zone 7 West SUP CH 10300 to 10150
7feb5d98-9dc7-440c-af46-c5a47c66d70c |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-027 - Zone 7 West SUP CH10470 to CH10500 + SW Traffic Island
304f9573-b044-49d7-adc6-3b52b852510d |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-028 - Z7 West Maintenance Strip CH 10370 to CH 10470
aa439409-1936-4172-aff0-a6da7741206e |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-029 - Z7 West maintenance strip CH 10370 to 10 250
9637c674-aa34-4321-801e-029adb79949b |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-030 - Zone 7 East - SUP 11100-11230
cbb743c6-828d-4fe0-8c2a-d2afd026dc3d |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-031 - Zone 7 East - SUP 10830-10980
09d44a1f-2d68-4c69-a1a1-de69a993c485 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-032 - Zone 7 West Stage 1 SUP - CH10100 to CH150
6ef2b0dc-9b5d-46b2-8107-f9ca4af6fcaa |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-033 - Z7 West Stage 1 Maintenance Strip - CH10150 to CH10330
2377377b-a452-47bb-9651-3706dfbaff07 |  | checklist-sectioned | pass | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-034 - Zone 7 East - Driveway
eb1e3e87-5316-4064-ba62-5f64cc30dd92 |  | checklist-sectioned | work-in-progress | 0af71435f38629ad08d8c3d27542ef98845269e2bf0e3bcf5cc17c2827d97409 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-035 - Zone 7 East Type-15 11112-11130
03bda441-557e-4f7f-a72b-75e8e7071f4e |  | checklist-sectioned | work-in-progress | b0f68f28fd8d787342d5951aa3f8c309df3f0428a3ce924fd67f61367a464f09 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-036 - Zone 7 East Maintenance strip 10870-10970
c2000aac-6265-43a7-9312-7f8bf2b547e1 |  | checklist-sectioned | work-in-progress | b0f68f28fd8d787342d5951aa3f8c309df3f0428a3ce924fd67f61367a464f09 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-037 - Zone 7 East - SUP 10820-10860
3428b512-7052-4cc9-bf97-22f52b5a26c6 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-038- Zone 7 East Maintenance strip 10970-11130
6c34f4bf-874e-4bd1-bca1-d9d06d968046 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-039- Zone 7 East Maintenance strip 11130-11280
50096962-42c5-47a1-a7eb-a243474a24de |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-040 - Zone 7 Mickleham Rd North - Median Infill North End
196553ff-3431-4b7a-aba0-7b7a4ec4fc08 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-041 - Zone 7 Mickl. Rd North East SUP CH 40500 - CH 40630
4e592b29-08af-4148-a097-67bdfca7f465 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-042 - Zone 7 Vantage 11850-11880
5601438c-ee0d-44cb-87e0-5149ff123285 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-043 - Zone 7 North - 1540 Mickleham Rd Driveway CH40556-40580
b5ac586e-9ab3-4f69-abf5-330500c9b3d1 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-044 - Zone 7 Mickl. Rd North East SUP CH 40495 - CH 40520
7e5b886c-4099-43a6-9e65-facf45932584 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-045 - Zone 7 Mickl. Rd North East SUP CH 40430 - CH 40490 ; CH 40400 - Ch40370
6008a864-c807-4028-ba13-b4fd217ec195 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-046 - Zone 7 North - 1530 + 1540 Mickleham Rd Driveway CH40457-40495
dcf50f14-0d76-40d8-a48b-8b1c2db46fce |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-XXX - Ch 40380 to 40400
d6edadca-c5df-47f2-bc51-28b151e753fb |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-047 - Zone 7 Mickleham North Median - Maintenance Strip (NB: CH30434-30471, SB: 40371-40412)
f984ec65-68f0-45eb-8c56-74023c11eb9e |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-048 - Zone 7 East Mickleham to Debonair Median - Maintenance Strip (CH11190-11288)
b4b31fd1-d042-4d9f-992c-516d8439f161 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-049 - Zone 7 Mickleham Road North (CH40527-40631) - Spoon Drain
0acc7e70-c4e1-463f-9468-b8b10b9b3543 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-050 - Zone 7 Vantage CH11825-11870
06f16dc5-c320-4474-99c8-e81d1f05676a |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-051 - Zone 7 East Mickleham to Debonair Median - Maintenance Strip (CH10965-11288)
74f4d9a2-f76f-49e4-999f-fc47435c35ed |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-052 - Zone 7 Mickleham Road North (CH40380-40527) - Spoon Drain
f2c5045b-197c-4ff0-b615-8ad92bd566a6 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-053 - Zone 7 Debonair Pde SUP - SW Corner (CH11320-11325)
7553c83a-25fc-4bf6-b79e-6dd33a89e1aa |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-054 - 1570 Mickleham Rd North Driveway (CH40717-40725)
454ce9f7-3931-4050-82b5-9941cfc99a4e |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-055 - Zone 7 East Stage 1 Mickleham to Debonair - Maintenance Strip (CH10845-10965)
98aadb42-998b-477c-9697-9b1ebd3435a2 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-056 - Mickleham Rd Intersection NE Traffic Island (CH40341-40359)
19011b13-46df-46c3-994b-c43c6b965a68 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-057 - Craigieburn Rd Intersection NE Traffic Island (CH20528)
b161d7eb-7a1d-4394-a680-dcef71352cdc |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-059 - zone 7 stage 2 mick Rd - 10540 to 10730
f118b198-0ff5-453a-a360-3e27c40977fe |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-058 - Zone 7 Mickleham Intersection NE - Corner Infill (CH20527-20557)
0099245c-e611-49d4-9b27-a0ec49146800 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-063 - Zone 7 East Stage 2 (CH20705-20750)
806b240d-bfd8-483f-b5d7-04a0aa3ae275 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-060 - Zone 7 West Stage 1 - Maintenance Strip (CH10105-10155)
5c5e1839-e096-4fca-8ada-fc10c2a7c08d |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-061 - Zone 7 East Stage 2 - Maintenance Strip (CH20550-20750)
eb02e281-6bb0-4e67-8fac-ba4dcaa034f9 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-062 - Zone 7 Mickleham Rd North West -SUP (CH30500-30600)
e9c29752-6753-4b76-8d47-8599df12c6bc |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-064 - SUP Zone 7 West Stage 2 CH 20400 to CH 20450
03ee829f-cdac-4080-9b46-97fac8d6e439 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-065 - Zone 7 Mickleham Rd CH 30500 - 30450
d9a2d853-984d-4d28-a7d0-b2d02a06462a |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-066 - Zone 7 Mickleham Rd North West - Remaining Sections (CH30600-30621; 30681-30698)
87f97f5d-b88f-49b5-9329-0370e3b646b8 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-067 - Zone 7 Mickleham Rd North West Driveway (CH30603-30613)
72fd307b-60f2-4bf6-8b57-0ad1d3f15beb |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-068 - Zone 7 Mickleham Rd North East x2 Driveways
4c969fa9-0c89-4056-a7fc-4fbbbf8b38a5 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-069 - Zone 7 Mickleham Rd North East Guard Rail Footing 40358 - 40364
67fcec60-4f9d-40c1-b482-e04fbb7d0a6d |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-070 - SUP Zone 7 West Stage 2 CH 20310 to CH 20400
e2e8f621-d9bd-449a-a002-1dbfd6bd1516 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-071 - SUP Zone 7 West Stage 2 + NW Mickl Rd CH 20450 to CH 20490
6b6361d9-f831-42c2-9b3c-6744e9a06df8 |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-072 - 3 bullnose mick intersection
7b230d07-184d-4798-a3cf-165d2f8da326 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-073 - Zone 5 Aitken South - Median Island and Bullnose Northern Part - CH60535 to CH60465
c9da3eb0-18ad-47f4-9350-e09ca6857599 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-074 - Zone 5 Aitken South Stage 2 - SUP
94920465-fa7c-4ed9-8200-7d5f7520787c |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-075 - Zone 7 West Stage 2 - 730 Craigieburn Rd Driveway (CH20280-20291)
9d404241-cbba-4214-819d-74975b936f23 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-076 - Zone 7 West Stage 2 - SUP (CH20256-20313)
6ad34d0d-7092-4f73-ae74-706afb6e26d7 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-077 - Zone 7 West Stage 2 - SUP (CH20175-20255)
949a725c-878a-400e-a107-894c12e2ee88 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-078 - Zone 7 West Stage 2 - SUP (CH20130-20175)
a487c5c2-3cca-4cf9-a2bc-7bb4fc8e256a |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-079 - Zone 7 West Stage 2 - SUP Rework (CH20256-20313)
a21887ea-7551-41b3-b200-7c31e340161b |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-080 - Zone 6 East Vantage Traffic Island - Left Half (CH11870-11880)
91c296ac-2895-4613-86b5-e087c9bc69ca |  | checklist-sectioned | not-started | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-081 - Zone 6 SUP CH12450-12590
271c8200-3c30-4828-91d1-de0de9f0825c |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-082 - Zone 6 East Vantage Guard rail footing - (11900-11923)
5d9cfc59-0b1c-47ad-91d8-26c0813a10da |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-083 - Zone 7 West Stage 2 - New 760 Craigieburn Rd Driveway (CH20080-20090)
8ec26c60-84f2-40da-b7da-0fa71dfe702b |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-084 - Zone 7 West Stage 2 - SUP (CH20100-20130)
ff1f73c4-789c-42df-93b2-166072201ac9 |  | checklist-sectioned | work-in-progress | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-085 - Zone 7 West Stage 2 - SUP (CH20060-20100)
98a1cd49-7c8b-42f1-b0a2-6b8804dc08f4 |  | checklist-sectioned | pass | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-086 - Zone 7 East Guard rail ground Beam ch10850 to CH10750, 10610 to 10630
ac70c05f-f661-4d77-bea9-0d96da24c8d0 |  | checklist-sectioned | pass | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-087 - Zone 7 East Guard rail ground Beam CH10550 to CH10650
e7d97bcf-ddb8-402c-8677-06af7a33ff2e |  | checklist-sectioned | pass | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-054 - Traffic Island, Median Island & Driveways | ITP-054-A2-LOT-088 - Zone 7 East Guard rail ground Beam ch10650 to ch10750
727fa296-813d-436d-bc59-479b103228f4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-065 - Wire Rope Safety Barrier (WRSB)
e130a071-d950-42e9-8488-e59ad2f9da7a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-074 - Permanent Fencing
6663e4af-a5a0-436b-8140-3aba1b431b2a | Child 3 - Conformance(ded3d15b-2ac6-5e23-99db-1b41fe783b15) -- Final Inspection - Work Completed On(4c3226d4-a07c-4fd8-90e9-42a4cc182f84): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | eef7ab9006207d584f5fd08a8dfa93ae2808e757295a9880d75b7a01fde80095 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-074 - Permanent Fencing | ITP-074-A2-LOT-001 - Zone 7 West - CH 10090-CH 10240
1bad43d3-3b79-431c-9ce2-65cbcad46ad8 | Child 3 - Conformance(47844070-b33e-5610-9157-57957a21947f) -- Final Inspection - Work Completed On(f8198792-a9d2-46e5-bc82-77356a7f8a61): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | eef7ab9006207d584f5fd08a8dfa93ae2808e757295a9880d75b7a01fde80095 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-074 - Permanent Fencing | ITP-074-A2-LOT-002 - Zone 7 West - CH 10240 - CH 10295
d6142e18-ff0d-47b1-b2a5-6baf01da9ac0 | Child 3 - Conformance(dafbf94b-8458-5025-a1fe-299f6e974587) -- Final Inspection - Work Completed On(8ad2a6b6-b601-4465-b694-592716a5f0a9): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | eef7ab9006207d584f5fd08a8dfa93ae2808e757295a9880d75b7a01fde80095 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-074 - Permanent Fencing | ITP-074-A2-LOT-003 - Zone 7 West - CH 10360 - CH 10490
800d2941-4ae8-4df2-b138-22b448ce71ca | Child 3 - Conformance(a9241b32-4da3-5d45-bf5f-1c77b35342b4) -- Final Inspection - Work Completed On(9ad80103-c6f9-4f8c-82eb-0ad21ea24179): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | f3b70fc5f9eebbf016e22ae98a1560924af9a1240a24fc432c9982d5a86ac7e3 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-074 - Permanent Fencing | ITP-074-A2-LOT-004 - Zone 7 West - CH 10295 - CH 10360
22c7bc1e-c74e-4be2-85eb-f196c2a99820 |  | folder-normal | fail |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement
28785aa4-ce94-42e0-b4c2-8778a95a021b | Child 3 - Testing(80a9b017-3f85-59e2-baf3-585a285c7465) -- Final Inspection - Work Completed On(53e50fc2-da89-4887-8a19-fa9cb1898f1b): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-001 - Zone 7 West Craigieburn Rd - CH10040-10175 - Base Layer
bc510615-5479-4db5-b6e3-b779320b338c | Child 3 - Testing(dd367b17-3ff2-57b6-90d2-f8bad1fac59b) -- Final Inspection - Work Completed On(d2eb3390-187d-422a-8dbc-a45c6deacebe): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | fail | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-002 - Zone 7 West Craigieburn Rd - CH10040-10175 - Intermediate Layer
f7f46de8-0979-4f3a-83bd-9e4009838c58 | Child 3 - Testing(9c61f7fa-8141-55e4-8e9b-6c4aaa20859c) -- Final Inspection - Work Completed On(8058781f-ea09-4f57-b786-43976b7284df): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-003 - Zone 7 West Pavement 6 Area - CH10000-10040 - Base Layer
d7cae2f0-c50b-4df2-9eda-319667149cee | Child 3 - Testing(48b5474b-28b0-54b1-9a14-d7947508c1ba) -- Final Inspection - Work Completed On(c1c2e0eb-a787-4dd7-87d8-d8f76f629220): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | fail | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-004 - Zone 7 West Pavement 6 Area - CH10000-10040 - Intermediate Layer
2cafccbd-447c-4731-9293-c3bfc8dbb6dc | Child 3 - Testing(6ff73742-ac8d-5529-ae7f-5ebd73669fa4) -- Final Inspection - Work Completed On(c894532f-8847-4e10-9089-eb4475021a5a): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-005 - Zone 7 East Type 1 base course - CH10650 to CH10780
abbc798e-9941-4693-83ca-c27904e8db15 | Child 3 - Testing(444b97f9-ff09-5945-b92d-e28a1bc6302d) -- Final Inspection - Work Completed On(7498df21-e98c-42c0-b1d0-a7823b6df05c): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-006 - Zone 7 East Type 1 base course - CH10780 to ch10850
eb62ce8a-9bbe-4a31-91ad-6a9c0353643a | Child 3 - Testing(30b77cc5-07f2-549d-a32b-a1f3ba8dfff5) -- Final Inspection - Work Completed On(63272dfc-9a99-4723-9754-5081ba499c89): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-007 - Zone 7 East Type 1 intermediate - CH10650 to CH10780
a3af761d-632f-4cf8-9b33-bf5f051700dd | Child 3 - Testing(b6c2ac58-0f10-5c55-97fe-4094ecad1984) -- Final Inspection - Work Completed On(25c8c11d-58ea-45d6-a51d-87b6d5538159): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 701c5d31fe53ea33e7a1b061365b83bc717e51034c3537b10866d23733cfadd8 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-008 - Zone 7 East Type 1 intermediate layer - CH10780 to ch10850
965a4ca0-9bbe-43ab-9d46-a4b05422d489 | Child 3 - Testing(8451182a-4a06-5d7c-82e9-eda9d73bdb0b) -- Final Inspection - Work Completed On(7884bd2f-13b4-4cc4-bf35-0b9bf588d053): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-009 - Mickleham South (SB) Layer 1 SF - CH40050-CH40240
5c41dc5d-67d0-4ec7-8f8f-614c26b7041e | Child 3 - Testing(3d20e3a7-0b16-5864-a623-90e6900bc434) -- Final Inspection - Work Completed On(6d622146-0426-45bf-aabc-69fc93082205): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-010 - Mickleham South (NB) Layer 1 SF - CH30100-CH30320
37d823d1-eee5-480b-a450-74741fdad62e | Child 3 - Testing(a0ef5ecb-839d-585f-a156-ab4d6b0f3b77) -- Final Inspection - Work Completed On(ecb3fb5d-f0d2-4050-a845-e8cc2dc95683): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-011 - Mickleham South (SB) Layer 2 SI - CH30102-CH30316
f17199b8-ec94-47c9-9d49-cf4f566004b1 | Child 3 - Testing(9703eb17-b087-5583-8f97-166f6e04fa65) -- Final Inspection - Work Completed On(30d52ac3-95ee-491e-ba7c-566efb3de6d3): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-012 - Mickleham South Layer1 SF - CH30020-CH30100
921ac93b-56bf-4fd2-91b6-db777d745e57 | Child 3 - Testing(7d24624d-0f03-52ec-ac26-10d6345eaf95) -- Final Inspection - Work Completed On(94b517e6-9a38-4074-a580-37f64964ac38): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-013 - Mickleham South (NB) - Layer 2 (SI) - CH30020-CH30316
c96f761f-f850-4c56-af41-f7e748834ca2 | Child 3 - Testing(bd3c2fbc-86c8-5e01-863e-2d75af09192d) -- Final Inspection - Work Completed On(4116905b-87aa-406a-9614-d0bd9fbaceba): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-014 - Mickleham North (SB+NB) - Layer 1 (SF) - CH40500-CH40750
648167e8-59dd-4747-a18e-faf9fd477db1 | Child 3 - Testing(3ec3288d-8608-5595-adf8-41c7e335cbbf) -- Final Inspection - Work Completed On(f18c06b7-29a1-45ea-9eb9-accbbbe81eab): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-015 - Mickleham North (SB+NB) - Layer 2 (SI) - CH30520-CH30785
3beeebed-4f6d-480c-8096-e6f143a9e744 | Child 3 - Testing(9b5e5820-5eea-5b3d-811d-30d414f61a09) -- Final Inspection - Work Completed On(0cf0c1b3-2f59-4dd6-b638-5b8c2bc2360d): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-016 - Mickleham South - Pavement 6 Area - Layer 1 (SI) - CH29980-CH30020
061ae562-92f5-4f59-a421-fa520065caca | Child 3 - Testing(e1e2252b-0a24-594b-adc9-331561127592) -- Final Inspection - Work Completed On(6be24d1a-176c-4fc7-8f11-f13c6c84d563): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-017 - Mickleham Intersection (SB) - Layer 1 (SF) - CH40240-CH40500
5ee7cdb1-1552-4439-9a34-c8bf720e60d2 | Child 3 - Testing(bbb9e44f-f1d0-5f75-8c54-4c5d4946d638) -- Final Inspection - Work Completed On(974756a6-9c8d-4c04-95e9-b86907453887): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-018 - Mickleham Intersection (NB) - Layer 1 (SF) - CH30320-CH30570
9277520a-fe20-4f18-a03f-94f2e9ed27bc | Child 3 - Testing(fa50dfd3-20ef-5ef0-aec5-6c1d1cf84193) -- Final Inspection - Work Completed On(27b36db4-b17c-407f-bd3d-2f71391e1746): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-019 - Mickleham Intersection (NB+SB) - Layer 2(SI) - CH30316-CH30520
a46b9493-0693-49f2-b742-7766304da08d | Child 3 - Testing(f53ca810-2d17-5877-a6a9-f18baf8849e2) -- Final Inspection - Work Completed On(f4423866-92d3-4726-b75f-caa5642c3998): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-020 - Mickleham Intersection (West going EB) - Layer 1 (SF) - CH20470-CH20490
d2ae5c40-6214-4ae8-8872-0f078b1ea690 | Child 3 - Testing(b3ba86a1-aa5c-5f69-9c91-354604c7da29) -- Final Inspection - Work Completed On(c3426ac0-fefa-4207-a8dc-82080ce2a0f5): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-021 - Mickleham Intersection (West Sliplane going WB) - Layer 2(SI) - CH10550-CH10570
e424063d-b8bf-4dae-8fab-38ccd3e8cf5c | Child 3 - Testing(8df123e7-ff61-50e3-9dba-19faaa8dfaca) -- Final Inspection - Work Completed On(8be61a70-21fa-44f9-abe6-54432998420d): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-022 - Mickleham South - Pavement 6 Area - Layer 2 (SI) - CH29980-CH30020
aec8746a-8c02-45d1-bf1b-f546cf0dbe43 | Child 3 - Testing(b64d5ad1-4c80-50f9-98dc-5ee8e0080690) -- Final Inspection - Work Completed On(30a70c31-9fbc-4723-b6de-30054407b187): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-023 - Mickleham Intersection (SE Sliplane - WB) - Layer 1 (SF) - CH10550-CH10570
21182ab2-f860-4b99-a3ce-4ff8db7c3fa9 | Child 3 - Testing(9bdf31c6-937d-5f12-8411-943c9772e979) -- Final Inspection - Work Completed On(26353774-8482-41c2-9b4a-6d437b226810): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-024 - Mickleham South (SB) - Layer 2 (SI) - CH40210-CH40350
7186c230-f623-40b7-9d5f-e765d4bf5715 | Child 3 - Testing(3f98207a-84ef-50f5-b2ee-61b3168d5253) -- Final Inspection - Work Completed On(94fba46f-dab7-40ae-b58d-d51c82d13bbb): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-025 - Mickleham Intersection (West - EB) - Layer 2 (SI) - CH20470-CH20490
d734bb46-e956-4267-a7f4-17696066564f | Child 3 - Testing(e6627f50-ef05-50d2-a8ce-9d723f00d755) -- Final Inspection - Work Completed On(5335c614-81f9-41de-ad86-0fb57bd570ca): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-026 - Mickleham Intersection (North-West sliplane) - Layer 1 (SF) - CH20470-CH20490
8d14c2ea-a3d2-497b-97f4-277360e174f2 | Child 3 - Testing(d9c85986-0517-5daa-b90d-b3af4fa4c9fb) -- Final Inspection - Work Completed On(aada6f91-46cf-49c4-a01f-aef0d19273a7): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-027 - Mickleham Intersection (EB lane) - Layer 1 (SF) - CH20515-CH20530
939bee8f-2715-4ba1-93a7-87d6d04650f4 | Child 3 - Testing(4f819c53-215d-5db0-ae93-f0394cc9215e) -- Final Inspection - Work Completed On(e5a5a63a-4a2d-4d2b-898c-598bfe08a340): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-028 - Mickleham Intersection (WB Lane) - Layer 1 (SF) - CH10570-CH10650
c361fbb7-b4d4-49a8-9736-19d9b6b3a8b2 | Child 3 - Testing(e3210027-7ee3-578f-9e1e-08f3b6ce524a) -- Final Inspection - Work Completed On(40181f46-2cdf-4bc4-99fb-f35a4f79e5ad): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-029 - Mickleham Intersection (North-West sliplane) - Layer 2 (SI) - CH20470-CH20490
82803596-3373-4c10-ada5-2868fda75f5b | Child 3 - Testing(e24e022b-b781-59bd-b1a7-151c5f851822) -- Final Inspection - Work Completed On(6c8b5ac7-fc36-4d3f-9b2b-5e6794cce9a2): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-030 - Mickleham Intersection (EB lane) - Layer 2 (S1) - CH20515-CH20555
a05a0040-5227-45e2-9dfd-689221c0d6f2 | Child 3 - Testing(d56a9165-7e17-5d62-b2a7-dd8f4735ac60) -- Final Inspection - Work Completed On(41f6e620-b521-4974-8bd2-08e6f65a8157): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-031 - Mickleham Intersection (WB Lane) - Layer 2 (SI) - CH10570-CH10650
e955bf78-8426-40c5-ba34-49d1bef12130 | Child 3 - Testing(3ebbc31a-e4d5-5c99-a3cd-492930583d59) -- Final Inspection - Work Completed On(cf4f9cd0-2256-420a-ba12-43c5fc44db38): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-032 - Mickleham North - Regulation Layer (SI) - CH30785 - CH 30850
8c88ae49-acec-4548-b287-16e5b868c938 | Child 3 - Testing(9bd37e92-23fb-5bc3-81eb-a85eab720d8a) -- Final Inspection - Work Completed On(7cf0ba53-cbb3-4910-8afe-abb5b36c4361): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-033 - Mickleham North - Layer 1 (SI) - CH30785 - CH30850
6ad5cf1e-d7e3-41c6-9d43-72e516b7b414 | Child 3 - Testing(698f659b-c002-56bf-a51c-461797baf95b) -- Final Inspection - Work Completed On(a51cd0be-fdfb-4e43-8511-551c6b66ac24): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | pass | 20ee349eb857cd91aa67acb2d9fafc20f3b4225d4ccff5d0add2b6bb87be01ec | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-034 - Mickleham North - Layer 2 (SI) - CH30785 - CH30850
28ef46f5-e844-4ac0-8b01-1f720f923cfc |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-035 - Debonair Layer 1 - CH11250-11350
fdef5f7c-717e-4371-b5cf-283e9d708c65 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-036 - Debonair Layer 2 - CH11250-11350
09fd0f1f-37fa-4bc3-98d1-55d8697afd2c |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-037 - Zone 7 East - Mickleham to Debonair - Layer 1 - CH10880-11100
3c137ecb-bbc2-476c-aec7-baa18a6bae37 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-038 - Zone 7 East - Mickleham to Debonair - Layer 2 - CH10880-11100
457584ce-1bc5-44de-9e86-01ea8e68cd14 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-040 - Zone 7 East - Mickleham to Debonair - Layer 1 - CH11100-CH11260
a3cd2a58-9668-495d-bdb4-b2d8d1d4bfa4 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-041 - Zone 7 East - Mickleham to Debonair - Layer 2 - CH11100-CH11260
7889a77c-ddf7-453d-aeb6-734ef45b68c6 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-042 - Zone 7 West - Layer 1 SF - CH 10380 to CH 10200
3b23d645-150b-42e2-b6e0-8bb9bc97c446 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-043 - Zone 7 West Layer 2 SI - CH 10380 to CH 10200
6795ce71-6bc3-4d7b-8b4a-8781dad3ae70 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-044 - Zone 7 West CH 10120 - CH 10200 L1 SF
6f389404-884d-4b02-968e-37d2e8375344 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-045 - Zone 7 West CH 10380 - CH 10480 L1 SF
3273c94e-9f8a-4fe1-80a6-7ed0097338ee |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-046 - Zone 7 West CH 10120 - CH 10200 L2 SI
a0ad0e96-8166-40c7-b464-24b0fe79c018 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-047 - Zone 7 West CH 10380 - CH 10480 L2 SI
49cc066a-3ce2-4d32-b4a0-553e843ae0eb |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-048 - Zone 7 West SW Slip Lane L1 SF
8908d809-a7e0-4d5b-8dee-48b6bd67ec9d |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-049 - Zone 7 West SW Slip Lane L2 SI
e95f1158-aa90-4de8-a03a-272617e4f7d8 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-050 - Zone 7 East - Mickleham to Debonair - Layer 1 - CH10830-CH10880
61e45e6c-755a-4fcf-a2c8-8ca638414ea1 |  | checklist-sectioned | pass | f32b252f5af3c6cf79a392cf888978c9baf0ccc93ee26823f10513349d1d3f1f | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-051 - Zone 7 East - Mickleham to Debonair - Layer 2 - CH10830-CH10880
48d032d5-1cd3-4a7d-8e19-fac46118e62b |  | checklist-sectioned | work-in-progress | 513cd577595f1765e7964cb848abc09127cc03e08556897dac413797d729ca9c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-052 - Zone 5 Aitken North - Upper Section - Layer 1 - CH60860-CH60940
9fe2734d-a788-40a8-8171-51fafbf84d15 |  | checklist-sectioned | work-in-progress | 513cd577595f1765e7964cb848abc09127cc03e08556897dac413797d729ca9c | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-053 - Zone 5 Aitken North - Upper Section - Layer 2 - CH60860-CH60940
f74e2299-f888-46c4-93ef-68a0a9ec3eb1 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-054- Zone 7 East CH11340-11650 L1
89f60e0b-80a6-49af-8529-cf86fcc4fbbe |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-055- Zone 7 East CH11340-11650 L2
82570cc5-d3fb-48a6-bea4-1bb19996553c |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-056 - Zone 7 Vantage -Asphalt L1 CH 11825-11900
73274b5f-ce86-49e2-a582-552a892ccab7 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-057 Zone 7 Vantage -Asphalt L1 CH 11840-11870
1f1b5e60-f8c1-4a70-b9f2-ad338a439f85 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-058 - Zone 7 Vantage -Asphalt L2 CH 11825-11900
e837ea18-53f1-4abc-a2ec-01af3c440d0f |  | checklist-sectioned | pass | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-059 - Zone 7 East - Stage 2 - Slip Lane and Mickleham NE - SI Layer - CH20520 to CH20760
38ff7dfb-ffb6-4144-a285-fc45afb296d0 |  | checklist-sectioned | pass | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-060 - Zone 7 East - Stage 2 - Slip Lane and Mickleham NE - SF Layer - CH20520 to CH20760
418aaa9b-1e3c-442f-b312-4bda5c1190c2 |  | checklist-sectioned | pass | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-061 - Zone 5 Aitken South - Southbound - Layer 1 (SF) - CH60520 to CH60360
56a3d162-2807-445c-8067-f718640410dd |  | checklist-sectioned | pass | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-062 - Zone 5 Aitken South - Southbound - Layer 2 (SI) - CH60520 to CH60360
5f2eb98f-d860-4a22-a75d-6e0811fe4d6e |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-063 - Zone 5 Aitken North - Mid Section - Layer 1 - SF (CH60520-60360)
eed658f2-6a9c-49a7-aead-1750d32d3912 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-064 - Zone 5 Aitken North - Mid Section - Layer 2 - SI (CH60830-60630)
51c87066-afe7-4f2e-92db-a1aea96776be |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-065 - Zone 7 West Stage 2 - SF Layer (CH20170-20480)
7ce1c608-c5a8-4879-aa25-e7ce38269343 |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-066 - Zone 7 West Stage 2 - SI Layer (CH20170-20480)
d9e68401-020e-4c9e-aeed-1d89ddf79fc5 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-067 - Zone 5 Aitken South Stage 2 - Layer 1 - SF (CH60050-60550)
74282ecf-53ba-4051-a64d-f56e0f95226f |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-068 - Zone 5 Aitken South Stage 2 - Layer 2 - SI (CH60050-60550)
42009584-660e-4a63-83cf-584278c98b37 |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-069 - Zone 5 Aitken South Pavement Type 6 Layer 1 - CH60050 to CH60140
246546a0-1024-43ca-b8f9-2374d6fcaf43 |  | checklist-sectioned | not-started | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-070 - Zone 5 Aitken South Pavement Type 6 Layer 2
5abac41b-08ba-4382-9191-f5130bbb17b1 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-071 - Asphalt layer 1 champ to van 11900-12240
d7d2ff32-1d51-4923-a0ca-ec0c0dfc3553 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-072 - Asphalt layer 2 champ to van 11900-12240
965c3e51-e213-46ae-9c92-44c2573cf4a5 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-073 - Asphalt layer 1 Vantage West 11650-11820
015ecfef-b2f4-4b26-8566-f69fb60676b4 |  | checklist-sectioned | work-in-progress | ITP 0075 - Asphalt Placement | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-075 - Asphalt Placement | ITP-075-A2-LOT-074 - Asphalt layer 2 Vantage West 11650-11820
463b49e3-d278-4a70-8616-4c37febaa60b |  | folder-normal | not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-076 - Permanent Roadside Signage
b12052c9-669d-4762-87d1-99051b898c8c |  | checklist-sectioned | not-started | 52890fdb9a4776ad65649337ba59773716c1d02d7711097de8fc51f1b2918cad | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-076 - Permanent Roadside Signage | ITP-076-A2-LOT-001 - Zone 7 East Debonair Pde
dce06b86-8189-40d0-87aa-2083501df1ed |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction
9d8f1bc0-2a27-4c6d-a51a-47337a2014c4 |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-008 - Zone 7 Mickleham Road - Pit 1088 - Base
00de5c06-8f8e-4629-b64a-899803007ea7 |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-009 - Zone 7 Mickleham Road - Pit 1088 - Walls
d9f94e48-b631-43a4-b6c2-7a4441d9650f |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-010 - Zone 7 Mickleham Road - Pit 1088 - Soffit
b98737b7-2ff2-4a8f-8907-6dfb2dc3fb3a |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-011 - Zone 7 Mickleham Road - Pit 1087 - Base
5efc68e7-27ec-4120-a98e-72bdff37f20a |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-012 - Zone 7 Mickleham Road - Pit 1087 - Walls
a1ce07ef-a521-4c66-b7c0-e1aca5b2d01e |  | checklist-sectioned | work-in-progress | de1e644d2c927a8cff506ad67ee500c5c37d9c1d178e8aeaf755654ca91995ce | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-013 - Zone 7 Mickleham Road - Pit 1087 - Soffit
22a0e635-06cd-4d57-aaeb-cfacce5dab06 |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-014 - Zone 7 Mickleham Road - Pit 993 - Base Slab + Walls
3ae3b932-50f2-4ac7-b375-9826e1fd4682 |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-015 - Zone 7 Mickleham Road - Pit 993 - Haunch + Slab
04607289-d05d-4504-80ef-92129693b6ab |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-016 - Zone 7 Mickleham Road - Pit 994 - Base Slab + Walls
8bbe6f02-c482-4712-b17b-da70b2cb6eeb |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-017 - Zone 7 Mickleham Road - Pit 994 - Haunch + Slab
91743ebf-2b33-4726-b84f-5ff22c8e5064 |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-018 - Zone 7 Mickleham Road - Pit 995 - Base Slab
255996e6-bb59-4615-9c6a-9aee055f5bab |  | checklist-sectioned | pass | f9088a1f8bb96dac02caf3e8d75cd1c5381adb3bc3a2cbf261a8fad4d01a1114 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-019 - Zone 7 Mickleham Road - Pit 995 - Walls
62a6f6a1-3ffa-40a8-9998-dac022437acc |  | checklist-sectioned | pass | 35c16041363e9c869ebe5ceca34f48ba41745f77463c182d0f19ce674f5aa807 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-020 - In-situ Drainage Headwall 992 - Base
affb474b-40b3-481e-b1f5-bb507464347e |  | checklist-sectioned | pass | 35c16041363e9c869ebe5ceca34f48ba41745f77463c182d0f19ce674f5aa807 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-021 - In-situ Drainage Headwall 992 - Wings
f9e34c0d-0b92-4026-bac8-03a9ff02ebf8 |  | checklist-sectioned | pass | 1f6c564fe622ad092de712fe81adc4fd820ea812ebccb4c70f7cb9b431a5b246 | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-078 - Insitu Pit Construction | ITP-078-A2-LOT-024 - Zone 7 East Rising existing Pit 450a-G
9124d4dc-1808-4207-9925-0f7c4fd4d37c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-081 - Structural Crack Repair
c0fe1cff-d2b8-403b-94e0-924ef1df46f4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-082 - Structural Patch Repair
0d7a9c57-f532-4503-a6ef-96c3f097afc2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-083 - Precast Concrete Install
f81c0ab3-00ab-4813-b082-71ccf7e83ec0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials
db7e2c9a-417f-4d65-bcdf-397aef0f2bca |  | checklist-sectioned | not-started | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A2-LOT-004 - Zone 7 East Stage 2 (CH20770-21275)
e9217591-79d9-4842-8d75-4c9f57eb6bcf |  | checklist-sectioned | pass | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A2-LOT-005 - champion intersection 12300-12320
ebc334d9-ffb9-49de-9742-34860372dd18 |  | checklist-sectioned | work-in-progress | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A2-LOT-006 - champion intersection 12400-12450
5c70907b-8a61-40ac-bba6-4f07e4fefa95 |  | checklist-sectioned | not-started | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-084 - Lime Stabilisation of Earthwork Materials | ITP-084-A2-LOT-007 - 12600-12750
165af35d-a4c2-4411-b188-7aa0e9e8d491 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-085 - SUP Installation (HCC)
94e1ed19-6c56-497c-a9b5-028c1ec8a4cc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | ITP-086 - Welding Carbon Reinforcement
c2face0d-6472-42a0-8d74-a976519191bf |  | checklist-sectioned | work-in-progress | ITP 0086 - WELDING CARBON REINFORCEMENT | checklist | FALSE | FALSE | AREA 2 ITP's | ITP-086 - Welding Carbon Reinforcement | ITP-086-A2-LOT-001 - Aitken bridge CH12520
dde39635-2c9c-4017-8a43-21dcc9d8a40a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | Temporary Pavements
9f00d9ac-31b5-4b33-b8d5-29413a80253a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | AREA 2 ITP's | Temporary Pavements | Lot 001 - Zone 7 East Switch
00215924-1d13-4321-8363-82e088ca8baf |  | checklist-flat | work-in-progress | ade09b74f5834fd1a67b7f7d517e5a6816f9030efe16fdd9ef3e7194d308a477 | checklist-flat | FALSE | FALSE | AREA 2 ITP's | Temporary Pavements | Lot 001 - Zone 7 East Switch | 001 - Subgrade Prep
5baf1e0d-1b16-418d-965a-8f24d97ddfad |  | checklist-sectioned | not-started | 4e07e0d72b0a18fb4e858a1b48637724dcd0cc0e1956dcd3ac8f3718f79f5ddf | checklist | FALSE | FALSE | AREA 2 ITP's | Temporary Pavements | Lot 001 - Zone 7 East Switch | 002 - Class 3 CR
4ff307ce-2040-4f04-8614-c8d41e51dcbc |  | checklist-sectioned | not-started | 4e07e0d72b0a18fb4e858a1b48637724dcd0cc0e1956dcd3ac8f3718f79f5ddf | checklist | FALSE | FALSE | AREA 2 ITP's | Temporary Pavements | Lot 001 - Zone 7 East Switch | 003 - Class 2
5e2aa5ca-1a6e-405e-af14-d4e07abfd32d |  | checklist-sectioned | not-started | f3a420dca415364687d33e278fafc67c4f5af5854279ddd37ff785b6c6793af0 | checklist | FALSE | FALSE | AREA 2 ITP's | Temporary Pavements | Lot 001 - Zone 7 East Switch | 004 - Asphalt
b6fa1a5f-805a-4639-856f-c61fc45110f7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's
cfc4b088-ab39-440c-8520-bea8a6e6c31f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works
6b5a0ae8-d7a3-40ef-8ec2-56eb50f909d4 |  | checklist-sectioned | work-in-progress | 9e4f6c24df696f3fa8699709ac6f6bdca85463d516838f4e29f67ca7166ebc56 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-001 - G1747 Gas Protection Works - Waterview Blvd NW corner
cc32a09f-ea8f-464e-8590-51e7bfd654b9 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-002 - G1753 - North-South crossing, intersection of CRG Rd & Champion Pde
2c810505-b61a-48f0-9d4d-c563f5a23050 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-003- G1747 Gas Protection Works - water view NW corner
5f8dc4b6-0b16-4ca3-a1ce-f9965f4b49f4 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-004 - G1730 Gas Protection Bridgewater rd intersection
f73d2afb-b634-4448-9b6a-e645d1f33b69 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-005 - G1763 Gas Protection Debonair Pde
5f710ec2-4b22-4579-a6c7-cfbccd57cc93 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-006 - G1702 Gas Protection Hardy Ave
ef64814a-9250-43a1-bf64-c3d2615630ef |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-007 - G1745 Gas Protection East Side of Aitken
cd84bab5-65f1-4c0b-8795-36eca5b0b15f |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-008 - G1709 & G1710 Gas Protection Crossing Benston St
ca9e5489-ddb0-488f-8a7c-4fe6bceb1aca |  | checklist-sectioned | work-in-progress | 2d60f00ad926559bbf92c154098d77c935e305e3b9deafcabe4a22933bfc0a13 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-009 - G1712,G173,G1714 - Newbold Ave
2756b188-941e-43c4-9d59-48668c258c61 |  | checklist-sectioned | work-in-progress | 9e4f6c24df696f3fa8699709ac6f6bdca85463d516838f4e29f67ca7166ebc56 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-010 - G1718 Plumpton Ave
84837880-83ab-46e7-8532-8e613171ab9b |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-011 - G1758 Highlander East
2755f594-2239-44f6-9d60-7f0f3c48e9e0 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-012 - G1757 Highlander West
9283b251-0e2d-461c-a1b1-f001e2c70128 |  | checklist-sectioned | not-started | 436bce58b28670bb694c55cf33743000dbf204e6f976b53dc214208e9b9b6c5d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-013 - G1760 Vantage Blvd
59d07eed-58e3-4d05-8e74-20b7e3109942 |  | checklist-sectioned | work-in-progress | f2851d1de63a846e571e36badc29043405f82257ed196d54bbbc0ec387e18a3d | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-040 - Gas Protection Works | ITP-040-UT-LOT-014 - G1728 Gas protection North Side of Craigieburn Rd East of Selwyn
cb1ebbdb-b168-4612-931c-2de4b6034f11 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-041 - Water Protection Works
0d642141-cddc-4a62-bfd5-b2d43b98c8ee |  | checklist-sectioned | not-started | 8bfecbed0cb29ee0f647cc5e6111d23ed77e8b245b65a25add84b19772688f83 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-041 - Water Protection Works | ITP-041-UT-LOT-001 - Private water service - East of Selwyn Area 1 (50mm)
3b08da6f-aa58-45e7-b4ff-0094ca3d1631 |  | checklist-sectioned | work-in-progress | 8bfecbed0cb29ee0f647cc5e6111d23ed77e8b245b65a25add84b19772688f83 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-041 - Water Protection Works | ITP-041-UT-LOT-002 - W1713 Watermain Protection Belsay
cfcc8494-4105-46a5-98d0-e9036847bb9e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works
e3426c96-bcbf-446d-92f5-2a38af101d78 |  | checklist-sectioned | not-started | 43195065d7fdd769d9e3300469895adc466329df285862d5ef4b74f7f4772431 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-001 - OF1738 - East of Bridgwater Rd - 35m
fd22727f-8266-4771-9887-a20ecd128c58 |  | checklist-sectioned | not-started | 43195065d7fdd769d9e3300469895adc466329df285862d5ef4b74f7f4772431 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-002 - OF1707, OF1708, OF1709, OF17115 - Between Hardy Ave & Benston St - 120m
aa3ccc6b-2d46-4c07-9dce-6ba8e0945c12 |  | checklist-sectioned | work-in-progress | 645623f391109a203af6f147bf3ab43f68cc02664ac560d202c4032ceec081a6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-003
7ddfa435-f45a-4f95-b98d-2e38c9b1cde0 |  | checklist-sectioned | not-started | 43195065d7fdd769d9e3300469895adc466329df285862d5ef4b74f7f4772431 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-004 - OF1773 - East of Aitkens - 20m
8bd5af58-fd05-40cc-bce8-0c8cef1e03a8 |  | checklist-sectioned | not-started | 43195065d7fdd769d9e3300469895adc466329df285862d5ef4b74f7f4772431 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-005 - OF17108 - North-South, east side of Mickleham Rd intersection
e0d984cd-094d-4e8d-9f00-990d72b9ff8c | Child 4 - Completion(87359522-dfc6-528f-ab51-4af6413c778f) -- Final Inspection - Work Completed On(7d15ffae-a932-48af-9c64-0c6fe620c9c1): checkpoint-no-status has incorrect meta.stepType checkpoint-status | checklist-sectioned | work-in-progress | 9dbb1a0cfe238b824de4868c755d4202cc38b06ff02154290835e766ea5edcb9 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-007 - T1726 East-West Crossing Mickleham Rd
1f5f171f-be8b-43ee-bf99-fb5c0a447127 |  | checklist-sectioned | work-in-progress | 7c7b225055ca7c2ba617f1c3de616d5095c2e1829c768304708a83c61fc6b77a | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-042 - Comms Protection Works | ITP-042-UT-LOT-008 - T1726 East-West Crossing Mickleham Rd
3a335592-fa11-46f7-9c7c-5922a74016c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-043 - Electrical Protection Works
9cafd5aa-3815-4964-aced-0a8152b57061 |  | checklist-sectioned | not-started | 6f9d4950fae40257fbcaaa76e261d6d0a54c55ce955592bf5eaff8fa5fb3924b | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-043 - Electrical Protection Works | ITP-043-UT-LOT-001 - E1754 - North-East side of Waterview Blvd - 40m
1aa3b0fb-2d1c-4374-a523-d65fd3a6a5cb |  | checklist-sectioned | not-started | 6f9d4950fae40257fbcaaa76e261d6d0a54c55ce955592bf5eaff8fa5fb3924b | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-043 - Electrical Protection Works | ITP-043-UT-LOT-002 - E1748 - North-South, east of Aitken Blvd - 25m
ee25890c-d11f-40f8-b2a5-5745bce055cb |  | checklist-sectioned | not-started | 6f9d4950fae40257fbcaaa76e261d6d0a54c55ce955592bf5eaff8fa5fb3924b | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-043 - Electrical Protection Works | ITP-043-UT-LOT-003 - E1738 - East-West crossing, west of Waterview Blvd & CRG Rd - 15m
fd010196-603c-4a35-ab88-6052cc84056f |  | checklist-sectioned | not-started | 6f9d4950fae40257fbcaaa76e261d6d0a54c55ce955592bf5eaff8fa5fb3924b | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-043 - Electrical Protection Works | ITP-043-UT-LOT-004 - E1769 - East of carpark entrance Area 1 - 7m
26df51f6-3bd0-4e4a-a897-a0096c7072a2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals
47b87cb8-bf7b-4b1b-8f4c-19f025519e1b |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-001 - HUME HIGHWAY
afa46f8a-031c-4a2e-a96d-04c206ecd2d7 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-002 - CRAIGIEBURN ROAD/CRAIGIEBURN ROAD WEST
de929f26-7bd3-46e7-b973-d5e94e262c3c |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-003 - P.O.S BETWEEN BENSTON STREET AND HARD AVENUE
bc441019-89d1-4d4a-a1a4-c7eeb7a9c849 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-004 - HANSON ROAD
82584f9c-4038-4e93-b89c-963dac43fb4a |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-005 - P.O.S BETWEEN RAYFIELD AVENUE AND BELSAY PLACE
30b75bff-46ca-45cc-8371-fc6b36fdee27 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-006 - CFA STATION ACCESS
8e1f82d4-dc33-44ab-ad05-19dc402312bf |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-007 - BRIDGEWATER ROAD
2ee91ada-7fb6-42ff-a12d-293485d16dcd |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-008 - CIMBERWOOD DRIVE
b9c7eb53-9a86-4151-a78f-47dcb361d3e1 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-009 - DORCHESTER ROAD
532317d4-8ae1-49c0-a337-474fb67821e6 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-010 - LYGON DRIVE
f574ed1e-d5f3-44f3-bd55-b6dcf8598576 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-011 - MAIN STREET/BALYANG WAY
90313b13-3a2c-49ce-b4c0-0c6727702737 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-012 - AITKEN BOULEVARD/SHOPPING CENTRE ACCESS
9dd93528-e0a7-4b8e-86c4-fcd59fa1710a |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-013 - CRAIGIEBURN ROAD/AITKEN BOULEVARD
f7924ba7-a99e-4b03-a68f-5c77d0ad4a37 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-014 - WATERVIEW BOULEVARD
2242d5dd-413b-4afa-9f4f-a8f38ddd28f7 |  | checklist-sectioned | not-started | 58cbff026994dda8935f06e644ef0c4351d554d15f0c4ff01103e56f7503c5f6 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-015 - HIGHLANDER DRIVE/VANTAGE BOULEVARD
5bd43f50-f9d6-4e0d-b7d2-a6199cb30818 |  | checklist-sectioned | work-in-progress | d9eed5e2160fa8ace8a410bcd70aaa3ad7fa56ed29692a769c797dd1db1ca237 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-045- Installation of Traffic Signals | ITP-045-UT-LOT-016 - MICKLEHAM ROAD
0b1a8c5c-6832-498d-adda-29166ae160c2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting
ef37af07-c2a9-46aa-9d13-c91b82649ced |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-001 - Lighting Zone 1 - Hume Hwy to Hard Ave
519acb28-bd52-4530-9041-f6247e1f89c5 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-002 - Lighting Zone 2 - Hardy to Rayfield Ave
1a73334e-b0b5-4c83-acb1-805c0bcc2f18 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-003 - Lighting Zone 3 - Rayfield to Dorchester
0f0d4642-9402-4e0d-8efe-fa019acaa521 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-004 - Lighting Zone 4 - Dorchester to Aitken Blvd
26ed4b4b-ea20-4386-8635-2afc12265de3 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-005 - Lighting Zone 5 - Aitken Blvd
c09ec0a1-b927-4d91-abad-19b0d00056ae |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-006 - Lighting Zone 6 - Aitken Blvd to Champion
e8cfe5b1-8adf-48ae-ad47-bb00ac9a08d1 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-007 - Lighting Zone 7A - Champion to Debonair
204b5be8-2980-4fc8-bdd6-cca5a30edfe3 |  | checklist-sectioned | work-in-progress | 834689977310a5472dc8a05926e636c6679da24acae0972e8a7f8ef20d8d0e5c | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-060 - Installation of Unmetered VESI Public Lighting | ITP-060-UT-LOT-008 - Lighting Zone 7B - Mickleham Road
23b01b3a-f30f-4ac1-b410-58e50e0fba67 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-066 - Direction Drilling
40f9e95f-0867-4020-955b-98b7da9da9d7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation
cd9bf4fe-f5e3-4eda-953f-195c716eaee6 |  | checklist-sectioned | pass | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-002 - Area 3/Sheet 1 - Zone 7 - Mickleham Rd Electrical Conduit Installation
ccde4b3b-291b-4649-bf28-9341bea3a927 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-003 - Area 3/Sheet 3 - Zone 7 - Mickleham Rd Electrical Conduit Installation
7e774b40-cbd1-4b07-a07c-5eac82dbbbef |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-004 - Area 2/Sheet 1 - Zone 7 - Highlander Dr Electrical Conduit Installation
2ae2209b-72f9-4646-8193-f6c8f3ae34b5 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-005 - Area 2/Sheet 2 - Zone 7 - Champion Pde Electrical Conduit Installation
69917459-0b07-4e1f-8614-12b96630155d |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-001 - Area 3/Sheet 1 - Zone 7 - Mickleham Rd Electrical Conduit Installation
5d97263d-f26a-4279-a8e7-c804f82be432 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-006 - Area 2/Sheet 3 - Zone 7 - Waterview Blvd Electrical Conduit Installation
7aedded0-31ce-4c94-b6fe-853be51becd8 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-007 - Area 2/Sheet 4 - Zone 7 - Aitken Blvd Electrical Conduit Installation
8d45fc8a-c047-430b-b528-72831fd2acd9 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-008 - Area 2/Sheet 5 - Zone 7 - Balyang Way Electrical Conduit Installation
cd718c10-665f-434b-be06-9e47184c44d2 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-009 - Area 1/Sheet 1 - Zone 1 - Hardy to Benston St Electrical Conduit Installation
841758cb-747c-41f3-b257-a0fbbb5c10cf |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-010 - Area 1/Sheet 2 - Zone 2 - Benston St Crossing to Hanson Rd Electrical Conduit Installation
23c8f18b-477a-4244-9e88-a3ab417fab4b |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-011 - Area 1/Sheet 3 - Zone 2 - Hanson Rd to Plumpton Ave Electrical Conduit Installation
66a7a59f-44c0-4c23-ae5e-5a8bb0b0eb4c |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-012 - Area 1/Sheet 4 - Zone 3 - Plumpton Ave to Belsay Place Electrical Conduit Installation
a378442e-e35a-4e75-83d0-1d31cd2b8f89 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-013 - Area 1/Sheet 5 - Zone 3 - Belsay Place to Bridgewater Rd Electrical Conduit Installation
cb48dbac-7f77-4c8c-ba47-421f5a28a2c9 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-014 - Area 1/Sheet 6 - Zone 3 - Bridgewater Rd to Cimberwood Dr Electrical Conduit Installation
45af2bac-a716-409c-b964-7025c1b90bfa |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-015 - AS3000 works - 1 Tudor Court
0146cb56-b58d-4bf9-a0bd-dcfd5556d988 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-016 - AS3000 works - 2 Tudor Court
c82e2c33-4439-40d2-be32-3fe611c27c50 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-017 - AS3000 works - 230 Craigieburn Road
9baa8521-ec18-4381-912a-e9a5e2595453 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-018 - AS3000 works - 228 Craigieburn Road
ec8bfcdd-4ff6-4489-84c3-2a8e155fda1d |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-019 - AS3000 works - 224 Craigieburn Road
4c2d2d0a-0add-4d24-8e70-f8e97fe33d5a |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-020 - AS3000 works - 222 Craigieburn Road
47f7b2bf-8a14-4591-a724-5cc068f3736b |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-021 - AS3000 works - 220 Craigieburn Road
4f32ca85-5852-406d-bcfa-62f2fffb8448 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-022 - AS3000 works - 218 Craigieburn Road
698081ba-3a9e-474d-9ddd-0e0c07f85166 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-023 - AS3000 works - 184 Craigieburn Road
a96e528b-02f4-4600-aaea-1f0d732a301f |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-024 - AS3000 works - 182 Craigieburn Road
61dc4a01-4e19-4f67-853c-227aa6408837 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-025 - AS3000 works - 180 Craigieburn Road
e987091f-204d-45b3-ab7a-7de07a0282bd |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-026 - AS3000 works - 15 Craigieburn Road
73be3c5e-d880-4743-bd17-7b9b20247d5e |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-027 - AS3000 works - 17 Craigieburn Road
a418a061-403d-4cef-a0c5-83bb6a1a93c6 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-028 - AS3000 works - 19 Craigieburn Road
b9386dea-ec69-44ed-b0ac-545781b066c2 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-029 - AS3000 works - 21 Craigieburn Road
4201007c-fe92-4e27-9b50-96f601be565b |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-030 - AS3000 works - 23 Craigieburn Road
59c94c4c-9787-415d-b9c2-a8cd657a9afa |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-031 - AS3000 works - 25 Craigieburn Road
93ff384c-eaa3-4666-b196-c4afd3956fd9 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-032 - AS3000 works - 27 Craigieburn Road
adb96bb3-bb25-4778-99fc-d7a08f5d82bd |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-033 - AS3000 works - 35 Craigieburn Road
e7b6f984-033f-440e-862a-78f1a2aec050 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-034 - AS3000 works - 43 Craigieburn Road
b24f3266-8815-4b73-8143-0b39688dc00a |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-035 - AS3000 works - 45 Craigieburn Road
50f23335-9b66-4fc7-b5c9-5cc7742ccd64 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-036 - AS3000 works - 47 Craigieburn Road
b6592b07-31a8-4a9a-9f88-f4692fd45c89 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-037 - AS3000 works - 49 Craigieburn Road
70531bf1-8f58-4246-96b8-c7bfef281cbf |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-038 - AS3000 works - 120 Craigieburn Road
441514fe-b5f8-4ba2-b009-fac438aef238 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-039 - AS3000 works - 122 Craigieburn Road
686cc434-e1d0-4b8d-92b3-79538a203ffc |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-040 - AS3000 works - 124 Craigieburn Road
47f3c22c-2b98-415b-9699-b2dee35d7519 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-041 - AS3000 works - 126 Craigieburn Road
93946e83-4d86-486f-8843-fa5a661d39da |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-042 - AS3000 works - 130 Craigieburn Road
ea9f507e-2c13-48cc-aab1-bf0a9f5b0e98 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-043 - AS3000 works - 132 Craigieburn Road
331e1156-92d4-4765-a978-add0ab75758a |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-044 - AS3000 works - Sports Centre
14e732ca-f021-43b7-8ce0-e8fbf42cbfb4 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-045 - AS3000 works - Coffee Shop Craigieburn Plaza
a8958d15-d73e-4610-86ed-b524635484c9 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-046 - Telstra Relocation Works - Package 1
3aeb97b7-6f1f-4b1c-b99d-44a59cbbe49f |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-047 - Telstra Relocation Works - Package 2
bd4c71c0-131e-4865-bed8-bed388648231 |  | checklist-sectioned | work-in-progress | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-048 - Telstra Relocation Works - Package 3
ce2296bc-1a5a-4fba-b4cb-ff1e4cc2693d |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-049 - Telstra Relocation Works - Package 4
fd27a3aa-2ae5-441f-a901-3e9643bb9c3d |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-050 - Optus Relocation Works - Package 1
a8ed4c4c-7169-4527-a424-0fe061aa6f35 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-051 - Optus Relocation Works - Package 2
a8bc37cc-3bbd-4ef9-b27a-c0b79ac3a26e |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-052 - Optus Relocation Works - Package 3
d2b55c62-55c6-45d0-91ec-5d0342642c70 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-XXX - Desc
61d9a0e2-8fc8-432d-ac70-3a457143b0ae |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-XXX - Desc
3b81dfe3-46c3-49c2-8244-841b38eeed62 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-XXX - Desc
8b354d1a-dbc0-4889-9723-6f65909acb77 |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-XXX - Desc
9b438da6-f5ab-43c3-a3ec-a287d7a070ee |  | checklist-sectioned | not-started | ITP 0077 - Electrical and Communications Conduit Installation | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-077 - Electrical and Communications Conduit Installation | ITP-077-UT-LOT-XXX - Desc
d4275b17-acbc-45fb-8321-00d68875853f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction
9fa15fd3-fc09-47ef-a2c8-8168195d900d |  | checklist-sectioned | work-in-progress | 9d6603ea9d118eaf5098e17babd55ceda8f7d79c5a9fe50f7776fcb9b5327dd5 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-001 - Church Watermain
7946177c-1d40-4e0f-b318-e40a7ebbc01d |  | checklist-sectioned | not-started | ITP 0079 - Watermain Construction | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-002 - Church Watermain
112f8f2a-497c-4769-aa8d-2f36cb13cf4d |  | checklist-sectioned | not-started | ITP 0079 - Watermain Construction | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-003 - Church Watermain
4ad4a31f-dd2a-445a-8c2b-6adb11688833 |  | checklist-sectioned | not-started | ITP 0079 - Watermain Construction | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-004 - Whites Lane Sleeve Install
5a865e41-30b3-4130-90d4-3a43ae8e4bf5 |  | checklist-sectioned | pass | a81c0cbac7680ec98a56155a03fd299431e1e1aeef4d6e60fe70a88c515e6c64 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-005 - RW1712 Champion 180PE Recycled water
885fd855-1d64-43de-b498-e04b1a5d3484 |  | checklist-sectioned | pass | a81c0cbac7680ec98a56155a03fd299431e1e1aeef4d6e60fe70a88c515e6c64 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-006 - W1758 150mm Potable water Steel Main
6a863585-4e52-4fa6-963c-3a9c07720bc5 |  | checklist-sectioned | pass | f3f97231b5860cc59158ba65e8189c6cf6622c94d7f06225845a53df98c2d998 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-007 - RW1708 Recycled water relocation Aitken Blvd to Waterview Blvd
126b8aa3-feff-43bf-a3a3-6b88a8db91c8 |  | checklist-sectioned | pass | f3f97231b5860cc59158ba65e8189c6cf6622c94d7f06225845a53df98c2d998 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-008 - RW1707 Recycled Water Relocation 280PE - Balyang
77075ae5-b57e-4ebf-9ec1-19240b2df104 |  | checklist-sectioned | pass | 08353a7d80adaa856fb105f8f5beebd4a6754c9114b00c50f3645e3fe6f904cd | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-009 - 280PE RW3080 Recycled Water Relocation Aitken Creek
02dd141e-50ff-4408-9ac3-b4b4df11a65e |  | checklist-sectioned | pass | 7f34c35c109e950291506cb55490ed9a9a35a67b8930811f0abc5d19129ce495 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-010 - 280PE W1748 Water Relocation Aitken Creek
79a43035-686c-424b-a9e2-aed3b6deff64 |  | checklist-sectioned | pass | 08353a7d80adaa856fb105f8f5beebd4a6754c9114b00c50f3645e3fe6f904cd | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-011 - W3118 280PE Water main - Dorchester
72e73754-ba4c-4604-8170-ffd5a948f0ac |  | checklist-sectioned | pass | 7f34c35c109e950291506cb55490ed9a9a35a67b8930811f0abc5d19129ce495 | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-012 - W1715 DN337 steel Watermain Bridgewater
c1bb9527-60e1-4ec6-a272-7278dbe7391b |  | checklist-sectioned | pass | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-013 - W1745 West of Main St 450mm PE Water
3bd249ba-8ae2-4484-b02d-2d26d73c9b45 |  | checklist-sectioned | pass | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-014 - Aitken East By Pass
d568aaaa-28db-4394-b06f-5042387f2f3a |  | checklist-sectioned | pass | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-015 - W1749-W1750 Waterview Water Relocation
52d2b1f1-43bf-45ba-93ae-2094dd496e5e |  | checklist-sectioned | pass | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-016- RW1720 Recycled Watermain Vantage Blvd
5f444061-3391-4387-a22a-b931dfd22bcb |  | checklist-sectioned | pass | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-017 - W1788 North West Aitken Blvd Watermain Relocation
2a0d7283-fbe5-48bf-b90d-f29bd5d4c18f |  | checklist-sectioned | work-in-progress | 0c1d11c77aae592e682e9187bc8e44d747e41c25529e01dc95ea206e1cd78abb | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-018 - RW1729 North West Aitken Blvd Watermain Relocation
278046d5-3071-4756-b5f0-dc4a20d5326b |  | checklist-sectioned | not-started | ITP 0079 - Watermain Construction | checklist | FALSE | FALSE | UTILITIES ITP's | ITP-079 - Watermain Construction | ITP-079-UT-LOT-TRIAL
d1fbfece-c165-4898-9db0-c4ec8acf8cac |  | folder-normal | fail |  | step | TRUE | FALSE | Material Inspection Checklist
eb4b3ddc-7746-4c1c-8cc5-77ebdb4f6e4f |  | folder-normal | fail |  | step | TRUE | FALSE | Material Inspection Checklist | Area 1 Checklists
8ed92aec-d8d1-4352-a221-8fd76f153964 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-001 - Hume North & South Median 375mm RCP & box culverts
8a74f2df-52cb-49a5-a81d-e666f3e707d5 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-002 - Hume North & South Median 22No. 375mm Stormpro
2cb677dd-96cc-49d9-9066-a9c03ecbe1cd |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-003 - Hume South Median Pits 1014 to 1022
da4fee19-a966-436c-8224-be2c18a13300 |  | checklist-sectioned | fail | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-004 - Hume North Median Pit 1001 pit 1002
7a8d1d62-135d-49e7-8d9a-01d1a704efa3 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-005 - Hume North Median Pit 1004 pit 1010
8bc583d6-daf6-4da5-9816-79d75d743b45 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-006 - Hume North Median Pit 1003
2800105a-38c5-4b9c-aaf9-a03dc0a968cb |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-007 - Hume North Median Pit 1001
fa4e67b6-4432-4330-b608-7ae497095845 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-008 - Zone 4 West - Pit 226 - Pit 234
e30371db-3e23-4363-8283-88106449ea1f |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-009 - Hume North Median Pit 1005 & 1012
3e2dd3af-706e-47a5-b174-a3568925cc0c |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-010- Hume Compound- Cover AND Composite
7fa18d6c-1a16-4b1f-8604-e5e1a7f2ebd4 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-011- Hume Compound- Lintel SM2
578b0e54-ab16-4afb-b6ff-31a0e8ee20ce |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-012- Hume Compound- Lintel SM2
b3f2a56d-cf3b-4701-a545-0228e8833f68 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-013- Golf Course West - Riser 226 - 231
def0546c-ab33-4d57-980b-792934661903 |  | checklist-sectioned | pass | 389f0b076fbb48ba2e495a4ff22a5f5a0b3b9c941eb4d721eafb2f4b9d6dfef3 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-014 - Hume North Median - Apron SD1411
7c4b6dfb-9432-4dc9-8dfb-8724a98b40af |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-015 - Golf Course West - Riser 232 & 234
1d0a5587-7664-46e1-8e03-84f5393fbdb4 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-016- Golf Course West - Riser 233
29519640-b031-40d3-a945-08a098e83e50 |  | checklist-sectioned | pass | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-017 - Hume North Median - Apron SD1411
503c4234-6fde-44c4-a17e-62c9a5476536 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-010-A1-MI-018 - Aitken South - Subsoil pits & Flush out Riser
2ff814d6-0acd-4ba6-8f96-4f69c562ca0d |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-010-A1-MI-019 - Main Compound - Subsoil pits & Flush out Riser
bdb6ed38-543a-4a5a-bec8-dff6ddaacc99 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-020 - Zone4-2nd load-Stormpro pipes
687ac66f-961f-4dda-ac0e-667631c914d7 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-010-A1-MI-021 - Hume Compound - Subsoil pits & Flush out Riser
f7c19235-4e51-4cfa-b586-34bb6b0d5275 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-010-A1-MI-022 - Golf Course and Hume Compound - AGI pipes
0c43fdc7-54f9-4267-a8eb-cd3cf54ed716 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-023 - StormPro-Zone3 and Zone4-1st and 3rd load
1bb4aea4-d33d-46dd-b73b-a70ab0cd3703 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-024 - Memorial Park 375mm Stormpro
523537a7-83f5-4d02-ad34-672d0d73dbb0 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-025 - Hume South Headwall - Reinforcement bars
16f81fee-d87e-4e97-9cfc-b71208104aa7 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-026 - Zone 3 - Pits 305,92,192-2,120,346,192,305-a,091,192-1,090
be47fe00-fdd3-4400-ad1e-281a41b0e17f |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-027 - Zone 3 - Pits 304, 167, 093
662dc6f2-3b7c-4007-b681-a48f4bd90887 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-028 - Zone1 -Memorial Park - 166-2, 166-3, 070, 006-1, 009, 349, 004, 006
66a9bc1a-af65-400a-ab6b-68806e4b70b7 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-029 - Hume South Median- Cover and Frame - 2 PCS
928f9b71-28e5-4dc8-bb36-101b91d99dc4 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-076-A1-MI-030- Hume Medians - Permanent signs
b97da05f-2747-43b6-8d2f-e65d7ddb3118 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-031 - Zone1 -Memorial Park - 009-1, 009-1R, 009-2
19e818f3-5d43-405e-b2ab-859e748214bd |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-032 - Zone1 - Hume Compound - 6 Lintels , 2 Corbel and 1 Grate and Frame
fe846954-3a21-4eef-98c9-bf7481086c2e |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-033 - Zone 3 - Pits - Batch 16-2- Pit114, 53,297,135,113
18f48554-c2f3-4dfb-aebd-235fa07e0c3a |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-034 - Zone 1 (Memorial Park) - Pits - 007-R, 265, 331
73448bc9-0c86-41ca-9e06-2d574385ed54 |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-035 - Zone 4 - Pipes (Order 11) 1/2 (RCP750) - Hume Compound
90dedff6-e150-455f-9b89-c2b6353cecb1 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-036 - Zone 4 - Pipes (Order 11) 2/2 (RCP750) - Hume Compound
8f8e859a-9785-44ec-939b-58fe316ea566 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-037 - Zone 1- Pipes (900 RCP) - Memorial Park
0f459f2d-b23b-4fd8-a542-a7c11efa7434 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-038 - Zone 1 - Pipes (600 RCP) - Memorial Park
368bc150-3649-467a-9841-ba4494b1c9f1 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-039 - Zone 1- Pipes (1050 RCP) - Hume Compound
9ec8d1b7-4c05-443a-8999-bb2288d48875 |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-040 - Zone 1- Pipes (375 RCP) - Memorial Park
6e6cc8e3-72f3-406a-96eb-4ffeeef71b74 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-041 - Zone 1- Pit - 009-2-Riser
89bb76a5-cef1-4216-900d-13d175c696d1 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-041 - Zone 1- Pipes (450 Pipes)
2b15d311-27eb-4a69-b8d7-0923b36ee8fb |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-043 - Zone 1 Memorial Park Pits - 201, 003, 199
e9fbad2b-0ea3-4cf5-8cd2-793616a859f5 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-044 - Zone 3/4 - Pits 302-TS,142,255,17-TS,17-1,044-1,086,259-1,302
8c249c3b-d58b-4d73-9f57-989e8b391095 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-045 - Zone 3/4 - Pits 294,294-R,295
ead4893b-be5a-413f-90e9-f9dd1649f69b |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-046 - PIT 133,118,088,103,113
e734f6ee-d5b8-400c-9dbd-5a20548ae3a9 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-047 - Occo pits 072, 117, 259-1-R, 84-R, 094-R, 140-1, 259, 225
c1b0a496-d39b-4be2-8db4-390d0bb809b6 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-048 - Class B Lids, SM2 Lintels, Corbel, Grate Lid
f1c808c5-6cd8-46d8-8da5-c44aad937273 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-049 - Occo pits 242, 293, 299, 180R, 294R, 295R, 278-R
4d74aed8-41f9-429a-9d24-e363f0b4ccca |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-049 - Memorial Park Pits - 261-1, 201-TS, 311-TS, 054-TS, 270-TS, 283, 261-1-TS
e7c142ef-c527-4a8a-9c17-9d77b740bd4d |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-050 - Pit 328, 140, 017-R, 017-1-R, lintels and covers
175fd034-7d4a-48d9-a1f9-5133aaa3bf22 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-051 - Memorial Park Pits - 166, 166-1, 007
dfa63be7-5d41-4b7e-8296-42d9b41c9272 |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-052 - Memorial Park - 525 RCP
4c1e37d5-70f5-4407-a88e-72fcd3514d56 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-053 - RCP - Zone 3
3dbf84b2-ed8c-4910-ab5f-00edd5750feb |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-054 - Pit 278, 266, 240, 85-R, 235-R, 241-R, 246-R, 274, 235
d886fcde-9c0f-43cd-8526-8943db4c53c5 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-055 - Pit 270
90eebe24-1053-475e-99d1-0af6a7a37d6c |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-056 - Pits 171, 180, 239, 205, 236, 247, 245, 052, 250
02dc594c-24a9-41e9-85ce-526439aeb89d |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-057 - Memorial Park - Pit 261-1
801d7699-4fce-4e4c-ab65-82b1a3d20738 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-058 - PITS 337, 084, 085, 241, 243, 244, 246
8e633be8-9b79-48db-ac44-bcad4ec95d98 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-059 - PITS 054, 366-1, 271, 030, 001, 359 - Memorial Park
137ee8f5-4090-4949-a85a-204d42424ba8 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-060 - 005, 257, 389, 291, 331-1, 008 - Memorial Park
1a600e7c-63cf-46e3-8306-598aae0ca83c |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-061 - Pit 342
f18c81e2-e196-4a20-84e1-10f8e3da7b0e |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-063 - Pit 18, 249, 275-TS, 321-TS & 63-1- Memorial Park
802dd527-0af5-4f0a-97b6-e5791e03abde |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-064 - Pit 11-TS, 11- 2- TS - Memorial Park
52d3fd19-85ff-4111-b437-4963485df190 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-065 - COVER AND FRAME COMPOSITE 1000X750 - SEP CLASS C X 9 - HUME COMPOUND
0ca025a3-7bcf-415f-a075-79f4ef6efea1 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-066 - pits 30-1,31,39,40,43 & 237 - HUME COMPOUND
18305ecd-a8cb-42f9-b89c-f70de051e391 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-067 - pit 282 - HUME COMPOUND
7cffe810-3244-4b8d-b434-00a96113f92d |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-068 - RCP PIPES 1050 mm X 10 PCs - MEMORIAL PARK
d04336bf-0206-4b4f-9bf7-d12084da1f27 |  | checklist-sectioned | not-started | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-069 - RCP PIPES 900 mm X xxx PCs - HUME COMPOUND
c584956e-900d-4fa4-8078-de3f62f5c589 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-070 - Pits - (009-3, 011, 275, 386 - Hume) (38, 42, 364,366 - Memorial)
befa66fd-723e-4210-bdd4-39c04648be05 |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-071 - Pits - (170, 159, 403, 197,198,200,292,154,175,195)
3f18fd3f-85d2-4b7b-82b1-0e685131ae70 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-072 - Pits - (176,280,307)
af92a583-429c-43ce-8c90-8a4217669eb5 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-073 - StormPro 900, 525 and 375 - 8 Nov 22
5587549e-5cbb-490a-b3e7-61aae032ff28 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-074 - RCP 300,lintels and green covers
5c83a1da-7395-4727-a3c0-18f1da10aae5 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-075- Pit 260, 261 Corbel, lintel, grated and heavy duty cover
d5fdba88-a579-481c-b1cb-7c49382f09fb |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-076- Pit 54-1,54-2,54-3-GRATED PIT -MEOMRIAL PARK
914a76e4-4b87-49b3-8a4d-da8502390dc3 |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-077- Pit 261 - SIDE ENTRY PIT -MEOMRIAL PARK
28e88d72-f016-47cd-80de-da3c39a1501f |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-078 - Pit 182 - JUNCTION PIT + TOP SLAB - MEOMRIAL PARK
cdbead39-3ec4-419e-bda3-9f3d606bbdb6 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-079 - StormPro 525 and 375 - 9 Nov 22
130c4727-6705-4e61-9d67-58ae63c35cb2 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-080 - Kit cover concrete SD1301 SM2 single lintel Vicroads - 11 Nov
1ee221f4-e400-4e87-b3de-b81cbc9a7f31 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-081 - Pit 017-1,017,173TS,307,280,176,195,175,154,292
4140eb7d-6681-416a-95b8-f76d0c0b8d76 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-082 - Pit 200,198,197,403,159,170
898f18c5-c521-4ee9-9d80-7abd70d22823 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-083 - Pit 196,324,375,172a
0a507790-d5a8-4eb9-af40-06b172bc5772 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-084- Pit 63 - SIDE ENTRY PIT -MEMORIAL PARK
e26fe8d5-51ca-4429-8e48-ca435d7f7377 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-086- Pit 321 , 011-2 - SIDE ENTRY PIT -MEMORIAL PARK
ddaf2411-8164-416e-be8b-5aa590a65c6e |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | TP-017-A1-MI-087- Pit 54 -TS , 282 - TS - TOP SLAB - HUME COMPOUND
2f34fd5a-2627-478b-a1de-597f644b3e02 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | TP-017-A1-MI-088- Kit cover concrete x 6 - Zone 3.2
6d4cf29f-aa02-40c6-8abb-590acf7004da |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | Order Acceptance Certificate - Lot: MI89
c897d320-c5a0-4887-b85e-d0b88c078d5d |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-090- Pit 20 (GSEP), Pit (023,24,25,32,35) SIDE ENTRY PIT - MEMORIAL PARK
e25c59f8-02d2-4d5c-b153-f93bbdee3e98 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-091- Pits 011-1, 036, 039, 064-R, 119, 237-1, 237-2, 329, 383, 384-1R, 384-2R, 384-3R - Hume Compound
cbf9c52f-09f4-4533-99e8-568fb8668b67 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-092--Pits 064R and 384-3R - Hume Compound
80f7ea32-8b3f-4261-90cd-88803b82579b |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-093--Culvert 300x450. Zone 3.2
453100cc-9737-4584-aa87-cd9a86b01c74 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-094- Pits and Risers-106, 211, 214, 212, 207, 207-R, 286-R, 214-R, 215-R, 212-R - Golf Course West
17ee05bf-8d56-45f2-89c9-018c59313712 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-095. PITS AND RISERS- 211-R, 398-R, 106-R, 203-R, 187-R - GOLFCOURSE WEST - 287 - Z3.2
6b8208a9-7328-48b4-8167-f462d232bc22 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-096 - CULVERTS 450 X 300 , 900 X 300 - CLOVELLY WEST
42dc4dd1-58e6-4967-b93c-4d5ded8b4693 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-097 - Zone 1 - Pits 016 AND 391 - Hume Compound
3d33b39e-83f0-47f2-aa8f-b46f2fde71fb |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-098 - Pit 009-4, 012, 012-1, 357 - Hume Compound
4cf73bc8-caee-44ab-8023-de5fca812d12 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-099 - Pit 229, 066, 299, 321-2, 050, 142, 098, 321-1, 299-1, 321-3 - Hume Compound
cd1c9e59-0094-41e4-a842-5c6a3223d7d6 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-100 - Pit 044-R, 140-R, 140-1, 143-R, 002 - Hume Compound
53fdae6d-effa-4688-92ce-93f4463a967d |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-101- pit 172, 172aR- Z3.2- 215 - Z4.1 and 4x Corbels - main compound
d522d1fb-4760-4d0b-80f0-0cfe544ac625 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-102 - Pit 064-1, ENC x1 - Hume Compound
728b2a2e-7724-4d85-877d-c62be092ceb4 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-103 - Pit 173 - Z3.1
05780ecc-0357-4784-8184-fc8e667503ce |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-104 - Pit 263, 216, 216-R, 217, 217-R, 218, 218-R, 219, 219-R, 220-R - Z4.1
c1a1efbf-4e9d-4eea-a270-798d46914d30 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-105 - 221-R, 222-R, 223-R, 224-R, 264-R, 399-R - Z4.1
2d9a8c04-82e0-4b97-9e50-d7fb9876498f |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-106-TRAFFIC SIGNS-BATCH#1-bRIDGEWATER
887be75a-0e79-4832-ad39-9a446fdb90ef |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-107-TRAFFIC SIGNS-BATCH#1-BRIDGEWATER
d618f4f4-2d3c-494c-9aa8-59a6436ba1b6 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-108-TRAFFIC SIGNS-BATCH#1-BRIDGEWATER
8f8bba05-968f-42fe-8ec8-aea441eda1c2 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-109-TRAFFIC SIGNS-BATCH#1-BRIDGEWATER
d6276c92-a63e-4381-a0cf-80e7c3e76a02 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-110- drainage pit 151, 019, 099, 187
281c11b0-13ec-410a-927e-cc60ef8875c8 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-111- drainage 153, 153-1, 019, 152R, 151R, 150R, 149-1R, 099R, 062R, 019R
76c360fc-09ed-4d49-a6b0-8239da0b969e |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-112- drainage pit 204,223,224,220,221,222
86120246-3b70-4572-b654-e6634bcf358b |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | ITP-017-A1-MI-113- drainage pit 398, 084R, 152-1R
4a71794b-2ebf-4eb8-8827-16f8d1328936 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 1 Checklists | Order Acceptance Certificate
4d713f0f-ecd2-496b-8c76-a426c0cb894b |  | folder-normal | fail |  | step | TRUE | FALSE | Material Inspection Checklist | Area 2 Checklists
b90f11f4-593c-4c50-a8a2-978705438b0e |  | checklist-sectioned | not-started | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Order Acceptance Certificate - Lot: DRAFT
dfbd98a0-4b7d-48fc-b712-71d2695c8a1a |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-001 - Mickleham Rd Zone 7 - 08/02/2022 RCPA RCP pipes
f1229cee-88a5-4778-b769-9caf1dc4687a |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-002 - Mickleham Rd Zone 7 - 02/02/2022 Auspits Batch 3 Pits 951, 952, 955, 956, 766A, 766B, 511B, 762, 763, 765
e724f68e-2572-433e-b66d-a1eb85b44b17 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-003 - Mickleham Rd Zone 7 - 02/02/2022 Auspits Batch 3 Pits 769, 771, 773, 800A
0139cfb8-2730-4b46-bb89-9ed3df52db16 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-004 - Mickleham Rd Zone 7 - 02/02/2022 Auspits Batch 3 Pits 950, 778A, 803B, 817A, 817B, 817
68625293-f984-4a61-9189-2458102790b5 |  | folder-normal | pass |  | step | TRUE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo
1c585b02-edf7-4828-b868-8816a1620979 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-007 - Zone 7 - 08/02/2022 IPlex BlackMAX SN8 Pipes
b265194f-742d-46d6-aca1-595c7c55d73a |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-008 - Zone 7 - 09/02/2022 RCPA, RCP & RCBC pipes
598d1c31-1091-4c4b-bdc9-ef7da07fa947 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-006 - Zone 7 - 08/02/2022 EnviroPipes HDPE SN8 Pipe
eac0dcac-d67a-4945-96a0-d408861dff30 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-012 - Zone 7 - 11/02/2022 Auspits Batch 1 Pits 559, 560, 561, 562, 563, 564, 565, 567, 571, 572
dc8ef339-fefd-472e-851b-e6f847825e04 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-013 - Zone 7 - 11/02/2022 Auspits Batch 1 Pits 573, 577, 578, 579, 580
67e06f64-318e-475b-8158-63f19bf8aab5 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-005 - Zone 7 - 03/02/2022 RCPA RCP pipes
8f750f8c-c41b-4256-99a4-ca2570b22b75 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-015 - Zone 7 - 17/02/2022 RCPA, RCBC culverts
36db5b39-fde9-4527-b4ec-273608db4e8b |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-016 - Zone 7 - 18/02/2022 RCPA, RCBC culverts
7c1721c2-878b-45d0-8864-615ca67a8562 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-018 - Zone 7 - 21/02/2022 RCPA, RCBC culverts
76f8d083-fc44-4cfd-9250-727b84ff8d0a |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-017 - Zone 7 - 18/02/2022 Auspits Batch 1 Pits 567A, 567B, 567C, 572A, 573A, 573B, 573C
e9a8025d-6ec2-40a7-8b67-601219434481 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-009 - Zone 7 - 09/02/2022 Convic BlackMAX SN8 Pipes
3a35ffd4-86f7-4e76-a94f-5d7e286f7281 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-011 - Zone 7 - 11/02/2022 Convic BlackMAX SN8 Pipes
07daa688-c411-4800-a955-9062b09aae59 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-019 - Zone 7 - 22/02/2022 RCPA, RCBC culverts
80a68c31-1f2d-473a-a38b-74a884808bda |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-010 - Zone 7 - 10/02/2022 Convic BlackMAX SN8 Pipes
407191e4-4793-40a1-9d46-8e85b82d11a4 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-020 - Zone 7 - 23/02/2022 RCPA RCP pipes
63893d53-b89c-4ac6-b365-d2693abcae4d |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-021 - Zone 7 - 24/02/2022 Auspits Batch 1 Pit 566A; Batch 3 Pits 522, 522A, 521B, 521C, 521A, 764, 763R, 767, 957
e668877a-1923-4793-8925-39ccc1f6f07d |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-023 - Zone 7 - 25/02/2022 RCPA RCP Pipes
18098fdc-7701-4366-828d-c09bd6e12f73 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-022 - Zone 7 - 24/02/2022 Access Covers Pits (Full Set)
db403f6c-82e3-461b-b198-32f52070d5db |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-024 - Zone 7 - 09/03/2022 Auspits Batch 1 Pits 568, 569, 575, 576; Batch 4 Pits 502A
c7d187e2-21d4-4b47-be86-1de98b34c8c2 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-025 - Zone 7 - 11/03/2022 RCPA RCP Pipes
1b07abe7-98d6-4e94-bcca-b00aa3535d9d |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-026 - Zone 7 - 15/03/2022 RCPA RCP Pipes
69ae9915-48a1-4646-b58e-f265249f66c1 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-027 - Zone 7 - 15/03/2022 RCPA Culverts
f2568b3a-bca4-4b2c-bf1c-552f9b0863f4 |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-028 - Zone 7 - 15/03/2022 Aus Pits
22f2121e-bcf8-4a67-9123-142360d05f4b |  | checklist-sectioned | pass | d48b301c63c248bed1c43171e037504d4cd5d3c3b112a2a6565cd87388150140 | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | Zone 7 Mickleham Road Occo | ITP-017-A2-MI-029 - Zone 7 - RCBC 25/03/22
8a888d45-1fc3-4fc0-8897-e06720c3d6d1 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-030 - Craigieburn Rd - 17/02/2022 Auspits Lintels
e5d888c9-a471-43e6-8178-de1a027dc22c |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-031 -Craigieburn Rd - 11/02/2022 Auspits Pits 559,560,561,562,563,564,565,567,571,572
c8f46b24-ffce-4a1a-b744-c2331ff58c7d |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-031 -Craigieburn Rd - 11/02/2022 Auspits Pits 573,577,578,579
b8e791f9-6ee5-43aa-9898-63f603a5cd57 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-032 - Craigieburn Rd - 23/02/2022 Auspits PIT COVERS
07dc30ed-feea-41db-8579-cd40e7c182d8 |  | checklist-sectioned | fail | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-032 - Craigieburn Rd - 23/02/2022 Auspits PIT COVERS, LINTELS, PIT 766, 767
a6336d3e-e5d9-410d-9b14-f67d66cfdc61 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-033 - Craigieburn Rd - 23/02/2022 Auspits PIT COVERS, ENCASEMENT
9b554330-0a1f-4e4a-8534-93c0dcebde6c |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-034 -Craigieburn Rd - 02/03/2022 Auspits Pits 511,512,753a,754,756,803,804a,501b,802c,755aa
65e289d3-1f88-46af-92e5-bebeb42f1c3e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-034 -Craigieburn Rd - 02/03/2022 Auspits Pits 508,509,752E
648f69cb-6f79-458f-afe6-4100aef21c5b |  | checklist-sectioned | fail | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-035 - Craigieburn Rd - 04/03/2022 Auspits Lintels
af7e527b-d2cb-4023-ab8c-66c91f53f9e0 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-036 -Craigieburn Rd - 11/03/2022 Auspits Pits 1163,688AB,688AA
ad14ca39-6bbe-403e-bd88-9c3a35e39ef8 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A1-MI-037 -Craigieburn Rd - 11/02/2022 Auspits Pits 1001,1002
1e29bbc1-d481-458a-9149-ec8ee9a69033 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-038 -Craigieburn Rd -24/03/2022 Auspits Pit 588a
0232305f-3a2f-4fbe-bea3-3a73ce79cc91 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-039 -Craigieburn Rd -24/03/2022 Auspits Pit 587a
9ece07cd-38b4-4b07-8ee8-bf71dee3d323 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-040 -Craigieburn Rd - 28/03/2022 Auspits Pits 450,450a,558,558b
8653e039-f569-4903-80f5-11637b68ba9e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-041 -Craigieburn Rd East - 04/04/2022 Auspits Pits 559-R
364879a8-8b33-4189-ac9f-d3f71c7cf447 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-042 -Craigieburn Rd - 05/04/2022 Auspits Pits 557A,557A-R, 558b-R
d0e533b5-e365-40b5-9de3-46b17226ce63 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-043 -Craigieburn Rd - 06/04/2022 Auspits Pits - RISER 558-R
5f317327-7f3d-4c5f-9306-a25e21991c20 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-044 -Craigieburn Rd - 11/04/2022 Auspits Pits 541-R, 544, 546, 549, 550-R, 551, 552, 553, 554, 554-R
b9c10f11-e100-4d99-8cba-2a2c68f280da |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-044 -Craigieburn Rd - 11/04/2022 Auspits Pits 555, 556
9e1ed9a5-a2d4-4153-9dbd-de2e289e5f7b |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-045 -Craigieburn Rd - 27/04/2022 Auspits Pits 542, 542-R, 544-R, 547, 555-R, 556-R
d05687da-98f5-48f9-ab83-6eb69b37f91a |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-046 -Craigieburn Rd - 02/05/2022 Auspits Pits 543, 543-R, 552-R
abfdb7a8-acdd-4bda-911c-d8426ab0bba5 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-047 -Craigieburn Rd - 18/05/2022 Auspits Pit 545
48c86f81-5fd5-4d36-83d0-06f3ec162c89 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-048 -Craigieburn Rd West- 03/03/2022 Access Covers
2d919555-651a-4613-b391-2dd3aba7698b |  | checklist-sectioned | fail | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-049 - Zone 7 - 23/02/2022 RCPA RCP pipes
7bf498c1-379b-4054-915e-f987071d626a |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-050 - Zone 7 - 03/03/2022 RCPA Base Slabs
0d301a51-ba0d-44d9-8ac8-375d5303377d |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-051 - Zone 7 - 01/03/2022 RCPA, RCP pipes
60280978-b142-4734-a016-d864f1119928 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-052 - Zone 7 - 4/04/2022 RCPA, RCBC culverts
a447d09a-df51-4181-ab5b-b0c5c6389d0e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-052 - Zone 7 - 7/03/2022 RCPA, Rings
42de427c-2ca3-47dd-8e2d-2bdf00ebc74e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-053 - Zone 7 - 11/03/2022 RCPA, RCP pipes
125af667-0f02-4cb3-b56f-0f1df8fa2588 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-054 - Zone 7 - 16/03/2022 RCPA, RCP pipes
ad8c4902-ef18-4b3d-991e-9fa45e33718c |  | checklist-sectioned | fail | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-055 - Zone 7 - 25/03/2022 RCPA, culverts and Base Slab
6049c708-49eb-47e5-9be0-854f076eb24f |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-056 - Zone 7 - 13/04/2022 Convic BlackMAX SN8 Pipes
04112d1f-dd5d-4739-a318-9b3bb790ede8 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-057 - Zone 7 - 08/02/2022 EnviroPipes HDPE SN8 Pipe
f6f5b1af-ae45-43e0-ad36-4cb6765e9e32 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-058 - Zone 7 - 28/04/2022 EnviroPipes HDPE SN8 Pipe
4378ed2d-47dc-4e2d-9f5a-4d8c6c6d91a3 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-059 - Zone 7 - 02/03/2022 EnviroPipes HDPE SN8 Pipe
eb13bb28-34fb-4144-be33-6eab3086167d |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-060 - Zone 7 - 02/05/2022 EnviroPipes HDPE SN8 Pipe
d01b238b-f54a-4dfb-bd25-afc6d29d1804 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-061 - Zone 7 - 03/05/2022 EnviroPipes HDPE SN8 Pipe
da5456a2-50de-4559-a759-fb0eecb81582 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-062 - Zone 7 - 01/03/2022 EnviroPipes HDPE SN8 Pipe
f43edac4-6a82-43e1-9210-18e57519785c |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-063 - Zone 7 - 04/05/2022 EnviroPipes HDPE SN8 Pipe
e71e32fb-cdcb-4244-871b-fc97c886847e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-064 - Zone 7 - 2/05/2022 Convic Enviropipes
7d56999a-68d2-4df5-8b79-7201f5feb0c1 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-065 - Zone 7 - 7/04/2022 Convic Enviropipes
95cc287b-12a5-432f-ae53-d942515bb64f |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-066 - Zone 7 - 07/03/2022 - SVC Risers
cc42435a-3d84-4a29-8949-259813fcb5de |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-067 - Zone 7 - 10/03/2022 - SVC Risers
c171a788-ac00-45b9-9665-aa5e53e45f9f |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-068 - Zone 7 - 22/02/2022 - SVC Risers
f6d7723f-1599-455e-b53c-e27b5c63b2e3 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-069 - Zone 7 - 10/02/2022 - Fastway Agi pipes
b591ce43-6025-4bab-8215-d71b21499651 |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-070 - Zone 7 - 02/02/2022 - Fastway Agi pipes
ad97126d-bfba-4187-867c-ea28af5c206e |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-071 - Zone 7 - 10/02/2022 - SVC Risers
885a014e-7ff3-4fd6-a9b4-65acedee7a1c |  | checklist-sectioned | work-in-progress | 8f7795ba5756bb7c1b8eede7914ae95199feba474f2f599c537022dd776d8fda | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-072 -Craigieburn Rd - 24/05/2022 Auspits Pits 865,866,867,868,869,870,871,872,873
4f4c8a63-7711-48dc-b659-c7f45e294b06 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-073 -Craigieburn Rd - 01/06/2022 Auspits Pits 867A, 868A, Cover
4d414f38-fd22-4d83-ace3-0e5a72c420e4 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-074 -Craigieburn Rd - 08/06/2022 Auspits Pits Grates and frames
2c1b7b9b-fc34-4e78-8a61-07bc81542917 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-075 -Craigieburn Rd - 600 dia RCP - 30/06/2022
a967e808-bb7a-45fd-a1db-b8779e32ecc8 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-076 -Craigieburn Rd - 600 dia RCP - 04/07/2022
4ec6473b-be73-4300-bf49-e42619c25df4 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-077 - Zone 5 Aitken Blvd - Pits - 05/09/2022
67d78b73-242a-481d-8dcb-a7ef1a6df6d7 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-078 - Zone 5 Aitken Blvd - Pipes - 05/09/2022
1729fd6a-2815-43b4-9414-18d5bb7c310f |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-079 - Zone 5 Aitken Blvd - Pipes - 06/09/2022
821edc6c-772d-4aa5-936d-1dd57511840b |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-080 - Zone 5 Aitken Blvd - Catch Pits - 13/09/2022
c81ed840-850f-4a33-9848-d95520aea134 |  | checklist-sectioned | pass | 8dc99879cf2ab930a0dd4c0a29de1c7907df86ec5f25bcde371cc30dffb92eaf | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-081 -zone 6 20 box culverts - 13/09/2022
08ee22d3-26b8-470e-91f1-6ac7c2f74e9d |  | checklist-sectioned | pass | 8dc99879cf2ab930a0dd4c0a29de1c7907df86ec5f25bcde371cc30dffb92eaf | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-082 -zone 6 30 base slabs - 13/09/2022
7e70cce9-b2e8-4c4b-b33e-477d5bb4d81d |  | checklist-sectioned | pass | 8dc99879cf2ab930a0dd4c0a29de1c7907df86ec5f25bcde371cc30dffb92eaf | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-083 -zone 6 21 box culverts - 13/09/2022
1400c9a8-f8c3-4eba-a339-455d786ef160 |  | checklist-sectioned | pass | 8dc99879cf2ab930a0dd4c0a29de1c7907df86ec5f25bcde371cc30dffb92eaf | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-084 -zone 6 11 base slabs - 13/09/2022
0d8fe4ff-0ebc-4161-8138-19f559b5dd74 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-085 - Zone 7 Mickleham Road Headwalls - 21/09/2022
6a051da9-023b-44bc-9b4c-ec6b3da8071c |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-086 - Zone 7 West Stage 2 (375 dia RCP) - 60 pipes - 30/09/2022
f7faa0f0-651a-43fc-a684-1f8d7da7c71d |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-087 - Zone 7 West Stage 2 - 04/10/2022 Auspits Batch 5, Pits 1001; 1003-1011
94f042bb-9780-4066-be60-f04118b88ba7 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-088 - Zone 7 West Stage 2 - 04/10/2022 Auspits Batch 5, Pits 1012
15b29e92-8764-4ff4-bae9-46d3f41d8f8a |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-089 - Zone 7 Mickleham Road Headwalls + Pit 1002 - 10/10/2022
fb3ac908-1855-49ec-be7e-4259e561d88f |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-090 - Zone 7 Mickleham Road Headwalls (SE) + East Stage 2
17948cc8-a0a7-46ad-9772-d002f55ed70a |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-091 - Zone 5 Aitken Blvd North Pits & Risers - S1SB - 1/3
b141e749-d6a9-48e9-9a91-05988758467e |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-092 - Zone 5 Aitken Blvd North Pits & Risers - S1SB - 2/3
14689d0d-70c0-4796-990d-f6afafcf5e4c |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-093 - Zone 5 Aitken Blvd North Pits & Risers - S1SB - 3/3
0868f8bc-04e9-428f-857e-de04bc1b618b |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-094 - Zone 5 Aitken Blvd North - S1SB - Pipes 16/11/2022
3cf0ff6e-974e-46c9-acc2-f0c4b5fd771e |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-095 - Zone 5 Aitken Blvd North - S1SB - Pipes 18/11/2022
b9718ef9-74cb-4161-a6d9-c0b0d1c04280 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-096 - Zone 7 Mickleham Road Headwalls (NW)
04a0fa8a-978a-43a2-9c56-1469f69d4c9c |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-097 - Zone 5 South S2 375 RCPs
87f5e82b-c56b-4ce9-bec6-3c46d7b0f766 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-098 - Zone 5 North 525 RCPs
7a2f2f11-aee9-419a-9dce-453499073576 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-099 - Zone 5 North 375 RCPs
e8e73ac7-252d-4be5-bbf8-cba4d7429f74 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-100 - Zone 7 West 300x225 RCPA Box Culverts
33b30988-410a-43fb-b173-69cad78d29ed |  | checklist-sectioned | not-started | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-101 - Zone 7 East Stage 2 - RCPA RCP375
1e2d49cc-0b47-4ba6-af43-f5c99a4da93c |  | checklist-sectioned | fail | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-102 - Zone 6 Aitken to Waterview - Batch 37 - 15/03/2023 - 1/2
72ea0647-cb3e-4fd7-9837-93a23bcf50d5 |  | checklist-sectioned | pass | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-103 - Zone 7 East 300x225 Modcast Box Culverts
0769e67b-b6e7-4f97-81e0-c54c1a675bea |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-104 - Zone 6 Aitken to Waterview - Batch 37 - 15/03/2023 - 2/2
0c3c15d1-9976-46bc-9510-436bb573de32 |  | checklist-sectioned | work-in-progress | Order Acceptance Certificate | checklist | FALSE | FALSE | Material Inspection Checklist | Area 2 Checklists | ITP-017-A2-MI-105 - Zone 6 Aitken to Waterview - Batch 37 - 13/04/2023
15d61ae4-7a78-4f4b-bac8-1885d9de82d5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Defects - Final Inspection
521bfa4b-b523-402d-b8ae-050985e8c364 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Defects - Final Inspection | External
a31ee608-10c4-4576-9914-515ff282fcc8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Defects - Final Inspection | Internal
006c346a-15a1-495b-be63-8576e85517e7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan
e6c15ac6-c0ba-40c6-8a23-96cc1a763aa0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-001 - Crack in Kerb - NB Verge - 20m North of approach terminal
3691ffa6-6099-42c7-9eb9-19dee0f563ac |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-002 - Crack in Kerb - NB Verge - Near Pit 1181
1b75a7b9-873a-4455-ac72-b517791509b9 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-003 - Crack in Kerb - NB Median - 50m south of intersection
f0e96173-47b2-4cbc-9f6a-7eb9d4676919 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-004 - Crack in Kerb - NB Median - Opposite 20m North of approach terminal
ba698152-aa81-493e-b4e4-0f15b3c14965 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-005 - Crack in Kerb - NB Median - 20m south of intersection
e7417487-a7a5-439b-8090-e52697467ee6 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-006 - Remove Pram crossing - Not DDA compliant. Too high - NB Median - Tip
670abd6f-76cf-4414-a03a-1ac875ee2330 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-007 - Crack in Kerb - SB Median - U-turn Bay
7c8892cd-a57f-40c1-8125-9de1f8d1b937 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-008 - Crack in Kerb - SB Verge - 100m south of intersection
057612bd-c0ca-48d2-afd0-b8de7abe2d98 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-009 - Crack in Kerb - SB Verge - 50m South of intersection
22e525ba-2b45-48f7-918c-56ff5427715e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-010 - Crack in Kerb - SB Verge - 70m south of intersection
766973ad-0bfa-4fff-8f76-d1d9f81c1bf1 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-011 - Crack in Kerb - WB Verge - 10m East of Guardrail Footing
5835ec91-9339-4490-a5db-d8c5014c47c4 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-012 - Crack in Kerb - WB Verge - 110m East of Guardrail Footing
469f3e75-6c4a-4589-a867-23d12ca8fd11 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-013 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
b91060dd-b83d-4302-b3be-1cfc8930454a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-014 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
be274cdc-ddc0-498f-90f4-85564da098f7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-015 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
da0a9a57-ea25-48c8-adad-676409fbfa73 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-016 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
12d59c97-0b68-4274-9550-9de8755df974 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-017 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
8b870572-e2f4-47cc-b846-db31e8927535 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-018 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
5ca2a903-4b17-4c79-8c11-90f7b3cfcf12 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-019 - Crack in Kerb - WB Verge - 140m East of Guardrail Footing
53f13eb6-2d83-40d5-b12a-632379d1abb5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-020 - Crack in Kerb - WB Verge - 150m East of Guardrail Footing
0c86c9fc-c41d-4f3e-93c5-3198c0652967 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-021 - Crack in Kerb - WB Verge - 180m East of Guardrail Footing
b0fc9f90-8e0d-46a3-af70-80ef01563413 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-022 - Crack in Kerb - WB Verge - 200m East of Guardrail Footing
e97e125a-2086-4cac-b627-f314eec1f239 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-023 - Crack in Kerb - WB Verge - 20m East of Guardrail Footing
f3584ad1-9736-4464-a1ca-b30c061ca94c |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-024 - Crack in Kerb - WB Verge - 230m East of Guardrail Footing
125fd34a-45d1-4856-b007-d694e74df14c |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-025 - Crack in Kerb - WB Verge - 260m East of Guardrail Footing
24bc1d6e-7867-4df1-bf55-92a8e4c89f94 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-026 - Crack in Kerb - WB Verge - 275m East of Guardrail Footing
993154fa-d60a-44c3-b96e-80847188ae5f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-027 - Crack in Kerb - WB Verge - 290m East of Guardrail Footing
6c465a90-a271-4473-b10f-6183183f0336 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-028 - Crack in Kerb - WB Verge - 30m East of Guardrail Footing
5dbfd7d9-84c8-474e-847e-b81caa09bcee |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-029 - Crack in Kerb - WB Verge - 310m East of Guardrail Footing
2910254d-4eeb-491c-8e27-cb1135d3660d |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-030 - Crack in Kerb - WB Verge - 40m East of Guardrail Footing
c7752da7-3d68-4c91-9f40-ffba1b4fc9e7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-031 - Crack in Kerb - WB Verge - 45m East of Guardrail Footing
7b821db9-32f7-4bfb-b10f-50c970643ed2 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-032 - Crack in Kerb - WB Verge - 50m East of Guardrail Footing
cc408c4b-9484-4fcb-9c1a-cc9ff037375a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-033 - Crack in Kerb - WB Verge - 60m East of Guardrail Footing
96db2bde-1241-4dc8-aaf1-3377552f98ba |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-034 - Crack in Kerb - WB Verge - 70m East of Guardrail Footing
8f304973-7090-491c-a100-209c63125f03 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-035 - Crack in Kerb - WB Verge - 80m East of Guardrail Footing
7f7a2714-4f7c-4e74-bcef-ee68fab93a3b |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-036 - Crack in Kerb - WB Verge - 90m East of Guardrail Footing
d1965ceb-ad8e-4a8e-b6db-31a275640e99 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-037 - Rectify Guardrail Footing/Kerb. Pit lid too proud - WB Verge - 160m East of Guardrail Footing
3fbe4162-d321-4188-bfa5-9df17f510c9a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-038 - Step present. To be removed - WB Verge - 70m East of Guardrail Footing
45ca453a-4c61-46d4-af24-007621b4c336 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-039 - Ableflex not installed to full length - WB Verge - 120m East of Guardrail Footing
2fc35b39-69be-4b96-bc6c-f7fe1252715f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-040 - Crack in Kerb - WB Median - 20m West of temp pavement
35a6c0d9-9338-48c7-ad1b-95666ee12363 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-041 - Crack in Kerb - WB Median - 30m West of temp pavement
fa51ee0c-87f9-46c2-8f17-82bfa9a37c08 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-042 - Crack in Kerb - WB Median - 40m West of temp pavement
481b8e8c-f10a-4689-80b6-f9d0ada28d68 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-043 - Crack in Kerb - WB Median - 50m West of temp pavement
15191d39-905f-4710-b3bf-daf9cee16a53 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-044 - Crack in Kerb - WB Median - 60m West of temp pavement
0d3463f8-1222-4f7b-a32a-5bd2ac3234fc |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-045 - Crack in Kerb - WB Median - 70m West of temp pavement
b5b5315a-6f89-45cf-8d13-de77ae222c60 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-046 - Crack in Kerb - WB Median - 90m West of temp pavement
38e91667-f02c-4345-b58c-c48b407abaf3 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-047 - Bucket has chipped kerb - EB Verge - 100m from Eastern GR terminal
8a9dfdf1-7064-4552-8382-718ecf33a093 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-048 - Crack in Kerb - EB Verge - 110m from Eastern GR terminal
fb3afc82-12d9-44d2-a72b-f73871436a96 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-049 - Crack in Kerb - EB Verge - 30m from Eastern GR terminal
80c9751a-36cd-4928-849f-6bc9c85b4851 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-050 - Crack in Kerb - EB Verge - 40m from Eastern GR terminal
35bc9ae4-8b6a-4f8b-979e-873728692e9e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-051 - Crack in Kerb - EB Verge - 50m from Eastern GR terminal
2cf38061-49c0-4a02-bab7-ae63cea83cec |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-052 - Crack in Kerb - EB Verge - 60m from Eastern GR terminal
165aa0bf-4725-463b-91c0-49d47e56b983 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-053 - Crack in Kerb - EB Verge - 70m from Eastern GR terminal
a2557ccc-b8f9-4be5-b714-5e0dd4daa224 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-054 - Crack in Kerb - EB Verge - 80m from Eastern GR terminal
62bd7c70-6aa0-4f09-b3cf-c2f1f9a7c34e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-055 - Crack in Kerb - EB Verge - 90m from Eastern GR terminal
9073b779-1cb3-4fe5-8d02-2e2aa32388ed |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-056 - Crack in Kerb - NB Median - 20m from intersection
936b2c4e-ee81-464b-87b6-97040072982a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-057 - Crack in Kerb - NB Verge - Start of U-turn Bay
ec886440-206f-4699-9f85-0eb6d9f63056 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-058 - Crack in Kerb - NB Verge - Start of U-turn Bay
9804eb7d-dca0-45b2-ace2-9a0d233c2c21 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-059 - Patch Repair - Kerb - NB Verge - 20m south of U-turn bay
4c48036d-4747-479a-8cb6-c566c6159add |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-060 - Crack in Kerb - SB Median - 20m south of North median tip
23a9d7ad-e34e-4fee-9ba1-48b505e70ae0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-061 - Patch Repair - Kerb - SB Verge - 40m North of U-Turn Bay
910bd228-c03d-4c5a-ad56-ab38df170ba7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-062 - Crack in Kerb - SB Verge - 20m North of U-Turn Bay
ac85e766-187d-40b9-ba1f-16d3a0c5c5b7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-063 - Crack in Kerb - U-Turn Bay
7c44e4c4-e560-4db8-b07d-61017e4ed08e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-064 - Cracked Kerb - NB - Kerb on Verge - CH30600
4a97dbc2-3486-4ba5-af36-46573bb70091 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-065 - Subsoils located below invert of outlet pipe. Pit close to end terminal of guardrail
a6b84a3c-70db-4b25-8051-832a5a2442b1 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-066 - Subsoils located below invert of outlet pipe. - NB - Verge - Pit 1069
65e7a645-3923-4500-bf9f-872f2b4cd9b2 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-067 - Chip in Kerb - SB - Verge - CH40600
13e85e2d-20fe-4e1e-b762-12b2657d2ccf |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-068 - Chip in Kerb - SB - Verge - Pit 1046
974ba867-df5a-4535-9495-006a53dfaf54 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-069 - Cracked Kerb - SB - Verge - CH40410
701cfaea-dd21-49dd-9949-18ee9d692129 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-070 - Incomplete pit works - Pit 559
1bbe8128-3663-4ada-ae30-40cfe887521a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-071 - Incomplete pit works - Pit 558C
410a9079-b223-4ac8-bac8-c47772f18675 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-072 - Unfilled barrier cutouts - Zone 7 Verge - Debonair to Mickleham
2f23e278-4b82-4a5b-9a57-4b9c49ce4bec |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-073 - Crack in pavement - Pit 559-560
b83d74e2-02de-492f-859b-dcf3939984d8 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-074 - Incomplete pit works - Pit 560
af7a2713-f7bb-48d4-a0d1-af85ff4cb329 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-075 - Lumpy Topsoil - Pit 560-561
bc6c2200-04c8-47cc-a01c-218f44130ecc |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-076 - Incomplete rectification of crack - Pit 560-561
e7317b77-0d27-40e4-a54f-90443be26e9f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-077 - Incomplete pit works - Pit 561
25a50f15-665f-4a16-8069-2ce279eb00b4 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-078 - Adjacent wall too steep - Pit 561
d0d51be7-a27b-4328-aae6-eb73f0b38201 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-079 - Incomplete pit works - Pit 562
bb4998e4-f722-4638-bcf9-29610d4e570b |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-080 - Incomplete pit works - Pit 563
3a10c197-427b-4096-a1e5-e225370df96c |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-081 - Incomplete rectification of crack - Pit 563
852aa1aa-c6d2-4c62-801f-958902af4e6e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-082 - Chip near Kerb edge and pavement - Pit 563-564
f1b28834-0d31-4661-9786-ac1cb8c734dc |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-083 - Incomplete pit works - Pit 564
54bf8d0e-66ec-4cfb-b74f-ea3e3ab80853 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-084 - Incomplete rectification of crack - Pit 564-565
821f4acc-af08-455a-91c7-b4ef855a5b2e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-085 - Incomplete rectification of crack - Pit 564-565
6f9e4d8c-8e4a-4dc7-966d-444c6a441d11 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-086 - Incomplete pit works - Pit 565
a824f619-cadc-4a7d-8926-8ac6baf5826b |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-087 - Incomplete rectification of crack - Pit 565-566
372e101e-81f7-4d65-971d-f7560294de26 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-088 - Crack in pavement - Pit 565-567C
d7e4cbac-6d3a-493c-89bf-428d68316fe0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-089 - Cut in pavement - End terminals (Pit 567)
2e3ee98c-ea2c-470f-b042-140b604dcfe6 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-090 - Incomplete rectification of crack - Pit 567
97a80ca3-9277-479a-9ae8-b6c4b48d4ce2 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-091 - Incomplete pit works - Pit 567C
ff407617-b63a-4d5b-8f84-b9a8e10e66d0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-092 - Crack in kerb - Pit 571-572
b6a7524f-4b5e-4901-a424-1ec3b394eeb8 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-093 - Crack in pavement - Pit 573
2915d6c6-2cb4-4e20-acf3-83c58c29733b |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-094 - Chip in pavement - Pit 573
e92ed85a-b5d1-438b-a64b-9a9e4e4ed7e1 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-095 - Crack in pavement - S1 Pit (West of vehicle cross over)
91afb576-1318-4321-8c9a-5fe28767fb2e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-096 - Crack in pavement - S1 Pit (West of vehicle cross over)
67354abd-61cd-4a40-a6eb-b853d8810273 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-097 - Crack in kerb - Pit 548
6e61f7ab-2f36-43dc-849f-b21840a09e52 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-098 - Crack in kerb - Opposite Admiration Drive & Reverence Drive intersection
b599134c-792f-486d-84fc-9be032f07b31 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-099 - Incomplete pit works (not inspected but same defect expected) - Pit 567
9bd5cdf4-2851-4541-96f0-d73c30408600 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-100 - Incomplete pit works (not inspected but same defect expected) - Pit 568
ab9fca89-f462-4edf-911e-753787e3996e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-101 - Incomplete pit works (not inspected but same defect expected) - Pit 569
1ed8f1aa-a3d5-41fb-b9a8-dbb55c09e1a7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-102 - Incomplete pit works (not inspected but same defect expected) - Pit 571
afdf6924-b59b-4660-b326-5b3a0816ef42 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-103 - Incomplete pit works (not inspected but same defect expected) - Pit 572
0b3bc74c-079e-4ca2-af89-4ac7ce033d15 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-104 - Incomplete pit works (not inspected but same defect expected) - Pit 573C
31d224fa-5ec8-4ef2-94d3-542494906b38 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-105 - Incomplete pit works (not inspected but same defect expected) - Pit 573
ed479179-c7c9-4f93-b7c6-1b71b940dcfc |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | DEF-FUL-A2-106 - Incomplete pit works (not inspected but same defect expected) - Pit 566
962835ed-ecfb-417b-9797-31612038c591 |  | checklist-sectioned | not-started | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Fulton Hogan | Defecting Checklist - Test
f8bf15b3-78c2-4209-909e-c658b97cc98e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Defects - Final Inspection | Internal | Subcontractors
4a1e736d-386c-482d-a49c-315b953261a6 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DOW-A2-001 - SB Verge - 70m south of intersection - Patch Repair - Kerb
34274b49-a236-46f1-b0e2-2658fbf876c5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-001 - NB - Verge - Pit 1161 - Pan of side entry pit is too steep and not rounded as per SD1301.
bbd08b8c-3c5b-4ff8-8750-66870641a22f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-002 - NB - Verge - Pit 1092 - Pan of side entry pit is too steep and not rounded as per SD1301.
aa59d1b8-e2b5-47c6-aa6c-46c18bf83b5f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-003 - NB - Verge - Pit 1079 - Pan of side entry pit is too steep and not rounded as per SD1301.
ea215899-fa94-481a-9f6d-3a1fc3320cfe |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-004 - NB - Verge - Pit 1096 - Pan of side entry pit is too steep and not rounded as per SD1301.
89f82010-564f-45f9-9510-70015a9bd894 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-005 - NB - Verge - Pit 1069 - Pan of side entry pit is too steep and not rounded as per SD1301.
03cb0b87-c327-4741-bb26-8698e8677809 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-006 - SB - Verge - Pit 1044 - Incomplete Work - Lintel
c83fd63d-19f5-4965-a5fc-e1da55e9aba0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-007 - Pit 1013 - Pit works incomplete
ebe926cd-2238-4242-80df-92ef5f5818c5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-008 - Pit 993 - Pit works incomplete
91a52435-3af0-4faf-a632-f3d078f42d90 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-009 - Pit 1088 - Pit works incomplete
d22e8d0d-5b17-4403-8d7f-5f40b632f8b7 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-010 - Pit 1161 - Pit works incomplete
17bacb51-4e48-440a-b196-f5e41ab88f3f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-011 - Pit 1092 - Pit works incomplete
da44dfa5-02a3-4331-bc89-a6bc4c3f1231 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-012 - Pit 1079 - Pit works incomplete
13efaeef-14fe-41f4-a053-eafcfadc73eb |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-013 - Pit 1069 - Pit works incomplete
795edc2e-ef06-401d-8ba3-9a9826a883df |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-014 - Pit 1037 - Pit works incomplete
db1ad3b4-1b2e-457c-a0c7-7b5f5abcb8e2 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-015 - Pit 1036 - Pit works incomplete
fcfbaae0-18c1-441a-b885-30e2ac2ad523 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-016 - Pit 1035 - Pit works incomplete
7c701e96-5f71-4ba3-9928-b321e44d0900 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-017 - Pit 1034 - Pit works incomplete
b073f46b-8036-457c-b7df-d5828828cfa5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-018 - Pit 1033 - Pit works incomplete
68dc2571-b830-4a7e-afaa-8e69476c5e39 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-019 - Pit 1038 - Pit works incomplete
d883491f-46f8-40c9-9568-2b1399d8a8dd |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-020 - Pit 1039 - Pit works incomplete
9335b4c2-fb9f-43c3-bdbd-7a1db16256fb |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-021 - Pit 1040 - Pit works incomplete
8ade81a5-24da-48f5-bb79-1ecdae138e9b |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-022 - Pit 1041 - Pit works incomplete
623f51e1-f591-4b01-8b0b-0f66943abb53 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-023 - Pit 1042 - Pit works incomplete
68bb8244-5e46-4dd3-af43-ffa7faaeb2a0 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-024 - Pit 1043 - Pit works incomplete
9cf40804-4bcc-4eb9-8dc6-c9b44f0c1778 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-025 - Pit 1044 - Pit works incomplete
48ced7f9-dc99-4d6d-9332-8c7b50b5ec28 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-026 - Pit 1045 - Pit works incomplete
c72f95a2-a1d0-42e9-b0b3-9e997edba4b6 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-027 - Pit 1046 - Pit works incomplete
a316df4e-cb34-405e-8689-8f11b82ac39a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-028 - Pit 1047 - Pit works incomplete
849fc571-87ea-4837-b126-1b1908a6836c |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-029 - Pit 1048 - Pit works incomplete
75eedd34-b25a-459e-a487-1af69e3cf83d |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-030 - Pit 1049 - Pit works incomplete
5dd48fe1-cc8f-483b-92da-3227af47022c |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-031 - Pit 1050 - Pit works incomplete
342d7691-2dc9-42b7-9d00-56507bfea1b5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-032 - Pit 1190 - Pit works incomplete
4fa5782d-5977-484a-95d1-7f506a15f21f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-033 - Pit 996 - Pit works incomplete
f4e12784-50d4-4ccd-a29a-de0e967c9d11 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-034 - Pit 998 - Pit works incomplete
bfd9df5c-5559-4388-977f-a3a230053d59 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-035 - Pit 1193 - Pit works incomplete
a5079f02-9e5d-4830-a051-d12658415788 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-DUN-A2-036 - S1 Pits - Mickleham South - Works incomplete
7e7ca85f-542c-400c-9cdc-d403b4927018 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-001 - Pit 1001 - Gatic Lid not aligned with pit
c075956a-d9a3-4d04-97b8-56f5e5b0807f |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-002 - Pit 1002 - Hole present beneath invert level
d3adf107-ca54-4377-b5e9-9f55a42c4003 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-003 - Pit 1004 - Midpoint of pit base is too high
9b68f3ed-c214-4e16-b4a5-2390e798f1f5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-004 - Pit 1015 - Pipe surround not grouted
4acee1a1-63ec-41df-9397-7a5bed7e59e1 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-005 - Pit 1016 - Pipe grouting too rough
857ff3ec-f3ac-4077-838e-305ad89a5995 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-006 - Pit 1017 - Pipe surround not grouted
20d23cd7-a7bb-4f73-a28a-4b5d4ad16b37 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-007 - Pit 1018 - Pipe grouting too rough
bfe40233-bcd1-4197-bfe1-eb2b65b1db87 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-008 - Pit 1019 - Pipe surround not grouted
e7d7bee0-49c8-4f9f-984e-1ef96315bd3a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-009 - Pit 1020 - Pipe surround not grouted
1c2ea842-0946-4a06-ac58-43300e622f83 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-010 - Pit 1021 - Concrete debris left in pit
fb71392e-869b-4126-8c25-7835866f973a |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-011 - Pit 1022 - Pipe surround not grouted
263f94dc-3e89-4770-92f2-29cfebb4dac5 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-012 - Pipe 1014-1015 - Pipe grade is less than spec
42012266-20d3-4c14-aa52-70f6b105e503 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-013 - Pipe 1015-1016 - Pipe grade is less than spec
19988d6b-f2d7-49d5-b678-d10f98259292 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-014 - Pipe 1016-1017 - Pipe is flowing backwards
5d7330fd-f147-45a0-87fc-3ac08f11a57e |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-015 - Pipe 1017 to 1018 - Pipe grade is less than spec
01d11226-ae90-40c0-994a-ffe4f1f53400 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-016 - Pipe 1018 to 1019 - Pipe grade is less than spec
ca6f3b6b-f99a-4e30-8071-1ef86dd0a402 |  | checklist-sectioned | work-in-progress | Defecting Checklist | checklist | FALSE | FALSE | Defects - Final Inspection | Internal | Subcontractors | DEF-VID-A1-017 - Pipe 1021 to 1022 - Pipe grade is less than spec
58674c4e-3ee3-466c-8a1c-a1cd9c758d66 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Test Folder
9048194f-4f56-4eba-b2a3-983dfb32e34e |  | checklist-sectioned | work-in-progress | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | checklist | FALSE | FALSE | Test Folder | ITP-084-AX-LOT-XXX - Desc