## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-075-AX-LOT-XXX - Desc | itp |  |  |  | Yes | ITP 0075 - Asphalt Placement | 9fb03d06-6160-4b7b-a83b-cfefade42822
section | Lot Information
checkpoint | 1.0 Lot Information
textbox | Lot Created On
textbox | Lot Opened On
textbox | Work Commenced On
dropdown | Lot Type | CIL-Civil Lot, DRL- Drainage Lot, EAL- Earthworks Lot, ELL- Electrical Lot, UTL- Utility Lot, STL- Structural Lot
textbox | From and To Chainage
dropdown | Construction Element | PAVI - Paving
dropdown | Activity | PAVI - Asphalt Placement
dropdown | Design Package No | 1145-ACM-CVD-DPK-0002, 1145-ACM-CVD-DPK-0003, 1145-ACM-CVD-DPK-0004, 1145-ACM-CVP-DPK-0001, 1145-ACM-CVP-DPK-0002, 1145-ACM-CVR-DPK-0001, 1145-ACM-CVR-DPK-0002, 1145-ACM-CVR-DPK-0003, 1145-ACM-CVR-DPK-0004, 1145-ACM-ELE-DPK-0001, 1145-ACM-ELE-DPK-0002, 1145-ACM-LDE-DPK-0001, 1145-ACM-LDE-DPK-0002, 1145-ACM-SBA-DPK-0001, 1145-ACM-STR-DPK-0001, 1145-ACM-TSI-DPK-0001, 1145-ACM-TSI-DPK-0002, 1145-ACM-TSI-DPK-0003, 1145-ACM-TSI-DPK-0004, 1145-ACM-UTL-DPK-0001, 1145-ACM-UTL-DPK-0002
dropdown | Traffic Direction | EB - Eastbound, ME - Median, NB - Northbound, SB - Southbound, WB - Westbound
textbox | Engineer Responsible
textbox | comments
section | 1 - Preliminary Works
checkpoint | 1.1 Submission of Mix Design
note | Frequency: Prior to commencing paving
note | - - - - - - - - -
note | Acceptance Criteria: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec. Cl.407.06
note | - - - - - - - - -
note | Inspection / Test Method: Correspondence of receipt of mix design
note | - - - - - - - - -
note | Record of Conformity: VR approval Completed ITP
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
signoff | HOLD POINT
checkpoint | 1.2 Ensure underlying lot conforms
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved.
note | - - - - - - - - -
note | Reference Documents: Relevant ITP for underlying lot
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of Conformity: Inspection and Test Plan
note | - - - - - - - - -
note | HP*
checkpoint | 1.3 Visual Inspection of underlying lot
note | Frequency: Prior to Commencing
note | - - - - - - - - -
note | Acceptance Criteria: If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate Contractor's work for matters including the following:
note | (i) Homogeneous surface and pavement material
note | (ii) Uniform in texture
note | (iii) Free from tearing and scabbing
note | (iv) Free from laminations
note | (v) Free from loose and foreign materials
note | and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract.
note | - - - - - - - - -
note | Reference Documents: CTW-175S Special Condition 11 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
note | - - - - - - - - -
note | Inspection / Test Method: Visual Inspection
note | - - - - - - - - -
note | Record of Conformity: Inspection and Test Plan ITP Signed
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint | 1.4 Ambient Conditions for Placing
note | Frequency: Prior to commencing paving
note | - - - - - - - - -
note | Acceptance Criteria: The majority of the surface area to be paved has a temperature greater than or equal to the following:
note | Base & Intermediate Courses: 5°C for conventional binders or
note | 10°C for PMBs & Class 600
note | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
note | - - - - - - - - -
note | Reference Documents: 407.13
note | - - - - - - - - -
note | Inspection / Test Method: Verify
note | - - - - - - - - -
note | Record of Conformity: Thermometer / gauage
note | - - - - - - - - -
note | IP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint | 1.5 Planning of Joints
note | Frequency: Prior to commencing paving
note | - - - - - - - - -
note | Acceptance Criteria: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV):
note | (i) Transverse Joints Offset from layer to layer by at least 2m
note | (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. V
note | (iii) Wearing course shall be on lane lines.
note | - - - - - - - - -
note | Reference Documents: 407.17 (b) & (c) Pavement Drawings
note | - - - - - - - - -
note | Inspection / Test Method: Measure and mark out runs by tape measure or survey
note | - - - - - - - - -
note | Record of Conformity: Paving Plan
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
textbox | Responsibility: Project Engineer/ Asphalt Supervisor Superintendent
checkpoint | 1.6 Longitudinal Joints with existing Pavement
note | Frequency: Prior to commencing paving
note | - - - - - - - - -
note | Acceptance Criteria: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer.
note | - - - - - - - - -
note | Reference Documents: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
note | - - - - - - - - -
note | Inspection / Test Method: Visual Inspection
note | - - - - - - - - -
note | Record of Conformity: ITP Signed
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
textbox | Responsibility: Project Engineer/ Asphalt Supervisor
section | 2 - Asphalt Placement
checkpoint | 2.1 Commencement of placement
note | Frequency: Prior to commencing Paving
note | - - - - - - - - -
note | Acceptance Criteria: Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement.
note | - - - - - - - - -
note | Reference Documents: 404.13 405.07 407.18 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
note | - - - - - - - - -
note | Inspection / Test Method: Visual Inspection
note | - - - - - - - - -
note | Record of Conformity: Inspection and Test Plan
note | - - - - - - - - -
note | HP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
signoff | HOLD POINT
checkpoint | 2.2 Cold Weather Placement Management Plan
note | Frequency: Prior to commencing Paving (Seasonal)
note | - - - - - - - - -
note | Acceptance Criteria: Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
note | - - - - - - - - -
note | Reference Documents: 407.17C
note | - - - - - - - - -
note | Inspection / Test Method: Document review
note | - - - - - - - - -
note | Record of Conformity: Inspection and Test Plan
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
textbox | Responsibility: Project Engineer/ Asphalt Project Manager or Engineer
checkpoint | 2.3 Mix Design Confirmation
note | Frequency: Each lot
note | - - - - - - - - -
note | Acceptance Criteria: Check correct mix design as per pavement design has been delivered prior to laying mix.
note | - - - - - - - - -
note | Reference Documents: VicRoads Spec. Cl.407.06
note | - - - - - - - - -
note | Inspection / Test Method: Visual Inspection & Delivery Docket
note | - - - - - - - - -
note | Record of Conformity: Delivery docket Completed ITP
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor
checkpoint | 2.4 Running traffic on Placed Asphalt
note | Frequency: During Construction
note | - - - - - - - - -
note | Acceptance Criteria: Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic.
note | - - - - - - - - -
note | Reference Documents: 404.14 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
note | - - - - - - - - -
note | Inspection / Test Method: Verify
note | - - - - - - - - -
note | Record of Conformity: Inspection and Test Plan ITP Signed Thermometer / gauage
note | - - - - - - - - -
note | HP*
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor
section | 3 - Testing
checkpoint | 3.1 Placing Material
note | Frequency: Per Lot
note | - - - - - - - - -
note | Acceptance Criteria: 407.21 - DGA as per 407.22 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C.
note | - - - - - - - - -
note | Reference Documents: 407.21 405.08 404.14 417.12 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
note | - - - - - - - - -
note | Inspection / Test Method: Material Sampling & testing
note | - - - - - - - - -
note | Record of Conformity: Visual Inspection/ Compaction test results Visual Inspection/ Visual Inspection/ Field Report/
note | - - - - - - - - -
note | WP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Asphalt Supervisor Superintendent
checkpoint | 3.2 Survey Level Conformance
note | Frequency: Per 4,000m2 at completion of work
note | - - - - - - - - -
note | Acceptance Criteria: 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
note
note | Scale of Surface Level Measurement -
note | Granular or CT Subbase
note | Range (mm) Max S. (mm)
note | Scale A - +4 to -8 8
note | Scale B - +6 to -12 13
note
note | Asphalt Layers
note | Range (mm) Max S. (mm)
note | Scale A - +/- 5 8
note | Scale B - +/- 8 10
note | - - - - - - - - -
note | Reference Documents: VicRoads Sec 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
note | - - - - - - - - -
note | Inspection / Test Method: Document Review/ Site Inspection
note | - - - - - - - - -
note | Record of Conformity: Survey Conformance Report
note | - - - - - - - - -
note | SCP
note | - - - - - - - - -
textbox | Responsibility: Site Engineer/ Surveyor / Survey Manager
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date:
textbox | Work Completed On
section | Lot Verification
checkpoint | Lot Verification.
dropdown | Is the relevant RFI attached to the Lot? | YES, NO, N/A
dropdown | Is the relevant NCR attached to the Lot? | YES, NO, N/A
dropdown | Are any relevant Mails/ Transmittals attached to the Lot? | YES, NO, N/A
dropdown | Lot verified By | Babak Rudd-Project Quality Manager, Nicola Lodo (Area 2 Manager), Nicolas Terpstra (Delivery Manager),Other:
textbox | Other:
dropdown | Lot Status | OUTSTANDING, CLOSED
textbox | Lot Closed On
textbox | comments