## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 5af1e5f9-7def-446c-978e-45f8274a19d3 |  | checklist | [5 empty] | Yes | SYS - B03C - Level 1 - A31 | 0210c8dc-019e-45a6-a4bd-0ebcc35d864f
checkpoint-group | 556855c9-b22c-4049-a641-f5bea874a4ce |  | section | Bathroom
checkpoint-status | 2771c8d9-5107-44af-ba2d-c8a7010deb6b |  | checkpoint | Area floor level acceptable
checkpoint-status | b296c100-06b7-4b5b-b154-0deb63e7be51 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 7e70421f-b526-4a39-9b7f-8e46c4d496ec |  | checkpoint | Self leveling coverage completed
holdpoint | 220627a8-e26e-4839-bf2d-c32a03789dfe |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 30885581-bbe5-4981-9578-f755bf9c2ec5 |  | section | Ensuite
checkpoint-status | 8d7c8b3f-b219-4c86-89ea-84706d08727f |  | checkpoint | Area floor level acceptable
checkpoint-status | 2c6555fb-9fee-4ddf-9609-e5f464d52874 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 824b3418-fbc0-47c8-a910-ce2be990b215 |  | checkpoint | Self leveling coverage completed
holdpoint | 754b4812-1a07-4b97-9542-0207c53598e2 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-sectioned | 6f83e5e0-d52e-4d30-8c69-88c2e710443e |  | checklist | [5 empty] | Yes | SYS - B03B - Level 2 | 06236531-cc4a-4cdd-b915-e48e06f13917
checkpoint-group | 1267bbf0-3ab9-437b-a188-90499e4fe41e |  | section | B21 - Bathroom
checkpoint-status | 8370cd3d-d35c-4fc8-b1ad-1632c6b398e8 |  | checkpoint | Area floor level acceptable
checkpoint-status | b62e61fc-2d5c-45ad-9e72-579b19573107 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 763f2071-2d0b-4151-85b8-b246d3d3da0f |  | checkpoint | Self leveling coverage completed
holdpoint | 4cb288c6-51be-4fd8-a540-0fdf651411d2 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 679ca55c-58f7-4148-b91f-302f6adc7963 |  | section | B22 - Bathroom
checkpoint-status | cc9380f1-13a7-461f-9765-f96c24a22ff7 |  | checkpoint | Area floor level acceptable
checkpoint-status | 316b46d2-bcb4-40d9-931f-688879d6b94c |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d212e6db-3835-4380-a125-566499ed7d62 |  | checkpoint | Self leveling coverage completed
holdpoint | bdec24d0-d6a2-4e97-ad4e-9b33ae41fbf2 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 5a91c571-5a7e-4d3f-849e-e7fc1384b060 |  | section | B23 - Bathroom
checkpoint-status | 2f008e38-3a5b-4d70-af35-968e123fa0f5 |  | checkpoint | Area floor level acceptable
checkpoint-status | f29cfed8-6634-4c41-955a-132da03ee762 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 293e69e0-c726-48ef-a743-857f26b6bad9 |  | checkpoint | Self leveling coverage completed
holdpoint | fe296e2f-a1f5-4239-9a3f-79828ac36ded |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 4c702708-f21d-45b0-93ec-1eef8f40ebc5 |  | section | B24 - Bathroom
checkpoint-status | dda3a076-fa14-48d3-b34a-cca56ce86846 |  | checkpoint | Area floor level acceptable
checkpoint-status | 5aa18dbd-4b43-4d85-859a-4b260d02ba86 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 3757d1b2-970f-4784-887a-dcfb81541bc4 |  | checkpoint | Self leveling coverage completed
holdpoint | e3f13039-7912-480d-9f58-50100189d288 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 37c07bcf-e44c-4714-9276-7924b3954626 |  | section | B25 - Bathroom
checkpoint-status | 05567f1f-1806-47e2-b23f-1404951dce63 |  | checkpoint | Area floor level acceptable
checkpoint-status | eb2152ef-ea4d-4301-882d-a3b3f2029bc5 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 087dc026-1319-4f37-ad63-33608cfb544c |  | checkpoint | Self leveling coverage completed
holdpoint | 6414160d-8f46-424f-b538-e72fdd987f6f |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | a46896bc-0b4d-400a-85de-24e76dfc41fa |  | section | B26 - Bathroom
checkpoint-status | 3ed8f63e-94c3-415a-a335-55467f22a8f7 |  | checkpoint | Area floor level acceptable
checkpoint-status | e1713276-6863-43d7-9511-d4af5a72137a |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | b943be65-e0f9-48a0-bcd0-f1d0c8415feb |  | checkpoint | Self leveling coverage completed
holdpoint | 3857702b-5503-4490-868c-066fbd6c9554 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | e7abbaa2-e39e-4ffa-b6ad-fd5ea406e859 |  | section | B27 - Bathroom
checkpoint-status | f1d0d75b-0ccb-41d5-ab76-334fd21b090e |  | checkpoint | Area floor level acceptable
checkpoint-status | 44f47d91-937e-4ff1-8dd2-d29b00488c2f |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | aaf5f581-a47c-4592-8555-16e5220aa062 |  | checkpoint | Self leveling coverage completed
holdpoint | b6531d39-c177-4010-b5b0-696bd478bada |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-flat | 0021583f-f251-4ea8-9595-e1589fafdcd9 |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 2c22e3cc-73d4-4501-bdba-a0ee57c550d4
checkpoint-status | f60657de-6aff-444a-9b54-e432d769ac2e |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint | 068f2603-4606-49f2-ab29-eac9143c1fd2 |  | signoff | Request Variation Acknowledgement
checkpoint-status | e2fc5068-cbd1-4da6-9728-b87065efc52d |  | checkpoint | Variation Completed
holdpoint | 1fb007d8-aba1-42b4-bc70-3cebd2da79ac |  | signoff | Request Variation Signoff
checklist-sectioned | f2c6059b-64cc-4323-9f38-2ebb429943cd |  | checklist | [5 empty] | Yes | SYS - B03C QA | 31e809f1-6ec8-41a1-b649-9126511e8350
checkpoint-group | 0922ed62-914a-462f-b540-7e5e0994443c |  | section | Bathroom
checkpoint-status | 7d645cf9-adcd-4f5a-bf6c-6425f9e641de |  | checkpoint | Area floor level acceptable
checkpoint-status | 200da0ef-abf8-4163-9928-49deb188bc5e |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | a586a5fa-bd2d-4d42-8ecf-36faea3c5040 |  | checkpoint | Self leveling coverage completed
holdpoint | ab8f45d2-7572-45c7-b7af-21c02fdc82c0 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-sectioned | decfdfc9-07ef-4ae2-b19f-85abe358ad2a |  | checklist | [5 empty] | Yes | SYS - B03B - Level 4 | 32186cc6-86dc-4b40-9682-1c6fbf4a765a
checkpoint-group | 879977a0-0915-4339-bf9e-fe4aaeddbbfd |  | section | D21 - Bathroom
checkpoint-status | cc89367d-29d1-46f8-ab6c-c453bcc2b1ea |  | checkpoint | Area floor level acceptable
checkpoint-status | 98f0bf16-cf41-4182-a0fa-8fe933f5faed |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 112ef10c-b9cf-499f-b837-7dc0c3df038e |  | checkpoint | Self leveling coverage completed
holdpoint | 144ae513-9633-4287-bd2d-b3ef8787b065 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 9f137931-c98a-4b6c-8173-6534ab50ea22 |  | section | D22 - Bathroom
checkpoint-status | ac223b5f-5bb8-44ff-9233-539068d3a2b9 |  | checkpoint | Area floor level acceptable
checkpoint-status | d3142bba-32e7-47a8-b2fd-0fe97b15a327 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | dbb1ccc3-61bb-4b2b-a83b-289fe6117d79 |  | checkpoint | Self leveling coverage completed
holdpoint | 6fee2aec-9489-439b-aef3-bd890fe400aa |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | d761b857-2d13-4857-9389-d7b92de73d1d |  | section | D23 - Bathroom
checkpoint-status | 6f592550-d14c-4a40-a922-4d3ae2c14ed3 |  | checkpoint | Area floor level acceptable
checkpoint-status | de81053c-835a-4dbb-9220-ffaa6c2f9aad |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 16bbba0e-7380-4195-b2dc-46f65c7d83f7 |  | checkpoint | Self leveling coverage completed
holdpoint | acc14c12-ecd2-407b-9300-0d6bfe75ed29 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 2a3e8404-c5bf-4a5d-ac21-0c5daf3eb771 |  | section | D24 - Bathroom
checkpoint-status | a9279ff8-5470-426d-ad8a-e73ce58fa7d7 |  | checkpoint | Area floor level acceptable
checkpoint-status | 7f955a96-6ad6-496b-8b76-b9c41c7acd60 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e5494b6c-69ff-4259-9339-a6ae27dde1ea |  | checkpoint | Self leveling coverage completed
holdpoint | 4f0c44b9-5024-492e-b8a8-a96c6130eced |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | b15b8fda-be97-4190-8259-3e0b05643c5f |  | section | D25 - Bathroom
checkpoint-status | ae4c8971-cd3a-4cf2-9366-f95c7577a2ad |  | checkpoint | Area floor level acceptable
checkpoint-status | b8d8e3cd-c208-4cb7-8e05-9d55dce85a93 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 96439a63-1999-44d4-9013-a1f64bc41259 |  | checkpoint | Self leveling coverage completed
holdpoint | 805f05a4-a1ab-4bff-a3ea-2e3776576897 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 3a645b35-3862-4f94-b38c-aab3c20c615b |  | section | D26 - Bathroom
checkpoint-status | fd8dc8e1-12a4-468f-8583-40c7e23eefb2 |  | checkpoint | Area floor level acceptable
checkpoint-status | 557890e7-0126-4759-b36e-0b6adf3020c4 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 85471530-db73-4db6-b276-061734e0a1ed |  | checkpoint | Self leveling coverage completed
holdpoint | 91b715ba-f7fe-437a-8eda-1127ea97990d |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 01fe52f0-bd1f-4108-b506-b1d98df3f1af |  | section | D27 - Bathroom
checkpoint-status | ec70ba5a-7125-4867-a5c6-649682d65d55 |  | checkpoint | Area floor level acceptable
checkpoint-status | 972fad7a-59db-4e32-8a6c-451301420571 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | a5b8dca9-4e2e-4347-bc95-4ab5a349ac4e |  | checkpoint | Self leveling coverage completed
holdpoint | 74bed788-4ec8-41aa-afd8-76ba923dc324 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-flat | a5d4f7e9-9868-43d7-970b-a7ac87c56d34 |  | checklist | Pre-Commencment Checks |  |  |  |  | Yes | Pre-Commencment Checks | 3876b272-a9b3-480d-9f65-c60c43b16771
checkpoint-status | c736e430-89af-4e99-b01a-723611632716 |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status | 8026b13f-04c9-4364-87dc-c2a44fb9fb20 |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status | ad5dbf73-26c8-4f04-8a06-85bbe02e97c8 |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status | 67ccbe8c-cf93-45eb-9c62-0d98360160c1 |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status | 9c599faf-77b5-4d62-9614-4a4bc3311fba |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status | ae3ee528-0ed1-4089-bc02-ef6316e75013 |  | checkpoint | Matrix/insights Setup (if required)
checklist-sectioned | 72d27965-8c47-4e1c-9828-2bfe57d6676a |  | checklist | [5 empty] | Yes | SYS - B03A - Level 4 | 3c6d00d5-f4bd-4aab-9772-0f94cf9c3c85
checkpoint-group | ee7e2684-dac1-4652-ba26-22e62a9fbee4 |  | section | D15 - Bathroom
checkpoint-status | 96d100a0-b9d7-4b48-90f8-f0f5d49cc92e |  | checkpoint | Area floor level acceptable
checkpoint-status | a1c834da-c916-41e6-96ed-86e6e6de91bb |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f6fb25e6-0fbc-41ac-b1d4-ebc73edef6f1 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 90aea190-f5a8-4c98-bb94-95563e53a7cc |  | section | D16 - Bathroom
checkpoint-status | eee22a6c-4aba-4d66-9395-5b9dcf179ae3 |  | checkpoint | Area floor level acceptable
checkpoint-status | 7a256cfb-198b-4cd0-9b5c-053cd00536db |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 171240fc-7468-4369-9a71-bc7931191762 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 62b1e60d-8f7f-4752-b8bf-3034ee1a575f |  | section | D17 - Bathroom
checkpoint-status | e6d2dcb5-7e3f-4324-92fc-538e852ff575 |  | checkpoint | Area floor level acceptable
checkpoint-status | 37945ad5-1bf8-428d-92b0-ba4a31f73349 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 86ebd77b-cb9d-4daa-96cf-9c3d92d76ef7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 0da34a37-e9e6-4a73-ae55-8db0081fdf06 |  | section | D18 - Bathroom
checkpoint-status | 5177265a-313e-45fe-a2fa-55f98e6f872b |  | checkpoint | Area floor level acceptable
checkpoint-status | a6fb95e7-4ef6-402a-a8f9-143ccce2ac72 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 8cf610e1-caf8-49fb-a416-73576a56b901 |  | checkpoint | Self leveling coverage completed
checkpoint-group | dc1ff9e5-7654-427a-8e7d-73e926988023 |  | section | D19 - Bathroom
checkpoint-status | 4a33f024-8f24-43c2-b77a-05e1d674b410 |  | checkpoint | Area floor level acceptable
checkpoint-status | 77884b6c-25bd-4a56-b8df-cc5a3c480965 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9602a7f2-7d9e-47a5-b320-aa59e365d0c7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 866b50f1-cfe4-4a08-856d-f52c3f121a00 |  | section | D19 - Ensuite
checkpoint-status | d9c02361-b3b6-4804-85d8-add7285d58b0 |  | checkpoint | Area floor level acceptable
checkpoint-status | b7638189-c2d6-4136-b5c1-bdf2d1feb31c |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d5129f0b-e7a9-43e0-b3d2-55edea0ab4bc |  | checkpoint | Self leveling coverage completed
checkpoint-group | 8297dc3b-da27-4cd2-bbdd-a16165f5d5f7 |  | section | D20 - Bathroom
checkpoint-status | c166f072-e2b5-4be5-a90f-870455fc34d4 |  | checkpoint | Area floor level acceptable
checkpoint-status | 71fed123-7c9f-40c3-a273-4aa57bdbfb32 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 6b54584b-f09c-4897-a4f8-ff4c795c715d |  | checkpoint | Self leveling coverage completed
checkpoint-group | 00caf05c-7838-4678-8e28-7866ffceadcf |  | section | D20 - Ensuite
checkpoint-status | 6eaa6357-2839-4c24-a727-c88b6ba3c3a5 |  | checkpoint | Area floor level acceptable
checkpoint-status | ebf22158-221b-445b-bdbc-27c07bad6187 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 4ef222fb-ec28-4eb3-93a2-839dac1a2eb8 |  | checkpoint | Self leveling coverage completed
checklist-sectioned | bc5a69a3-afb5-4c96-894b-1339a948ec11 |  | checklist | Toolbox Checklist |  |  |  |  | Yes | H&S - Toolbox Talks | 71e33594-b1a3-4609-99fd-21b46c506d59
checkpoint-group | c084106e-cfe4-403a-b3e3-eb17dafd3cfe |  | section | Details
checkpoint-status | 6fd54970-82c3-4822-b90d-2cbf4435e7dc |  | checkpoint | Details Complete
text | 305f2185-4e3a-4417-ae95-885bb0b1de8a |  | textbox | Office location:
text | b2fd07dc-8f92-4010-8a71-46e71c03ff63 |  | textbox | Who is running this meeting:
text | 1d3d0b15-a56a-498c-b16b-2afa5f8e2573 |  | textbox | Company
text | 88e78785-0eea-4ad8-a896-1622379eacfc |  | textbox | Agenda items:
text | ce0224f5-54b8-47a5-b890-7a5416c69623 |  | textbox | Theme of the week (topic for focus):
checkpoint-group | be5dfa51-3e29-4164-ac29-8225aa1d0584 |  | section | Health and safety issues
checkpoint-status | 269c66b8-8206-4218-99f6-3817a7573ce9 |  | checkpoint | 1.
text | 2ec0fc9e-b14f-43a5-bb60-4df5d5ab3ab4 |  | textbox | Issues raised from site safety inspection:
text | 1b5fcc97-f30c-4727-a783-29c22206fa41 |  | textbox | Actions:
text | b5107b7c-d991-4507-a1a9-6180db10057c |  | textbox | By who and when:
checkpoint-status | 18140ea3-457c-4c4f-a76d-f20980ef13be |  | checkpoint | 2.
text | 8978adff-e266-4646-b125-178fba33a0dd |  | textbox | Issues outstanding from previous briefings:
text | 507afe6b-4ee7-4485-bd4b-99698d8e8f47 |  | textbox | Actions:
text | 7d92f59d-ce24-4ec9-8428-a92c87f559e3 |  | textbox | By who and when:
checkpoint-status | 32ed9ce4-2cd2-4c93-bcb8-c0451b148191 |  | checkpoint | 3.
text | 305b3039-3f3d-45b4-8536-fb028ee2010b |  | textbox | Employee-raised issues:
text | c98f50a5-1fb4-45b7-86e0-301132ec8b7c |  | textbox | Actions:
text | c250b53e-5070-459c-b01f-af8fcce5cdb7 |  | textbox | By who and when:
checkpoint-status | 8a2d5258-52ad-4b17-9fc5-08a4442e3b61 |  | checkpoint | 4.
text | 26f6b1aa-3048-4106-a64b-dc4e2cf75ec3 |  | textbox | Positive safe-action observations:
text | dd2ab926-5b94-46f6-a93f-eed5fa00233e |  | textbox | Actions:
text | 464cc30b-c155-4299-b08c-242a1821bd72 |  | textbox | By who and when:
checkpoint-status | b193527c-3230-4f10-9459-c3b0479476c5 |  | checkpoint | 5.
text | ba0166ff-1cef-49fe-a54e-fce60528feea |  | textbox | Incidents or injuries:
text | 8f9035d5-30e5-4ea2-9ec4-4d19df05b3fd |  | textbox | Actions:
text | 1a84fee3-7466-42bd-a3ff-39c2785201a3 |  | textbox | By who and when:
checkpoint-group | 4678f374-9044-4b50-a484-2c6fc24fe914 |  | section | Job plans reviewed
checkpoint-status | 60da5f74-6b68-4b23-b1db-bf027c967bd1 |  | checkpoint | Job/Task & Action/Outcome
text | cb9c1ca7-7b79-4c62-8f74-3a1d70af5886 |  | textbox | 1.
text | d396585a-1ce3-4d1e-b838-375ab4165dd0 |  | textbox | 2.
text | 4657beed-8141-41c2-926d-0d7204a497a2 |  | textbox | 3.
text | 1e162112-08ad-40c3-9d33-6c4bac52a906 |  | textbox | 4.
text | fd629f21-4050-47b3-b236-26daf8c94903 |  | textbox | 5.
text | a08ea05c-aa58-425b-9cb6-e2fa8951a414 |  | textbox | 6.
checkpoint-group | 087fea28-505b-4b1e-b841-9bd13c267a59 |  | section | Operational issues
checkpoint-status | 863ea76a-7662-41eb-a86e-7a122a2d6fb7 |  | checkpoint | Issue & Action
text | 301f9ad4-6682-45c0-aa57-7b074b0e8a13 |  | textbox | 1.
text | 1373bee6-816f-408a-97a0-72f99b461b6e |  | textbox | 2.
text | c487e999-fa82-493c-b540-e056d94778fb |  | textbox | 3.
text | 5341a99d-52f8-4c86-8e11-6e8adfb0627e |  | textbox | 4.
text | 8e55092c-df52-43d0-b019-a8e67550ae09 |  | textbox | 5.
text | b87136a8-71c4-41f7-9cdb-74d4b55b5521 |  | textbox | 6.
checkpoint-group | 8a1d6702-38ce-451c-bf29-7113fda577a8 |  | section | Other business
checkpoint-status | 44e1afea-3a2c-42e8-a42c-203f9f3f9288 |  | checkpoint | Item & Action
text | 2e63def1-4462-4998-b972-d5125960181e |  | textbox | 1.
text | 044404a1-6065-4d33-8f96-7da9ab2eaf3a |  | textbox | 2.
text | 1e321545-4537-44dd-9443-3ae2c58d572b |  | textbox | 3.
text | e3214f18-5e4b-42bf-856b-435adffda167 |  | textbox | 4.
checkpoint-group | 6e1071d7-6591-4b6a-81e8-75c8979a1ee4 |  | section | Attendees
checkpoint-status | d41e9f41-1f7b-4542-8eb9-4f49d7effa80 |  | checkpoint | Add name and Photo of attendees
checkpoint-group | 7eb51f91-7b7a-4d0b-9b02-b56bacfc1cb7 |  | section | Review by management
checkpoint-status | 67c826b9-0b16-4ba2-9175-8d5081b78908 |  | checkpoint | Reviewed and signed off
text | 054479d9-523d-4c50-88ce-626d6600059d |  | textbox | 1.
text | e1ea14ce-04e9-4c55-b0e6-131f75ee169d |  | textbox | 2.
checklist-sectioned | fc7f1232-8083-4e25-b921-f4b2db7fa6b0 |  | checklist | [5 empty] | Yes | SYS - B03B - Level 1 | 79be43c4-3e81-4c85-b2d9-2555e8359a53
checkpoint-group | 51058b9f-49e3-46ae-a1af-85977c39fd49 |  | section | A21 - Bathroom
checkpoint-status | f4670aac-fb42-4dc3-bdaf-2988e15e926e |  | checkpoint | Area floor level acceptable
checkpoint-status | 9e6586fd-ebf5-40d1-a99a-c4f9f638d4bb |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | b95e90fa-be8d-46ed-a858-f387cf144b9c |  | checkpoint | Self leveling coverage completed
holdpoint | 3ac765fa-f784-4f0c-b8d7-04977216f1dd |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 710e2056-2802-4f78-8c4c-e841bc24b243 |  | section | A22 - Bathroom
checkpoint-status | 54259cd9-417e-4529-be9a-0d4856f11a0a |  | checkpoint | Area floor level acceptable
checkpoint-status | 6e57ad66-e65e-436b-8e4f-deb611ac953b |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 31598748-ffd3-4b70-b24e-1752a512042c |  | checkpoint | Self leveling coverage completed
holdpoint | c5085732-78b2-455f-bd71-bc48e0eeb28f |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 1912a21b-d37c-4337-9d32-6d0d9d22df26 |  | section | A23 - Bathroom
checkpoint-status | 1d3036df-0b76-4a34-bbc8-987d2ff365df |  | checkpoint | Area floor level acceptable
checkpoint-status | 810bd02b-49ec-4b9d-85ea-9c3ab2bedd88 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e2d9c597-8792-4b43-980d-c58500b6d427 |  | checkpoint | Self leveling coverage completed
holdpoint | 3b0c46a5-bc89-41f7-8b76-7154d5ef4afc |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 8f4b4c6d-d3d7-4241-bad2-a3aea2082ed7 |  | section | A24 - Bathroom
checkpoint-status | 6a34a40e-e154-4e67-a037-bf6e2d93ac68 |  | checkpoint | Area floor level acceptable
checkpoint-status | db909517-0f55-40f6-bc8d-9c5f6b9e807c |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 659de1d5-6b2b-4d69-843e-d59d9f2c89f8 |  | checkpoint | Self leveling coverage completed
holdpoint | d5acb12c-cd3d-4257-a684-b13650fdc957 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-flat | b530f661-7e4a-44e2-b5a0-e023dfe3ed19 |  | checklist | Underfloor Heating checklist |  |  |  |  | Yes | Underfloor Heating checklist | 7acafa01-ca7f-4ea3-b157-fbd490dbe9dc
checkpoint-status | 01df7ced-0771-42ce-838a-a58e7b4ebdd6 |  | checkpoint | Area floor level acceptable
checkpoint-status | 3d99b422-b34e-41ab-8dd9-e4b44964b503 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 56e97243-c2f9-401b-9b2c-ce1e6fad0dd1 |  | checkpoint | Self leveling coverage completed
holdpoint | 42c566fd-30ae-4b20-a449-ff36d7441c6e |  | signoff | Raise Remedial/ Main Contractor Signoff
checklist-sectioned | 6b087787-2cb9-4902-b88d-8e3d3309b80a |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | H&S - Accident/Incident Report | 85e6c5f6-b98b-447c-8f26-2b3c8c77be18
checkpoint-group | 01a49aaa-bf3f-4ade-b665-7df18a7d64fc |  | section | Details
checkpoint-status | a955c209-3aa6-4a39-bfb9-6322e222dd2e |  | checkpoint | Details Completed
text | e9de5bfb-8771-4638-b38c-6460b4a51ce3 |  | textbox | Name of Investigator:
checkpoint-group | f3b4909d-c7a6-419c-83a3-2712d7166aae |  | section | Particulars of Incident
checkpoint-status | 96bdab3c-d444-428f-b7b7-ca6abbdf74e1 |  | checkpoint | Particulars of Incident Details Completed
select | 6b525f4e-f45b-4da7-8df5-23fe6bff84be |  | dropdown | Day of Incident: | Friday,Monday,Saturday,Sunday,Thursday,Tuesday,Wednesday
text | 7e5d562b-6c37-42a1-8dac-2df84d546b73 |  | textbox | Time:
text | 77139ee8-1724-49ec-b32f-6297f71fb24d |  | textbox | Project/Site:
text | a3d0113e-1792-4d2a-81a4-c196efecce04 |  | textbox | Date Reported:
checkpoint-group | f0439b2b-738e-4a4b-a2b3-d25289852fd4 |  | section | Injured Person Details
checkpoint-status | 998e2e26-891d-4c13-9695-96002b0b40c9 |  | checkpoint | Injured Person Details Completed
text | bcbcce61-cfa2-48bc-982c-c5b5e71a5820 |  | textbox | Name:
text | 557319b1-18ca-4e15-8145-bf19756ed742 |  | textbox | Age:
text | 17d87fda-3003-4f2f-800d-c104d51100a6 |  | textbox | Phone Number:
text | b250bb03-568c-46a4-930f-063d05523218 |  | textbox | Address:
text | 183cd7d2-02cd-4259-8bcf-687060e2ae22 |  | textbox | Reported date of incident:
text | cb2b501a-8ccb-408b-9bb5-195476e5b88e |  | textbox | Length of employment:
text | 9df08fae-8517-426e-a3fc-1ebb04a7daf1 |  | textbox | Time on job:
checkpoint-status | fb971ff8-2c64-4748-9088-ebfa7b30944f |  | checkpoint | Type Of Injury:
boolean | 7ade6143-a0ba-43c7-94c8-17ffd8a461cb |  | tickbox | Strain/sprain
boolean | 5738b1fe-e0ff-4949-ba49-7c573b173ca4 |  | tickbox | Fracture
boolean | 6b4511fb-6c5c-4a9b-b2a1-9c48b3371cfa |  | tickbox | Laceration/cut
boolean | 24005c68-47eb-4552-ba5b-1dc0d9723144 |  | tickbox | Bruising
boolean | 769c2254-a4b9-40f7-8c98-a1b987acd4f0 |  | tickbox | Scratch/abrasion
boolean | 8e754d90-98ee-4346-8ef7-4e37d0cd0355 |  | tickbox | Amputation
boolean | 0f62ffbd-d654-4a44-b6ca-c8c5fd6bcf05 |  | tickbox | Burn scald
boolean | c8c5f313-eb09-4171-b9df-32520fffab31 |  | tickbox | Dislocation
boolean | 7e48ef93-56fc-4c31-8441-2b6734f61a1c |  | tickbox | Internal
boolean | 74f4e66e-8287-4131-ab3d-ea35d3e9e914 |  | tickbox | Foreign body
boolean | c0050bb4-329d-4731-b3b6-b00f4fe27d01 |  | tickbox | Chemical reaction
boolean | 4e1cd37b-f7a7-49d4-b988-e1a523b2d87e |  | tickbox | Other
text | 7e4b43c5-0b61-4b6b-ba7e-ec7748fc5de3 |  | textbox | If other please specify:
text | 18e138ea-f591-4403-a2ad-9bddb2e1f2f8 |  | textbox | Injured Part of Body:
checkpoint-group | b3e7e1da-7545-40a9-bf69-4b857408de85 |  | section | Damaged Property
checkpoint-status | b3280628-3d85-4030-9ee5-9f4767640f18 |  | checkpoint | Damaged Property Details Completed
text | b40e64d9-5932-48a4-9420-88c8273d482f |  | textbox | Property/material damaged:
text | 7aa7cc35-9187-4c4d-96be-4b44ec4ab825 |  | textbox | Nature of damage:
text | 6eb6370f-545a-42cd-8129-fe259589d2bf |  | textbox | Object/substance inflicting damage:
checkpoint-group | 13ece58a-53da-4636-9106-ccfd1c85f4a5 |  | section | Incident
checkpoint-status | abae2707-aa55-4950-bd51-f59a68f3e32a |  | checkpoint | Incident Details Complete
text | 4cd700c0-230d-460a-83f9-fd60b8704fb7 |  | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
checkpoint-group | 73331339-686f-4ccf-bd31-52e0dca53952 |  | section | Analysis
checkpoint-status | e79abbd3-ac4f-4d5b-add6-dccacf7eaf21 |  | checkpoint | Analysis Details Completed
text | 04e074f8-e295-4677-856b-5c28255dd0ae |  | textbox | What were the causes (root and contributing causes) of the incident?
text | 1daea218-712c-4f70-9767-9a8134812e18 |  | textbox | Root causes – safety system failures:
text | c6818664-ec27-40a9-a8a7-26f7ef16536b |  | textbox | Contributing causes – unsafe acts and conditions:
checkpoint-group | 5fa59364-8487-4b98-a625-d1e34d59e2d7 |  | section | Prevention
checkpoint-status | 0724d24f-a214-47eb-b064-ca060d7fa8a2 |  | checkpoint | Prevention Details Completed
text | 68d803a6-e0f5-415b-a68d-026a47c8da2f |  | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
boolean | bc67a7a4-86be-476f-be81-80038ecf4d50 |  | tickbox | Completed
text | bfa9b6c8-e5a0-4595-b25a-fe1bafc23161 |  | textbox | By Whom:
text | e03e6bef-8361-4a24-8eef-856453f85d7a |  | textbox | When:
checkpoint-group | e926c609-59ad-4cab-a144-0490bba2099b |  | section | Treatment and Investigation of Incident
checkpoint-status | 07f9629d-40b1-4162-a9d6-ba1865654f6b |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | 659ceae3-0e40-4182-9989-845fda6a338f |  | textbox | Treatment and Investigation of Incident :
text | 0a690191-d11c-4abd-975b-a7dccd78628d |  | textbox | Name of person giving First Aid:
text | 26885b6b-063a-4c38-a2cc-5794f0204418 |  | textbox | Doctor/Hospital:
text | 1c479a88-1f1b-42c5-b9e7-6ce977689cb3 |  | textbox | Incident investigated by:
text | c19b857e-6fb6-4c5d-bb32-996e3a28f9fb |  | textbox | Date:
select | fc88a287-6242-4d70-8e73-0d2270065565 |  | dropdown | Worksafe NZ advised | No,Yes
text | 913c4a48-55ec-4ab0-aa2e-c6e004b75fe5 |  | textbox | Date:
checklist-flat | 8800eb39-76a2-41e6-b7e8-3c0443d89013 |  | checklist | Completion documents |  |  |  |  | Yes | Completion documents | 8c8ff329-9b56-42a4-ad55-9f4b48b8ffde
checkpoint-status | a0ad8227-4168-41d5-a624-8fa3245f3efa |  | checkpoint | PS3, warranties, etc
checklist-sectioned | f3a16906-4be5-4415-9e0c-f59129180529 |  | checklist | [5 empty] | Yes | SYS - B03A - Level 2 | 8d5ccb1c-231b-4b90-ae60-b51fa537bc88
checkpoint-group | 2b5de916-6d18-47dc-be77-6117ad91987f |  | section | B15 - Bathroom
checkpoint-status | dcf2aaf8-1578-4571-8b53-0da1fb463d75 |  | checkpoint | Area floor level acceptable
checkpoint-status | 00cecdfb-ab70-4766-999d-cb19f45ee51f |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d26e3f02-622b-48ac-b01f-c8826810f8d1 |  | checkpoint | Self leveling coverage completed
checkpoint-group | a30bfb9b-47fe-4e75-8a79-355ddc6d33f7 |  | section | B16 - Bathroom
checkpoint-status | cdc6c211-3f86-46b5-aa53-13bf6fc79545 |  | checkpoint | Area floor level acceptable
checkpoint-status | fc019536-2baf-4759-bd1c-36ca9770ce24 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 3545f9eb-378c-4083-ac14-31705ec8eeed |  | checkpoint | Self leveling coverage completed
checkpoint-group | b0df0bf2-ac2d-450a-88db-f1e99f38de5a |  | section | B17 - Bathroom
checkpoint-status | c7a7daab-747c-4bbb-95b5-3c41c342643e |  | checkpoint | Area floor level acceptable
checkpoint-status | 18d89523-41e8-47c8-a608-b3df12a8b439 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 2785fca8-fa72-4eb7-b667-fa9698b4cb60 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 2b7fd211-1a2d-4d48-b6c5-2a52789ebec4 |  | section | B18 - Bathroom
checkpoint-status | 6b9f2001-f1a0-4387-9f24-4ddc7c5a903c |  | checkpoint | Area floor level acceptable
checkpoint-status | 05add54e-846b-4cb6-b4db-22bf85496650 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f994e578-6173-47b0-912d-517a79b43670 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 77bca8a7-9c9c-4459-a66b-aac7f8d20403 |  | section | B19 - Bathroom
checkpoint-status | a885dcf1-a6a9-45da-a93c-6df65a2e6f39 |  | checkpoint | Area floor level acceptable
checkpoint-status | f97d4db1-7499-4f35-9cf6-9181bc6b9a0a |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | af088645-3abb-4c45-8fce-89b4a24259b0 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 3f580772-579b-45c6-874d-e2d5811d9aff |  | section | B19 - Ensuite
checkpoint-status | 81c28431-db30-4c1d-aa09-637256d5cd5f |  | checkpoint | Area floor level acceptable
checkpoint-status | 112078fc-b1fb-4665-8a1c-4e5c29dadd57 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 0046bcd7-995e-4af0-b4d7-aef9d4a81190 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 8d32431f-1a0a-473d-862f-05f0fc0ba08f |  | section | B20 - Bathroom
checkpoint-status | 3d6a3878-96b5-4681-8bb0-b581d2b62c53 |  | checkpoint | Area floor level acceptable
checkpoint-status | 72f6da62-5d47-4288-ab5d-93126679f015 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d1a11684-44a2-4061-9dcd-3f348fa75b99 |  | checkpoint | Self leveling coverage completed
checkpoint-group | f0bd94ef-a2e6-419f-9840-0da6b5f0ac84 |  | section | B20 - Ensuite
checkpoint-status | 1a87c2b9-9b07-4396-ba95-e94040d3496f |  | checkpoint | Area floor level acceptable
checkpoint-status | dd6226d9-6d7b-4f1e-9b67-2f58ebe8ec49 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 50048ef5-f0e7-4dc3-bee1-0fdbf75a7afc |  | checkpoint | Self leveling coverage completed
checklist-sectioned | 7b3cb71d-1a7a-4a10-a154-a3dc5c6fb23a |  | checklist | Site Inspection Checklist |  |  |  |  | Yes | H&S - Site Safety Inspection | 978d0f10-8387-429c-adc1-05f139ee3363
checkpoint-group | 0d1b76e5-856e-495a-a2e2-cca9e01050a6 |  | section | Details
checkpoint-status | b81a5f4a-d988-4902-8325-d458bafc8495 |  | checkpoint | Details Complete
text | 8b03cbae-c408-4ae9-a756-cca7018dea83 |  | textbox | Site/Location :
text | 52914ecc-91b7-4603-9495-6a1e5ad3bd75 |  | textbox | Date
text | 8ff362f0-afb9-45ca-87d4-347265a7e11e |  | textbox | Name of Inspector :
checkpoint-group | 0b1a66f1-8832-4d28-a48e-66e86e712ad4 |  | section | Site Control
checkpoint-status | ea28ca40-a95b-4914-964b-c8d32703f825 |  | checkpoint | Hazard Board and signage up-to-date
checkpoint-status | 5b4019af-6bfe-4667-a093-1a4ad6a47e1e |  | checkpoint | Environmental plan - issues
text | cae0f94e-0878-4302-855f-50626b9940cc |  | textbox | Toolbox talk last date:
checkpoint-status | 3d65fbb0-64ac-4785-a47b-5a73f57b821c |  | checkpoint | Safety inductions for all on-site
checkpoint-status | 8b75882b-91bc-47b0-9bc1-c90439a548eb |  | checkpoint | Safety notice board current
checkpoint-group | 254c84f9-0f95-40c0-850e-c4e354ff26e1 |  | section | Site Facilities
checkpoint-status | 14ad305c-6e07-4678-9a10-df9d302f165f |  | checkpoint | Offices clean, adequate & good lighting
checkpoint-status | 30bbb2c1-cfc2-4166-8385-8517aed409af |  | checkpoint | Smoko sheds - clean, portable water
checkpoint-status | b36370b9-59ee-478e-ad46-207717c3dbfa |  | checkpoint | Toilets - clean, washing water
checkpoint-status | 833a7f7c-6906-4d70-ab71-d61c855bf11c |  | checkpoint | Tool /equipment sheds adequate
checkpoint-group | 3526bdaf-bc95-4c5a-ab8a-ddba4a8cccdb |  | section | General Site Tidiness and Access ways
checkpoint-status | dce18d11-a8e2-4535-b69d-a5d2fa7ad119 |  | checkpoint | Clear, safe access to work areas
checkpoint-status | 81cb89bf-62bb-4af5-9cb7-1fc76a8b2cdc |  | checkpoint | Stairways and accessways clear
checkpoint-status | 9ba9c53d-1d1c-402b-9175-860d4fee8f4d |  | checkpoint | Hoardings /fence and gates secure
checkpoint-status | ba448df5-2ab1-4c47-906c-286815038732 |  | checkpoint | Loose materials secure from wind
checkpoint-group | 5780155c-e8df-4c50-87e5-e64c417d8080 |  | section | Personal Safety Equipment
checkpoint-status | 0a46a8ea-ae6c-4a0e-97fd-a617c15cc574 |  | checkpoint | Signage displayed and legible
checkpoint-status | f011dc00-a5c4-4a85-958b-1520ac776a7f |  | checkpoint | Hardhats being worn
checkpoint-status | d8465daf-e7e7-451c-8c84-2f75d176bd3e |  | checkpoint | Correct footwear being worn
checkpoint-status | ded79f3f-b8a4-47c6-82b4-dcdfaa5824a4 |  | checkpoint | Glasses /ear muffs /vests /masks used
checkpoint-group | 3134994d-1b26-422e-bac7-e7adb824dd3b |  | section | First Aid/Fire Prevention
checkpoint-status | 2c31cb4a-dc31-4994-92b6-6956a290c6b8 |  | checkpoint | First Aid Box Available
checkpoint-status | eee92b50-2db4-4f4d-b353-4113b5d26b7c |  | checkpoint | Accident register
checkpoint-status | 1f705336-700a-435c-aef8-77b4ffceeab1 |  | checkpoint | Fire Extinguishers
boolean | 12bab111-d5d2-4ba9-87f2-979c842a9df6 |  | tickbox | Available
boolean | 61ea2b23-6ac8-44f8-9d40-86c8daf1dd62 |  | tickbox | Current (12mth)
boolean | 3f3e012d-918a-4137-9689-dcced1049dcc |  | tickbox | Sufficient number
checkpoint-status | 6cce479e-20da-4899-8c6d-d185ed2c9581 |  | checkpoint | Evacuation
boolean | 7aa1d51b-82ee-46ea-a2d8-8922b951f5d1 |  | tickbox | Procedure current
boolean | 62e3bbb3-5108-4954-b02d-7071877274bd |  | tickbox | All emergencies incl
checkpoint-group | 3389d3b7-3229-44b8-a8a5-214f20379d09 |  | section | Cranes/hoist/lifting equipment
checkpoint-status | c08b2db8-bfeb-48d4-8583-134aa9096700 |  | checkpoint | Proper lift assessment plan done
checkpoint-status | 956afe21-b74d-42ad-8f8f-68722ca5b684 |  | checkpoint | Crane certification current
checkpoint-status | b6fa1bf6-cec1-462d-8549-d476b69bd417 |  | checkpoint | Slings/chains certified
checkpoint-status | 21eafa7a-0609-47b0-ac01-569dee584ed1 |  | checkpoint | Operator procedures in place
checkpoint-status | be4b0438-7033-48df-945c-bffcde362c4f |  | checkpoint | Inspections being done
checkpoint-status | 6fabd460-85c5-46f7-a418-3aee3fe22646 |  | checkpoint | Man cage available
checkpoint-status | 150a1e2b-0038-4432-9007-23e3718242c6 |  | checkpoint | Emergency plan in place
checkpoint-group | a1a6c591-99ff-4685-a6ba-12732332a779 |  | section | Compressed air equipment
checkpoint-status | 0508889e-1f07-4073-888a-4924da1f1721 |  | checkpoint | In good condition
checkpoint-status | a675ab17-9a30-4e06-8a03-1b3ec49a4a8d |  | checkpoint | Appropriate guards fitted
checkpoint-status | 56fb6645-5e47-4a70-b64a-d67a2c73d992 |  | checkpoint | Trained user
checkpoint-group | 0eb85350-18b9-42a2-ad86-f1dc75a29559 |  | section | Excavations
checkpoint-status | 58567862-4102-4b59-835e-7627ea9f8416 |  | checkpoint | Correctly Shored
checkpoint-group | f6b48a50-fcb8-41c8-853c-28d96d23f5eb |  | section | Welding/gas cutting
checkpoint-status | 6f4f4364-c1cf-4e29-9a6c-fdc6985b4668 |  | checkpoint | Hot work permits being issued
checkpoint-status | fa12b29b-1142-46a9-adf6-ef3e5ca96354 |  | checkpoint | Fire extinguishers on hand
checkpoint-status | a303430a-1b7f-4b85-b252-4c152f5cef5c |  | checkpoint | Operators using PPE
checkpoint-group | 8f6292a3-5b93-423a-acca-8d263d9c0672 |  | section | Electrical Equipment
checkpoint-status | 594e0fcc-2574-4081-bf83-74a4a57d4f68 |  | checkpoint | Main board lockable /weatherproof
checkpoint-status | f25adcfb-c122-440e-b3f6-5c776317ef80 |  | checkpoint | Current tagged and damage-free leads
checkpoint-status | d647d7f6-f1e9-4ae0-8015-92a375d17552 |  | checkpoint | Current tagged plant
checkpoint-status | 411358e8-8c6f-405f-bb09-ff3b579166d0 |  | checkpoint | Current tagged lifeguards
checkpoint-status | f1909a87-a308-4562-a2c9-8af8cc2e2535 |  | checkpoint | Leads safely placed
checkpoint-status | a56c0a79-a728-4bae-87b1-e9841c5853bf |  | checkpoint | Equipment in good condition
checkpoint-status | 91727049-2ae2-47e5-959a-3eb3c1804e0b |  | checkpoint | Appropriate guards on equipment
checkpoint-status | d5600c35-36b3-4b50-bd4f-a407134ed634 |  | checkpoint | Adequate temporary lighting
checkpoint-group | d2286511-94fb-4fdd-a37a-64d39090f4ba |  | section | Chemicals
checkpoint-status | c54aeb9b-8f99-40c3-8f57-b76212a5f4eb |  | checkpoint | Correctly stored
checkpoint-status | 2c612a53-a5d6-49e5-908d-89157c712d36 |  | checkpoint | Safety Data Sheet (SDS) available
checkpoint-status | c6bea90d-742c-472a-be4a-2d0e8b7a549b |  | checkpoint | Operators using PPE
checkpoint-group | 9ebd67f1-216f-4e6d-8f69-f9cfdbe2c51b |  | section | Tools
checkpoint-status | 9fdb5414-d52c-4307-9cde-1a3ae81068a4 |  | checkpoint | PAT tool WoF current and secure
checkpoint-status | b3d4fb1c-d6fe-4a95-804e-de372c0740be |  | checkpoint | Staff trained in tool use (SWPS)
checkpoint-status | a0812915-99d1-4c25-a0de-9f2ffd2ed947 |  | checkpoint | PAT signage on site
checkpoint-group | 41f4a38f-70bf-4b38-b009-817a40714e4b |  | section | Scaffolding
checkpoint-status | 14299200-5f5d-4674-b5bd-674acfa93954 |  | checkpoint | Notifiable weekly Scaftag/current
checkpoint-status | b36914ee-612b-4b0c-8517-bcb72a71930e |  | checkpoint | Handrails/mid-rails
checkpoint-status | 21af119e-d3cf-4877-a4fe-9d95fadfc529 |  | checkpoint | Toe boards
checkpoint-status | 387d5078-6115-426f-a57f-841f4d330c91 |  | checkpoint | Platforms
checkpoint-status | b0c24bb8-cf9c-4189-9bf7-0e47729a5ada |  | checkpoint | Ladders/stairs
checkpoint-status | 4e89dfdd-69fa-46f9-ab99-3fc290ee0988 |  | checkpoint | Base sound
checkpoint-status | 9058fe16-1790-4241-b669-a85ea72a8826 |  | checkpoint | Work platforms clear
checkpoint-status | 23465bca-2fee-4925-81c2-c6f96a8ab752 |  | checkpoint | Platforms trip free
checkpoint-status | 7ef82922-bc00-4d86-b719-fd895a9e5381 |  | checkpoint | Planks tied down
checkpoint-status | 69a37249-c08e-42fa-85fa-58068a7c77e4 |  | checkpoint | Headroom clear
checkpoint-status | a9f54db9-97f6-416d-aaba-ca7d647ac194 |  | checkpoint | Ties/bracing adequate
checkpoint-group | 7755514b-0777-4242-a924-80169d856232 |  | section | Ladders
checkpoint-status | b2587404-e045-4de2-a262-8720fa22ad40 |  | checkpoint | Good condition
checkpoint-status | 2bc07c3e-c75d-41ef-b677-3f00628e5c11 |  | checkpoint | Secured top and bottom
checkpoint-status | d3d11100-53ec-4b70-a91f-aa0b7d645514 |  | checkpoint | Stays to step ladders
checkpoint-status | b3191a73-1c77-4a86-b4ac-609ccdb84ed4 |  | checkpoint | Working 2 steps down
checkpoint-group | a59b26e3-07e5-45ba-935c-a35a7c4e5ac8 |  | section | Fall Hazards
checkpoint-status | 1b3d5cfc-b4bf-48c1-b59b-9453b894912a |  | checkpoint | Fall Hazards
checkpoint-status | 607260a0-8f6e-4a2f-88b1-1be82ef5d822 |  | checkpoint | Floor openings
checkpoint-status | 08f1e6ee-a983-4c53-9f3c-5607a84d0535 |  | checkpoint | Lift shafts
checkpoint-status | ade1f3b5-d82b-47cf-9d94-d01faad6adb9 |  | checkpoint | Stairs
checklist-sectioned | c4c6684f-b80f-475b-a1c7-1fc265351af2 |  | checklist | Install QA |  |  |  |  | Yes | Install QA | a04075cf-4dcd-43d0-a4ee-c363c0da4022
checkpoint-group | 2a4bc8c3-090c-4551-ba2b-d209275fdd6a |  | section | Screeding QA
checkpoint-status | a1b3f61e-0480-44db-b392-910fb92ed501 |  | checkpoint | General observations
checkpoint-status | a3130fde-2871-4771-99bb-0fdba8205365 |  | checkpoint | Screeding completed and falls as per spec
checkpoint-status | 1442b75a-9c98-40e0-a00f-6fe5d29e7408 |  | checkpoint | Concrete sitting flush or lower than lining
checkpoint-group | dc330703-c8d1-4b85-8403-0118bec8c78c |  | section | Underfloor Heating Install
checkpoint-status | ea1487a7-cf6e-4fec-96c9-3cfb1bc35a4a |  | checkpoint | Clean and sweep floor
checkpoint-status | 636954cb-a884-4498-8e1d-19d8eadd76e1 |  | checkpoint | Correct products used - as per specification
checkpoint-status | 65da4fe0-075f-4ce6-aa3f-a78b517359cd |  | checkpoint | Element is tapped with Warmup fixing tape
checkpoint-status | c292a79e-c05e-4519-a84f-c76438535a97 |  | checkpoint | Ensure element has been tested completed
checkpoint-group | 486300f5-addd-4a6f-a478-fee0b80c5abc |  | section | Handover
checkpoint-status | 741c5197-82c4-4c82-b099-f58be3fab7e7 |  | checkpoint | Works completed 100% as per spec and area left tidy
holdpoint | 3c009a0a-34a1-4b79-a0a0-b4a4771556a8 |  | signoff | Raise Remedial/ Request signoff
checklist-sectioned | e2dbbda2-e3b5-4f58-a154-ee9b63875fa8 |  | checklist | [5 empty] | Yes | SYS - B03A - Level 3 | a28385c0-419f-45b8-a03f-04ca55898a53
checkpoint-group | 21d72068-8abf-4cb2-9b5e-5482b595fae9 |  | section | C16 - Bathroom
checkpoint-status | 5b467608-6e4c-4414-ae65-b95e0b9ba3a8 |  | checkpoint | Area floor level acceptable
checkpoint-status | ba7efb26-32fb-49d5-9f81-88d21ac01da4 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 459953a4-3f35-486e-bebc-e2a0f072abb2 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 174c5694-2cbd-45bf-9002-5cac6ca26543 |  | section | C17 - Bathroom
checkpoint-status | c3b2c369-ad76-4f84-96e8-7f1ee2f9b000 |  | checkpoint | Area floor level acceptable
checkpoint-status | 8fd4561c-a36f-45f6-a780-9e16efddebf8 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 5d43d47a-f938-4372-908a-602ae41f2ae8 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 417aa4f0-264a-440e-8069-21f693f9e3f4 |  | section | C18 - Bathroom
checkpoint-status | 1dd18717-8b64-4f2d-a9f5-55452a850bda |  | checkpoint | Area floor level acceptable
checkpoint-status | d5f81909-fe99-4654-a9e7-5b3162fec9b0 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 156e7aee-1f5f-48b1-9aaf-5b65989ba546 |  | checkpoint | Self leveling coverage completed
checkpoint-group | ab68f140-c44d-4d0b-aeff-d39c91118fc0 |  | section | C19 - Bathroom
checkpoint-status | 8c5c2590-70c3-4f1e-9d19-3517f00e4235 |  | checkpoint | Area floor level acceptable
checkpoint-status | 44ac6f8c-5153-45eb-94e8-043781a57c0b |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 932c1c2f-c633-4c26-be95-bdd2c19b05a5 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 8731fc4a-e573-4fb3-a1cc-ad54e7c21247 |  | section | C19 - Ensuite
checkpoint-status | 01a414bd-49e4-4c66-a5fe-c4bbea1fdb93 |  | checkpoint | Area floor level acceptable
checkpoint-status | bd1d0aba-3d31-4a5d-88b9-b898fc7395ed |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 99292be0-6aa0-42ed-a52e-138af227957c |  | checkpoint | Self leveling coverage completed
checkpoint-group | 23c15dcc-653b-494a-a1a0-2da0011c24fa |  | section | C20 - Bathroom
checkpoint-status | 215a2253-2269-40b5-8ab3-a3cf8f8fe370 |  | checkpoint | Area floor level acceptable
checkpoint-status | d04dc2cc-1a97-46ce-8624-80f173e1b80a |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 32693735-e8da-4f48-8c9d-8ebd8b796ac6 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 6cbf9bd8-3193-485c-84f5-b90cd0b7f59e |  | section | C20 - Ensuite
checkpoint-status | e80b3db0-b3ff-4dee-bad0-1d489a4c2f2d |  | checkpoint | Area floor level acceptable
checkpoint-status | 07e98dba-17e7-4e82-a832-d4522692f5ea |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9d561967-fa5b-4272-be4d-27634ae23a1e |  | checkpoint | Self leveling coverage completed
checklist-flat | f12bb4fa-0d7c-4baf-9c99-9219da8552c9 |  | checklist | [5 empty] | Yes | SYS - Handover | aa974954-bc1e-453b-8fbe-0dc517b448b9
checkpoint-status | b11453f6-f6b0-494d-88ed-2685820148db |  | checkpoint | PS3s, warranties, user manuals and any other documents attached
checklist-sectioned | da848459-f060-41aa-9050-6e8d69528511 |  | checklist | [5 empty] | Yes | SYS - B03A - Level 5 | c05a2949-62b6-40ff-8a53-f015da9d735f
checkpoint-group | 54c03b24-1fa3-4235-9caa-11add8ec6179 |  | section | E15 - Bathroom
checkpoint-status | 5d9020be-89d2-4238-a769-05b2155daca5 |  | checkpoint | Area floor level acceptable
checkpoint-status | e9a0e023-bb9e-4275-b4f7-f4ee1b3368b8 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 7f901fc5-8a20-4a65-9d2f-7bf8af512f1a |  | checkpoint | Self leveling coverage completed
checkpoint-group | 7ca085b4-8098-4dc3-bda8-979f44118aee |  | section | E15 - Ensuite
checkpoint-status | 671a5478-7fd5-4dbe-b9fe-aab6967fcf56 |  | checkpoint | Area floor level acceptable
checkpoint-status | ca196b3b-f373-406f-8d62-51cb512c7811 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 5ff27228-ff3c-47c5-8571-b8354af8c5e4 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 0b7ccaa6-495d-4005-927c-c98a813abfef |  | section | E16 - Bathroom
checkpoint-status | 114f4209-b0ef-421d-9de9-483f27b78f3e |  | checkpoint | Area floor level acceptable
checkpoint-status | 22edad15-48b3-4abf-a645-a03f83766ef8 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 6042a02e-d4ad-413f-8a77-951624f3981d |  | checkpoint | Self leveling coverage completed
checkpoint-group | 137b718a-52b8-49c1-b393-fb8825d18dd2 |  | section | E16 - Ensuite
checkpoint-status | e9cf9434-89ff-4aff-a9c8-c8a6808074e2 |  | checkpoint | Area floor level acceptable
checkpoint-status | a767d11f-da2f-40a2-8e39-21d0f85c5300 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f6b31f89-818f-406b-9282-492d41b48935 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 537404a3-5ed8-4062-a7c4-2ba1285272bc |  | section | E17 - Bathroom
checkpoint-status | 231d2bdd-41cb-4211-b252-814db62b1db0 |  | checkpoint | Area floor level acceptable
checkpoint-status | 93b8b38f-4530-4f41-b7ad-4c2d3408c4da |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 8c854c39-5e0d-4389-8200-f1644ee375a7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 960d571c-84a8-4b9e-bd53-26203def64ee |  | section | E17 - Ensuite
checkpoint-status | 8a6c67fb-b0f3-48dc-8e90-6abc77b52d77 |  | checkpoint | Area floor level acceptable
checkpoint-status | 0ae762ae-77eb-4dc1-9283-98bd45e75b39 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 29f4825d-71d4-494a-b295-3a2b314c0085 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 2215c869-79b3-45ba-b4fa-d09e36c5cfe1 |  | section | E18 - Bathroom
checkpoint-status | 4bdbc844-b04e-45e4-a58f-810423f5b3b0 |  | checkpoint | Area floor level acceptable
checkpoint-status | ede6066f-ead0-451f-bdcc-855e82c1b396 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 07e17a2a-e48f-4828-9282-145923b020fe |  | checkpoint | Self leveling coverage completed
checkpoint-group | d03e8b47-ee06-45f8-aaa7-3f5d947cb755 |  | section | E18 - Ensuite
checkpoint-status | 137065f4-7585-43f3-a5c2-c2e2eb1ddb2f |  | checkpoint | Area floor level acceptable
checkpoint-status | 5aedf1e6-7abe-475f-8b58-656a0da4f488 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 1d9ab30f-df64-441f-9012-3ee478656b72 |  | checkpoint | Self leveling coverage completed
checklist-flat | 05cf1e0a-8f3a-4196-bad1-dfe2ed2c72e2 |  | checklist | [5 empty] | Yes | SYS - B03D - Bathroom | ce3ebfe2-cb6d-423c-ba23-edccef2e2b49
checkpoint-status | 19f235ac-1a77-46fc-abb1-b431c4df924d |  | checkpoint | Area floor level acceptable
checkpoint-status | e2f48b5e-4542-48c7-91be-57f36e2c1883 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 7cdc2920-ed24-4648-8272-403868d844c6 |  | checkpoint | Self leveling coverage completed
holdpoint | 000dc589-a682-4ef4-ac03-5efd50c7fead |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-sectioned | 44b6912a-6d2a-4ffb-bd71-99aef49e4511 |  | checklist | [5 empty] | Yes | SYS - B01A - Level 5 | d17eafed-fdb8-4c22-aa72-042544c128ce
checkpoint-group | b27c844d-748a-4473-8198-d0b952a4a71a |  | section | ALS 562 - Bathroom
checkpoint-status | 3ac5812c-92ca-4249-a30a-88990e86f545 |  | checkpoint | Area floor level acceptable
checkpoint-status | ef24a1ea-4b6b-45b2-bebc-781da0f697df |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 8945f0b8-2d1b-4f20-bc3d-93969c992694 |  | checkpoint | Self leveling coverage completed
checkpoint-group | f53b50a0-9098-4b2a-8cb1-286986294790 |  | section | ALS 563 - Bathroom
checkpoint-status | bdfeab5a-fc13-4654-bfd9-62a8d232f121 |  | checkpoint | Area floor level acceptable
checkpoint-status | 70058e8f-bc79-4de7-818b-2662048d07ed |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 6daa7133-4f52-4b88-8cf1-09b3f40ed270 |  | checkpoint | Self leveling coverage completed
checkpoint-group | b3d91b43-8341-4a4a-9d95-e7dd102b6c00 |  | section | ALS 564 - Bathroom
checkpoint-status | cc4ada58-67a0-4f86-b4c9-8234c7845287 |  | checkpoint | Area floor level acceptable
checkpoint-status | 47ad039e-1b9d-47b4-9be7-6e0035130529 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | a1e190e4-4d21-49c3-9837-65dcf24f2aed |  | checkpoint | Self leveling coverage completed
checkpoint-group | 9ca4033b-2922-48fe-8509-69685b57c1bc |  | section | ALS 565 - Bathroom
checkpoint-status | a3f78334-e4d9-4994-969a-eadfac241a1b |  | checkpoint | Area floor level acceptable
checkpoint-status | bac31f63-8d2d-4e36-bdb6-5910cda7dd08 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 87e536a5-06fc-4c3e-9718-b8e096dc2fb0 |  | checkpoint | Self leveling coverage completed
checkpoint-group | a7d32905-b0ef-4b6f-990d-43fd17bca308 |  | section | ALS 566 - Bathroom
checkpoint-status | 3bc20075-a2eb-4997-b83c-e0ee61dca16a |  | checkpoint | Area floor level acceptable
checkpoint-status | 99659d3c-ef54-438d-8993-ded4025b5db4 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 02947985-f58d-4069-9812-d024ee99b196 |  | checkpoint | Self leveling coverage completed
checkpoint-group | b4606ac1-5919-4daa-8151-ca9d5c9dad0e |  | section | ALS 567 - Bathroom
checkpoint-status | cc17b5a8-81b3-42e7-a400-4a444bdcc59c |  | checkpoint | Area floor level acceptable
checkpoint-status | 90158723-3f40-403d-8d18-228b8d0a3f78 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d8d43b0e-99b0-4f27-acc7-4bd875ada6e7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | a7d32328-7385-4a72-a7cd-52efff095a12 |  | section | ALS 568 - Bathroom
checkpoint-status | 5ee63b56-9a32-4c10-bc04-649299f4250d |  | checkpoint | Area floor level acceptable
checkpoint-status | 1fdbe95a-1d59-4bb3-9de1-4d4d5872e585 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 6685622f-11a7-46ec-9b9d-5e5c8b33b471 |  | checkpoint | Self leveling coverage completed
checkpoint-group | a490fab5-8435-4297-80bb-a00ce05297ea |  | section | ALS 569 - Bathroom
checkpoint-status | 9e63ae68-0e36-4591-b977-f340e50d9b0b |  | checkpoint | Area floor level acceptable
checkpoint-status | e344be99-5af0-4a9d-854e-92cf9d3bd222 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9872086f-7577-4d0e-9173-6d031d3e455d |  | checkpoint | Self leveling coverage completed
checkpoint-group | e42be333-9fa6-4ee4-8725-c8d8f5f18723 |  | section | ALS 570 - Bathroom
checkpoint-status | a93f61d0-adce-41c3-bea7-64b62afabc93 |  | checkpoint | Area floor level acceptable
checkpoint-status | dc31bf33-e727-476c-b15b-3880bedf64f1 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 66b73b69-9173-435c-bb1b-fc34090435c7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 71f9ca7d-4cd0-4066-8c02-d52c56a6b5ac |  | section | ALS 571 - Bathroom
checkpoint-status | eb8bc082-0040-4112-926d-0e34b23ffa3b |  | checkpoint | Area floor level acceptable
checkpoint-status | 330df24f-70ab-4d5c-8127-032f2a207aa4 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 8ef7a16d-79f8-4aad-8b59-8e750a08f8e2 |  | checkpoint | Self leveling coverage completed
checkpoint-group | c5373dd6-2578-4cea-8539-5af140f6ca39 |  | section | ALS 572 - Bathroom
checkpoint-status | fa3c2b12-b506-4448-bf37-eb3e83caf2d9 |  | checkpoint | Area floor level acceptable
checkpoint-status | 3b76b3d3-8dad-4f3b-b816-5271d16f9336 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 39af0253-ac65-4999-ad0c-e8358680e3fa |  | checkpoint | Self leveling coverage completed
checkpoint-group | 7f15d61c-6fd7-454b-9506-a353c46421cf |  | section | ALS 573 - Bathroom
checkpoint-status | 3a4f8527-cc70-47ec-8ee4-577570cc5a79 |  | checkpoint | Area floor level acceptable
checkpoint-status | 17bed1d3-8033-4270-a160-216b9b5a9d81 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 555cd761-b012-491c-816a-ad98ed8d1fb4 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 1459b076-a9c2-423b-bf2d-b5ee127b92f6 |  | section | ALS 574 - Bathroom
checkpoint-status | e3bb1a20-cbe7-42bb-bc80-e0304ab7dc22 |  | checkpoint | Area floor level acceptable
checkpoint-status | 7c47fcef-eb3a-42fc-ac2d-3f39d3b93e3d |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e821893d-9e3f-4fa2-9edf-c9a88a030c50 |  | checkpoint | Self leveling coverage completed
checkpoint-group | fc33176c-1d71-42cf-a92b-16dcced90109 |  | section | ALS 575 - Bathroom
checkpoint-status | d1f87e0b-dcfe-4a3d-9099-7a356834fabf |  | checkpoint | Area floor level acceptable
checkpoint-status | 1f56de23-f79d-4f2a-b943-a5c4e2fa428b |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 90c6b277-0f6b-45e5-98c9-b7d0ec885d57 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 6835e109-7d0d-4756-b613-2c70048f7ced |  | section | ALS 576 - Bathroom
checkpoint-status | dcaba717-6868-44b4-ad9c-4564c6e51fa7 |  | checkpoint | Area floor level acceptable
checkpoint-status | eb3c5bf4-2602-4a72-8aa0-f1840e55334f |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e53e6cd7-5070-4e7d-8964-916493af8195 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 13adb72e-e98f-4717-a585-bd54238c5676 |  | section | ALS 577 - Bathroom
checkpoint-status | 81f38c39-4d1c-4db3-a9fc-f9846a905ebf |  | checkpoint | Area floor level acceptable
checkpoint-status | 4daf6b4c-e228-4210-bee2-1a1fba595685 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 4a6586a1-18f4-4887-b0b4-83bd938e6843 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 9edc32e5-a592-4965-a30b-3efc73ef1776 |  | section | ALS 578 - Bathroom
checkpoint-status | 941ffbe3-2f4a-4f3a-9ed4-82f06f5f316b |  | checkpoint | Area floor level acceptable
checkpoint-status | 651f1ef0-e59e-4e8c-866f-7ae1ebcbe859 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 92de31c3-3a97-4150-a809-2834796cf5e1 |  | checkpoint | Self leveling coverage completed
checkpoint-group | e3772e2d-d1d4-46ca-b203-e29d43c3cf85 |  | section | ALS 579 - Bathroom
checkpoint-status | 6f6b8bee-51a2-403d-9f45-8c2b5df3338f |  | checkpoint | Area floor level acceptable
checkpoint-status | 2ee81b74-8eb9-4e59-ab39-8a0299d2c154 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e2a89cdd-4333-4829-8d77-f7c2a5a02b0c |  | checkpoint | Self leveling coverage completed
checkpoint-group | 206d292b-381e-4ae2-a67e-e374f1b6d8e8 |  | section | ALS 580 - Bathroom
checkpoint-status | 7b852de9-acb9-4fea-9c0b-c2fc99ff4e2a |  | checkpoint | Area floor level acceptable
checkpoint-status | 6e4fd879-4975-4b83-9646-bbb53dac9286 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e80f5f4d-ac22-425f-8bd6-d0f642022dcd |  | checkpoint | Self leveling coverage completed
checkpoint-group | 2a05fdc6-bb80-405b-b87e-9af24d365788 |  | section | ALS 581 - Bathroom
checkpoint-status | 9693831e-39fa-4923-ac4a-fa55cd64194c |  | checkpoint | Area floor level acceptable
checkpoint-status | 787d6c15-47a8-4b4d-8300-b4fd8122ddf6 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f91dda65-493b-416a-b8b6-7c4a3f8991c4 |  | checkpoint | Self leveling coverage completed
checkpoint-group | bd5aec96-cea0-4650-98e8-3a89d6719ec7 |  | section | ALS 582 - Bathroom
checkpoint-status | 954a6ba9-c711-40a9-a3e2-788baf46e2df |  | checkpoint | Area floor level acceptable
checkpoint-status | 89a98bfb-982d-458c-888a-1d6ab8baab42 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | fd84441b-c9fa-441c-a7f3-d3cb572e39a9 |  | checkpoint | Self leveling coverage completed
checkpoint-group | c25fb1b5-f1f3-4b9c-b97c-ca5fce3628d6 |  | section | ALS 583 - Bathroom
checkpoint-status | 0fdce426-9e44-4707-8dcb-4370992f3498 |  | checkpoint | Area floor level acceptable
checkpoint-status | 48f07f55-b5f9-479b-8966-35eb36831153 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 49b9f07d-7ead-4590-936b-9a44463fe3b7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | 7ee954c8-1cbf-4648-8d70-e48283748a11 |  | section | ALS 584 - Bathroom
checkpoint-status | 32f68765-55de-4c38-b50e-3b0a5ef5720a |  | checkpoint | Area floor level acceptable
checkpoint-status | e2eebcba-9d35-4f2a-9ee2-09a8f3d0319f |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 0e0a1efd-ebdf-463a-9858-4c514eef4ae7 |  | checkpoint | Self leveling coverage completed
checkpoint-group | f9a06b26-561a-4b79-9810-97d9c93795cb |  | section | ALS 586 - Bathroom
checkpoint-status | 8e3eda1a-6f72-4f44-9f8e-5ad370f96bce |  | checkpoint | Area floor level acceptable
checkpoint-status | ca348242-e713-41f5-a570-91c3be7c3480 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 5bb3817a-31f9-459a-8c05-de26157a5231 |  | checkpoint | Self leveling coverage completed
checklist-sectioned | f4821218-7810-4ed3-8ae9-0d67f48445ac |  | checklist | [5 empty] | Yes | SYS - B03B - Level 5 | d231d6ed-1b7a-4e74-bef7-b9ba1b741585
checkpoint-group | 972ea2be-f5f3-4b73-9fbc-0defa18d04cb |  | section | E21 - Bathroom
checkpoint-status | 1e6afd19-78e8-42dd-b20b-7813ec71e78f |  | checkpoint | Area floor level acceptable
checkpoint-status | 7b8f7bee-7a11-49e9-985a-5ac568ba66a7 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9e02a8df-45b0-4897-8289-6cb33e36e18a |  | checkpoint | Self leveling coverage completed
holdpoint | f5235bfc-c4ca-4432-9dcd-0c1d3fd4f855 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | b041bcd7-9817-4f49-ba56-9ea801eab8e2 |  | section | E22 - Bathroom
checkpoint-status | 1312bf95-f671-4e57-bc96-65d6276d0b2e |  | checkpoint | Area floor level acceptable
checkpoint-status | 7352d4ea-1094-4895-812d-a413a509d194 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 64d64d9b-49dd-40b1-822f-98a8f2a7d98f |  | checkpoint | Self leveling coverage completed
holdpoint | c5bf754f-2636-4b83-a547-e7babdae4f6a |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 34b74344-3883-4dec-b01b-8c2ebfc539bd |  | section | E23 - Bathroom
checkpoint-status | b42ce01e-89e1-467c-a5e0-56caef819484 |  | checkpoint | Area floor level acceptable
checkpoint-status | 8e538315-49e9-4aaf-beed-6ee4666fffcc |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f4feba9c-e73c-4f7d-b848-199129e17b87 |  | checkpoint | Self leveling coverage completed
holdpoint | a303ebb8-2334-44a4-a86b-687e1c86920f |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 116ff62d-7d20-40ea-b26d-b310d6d77ecb |  | section | #24 - Bathroom
checkpoint-status | b75fbea5-acd1-486d-a4c4-a0932a0bddd5 |  | checkpoint | Area floor level acceptable
checkpoint-status | 3af67515-3469-4b0b-a2ab-3b6e839635cd |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | e42ed24a-d99f-4fc3-8f5b-280469138e62 |  | checkpoint | Self leveling coverage completed
holdpoint | 5767e2a1-01e7-4fec-85d1-79058d351b1d |  | signoff | Raise Remedial/ Main Contractor Sign Off
checklist-sectioned | f8e32574-1a3c-4d27-a906-1255ae92f6e1 |  | checklist | [5 empty] | Yes | SYS - B03B - Level 3 | f8af9b66-0538-4429-b405-db60fdbcfb43
checkpoint-group | 23fa2a29-ebdc-41e3-ae0a-7c731a35e001 |  | section | C21 - Bathroom
checkpoint-status | 7162d1a4-ecee-44f7-9352-add9b84a5a48 |  | checkpoint | Area floor level acceptable
checkpoint-status | d8503292-5227-4f6b-8faa-034cde9ddd80 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 92a160b1-d6af-4d38-9561-6c5026790c82 |  | checkpoint | Self leveling coverage completed
holdpoint | 89176e73-26b2-4b31-932f-3315fa520f6d |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | a153854b-4df6-443f-b7df-f53ed2387a7a |  | section | C22 - Bathroom
checkpoint-status | a30899b1-b6e2-43f7-9c52-8c6e1ffec3ae |  | checkpoint | Area floor level acceptable
checkpoint-status | 33726d33-3ba9-40b7-a9bc-1274f56b21d8 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 4a68edbb-a4c1-45d0-b19d-5348b8380753 |  | checkpoint | Self leveling coverage completed
holdpoint | a0a9d0e4-4a52-47a3-9570-4f836c3c8dca |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 6bcded9e-056b-4517-823e-6a9a5f63821b |  | section | C23 - Bathroom
checkpoint-status | e7712106-c657-4a2d-aec3-33537b275b05 |  | checkpoint | Area floor level acceptable
checkpoint-status | c9ed5647-a941-4675-ab53-fffaf964966e |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | f837a2d0-3ac5-444c-8ddf-6350814d30e4 |  | checkpoint | Self leveling coverage completed
holdpoint | 9253f672-c666-40a9-96a0-aec49a85ab5d |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 81725839-57b1-47f0-9b33-863d7b928646 |  | section | C24 - Bathroom
checkpoint-status | f57c308f-143c-4ad3-b684-0df5d12ef42e |  | checkpoint | Area floor level acceptable
checkpoint-status | ac61ed06-33c2-422e-b032-68970fb961d8 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | d71a9197-1c3d-4368-a0a0-3d3dc1611700 |  | checkpoint | Self leveling coverage completed
holdpoint | 90b5eebb-34b4-488f-99f7-23e048b99f02 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | ead8c7c0-b7d4-4271-8ef7-28cf607a1b22 |  | section | C25 - Bathroom
checkpoint-status | 9244509e-9352-41e8-aaf7-be87b4acbe2f |  | checkpoint | Area floor level acceptable
checkpoint-status | ef35a1a7-47e1-4086-939e-2fea8c8d2877 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9c74028c-d148-488a-b18c-3a74a7af0bb2 |  | checkpoint | Self leveling coverage completed
holdpoint | 823af1ac-fd62-4c7d-9f7d-6aa1e325efbf |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | d399c818-9138-49b6-8482-95d2cbcf5217 |  | section | C26 - Bathroom
checkpoint-status | ed8dbfb3-7d40-404c-8ecd-ce8775202798 |  | checkpoint | Area floor level acceptable
checkpoint-status | 487e6947-0e29-4d20-8359-e45eab13e7ec |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | a55e5f67-0208-4fbc-9411-50fdeda3336f |  | checkpoint | Self leveling coverage completed
holdpoint | a84bc7c1-4550-4d36-a744-d084b2dcdd39 |  | signoff | Raise Remedial/ Main Contractor Sign Off
checkpoint-group | 329a7fac-4809-4bfc-9e62-0197bfe562da |  | section | C27 - Bathroom
checkpoint-status | c822ed46-efaa-415a-8724-ec6bd3279ae9 |  | checkpoint | Area floor level acceptable
checkpoint-status | 9c4fc783-d828-4971-9227-5ee76da17d96 |  | checkpoint | Wiring on the floor completed (photos attached)
checkpoint-status | 9c14e978-7176-48c5-af3f-c537bb5980fb |  | checkpoint | Self leveling coverage completed
holdpoint | 74e82b0a-6761-4bdc-a478-d779ea24c0e1 |  | signoff | Raise Remedial/ Main Contractor Sign Off