## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement & Surfacing - Subbase - Rev E | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Subbase - Rev E | 0f5e5930-b295-4394-bef5-bf0647e45f2a
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works start
label | Activity - H
label | By - PE
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works start
label | Activity - H
label | By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to activity being undertaken
label | Activity - H
label | By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to commencment of activity
label | Activity - H
label | By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
checkpoint | 3.01.07 - Stabilising Methodology
label | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
label | Standard / Specification - PS - 7.3.3
label | Verifying Document - Correspondence
label | Frequency - Prior to stabilisation start
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.08 - Acceptance of the SIL layer
label | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
label | Standard / Specification - PS - 4.8.3, Table 4.3
label | Verifying Document - Hold point relesed / Testing reports
label | Frequency - All sections before proceeding to the next layer
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
checkpoint | 6.02.01 - Sub-base MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - No less than 1 test every 5,000m³ (in place)
label | Activity - R
label | By - PE
checkpoint | 6.02.02 - Plasticity Index
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
label | Standard / Specification - Table 7.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | Activity - R
label | By - PE
checkpoint | 6.02.03 - Clay Index
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
label | Standard / Specification - Table 7.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | Activity - R
label | By - PE
checkpoint | 6.02.04 - Sand Equivalent
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
label | Standard / Specification - Table 7.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | Activity - R
label | By - PE
checkpoint | 6.02.05 - Particle size distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
label | Standard / Specification - Table 7.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | Activity - R
label | By - PE
checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
label | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | Standard / Specification - TNZ B/02: 2005 - 7.3
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.02.07 - Plateau Density Test
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | • Testing shall be at OWC.
label | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | Standard / Specification - PS - Table 7.2 - 2.3
label | Verifying Document - Plateau Density Report
label | Frequency - 5 tests per 10,000m2
label | Activity - I
label | By - PE
checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | Standard / Specification - TNZ B/02: 2005
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - I
label | By - PE
checkpoint | 6.02.09 - Surface shape control
label | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | • Vertical: - 25mm +5mm
label | • Cross fall: 0.5% on 2m straight edge
label | Standard / Specification - TNZ B/2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - Continuous
label | Activity - I
label | By - SV / PE
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
checkpoint | 6.03.01 - Stabilization Production Plan
label | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
label | Standard / Specification - NZTA B/6 7.2.3
label | Verifying Document - Correspondence
label | Frequency - 48H hours prior sabilising commencing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.02 - Longitudinal Joints
label | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
label | Standard / Specification - NZTA B/6 7.5.2
label | Verifying Document - Stabilisation Prodution Plan
label | Frequency - 48H hours prior sabilising commencing
label | Activity - H
label | By - PE
checkpoint | 6.03.03 - Stabilisation trial
label | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
label | Standard / Specification - PS - 7.3.3
label | Verifying Document - Triall Report
label | Frequency - prior to full scale production
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.03.04 - Stabilising Equipment
label | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
label | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Plant Approval
label | Frequency - Prior to works
label | Activity - H
label | By - PE
checkpoint | 6.03.05 - Stabilising Supervisor
label | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Supervisor Approval
label | Frequency - Prior to works
label | Activity - H
label | By - PE
checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
label | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | • Vertical: - 25mm +5mm
label | • Cross fall: 0.5% on 2m straight edge
label | Standard / Specification - TNZ B/2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
label | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | Standard / Specification - TNZ B/02: 2005 - 7.3
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.03.08 - Pre Stabilisation Compaction
label | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - IANZ NDMS
label | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
label | Activity - I
label | By - PE
checkpoint | 6.03.09 - Pre Stabilisation Crossfall
label | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - 1 test per 20m Prior to stabilisation
label | Activity - I
label | By - SV / PE
checkpoint | 6.03.10 - Stabilising Visual appearance
label | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Site Notes
label | Frequency - every 100m
label | Activity - I
label | By - PE
checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
label | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
label | Standard / Specification - Table 7.2
label | Verifying Document - Stab. Sheet
label | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
label | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
label | Activity - I
label | By - PE
checkpoint | 6.03.12 - Cement Average usage test
label | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
label | Standard / Specification - TNZ B6
label | Verifying Document - Stab. Sheet / Delivery Doc.
label | Frequency - Upon emptying the spreader and bulk tanker
label | Activity - R
label | By - SE
checkpoint | 6.03.13 - Control of cut depth
label | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
label | Standard / Specification - TNZ B6
label | Verifying Document - Stab. Sheet
label | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
label | Activity - R
label | By - SE
checkpoint | 6.03.14 - Plateau Density Test
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | • Testing shall be at OWC.
label | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | Standard / Specification - PS - Table 7.2 - 2.4
label | Verifying Document - Plateau Density Report
label | Frequency - 5 tests per 10,000m2
label | Activity - I
label | By - PE
checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
label | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
label | Verifying Document - IANZ Lab Reports
label | Frequency - 3 samples bag per stabilise day post hoe
label | Activity - I
label | By - PE
checkpoint | 6.03.16 - Mixed material testing (ITS)
label | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
label | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
label | Standard / Specification - TNZ B6 7.5
label | Verifying Document - Test Results
label | Frequency - 2 tests per stabilise day
label | Activity - R
label | By - PE
checkpoint | 6.03.17 - NDM Water correction
label | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
label | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
label | Standard / Specification - NZS 4407
label | Verifying Document - Corrected NDM Results
label | Frequency - Per Stabilise day
label | Activity - R
label | By - PE
checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
label | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
label | Activity - I
label | By - PE
checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
label | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | • Vertical: - 5mm +10mm
label | • Cross fall: 0.5% on 2m straight edge
label | Standard / Specification - TNZ B/2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
label | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
label | Standard / Specification - TNZ B6 - 7.8
label | Verifying Document - Site Notes
label | Frequency - For 7 days after stabilisation / Photos
label | Activity - R
label | By - PE
checkpoint | 6.03.21 - Benkelman Beam
label | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
label | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Benkelman Beam Report
label | Frequency - Every 10m of each lane – staggered between left and right wheel path.
label | Activity - R
label | By - SE
checkpoint | 6.03.22 - MDD / OMC / SD
label | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | Standard / Specification - NZS 4402:1986, Test 4.1.3
label | Verifying Document - Lab Report
label | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | Activity - I
label | By - PE
checkpoint | 6.03.23 - Sub-base stabilisation trial
label | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
checkpoint | 6.04.01 - Stabilization Production Plan
label | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
label | Standard / Specification - NZTA B/6 7.2.3
label | Verifying Document - Correspondence
label | Frequency - 48H hours prior sabilising commencing
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.04.02 - Longitudinal Joints
label | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
label | Standard / Specification - NZTA B/6 7.5.2
label | Verifying Document - Stabilisation Prodution Plan
label | Frequency - 48H hours prior sabilising commencing
label | Activity - H
label | By - PE
checkpoint | 6.04.03 - Stabilising Equipment
label | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
label | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Plant Approval
label | Frequency - Prior to works
label | Activity - H
label | By - PE
checkpoint | 6.04.04 - Stabilising Supervisor
label | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Supervisor Approval
label | Frequency - Prior to works
label | Activity - H
label | By - PE
checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
label | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | • Vertical: - 25mm +5mm
label | • Cross fall: 0.5% on 2m straight edge
label | Standard / Specification - TNZ B/2
label | Verifying Document - String sheet
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
label | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | Standard / Specification - TNZ B/02: 2005 - 7.3
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 6.04.07 - Pre Stabilisation Compaction
label | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
label | Standard / Specification - TNZ B/02: 2005
label | Verifying Document - IANZ NDMS
label | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
label | Activity - I
label | By - PE
checkpoint | 6.04.08 - Pre Stabilisation Crossfall
label | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - 1 test per 20m Prior to stabilisation
label | Activity - I
label | By - SV / PE
checkpoint | 6.04.09 - Stabilising Visual appearance
label | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Site Notes
label | Frequency - every 100m
label | Activity - I
label | By - PE
checkpoint | 6.04.10 - Cement Mat Test
label | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
label | Standard / Specification - TNZ B6
label | Verifying Document - Site Notes
label | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
label | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
label | Activity - R
label | By - SE
checkpoint | 6.04.11 - Cement Average usage test
label | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
label | Standard / Specification - TNZ B6
label | Verifying Document - Site Notes
label | Frequency - Upon emptying the spreader and bulk tanker
label | Activity - R
label | By - SE
checkpoint | 6.04.12 - Maintain OMC during stabilising
label | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
label | Standard / Specification - TNZ B6
label | Verifying Document - Site Notes
label | Frequency - Continuous
label | Activity - R
label | By - SE
checkpoint | 6.04.13 - Control of cut depth
label | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | Standard / Specification - TNZ B6
label | Verifying Document - Site Notes
label | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
label | Activity - R
label | By - SE
checkpoint | 6.04.14 - Mixed material testing (ITS)
label | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
label | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
label | Standard / Specification - TNZ B6 7.5
label | Verifying Document - Test Results
label | Frequency - 2 pairs of representative samples per day
label | Activity - R
label | By - PE
checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
label | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
label | Standard / Specification - TNZ B6 7.5
label | Verifying Document - Test Results
label | Frequency - 3 sample bags per lot.
label | Activity - R
label | By - PE
checkpoint | 6.04.16 - Plateau Density Test
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | • Testing shall be at OWC.
label | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | Standard / Specification - PS - Table 7.2 - 2.3
label | Verifying Document - Plateau Density Report
label | Frequency - 5 tests per 10,000m2
label | Activity - I
label | By - PE
checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
label | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - IANZ NDMS
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - I
label | By - PE
checkpoint | 6.04.18 - NDM Water correction
label | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
label | Standard / Specification - NZS 4407
label | Verifying Document - Corrected NDM Results
label | Frequency - Per Stabilise day
label | Activity - R
label | By - PE
checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
label | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | • Vertical: - 5mm +10mm
label | • Cross fall: 0.5% on 2m straight edge
label | Standard / Specification - TNZ B6 8.2
label | Verifying Document - Total station Topo showing levels compared to design
label | Frequency - Continuous
label | Activity - R
label | By - SV / PE
checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
label | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
label | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
label | Standard / Specification - TNZ B6 - 7.8
label | Verifying Document - Site Notes with photos
label | Frequency - For 7 days after stabilisation
label | Activity - R
label | By - PE
checkpoint | 6.04.21 - Benkelman Beam
label | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
label | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Benkelman Beam Report
label | Frequency - Every 10m of each lane – staggered between left and right wheel path.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.04.22 - MDD / OMC / SD
label | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | Standard / Specification - NZS 4402:1986, Test 4.1.3
label | Verifying Document - Lab Report
label | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | Activity - I
label | By - PE
section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
checkpoint | 7.02.01 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Activity - H
label | By - PE
checklist | ITP - Pavement & Surfacing - Basecourse - Rev 1 | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Basecourse - Rev 1 | 33752cb8-b125-4be2-a64d-64570c780a4a
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works start
label | Activity - H
label | By - PE
checkpoint | 1.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works start
label | Activity - H
label | By - SV
checkpoint | 1.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint | 1.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to activity being undertaken
label | Activity - H
label | By - SE
checkpoint | 1.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to commencment of activity
label | Activity - H
label | By - PE
checkpoint | 1.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
checkpoint | 1.01.07 - Subbase Approval
label | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
label | Standard / Specification - PS - Page 42
label | Verifying Document - ConQA
label | Frequency - Before proceeding to the next layer
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
label | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | Standard / Specification - TNZ B/02: 2005 - 7.3
label | Verifying Document - Survey / Level Checks
label | Frequency - 1 test per 20m
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.02 - Basecourse MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - No less than 1 test every 5,000m³ (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.03 - Plateau Density Test
label | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | • Every plateau to be completed at start of works and witnessed by a member of BBO.
label | Standard / Specification - PS - Table 7.2 - 2.3
label | Verifying Document - Plateau Density Report
label | Frequency - 5 tests per 10,000m2
label | Activity - I
label | By - PE
checkpoint | 3.01.04 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.05 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.06 - Sand Equivalent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.07 - Particle size distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per 1000m3 (in place)
label | Activity - R
label | By - PE
checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
label | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
label | Standard / Specification - TNZ B/02: 2005 - 7.6
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - I
label | By - PE
checkpoint | 3.01.09 - Surface Shape
label | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Survey / Straight edge Report
label | Frequency - Prior to sealing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.10 - Holding Water
label | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Visual Inspection / Site Note
label | Frequency - Prior to sealing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.11 - Maximum Width Variation
label | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
label | • Constrained : Zero
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Next layer or Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
label | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
label | • At other locations on pavement: –5 mm +15 mm
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.13 - Maximum Crossfall Variation
label | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
label | Standard / Specification - TNZ B/02: 2005 - 5.1
label | Verifying Document - Survey / Level Checks
label | Frequency - Before Surfacing
label | Activity - I
label | By - SV / PE
checkpoint | 3.01.14 - Benkelman Beam
label | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | Standard / Specification - PS - 7.3.2
label | Verifying Document - Benkelman Beam Report
label | Frequency - every 10m of each lane – staggered between left and right wheel path.
label | Activity - R
label | By - PE
checkpoint | 3.01.15 - NAASRA roughness
label | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
label | Standard / Specification - TNZ B/02: 2005 - 7.7
label | Verifying Document - Test Report
label | Frequency - Prior to sealing
label | Activity - R
label | By - PE
checkpoint | 3.01.16 - Running Course
label | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
label | Standard / Specification - TNZ B/02: 2005 - 10.1
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - S
label | By - SUP
checkpoint | 3.01.17 - Surface Finish post sweeping
label | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | Standard / Specification - TNZ B/02: 2005 - 7.8
label | Verifying Document - Photos
label | Frequency - Prior to sealing
label | Activity - R
label | By - PE
checkpoint | 3.01.18 - Tie in into Existing Pavement
label | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
label | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
label | Standard / Specification - TNZ B/02: 2005, 7.4
label | Verifying Document - photos, and survey data of undercut
label | Frequency - Every tying into existing pavements
label | Activity - I
label | By - SV / PE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.01.01 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
label | Standard / Specification - PS - Page 42
label | Verifying Document - Records
label | Frequency - Post construction
label | Activity - H
label | By - SV
checkpoint | 4.01.02 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Activity - H
label | By - PE
checklist | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp |  |  |  |  | ITP - Pavement & Surfacing - AP40 Material - Rev 1
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint | 2.01.01 - Basecourse CBR
label | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
label | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.02 - Running Course Material Approval
label | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
label | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
label | Standard / Specification - TNZ B/02: 2005 - 10.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test every stockpile
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.03 - Basecourse MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test per material type
label | Activity - H
label | By - PE
checkpoint | 2.01.04 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
label | Standard / Specification - NZS 4407: 1991 Test 3.10.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.05 - Weathering Resistance
label | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
label | Standard / Specification - NZS 4407: 1991 Test 3.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.06 - Particle Size Distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | Standard / Specification - TNZ M/4: 2006
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.07 - Sand Equivalent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.08 - Liquid Limit
label | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.09 - Plasticity Index
label | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.10 - Clay Index
label | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | Standard / Specification - PS - 7.2.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.11 - Accelerated Weathering Testing
label | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
label | • The levels of smectite clay minerals are not classified as “abundant”
label | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.12 - Repeat Load Triaxial Test
label | Acceptance / Conformance Criteria - In accordance with NZTA T15
label | Standard / Specification - NZTA T15
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.13 - Broken Face Content
label | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
label | Standard / Specification - TNZ M/4: 2006, 4.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Test per Source
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - Pavement & Surfacing - AP65 Material - Rev E | itp |  |  |  |  | ITP - Pavement & Surfacing - AP65 Material - Rev E
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
checkpoint | 5.01.01 - Sampling and testing
label | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
label | Standard / Specification - PS - 7.2.4
label | Verifying Document - IANZ Lab Reports
label | Frequency - five working days prior to delivery of the material to site.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Sampling and testing
label | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
label | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
label | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
label | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
label | Standard / Specification - NZTA B/6 item 5
label | Verifying Document - Lab reports
label | Frequency - Prior to Works start, per source
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
checkpoint | 5.02.01 - Sub-base MDD and OMC
label | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test per material type
label | Activity - H
label | By - PE
checkpoint | 5.02.02 - Cement for sub-base stabilisation
label | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
label | Standard / Specification - PS - 7.3.2, PS - 7.2.6
label | Verifying Document - Datasheets
label | Frequency - Prior to Use
label | Activity - H
label | By - PE
checkpoint | 5.02.05 - Crushing Resistance
label | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
label | Standard / Specification - NZS 4407: 1991 Test 3.10.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.06 - Weathering Resistance
label | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
label | Standard / Specification - NZS 4407: 1991 Test 3.11
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.07 - Particle size distribution
label | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
label | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.08 - Sand Equivalent
label | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
label | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.09 - Liquid Limit
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
label | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.10 - Plasticity Index
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
label | Standard / Specification - NZS 4407 Test 3.4
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.11 - Clay Index
label | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
label | Standard / Specification - NZS 4407 Test 3.5
label | Verifying Document - IANZ Lab Reports
label | Frequency - 0 to 400m³ - 2 tests
label | • 400 to 1,500m³ - 3 tests
label | • 1,500 to 4,000m³ - 4 tests
label | • >4,000m³ - 1 test for each additional 1,000m³
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.12 - Proportion of Broken Rock
label | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
label | Standard / Specification - PS - 7.2.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.13 - Organic Matter
label | Acceptance / Conformance Criteria - It shall be free of organic matter
label | Standard / Specification - PS - 7.2.2
label | Verifying Document - Photos
label | Frequency - Continuous
label | Activity - I
label | By - SE/PE
checkpoint | 5.02.14 - Accelerated Weathering Testing
label | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
label | • The levels of smectite clay minerals are not classified as “abundant”
label | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
label | Verifying Document - Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.15 - Repeat Load Triaxial Test
label | Acceptance / Conformance Criteria - In accordance with NZTA T15
label | Standard / Specification - NZTA T15
label | Verifying Document - IANZ Lab Reports
label | Frequency - 2 tests per source 4 weeks before use in the works.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
label | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
label | Standard / Specification - PS - Table No. 7.2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
label | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
label | Standard / Specification - NZTA T/19 - Table A7.4
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT