## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | DG-QA-TP018 Inspection and Test Plan (ITP) | itp |  |  |  | Yes | DG-QA-TP018 Inspection and Test Plan (ITP) | 45f2bc5c-246a-49b0-923f-48e53609874b
checkpoint-group |  |  | section | 1. Receiving Inspection
checkpoint-status |  |  | checkpoint | 1.1 - Service Locates
label | 6045ad6a-b573-5325-b704-71fa8eeb436e |  | note | Acceptance Criteria - Services located by Chorus and Delta prior to wokrs commencing
label | b3525edd-839b-55b4-a9b6-0e5ab7fc7b9e |  | note | Verifying Document - Photos
label | 0fad300b-f57a-537b-a09c-b28c1536e21d |  | note | Frequency - Once for each work location
label | 78b6f9a8-3424-5033-90d1-dea405906776 |  | note | Inspection Type (Visual, other) - Verification
label | f66a400a-bf2e-5752-900d-00543df0b5f1 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.2 - Temporary Traffic Management
label | e68c8162-3887-5256-8efa-586e6f634e3a |  | note | Inspection Point: Quality Control Activity - Temporary Traffic Management to be set up on site prior to any works commencing
label | fbf3213b-ecb3-52c6-b5db-305eebafb5dc |  | note | Acceptance Criteria - Temporary Traffic Management set up by qualified STMS according to approved plans
label | 13ff03fd-c3b4-5ed7-a425-8b094e2a542d |  | note | Verifying Document - Approved TM Plan
label | 2722667a-66ea-53ca-825c-3a5b286576d0 |  | note | Frequency - Daily
label | 57134c83-66af-5bed-8ac0-379b65484adb |  | note | Inspection Type (Visual, other) - Verification
label | c38cd082-f883-539d-b7be-f87c4105ece7 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.3 - Culvert Bedding
label | 54ac98e7-e2ea-540b-9412-95948af6592a |  | note | Inspection Point: Quality Control Activity - Scalas to be done on subgrade
label | 49988d8d-955b-52fc-9144-58b8a6d6aa37 |  | note | Acceptance Criteria - If scala test results lower than 3, add 100mm of compacted AP65
label | fd9f4b41-51b0-5e9e-96dc-eec787d62825 |  | note | Verifying Document - Photos, Field testing document
label | f09540a0-bde4-5fb1-a51d-a2502e066ac2 |  | note | Frequency - One lot of tests for each work location
label | 3a797265-f1ee-5f2b-b87a-a2f7df9f0fe6 |  | note | Inspection Type (Visual, other) - Hold Point
label | 0e8e5a55-50e8-5672-a3b9-42ef3ffeefb5 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.4 - AP65 Backfill
label | 65d4c908-52f4-538b-81dc-d944f18261b1 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | baae139e-6ef1-5605-afd6-b061b8f5f0fc |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 25
label | 6f3ee88b-e357-51a0-8dfc-d3fda5f58fac |  | note | Verifying Document - Photos, Field testing document
label | 8834281f-396c-518a-aa81-0d40edb36a22 |  | note | Frequency - Every 150mm lift
label | e43b16b3-ff51-5a91-a8e3-05229798d2c9 |  | note | Inspection Type (Visual, other) - Hold Point
label | a0e6e6a7-136d-5c1b-8589-6bce74d4b463 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.5 - AP40 Backfill
label | 2967c5b8-595d-5abd-8fe5-a0251daa99c1 |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on backfill
label | 28a7fd18-656c-5419-8f4e-8cb41a4d815f |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | de3c786f-5f82-5301-b1fc-1867a0627307 |  | note | Verifying Document - Photos, Field testing document
label | 0e77f767-1dd7-55ee-8d83-60f84c907d4d |  | note | Frequency - Every 150mm lift
label | 97948f30-dd5f-58ea-bfb3-2ab30f0e03dc |  | note | Inspection Type (Visual, other) - Hold Point
label | 1cd7386a-021f-5157-83b5-da8c70136d32 |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.6 - Pavement Strength
label | e33835f6-2856-5d1a-8f17-62660e0b629e |  | note | Inspection Point: Quality Control Activity - Clegg testing to be done on Pavement
label | 06834782-f401-5e2d-bddf-59e9eade8dae |  | note | Acceptance Criteria - Clegg Impact Value to be greater than 35
label | 0b376344-9917-5c4a-bc46-fc7132990bf7 |  | note | Verifying Document - Photos, Field testing document
label | 07c982ed-2556-5943-a48d-5026ad09e2af |  | note | Frequency - One lot of tests for each work location
label | 2699fe34-8793-5ba1-88a8-21bbc98953a1 |  | note | Inspection Type (Visual, other) - Hold Point
label | 73f9effc-830e-5ace-a902-483bcf9d145c |  | note | Inspection: By (Role Key) - Downer
checkpoint-status |  |  | checkpoint | 1.7 - Alignment
label | e784c8cf-0e23-5199-9483-78af6e9c3346 |  | note | Inspection Point: Quality Control Activity - 3 metre straight edge
label | 5a689631-2d88-5cce-bdc5-00abd06d0515 |  | note | Acceptance Criteria - Maximum 10mm
label | debb4dd8-7b33-5a3a-8ff3-bfa2bb578038 |  | note | Verifying Document - Visual
label | 28d4823c-efe9-58f9-917f-11f05c436355 |  | note | Frequency - One lot of tests for each work location
label | 22726955-649b-5b97-a45d-80e0a2e5fb0c |  | note | Inspection Type (Visual, other) - Verification
label | 204b270c-7136-5b27-8b22-4f72166e7db1 |  | note | Inspection: By (Role Key) - Downer
checkpoint-group |  |  | section | 2. Culvert Grade
checkpoint-status |  |  | checkpoint | Culvert Grade
checkpoint-group |  |  | section | 3. Photos
checkpoint-status |  |  | checkpoint | Photos