## Sheet3
Inspection and Test Plan Te Ara o Te Ata Concrete Culvert 17 ITP # MMA-QA-ITP-Z07-DR-CV017
| This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR |  |  | Approved by Construction Manager
Rev Number | Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01 | Libby Whyte | L.W | 2023-02-08
Rev 02 | Matthew Wenborn | M.J.W | 2023-05-02 |  |  |  | Danny Beasant | DB | 2023-05-02
Rev 03 | Libby Whyte | L.W | 2024-01-11 | Ramy Faragalla | Ramy Faragalla | 2024-01-11 | Matthew Wenborn |  | 2024-01-15 | Hardus Pieters |  |  |  | 2024-01-17
Rev 04 | William McCracken | W.M | 2024-01-17 | Ramy Faragalla | Ramy Faragalla | 2024-04-18 | Matthew Wenborn |  | 2024-01-25 | Hardus Pieters |  |  |  | 0702/2024
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Concrete Culvert | [7 empty] | Area Location / Work Breakdown: Culvert 17
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.1.0 Pre-construction approvals
1.1.1 | Construction Environmental Management Plan |  | MMA-ENV-RMP-RPT-15631 |  | Document Review | Prior to work starting |  | Approved CEMP | H |  |  |  | Signed CEMP
1.1.2 | Construction Work Plan |  | CWP |  | Document Review | Prior to work starting |  | Approved CWP | H |  |  |  | Signed off CWP
1.1.3 | IANZ accredited testing organisation |  | Details of proposed testing organisation |  | Document Review | Once prior to works commencing |  | Designer review and approval required on all test equipment calibration certificates and frequency on testing | H | H |  |  | Test and supplier certificates
1.1.4 | IFC's specification |  | MMA-DES-DNG-E1-10686 |  | Document Review | Once prior to works commencing |  | Obtain copy of the Concrete Culvert Specification | H | H |  |  | IFCspecifications or Written approval from PAB
1.1.5 | IFC drawings |  | Obtain IFC drawings |  | Document Review | Once prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC drawings or Written approval from PAB
1.1.6 | Approved Drainage Strings |  | MMA-DES-GEM-E1-REF-30611 |  | Document Review | Every new Drainage Line and prior to work commencing |  | Designer to confirm and approve strings to be loaded on the equipment | H | H |  |  | IFC Cover Form
1.1.7 | Approval of stockpile location |  |  |  | Document Review & Approval | Prior to works commencing |  | Approved stockpile location | H | H |  |  | ?
1.2.0 Material compliance
1.2.1 | Materials Approval- pipes and fittings |  | MMA-DES-DNG-E1-10686 Clause 4.4.1 TNZ F/3 AS/NZS 3725 AS 1646 |  | Material Submittal to DSR review | Prior to works commencing |  | All concrete pipes shall be class 4 Pipes and fittings shall comply with the requirements of AS/NZS 4058, AS/NZS 3725 and AS 1646. | H | H |  |  | Material Approval
1.2.2 | Materials Delivery- pipes and fittings |  | MMA-DES-DNG-E1-10686 Clause 4.4.1 AS/NZS 4058 AS/NZS 3725 AS 1646 |  | Inspection the new Delivery and review the Dockets and test certificates | Each delivery to site |  | All concrete pipes shall be class 4 Pipes and fittings shall comply with the requirements of AS/NZS 4058, AS/NZS 3725 and AS 1646. | H | R |  |  | Onsite Material Delivered Check Sheet Dockets Compliance Certificates
1.2.3 | Materials Approval – pre-cast Concrete Manhole units and wingwalls |  | MMA-DES-DNG-E1-10686 Clause 4.5 TNZ F/3 NZS 4058 NZS 3109 NZS 3114 |  | Specification compliance – manufacturer’s certificate to TNZ F/3 for pipe and pre-cast units | Prior to works commencing |  | Concrete manholes shall be designed to withstand HN-HO-72 loading. Precast manhole bases shall be supplied with a 150mm thick base slab and 150mm wide external flange cast at time of manufacture. | H | H |  |  | Material Approval
1.2.4 | Materials Delivery – pre-cast Concrete Manhole units and wingwalls |  | MMA-DES-DNG-E1-10686 Clause 4.5 & 4.13 TNZ F/3 NZS 4058 NZS 3109 NZS 3114 |  | Inspection the new Delivery and review the Dockets and test certificates | Each delivery to site |  | Concrete manholes shall be designed to withstand HN-HO-72 loading. Precast manhole bases shall be supplied with a 150mm thick base slab and 150mm wide external flange cast at time of manufacture. All concrete wing walls and catchpit chambers shall be precast proprietary products manufactured in accordance with NZS 3109, unless otherwise noted in Drawings. Minimum concrete strength shall be, f’c = 40 MPa. Surface finishes shall be F4 in accordance with NZS 3114. | H | R |  |  | Onsite Material Delivered Check Sheet Dockets Compliance Certificates
1.2.5 | Materials Delivery – Lids and Grates for Manholes |  | MMA-DES-DNG-E1-10686 Clause 4.5.4 TNZ F/3 AS3996 |  | Inspection the new Delivery and review the Dockets and test certificates | Each delivery to site |  | Grates and frames shall be ductile iron suitable for AS 3996 Class D traffic loading. All grates for catchpits and catchpit manholes shall be Hynds Hydro grates. All manhole covers shall be heavy duty “Non-Rock” type and rated for AS3996 Class D loading. Covers shall have a clear opening of 600mm. Manhole covers located within the carriageway must be locked or bolted shut. | H | R |  |  | Onsite Material Delivered Check Sheet Dockets Compliance Certificates
1.2.6 | Materials Approval – Weathering Index for Bedding, Haunch Material AP20 aggregate |  | MMA-DES-DNG-E1-10686 Clause 4.6.4 & 6.2 NZS 4407 Test 3.11 |  | Weathering Index test | Two tests per source 4 weeks before use in the works |  | The aggregate shall have a weathering quality index of AA to CA when tested according to NZS 4407, Test 3.11. | H | R |  | I | Material Approval Weathering quality index Test Report
1.2.7 | Materials Approval – Crushing Resistance for Bedding, Haunch Material AP20 aggregate |  | MMA-DES-DNG-E1-10686 Clause 4.6.4 & 6.2 NZS 4407. Test Method 3.10 |  | Crushing Resistance test | Two tests per source 4 weeks before use in the works |  | A minimum crushing resistance of 100 kN when tested in accordance with NZS 4407 test 3.10 | H | R |  | I | Material Approval Crushing Resistance test Report
1.2.8 | Materials Delivery – Grading for Bedding, Haunch Material AP20 aggregate |  | MMA-DES-DNG-E1-10686 Clause 4.6.4 NZS 4407 Test 3.8.1. |  | Grading Testing Inspection the new Delivery and review the Dockets and test certificates | 2 per 400m3, 3 per 400-1500m3, 4 per 1500-4000m3 and for over 4000m3, 1 additional test per 1000 m3 |  |  | H | R |  | I | PSD Test Report
1.2.9 | Materials Approval – Maximum Dry Density for Bedding, Haunching AP20 Aggregate |  | NZS4402 Test 4.1.1 |  | Standard MDD Test | 3 no. tests per source with minimum 5 points |  | Accepted by DSR | H | R |  | I | MDD Test Report
1.2.10 | Materials - Structural Fill for Overlay Zones (AP65) |  | MMA-DES-GEO-E1-SPC-3859 and AS/NZS 3725:2007 |  | As Per MMA-CON-CMA-ITP-31067 | As Per MMA-CON-CMA-ITP-31067 |  | Accepted by DSR | H | R |  | I | Test Reports
1.2.11 | Material Approval – Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 4.8 |  | Test | Prior to works commencing |  | Each load of riprap shall be well graded from the smallest to the maximum specified. Stone smaller than the specified 15 per cent size, will not be permitted in an amount exceeding 20% by weight of each load. The required riprap grading shall be hard, dense and durable and not susceptible to weathering and water action. No rock source shall have an average specific gravity less than 2.6. | H | R |  | I | Test Report
1.2.12 | Materials Delivery –Weathering Index of a Coarse Aggregate for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 NZS 4407 Test 3.11 |  | Weathering Index test | One test per 1000 m3 |  | The Coarse Aggregate shall have a weathering quality index of AA to CA when tested according to NZS 4407, Test 3.11. | H | R |  | I | Material Approval Weathering quality index Test Report
1.2.13 | Materials Approval –Crushing Resistance of Coarse Aggregate for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 NZS 4407 Test 3.10 |  | Crushing Resistance test | One test per 1000 m3 |  | A minimum crushing resistance of 100 kN when tested in accordance with NZS 4407 test 3.10 | H | R |  | I | Material Approval Crushing Resistance test Report
1.2.14 | Materials Approval –Solid Density of Aggregate for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 NZS 4407 Test 3.7.1 & 3.7.2 |  | Solid Density of Aggregate test | One test per 1000 m3 |  | ≥ 2.6 tonnes per m3 | H | R |  | I | Material Approval Solid Density of Aggregate test Report
1.2.15 | Materials Delivery – Grading for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 NZS 4407 Test 3.8.2 |  | Grading Testing | 1 per 500 m3 |  | As per section 4.8.1 of the Specification | H | R |  | I | PSD Test Report
1.2.16 | Materials Approval –Point Load Strength for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 ASTM D5731 |  | Point Load Strength test | One test per 1000 m3 |  | >1.5 Mpa | H | R |  | I | Material Approval Point Load Strength test Report
1.2.17 | Materials Delivery – UCS Rock for Rip Rap |  | MMA-DES-DNG-E1-10686 Clause 6.5.2 AS4133.4.2.2 |  | UCS Rock Test | One test per 1000 m3 |  | >30 Mpa | H | R |  | I | UCS Rock Test Report
1.3.0 Geosynthetics
1.3.1 | Designer Visual inspection of the bottom of the excavation |  | MMA-DES-DNG-E1-10686 Clause 5.8.1 |  | Inspection | Check each lot |  | No construction work within the trench shall commence until the bottom of the excavation has been inspected and the method of treatment approved by the Designer. | H | H |  |  | Onsite Checklist Daily Site Inspection
1.3.2 | Geotextiles |  | MMA-DES-DNG-E1-10686 Clause 5.22 TNZ F/7 2003 |  | Inspection | Ongoing |  | A minimum lap of 500mm shall be provided with the interface of any earthworks geotextile and any geotextile required in drainage trenches. All geotextile laps shall be orientated away from the direction of flow | H | W |  |  | Onsite Checklist Manufactures Certificate
2.0 Construction
2.1.0 Trench Excavation
2.1.1 | Trench Subgrade |  | MMA-DES-DNG-E1-10686 Clause 6.3 NZS 4402 Test Method 6.5.2 |  | Testing trench foundation material to assess is undercut is required. Scala penetrometer test as per NZS4402.6.5.2:1988 for non-cohesive materials. Table 18 The CBR value of the subgrade soils shall also be measured using the in-situ CBR test in accordance with NZS4402 Test 6.1.3. | 2 nos. Dynamic Cone Penetrometer tests / 5m of trench 1 per ancillary structure |  | 1- Pipe cover to permanent road subgrade greater 1.0 m - CBR >5% 2- Pipe cover to permanent road subgrade between 0.3m and 1.0 m - CBR >=8% 3- Pipe cover to permanent road subgrade less than 0.3m - CBR >=10% 4- Beneath temporary construction haul roads - CBR >=10% | H | W |  |  | Dynamic Cone Penetrometer Test Report
2.1.2 | Trench Benching |  | MMA-CON-CMA-ITP-31067 (around CU17 using the same design slope (0.5H:1V) as the finished geo slope) |  | 1.5m benches to be constructed starting from rock face | Daily |  |  | H |  |  |  | Onsite Check List
2.2.0 Pipe Bedding and Construction
2.2.1 | Construction of embedment side zones using AP20 |  | MMA-DES-DNG-E1-10686 Clause 6.4 AS/NZS 3725 |  | Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; | Two test “sets” per layer, 10m evenly spaced intervals on combined lifts upto 300mm lift |  | HS2 - Min 90% MDD HS3 - Min 95% MDD | W | W |  | I | Test Report
2.2.2 | Construction of Overlay Zone |  | MMA-DES-GEO-E1-SPC-3859 |  | Test 4.2.1 Nuclear Densometer Direct Mode or NZS 4407:1991 or Test 4.2.2 Nuclear Densometer Backscatter Mode and NZS 4407:1991; Undrained shear Strength | 1no NDM and 1no Shear Vane Test per 20m max canters at 300mm lifts |  | Min 92% Avg 95% MDD Average >150 kPa, All tests >120 kPa | W | W |  | I | NDM Test Report
2.2.3 | Construction of pipe |  | MMA-DES-DNG-E1-10686 Clause 5.9.3 AS/NZS 3725 AS/NZS 4058 |  | Visual test prior to backfill above the side zones – line and level, correct installation, and joints are all sealed. | Review every 10m and witness every 25m |  | Reinforced concrete pipes and pipe fittings shall be installed and marked in accordance with AS/NZS 3725 and AS/NZS 4058. Where required, jointing detail for elastomeric joints between pipe lengths shall be in accordance with AS 1646. Vertical Tolerance are as follows: 1- Pipes ≤ 1% grade: +/- 10mm variance 2- Pipes > 1% grade: +/- 20mm variance | W | W |  | I | Test report
2.2.4 | Construction of Wingwalls |  | MMA-DES-DNG-E1-10686 Clause 5.20 |  | Wingwalls shall be constructed on a compacted, 150 mm layer of AP65 granular material. Jointing between the connecting pipe and the back of the wingwall shall be completed using mass concrete. Visual inspection of joints between pipe and wingwall | Each Wingwall |  | Min 92% Avg 95% MDD | W | W |  | I | Test report Onsite Check sheet
2.2.5 | Construction of Antiseep Collars |  | MMA-DES-DNG-E1-10686 Clause 4.7 MMA-DES-DNG-E1-DRG-4052 |  | Antiseep collars to be embedded 200mm horizontally into side of trench and 400mm below base of trench. To be located every second pipe joint. The collars shall be constructed using 25 MPa concrete. | Each Anti Seep Collar |  | Accepted by DSR | W | H |  |  | DSR Inspection (Pre-Pour) Pre-Pour Check sheet Concrete Dockets Concrete Test results
2.2.6 | Construction of Cut Off Toes |  | MMA-DES-DNG-E1-10686 Clause 5.11 MMA-DES-DNG-E1-DRG-4070 |  | Cut off Toe to be embedded 1m (or note 4) from top of wingwall base, to be constructed as per IFC Drawings | Cut Off Toe |  | The wingwall cut off toe detail shall be installed at the foot of the upstream wingwall | W | H |  |  | Pre-Pour Check sheet Detail Sheets
2.2.7 | Construction of Inlet/Outlet Channels |  | MMA-DES-DNG-E1-DRG-4080, 4084 & 4093 |  | DSR to inspect geotextiles before rip - rap is laid. Max drop heights to be adhered to when placing rip-rap | Each Channels |  | Accepted by DSR | W | W |  |  | Geotextile Installation Check Sheet
2.2.8 | Fish Passage |  | MMA-DES-DNG-E1-10686 Clause 4.9 & 5.32 MMA-DES-DNG-E1-DRG-4060, 4061, 4080 & 4084 |  | 25% embedment depth with meandering low flow path from void filled riprap. Spat ropes for CU-17 | Review every 10m and witness every 25m |  | Accepted by DSR | W | W |  |  | Onsite Check sheet
2.2.9 | Construction of Safety Rail |  | MMA-DES-E1-DRG-4092 |  | Constructed as per IFC Drawings | Each Fence |  | Accepted by DSR | W | W |  |  | Onsite Check sheet
3.0 Post Construction
3.1 | Survey/as-builts |  | MMA-DES-DNG-E1-10686 Clause 6.5 |  | As built survey of coordinates and invert levels, structures, and pipe ends | Every 100m |  | Departure from the design level on the pipeline must not exceed 20 mm Departure from the design grade of the pipeline must not exceed 0.1% | H | R |  |  | Survey As-built Data
3.2 | Post Construction CCTV inspection |  | MMA-DES-DNG-E1-10686 Clause 6.5 NZ Pipe Inspection Manual |  | Check conformance with the specification and assess the asset condition post construction | For all pipelines > 225 mm Diameter At completion of trench backfill of minimum 5 m fill prior to final surfacing |  | Refer to NZ Pipe Manual Tables 4.4 & 4.6 | H | R |  |  | CCTV log Report as per the standard
Note on I48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Whats the purpose of this Fill 12 & 13 - can we delete this red text? Reply: Not sure have removed
Note on K48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this being done? Reply: Will be done alongside 2.1.3
Note on D60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added in TARP to all these rows