## Rock Armouring & Bulk Filling
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | G1202A - Waikaretaheke Overslip #3 |  | CPS Approver | Quality Approver | CPS Eng. | Robert Loomes
|  |  |  | Procedure: | Rock Armouring & Bulk Filling |  | Name / Signature | Name / Signature | Site Engineer
[7 empty] | Robert Lomes |  | Quality Eng. | Eddy Mardle
Inspection & Test Plan / Checklist
Lot No: G1202A |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEG-SH38-HAWKESBAY/ES3qCup35rBNqJf0bUFRkC8BpQO-dTZgqN1_SQYCHVXt0w?e=ts4iwu |  | Compliance with Work Instructions and Specifications
Detailed Location: -SH38 RS161 RP7.171-7.201
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Set out lateral extents of buttress. Geotech Engineer to confirm extent of works | Prior to commencement | Inspection | Fault ID 530 - Underslip Recovery Remediation Design Report | Survey receipt / sketch markup | Site Engineer | Geotechnical Site Engineer (CPS)
2 | Survey Setout | H | The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion | Prior to commencement | Inspection | Fault ID 530 - Underslip Recovery Remediation Design Report | Sketch | Site Engineer | Geotechnical Site Engineer (CPS)
3 | Excavate to Sub-Grade | H | Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation | Per area as required | Inspection by the Geotechnical Design Manager | Fill foundation must be approved, in writing, before filling commences | CS-4100 Subgrade Approval Checksheet | Site Engineer | Geotechnical Site Engineer (CPS)
4 | Excavate to Sub-Grade | W | Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review. | Per area as required | Scala Penetrometer | >= 1 test per 10 linear metres, where access is practical and available | Engineer or Lab Test Report | Site Engineer | Geotechnical Site Engineer (CPS)
5 | Material Compliance Testing | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | a. GRADATION D85/D15 = 1.9 b. D85 690 (MAX) AND 590 (MIN) c. D15 390 (MAX) AND 275 (MIN) |  | Site Engineer | Geotechnical Site Engineer (CPS)
6 | Material Compliance Testing | W | Rock Construction Material | 1 test per 1 000m3 | Lab Testing | D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3 | Lab Test Report | Site Engineer
7 | Material Compliance Testing | W | Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
8 | Material Compliance Testing | W | Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
9 | Material Compliance Testing | H | Bulk Construction Material | 1 test SET per 1 000m3 | Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve) | All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel). | Lab Test Reports | Site Engineer | Geotechnical Site Engineer (CPS)
10 | Geotextile Placement - Backface | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection |  | Photo's | Site Engineer
11 | Backfilling of Engineered Fill Embankment | W | Engineered bulk construction material 250mm lifts with material and regular compaction testing | 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill). | Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer. | 95% of MDD or clegg equivalent | Lab Test Reports | Site Engineer | Geotechnical Site Engineer (CPS)
12 | Construction of Engineered Fill Embankment | H | Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap | Prior to commencement | Visual Inspection | ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL. | Photo's | Site Engineer | Geotechnical Site Engineer (CPS)
13 | Geotextile Placement - Frontface | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection |  | Photo's | Site Engineer
14 | Riprap Placement | W | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photo's | Site Engineer | Geotechnical Site Engineer (CPS)
15 | Tie in to existin swales | W | Ensure drainage swales are insatlled to tie in with existing swales to esnure drainage flows correctly | Daily visual check | Visual Inspection | Fault ID 530 - Underslip Recovery Remediation Design Report | Photos | Site Engineer
16 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review. Red line mark up notes of design plan. | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
17 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on N14: Robert Loomes: Rows in yellow added 26/01 regarding testing and control of bulk material
Note on F16: Insert Frequency here
Note on H16: List Tests required from Spec & PRs here with criteria for a passing test - use multiple rows if required
Note on F19: Insert Frequency here