## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling
section | Details
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | Records - Survey receipt / sketch markup
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | Records - Sketch
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Excavate to Sub-Grade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation.
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Excavate to Sub-Grade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
label | Records - Engineer or Lab Test Report
checkpoint | 5 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - a. GRADATION D85/D15 = 1.9
label | b. D85 690 (MAX) AND 590 (MIN)
label | c. D15 390 (MAX) AND 275 (MIN)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material
label | Frequency - 1 test per 1 000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | Records - Lab Test Report
checkpoint | 7 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 8 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 9 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Bulk Construction Material
label | Frequency - 1 test SET per 1 000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve)
label | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
label | Records - Lab Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Geotextile Placement - Backface
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 11 - Backfilling of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
label | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
label | Conformance Criteria - 95% of MDD or clegg equivalent
label | Records - Lab Test Reports
checkpoint | 12 - Construction of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL.
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Geotextile Placement - Frontface
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 14 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 15 - Tie in to existin swales
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure drainage swales are insatlled to tie in with existing swales to esnure drainage flows correctly
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | Records - Photos
checkpoint | 16 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review. Red line mark up notes of design plan.
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 17 - Completion Sign Off From Fields Below
label | Records - Signatures