## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Pre and Post-Pour Checklist |  |  |  |  | Yes | Pre and Post-Pour Checklist | 94368965-4511-459d-94f6-05b4d0012452
checkpoint-group |  |  | section | Pump Set Up Items
checkpoint-status |  |  | checkpoint | Park concrete pump in location and setup within designated area. Line set-up not to disturb formwork, reinforcement and starter bars. Communication between operator and formwork in place
checkpoint-status |  |  | checkpoint | Has all pipelines/rubbers, safety chains, and locking pins been adequately and securely fitted
checkpoint-status |  |  | checkpoint | Has the placing boom movement been coordinated with the crane crew (if applicable)
checkpoint-group |  |  | section | Pre Pour
checkpoint-status |  |  | checkpoint | OHS&R and Environmental Measures: All safety, PPE requirements in place. MSDS sheets supplied. All documentation is current as per Project OHS&R Plan and EMP Plan. All Site personnel have been inducted. Environment Controls in Place.
checkpoint-status |  |  | checkpoint | Is there sand and plastic membrane in place where required in accordance with Structural specification and AS 3600?
checkpoint-status |  |  | checkpoint | Has the formwork been cleaned sufficiently to take concrete placement? Ensure the formwork and other trades have cleaned areas in accordance with Structural Specification and AS 3600.
checkpoint-status |  |  | checkpoint | Are all movement joints are placed in accordance Structural Specification
checkpoint-status |  |  | checkpoint | Has the laser been calibrated to the required level
checkpoint-status |  |  | checkpoint | What percentage of the element is ready for GB prior of the commencement of the pour
checkpoint-status |  |  | checkpoint | Has all trades completed works in the designated pour area? If not who?
checkpoint-status |  |  | checkpoint | Are all barriers in place to prevent falling from heights? Has all inserts, blockouts, penetrations, rebates, hobs been securely fixed? If NO, who has been notified?
checkpoint-status |  |  | checkpoint | Is there adequate access ways to work areas and in deep sections of casting elements?
checkpoint-status |  |  | checkpoint | Latest construction drawings checked prior to pour? Please attach if applicable
checkpoint-status |  |  | checkpoint | Is there sufficient cover between the reinforcement and formwork for concrete to be placed? If NO, who has been notified?
checkpoint-status |  |  | checkpoint | Is there enough access in tight areas i.e. near hobs, penetrations for concrete hand-equipment (trowels, etc.) to sufficiently finish the concrete?
checkpoint-status |  |  | checkpoint | Has concrete testing been booked for this pour element?
holdpoint |  |  | signoff | General Beton & RCC Sign Off
checkpoint-group |  |  | section | Post Pour
checkpoint-status |  |  | checkpoint | Has the concrete been placed at the correct RL, datum point checked and verified and in layers as per AS 3600?
checkpoint-status |  |  | checkpoint | Has all vibration of concrete been undertaken as per Structural Engineer's requirement and AS 3600?
checkpoint-status |  |  | checkpoint | Has all curing and concrete protection been undertaken?
checkpoint-status |  |  | checkpoint | Has all cleaning in regards to pump hoppers and excess concrete from the pour location been cleared?
checkpoint-status |  |  | checkpoint | Has an as-built been issued? If no, who is to issue this?
checkpoint-status |  |  | checkpoint | Has the required floor level finish been achieved?
checkpoint-status |  |  | checkpoint | Has all areas been checked for non-conformance elements?
checkpoint-status |  |  | checkpoint | Attach Post-Pour 3m straight-edge check annotated drawing (Only applicable for slabs).
holdpoint |  |  | signoff | General Beton & RCC Sign Off