## OHLE
ConQA Team Notes:
Document Title: |  | ITP-037-RAIL-Brunt-OHLE Structure Installation
ITP Description: |  | OHLE Structure Installation
Discipline (e.g. CIV/STR/RAIL) |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2023-05-16
ITP prepared by: |  | Nikhil Siram
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP to be used in Brunt Rd & Camms Rd Projects Only
Inspection & Test Plan - OHLE Installation
|  |  | Document No.: ITP-037-RAIL-Brunt-OHLE Structure Installation | [6 empty] | Revision: | 0
[10 empty] | Date: | 2023-05-16
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Responsible person | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Overhead Line Electrification | L1-CHE-STD-011(1) MEST 000002-02(1) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway | VRIOGS 001 AS 4100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Electrical Networks Standard Electrical Networks Principles and Performance | L1-CHE-STD-015(1) MEST 000002-06(1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Procurement Overhead Wiring Structural Steel | Overhead Wiring Design Drawings Approved Shop Drawings | Structural Steel dimensions and bolt hole confifuration fabricated as per approved shop drawings. Galvanising to be inspected and no defects present. Enter: Teambinder Material Approval number [free text box] | Visual inspection and measurement | Upon Completion of Fabrication and upon delivery on site | HP | MRPA | MRPA Engineer | ConQA Hold Point Release
2.2 | Procurement Overhead Wiring Small Parts Steel and conductor wires | Relevant MTM Standard Drawings | Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings. | Visual inspection and measurement | Upon delivery on site | HP | MRPA | MRPA Engineer | This ITP Signed Off
2.3 | Procurement Materials delivered/collected to stores/Site. | Contractor - Site Material Control procedure. Cat5 Material received -Brunt and Camms Tracking sheet | Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA | Document Review | Once for each supplier, prior to works start | IP | MRPA Issue CAT5 Receive | MRPA | This ITP Signed Off
3 | Preliminaries - Procedures & Documentation
3.1 | Produce Work Package Plan | Work Package Plan WAP_BR_184 | Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner. | Document Review | Prior to Works Start TBC in accordance with MTM Standards | HP | MRPA/ CAT5 | MRPA/CAT5 Engineer | This ITP Signed Off
4 | Pre-construction Activities
4.1 | Approval of IFC drawings | Contractor Design Management procedure. MRP-DPK-089-00-ETN | Ensure correct and most recent revision of IFC design drawings are used for construction. | Document/ Drawings Review | Prior to Works and at regular intervals. TBC in accordance with MTM Standards | HP | MRPA/ CAT5 | MRPA/CAT5 Engineer | This ITP Signed Off
4.3 | Task Specific Permits | Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS | Ensure all task and activities have relevant permits issued and received. Task Permits to be generated and signed off by appointed person. Task specific documents - MTM to issue permit to enter/Isolation permits etc. | Visual Document Review | Each Task prior to works start. TBC in accordance with MTM Standards | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
4.4 | Cantilever assembled. | Cantilever assembled as per IFC design. | Relevant checks followed and adhered to-Cantilever Fabrication Check sheet. | Visual Document Review | Each Task prior to works start. TBC in accordance with MTM Standards | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
5 | Construction Activities
5.1 | Cantilever installed. | Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1) | Work instructions in accordance to IFC design | Measure Visual | Each OHLE Structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
5.2 | Install SPS to correct height / position relative to track | Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway | Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly. | Measure Visual | Each OHLE Structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
5.3 | Cantilever checked once installed. | Cantilever checked as per IFC design drawings/MTM design range.Completed check sheet.CAT5/OHLE/CHK002 | Supervision checking to ensure that equipment is installed correctly. | Measure Visual | Each OHLE Structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
5.4 | Installation of wire supports at the correct height and stagger. | Install as per design drawings. | Engineer checking to ensure that equipment is installed correctly. | Visual | Each OHLE BWA structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
5.5 | Install to correct tension | Install as per design, use span/ambient temp. tension charts. | Engineer checking to ensure that equipment is installed correctly. | Measure Visual | Prior termination | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
6 | Post-construction Activities
6.1 | Defects/Temporary Works | IFC wiring layouts, cross sections and design drawings. | Ensure all Defects/Temporary works are capture and closed out correctly. Defect list to be provided at the end of Occo identifying planned work to rectify Attach Design mark up, Defect list, temporary bond register, and approved TW design | Document Review Visual | Each OHLE Structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
6.2 | Relevant documentation readily available. (As-built Survey) | As built drawings and check sheets to accordance to MTM Design spec. | Ensure delivery of relevant documentation to client. As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets. . | Document Review Visual | Each OHLE Structure | IP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
6.3 | Non-conformance Report (NCR) Closure | MTM Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP | CAT5/ MRPA | MRPA/CAT5 Engineer | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /