## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-037-RAIL-CAMMS-OHLE Structure Installation | itp |  |  |  | Yes | ITP-037-RAIL-CAMMS-OHLE Structure Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-037-RAIL-CAMMS-OHLE Structure Installation
label | ITP Description: OHLE Structure Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): RAIL
label | Revision Number: 0
label | Revision Date: 16/05/2023
label | ITP created by: Nikhil Siram
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Overhead Line Electrification
label | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
label | Reference - VRIOGS 001 AS 4100
checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
label | Reference - L1-CHE-STD-015(1) MEST 000002-06(1)
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Procurement Overhead Wiring Structural Steel
note | Reference - Overhead Wiring Design Drawings, Approved Shop Drawings
note | Acceptance Criteria - Structural Steel dimensions and bolt hole confifuration fabricated as per approved shop drawings. Galvanising to be inspected and no defects present.
textbox | Enter: Teambinder Material Approval number
note | Method - Visual inspection and measurement
note | Frequency - Upon Completion of Fabrication and upon delivery on site
note | Category - HP
note | Responsibility - MRPA
note | Responsible person - MRPA Engineer
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Procurement Overhead Wiring Small Parts Steel and conductor wires
note | Reference - Relevant MTM Standard Drawings
note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
note | Method - Visual inspection and measurement
note | Frequency - Upon delivery on site
note | Category - HP
note | Responsibility - MRPA
note | Responsible person - MRPA Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Procurement Materials delivered/collected to stores/Site.
note | Reference - Contractor - Site Material Control procedure. Cat5 Material received -Brunt and Camms Tracking sheet
note | Acceptance Criteria - Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA
note | Method - Document Review
note | Frequency - Once for each supplier, prior to works start
note | Category - IP
note | Responsibility - MRPA Issue, CAT5 Receive
note | Responsible person - MRPA
note | Verifying Documents - This ITP Signed Off
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Produce Work Package Plan
note | Reference - Work Package Plan, WAP_BR_184
note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
note | Method - Document Review
note | Frequency - Prior to Works Start, TBC in accordance with MTM Standards
note | Category - HP
note | Responsibility - MRPA/CAT5
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - Approval of IFC drawings
note | Reference - Contractor Design Management procedure. MRP-DPK-089-00-ETN
note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
note | Method - Document/Drawings, Review
note | Frequency - Prior to Works and at regular intervals. TBC in accordance with MTM Standards
note | Category - HP
note | Responsibility - MRPA/CAT5
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Task Specific Permits
note | Reference - Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received. Task Permits to be generated and signed off by appointed person. Task specific documents - MTM to issue permit to enter/Isolation permits etc.
note | Method - Visual, Document Review
note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 4.4 - Cantilever assembled.
note | Reference - Cantilever assembled as per IFC design.
note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
note | Method - Visual, Document Review
note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Cantilever installed.
note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
note | Acceptance Criteria - Work instructions in accordance to IFC design
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Install SPS to correct height / position relative to track
note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Cantilever checked once installed.
note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
note | Reference - Install as per design drawings.
note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
note | Method - Visual
note | Frequency - Each OHLE BWA structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Install to correct tension
note | Reference - Install as per design, use span/ambient temp. tension charts.
note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
note | Method - Measure, Visual
note | Frequency - Prior termination
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
section | 6. Post-construction Activities
checkpoint | 6.1 - Defects/Temporary Works
note | Reference - IFC wiring layouts, cross sections and design drawings.
note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly. Defect list to be provided at the end of Occo identifying planned work to rectify. Attach Design mark up, Defect list, temporary bond register, and approved TW design
note | Method - Document Review, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
note | Acceptance Criteria - Ensure delivery of relevant documentation to client. As built drawings and check sheets. CAT5/OHLE/CHK/002 check sheets.
note | Method - Document Review, Visual
note | Frequency - Each OHLE Structure
note | Category - IP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
note | Reference - MTM Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP
note | Responsibility - CAT5/MRPA
note | Responsible person - MRPA/CAT5 Engineer
note | Verifying Documents - This ITP Signed Off
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP