## Breakdown
William Sanders (PBI Height Safety)
B05
Façade QA
Roof
Area A (Grid A-E & 1-3)
[5 empty] | Anchor Points - Anchor Point Installation | FC - S - Anchor Points - Anchor Point Installation
[5 empty] | Anchor Points - Intermediate, Corner and End Plate Installation | FC - S - Anchor Points - Intermediate, Corner and End Plate Installation
[5 empty] | Anchor Points - Static line installation | FC - S - Anchor Points - Static line installation
Area B (Grid A-E & 3-5)
[5 empty] | Anchor Points - Anchor Point Installation | FC - S - Anchor Points - Anchor Point Installation
[5 empty] | Anchor Points - Intermediate, Corner and End Plate Installation | FC - S - Anchor Points - Intermediate, Corner and End Plate Installation
[5 empty] | Anchor Points - Static line installation | FC - S - Anchor Points - Static line installation
|  | Completion documents BCO10332878 |  |  |  | CST - S - Completion Documents

## Checklists
Type | Name
checklist-flat | FC - S - Anchor Points - Anchor Point Installation
checkpoint | Roof structure condition checked and acceptable. No rust or corrosion on roof, purlins or structure.
checkpoint | Positioning and installation of the plinth is correct and acceptable
checkpoint | Roof substrade is checked and acceptable and no visible damages.
checkpoint | Anchor plate alignment is correct. Fixing holes are aligned with fall of roof
checkpoint | Minimum of 2 toggles are installed. Toggles deployed fully at 90° to threaded bar and confirmed.
checkpoint | Anchor plate cover is installed.
checkpoint | Dome screws and anchor plate screws fixed to structure. Steel/ timber: 14 gauge tek screw and minimum of 4 screw fixings per anchor (2 holes), sealant and Neoprene washer installed. Sea spray zoning requires the screws to be stainless steel
checkpoint | Anchor ID label fixed on to anchor plate with all information noted - Installer info, Limitations of use, Last certification date, Next recertification date and Rated for single person use (15kN)
checkpoint | Anchor point installation completed and acceptable
Type | Name
checklist-flat | FC - S - Anchor Points - Intermediate, Corner and End Plate Installation
checkpoint | Roof structure condition checked and acceptable. No rust or corrosion on roof, purlins or structure.
checkpoint | Positioning and installation of the plinth is correct and acceptable
checkpoint | Roof substrade is checked and acceptable and no visible damages.
checkpoint | Anchor plate alignment is correct. Fixing holes to be aligned with fall of roof
checkpoint | Minimum of 2 toggles are installed. Toggles deployed fully at 90° to threaded bar and confirmed.
checkpoint | Anchor plate cover is installed.
checkpoint | Intermediate Plates: Dome screws and anchor plate screws fixed to structure. Steel/ timber: 14 gauge tek screw and minimum of 4 screw fixings per anchor (2 holes), sealant and Neoprene washer. End Plate and Corner Plate: Dome screws and anchor plate screws fixed to structure. Steel/ timber: 14 gauge tek screw and minimum of 10 screw fixings per anchor (2 holes), sealant and Neoprene washer installed. Sea spray zoning requires the screws to be stainless steel.
checkpoint | Static line components attached to static line plates - Tensioner, Shock Absorber and End Swage.
checkpoint | Installed 8mm SS 7x7 cable to static line plates. Crimped the cable to the end of the static lines. 5 Crimps per end. Tensioned the static lines with the tensioner and tension indicator.
checkpoint | Anchor ID label fixed on to anchor plate with all information noted - Installer info, Limitations of use, Last certification date, Next recertification date and Rated for single person use (15kN)
checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
Type | Name
checklist-flat | FC - S - Anchor Points - Static line installation
checkpoint | Line tensioner and indicator checked and acceptable. Attachment to end stanchion secured. Lock in pin cir-clip secured. Tension indicator disc can be rotated manually. Swaged cable termination secured, no evidence of slipping. All locknuts and fixings secured. No visible damage to unit/structure.
checkpoint | Anchorage cable installation checked and acceptable. No cuts or frays to cable. Cable correctly tensioned and not touching the roof deck. Securely attached to end stanchions. No visible damage.
checkpoint | System traveller checked and acceptable. Slide latch operates freely. Gap between tongue & shuttle inner casing when closed and latched with karabiner, 5mm maximum. Karabiner fits securely when slide latch closed. Karabiner gate lock device operates securely. No visible damage to unit.
checkpoint | Static line installation completed and acceptable
Type | Name
checklist-flat | CST - S - Completion Documents
checkpoint | PS3s(BCO10332878), warranties, user manuals and any other documents attached
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS