## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Balustrades |  |  |  |  | Yes | Balustrades | 5b951393-ad20-48d8-875b-b699a5100e7c
checkpoint-group |  |  | section | Incoming Material Inspection
checkpoint-status |  |  | checkpoint | Types of material delivered
label | 66b8d4de-7d49-5b88-8e19-1e8cd3f52eeb |  | note | Balustrades
label | 1450c428-4f3a-5c23-9388-394bbbb96672 |  | note | •125x25 TOP RAIL
label | 5573f767-bac4-506e-bc8a-03fc7177a652 |  | note | 45x35 Glazing Channel
label | b0245977-528a-5383-89ab-a8bb3c8cd78b |  | note | 50x50 Posts
label | a67239b4-4daa-5a8c-8563-1e36d52b0149 |  | note | 12.38mm Grey Laminated Glass
checkpoint-status |  |  | checkpoint | Confirm location setout, setting out check
checkpoint-status |  |  | checkpoint | Cleanliness of floor
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Apply Set Out Marks Core Drill
checkpoint-status |  |  | checkpoint | Core Drill Set Out Marks and remove core holes
checkpoint-status |  |  | checkpoint | Fill Core holes With non shrink grout
checkpoint-status |  |  | checkpoint | Install balustrades as per set out
checkpoint-status |  |  | checkpoint | Protection - Top Only
checkpoint-status |  |  | checkpoint | Install glazing when balustrades set or when builder requires
checkpoint-status |  |  | checkpoint | Quality checks
checklist-sectioned |  |  | checklist | Louvres |  |  |  |  | Yes | Louvres | d6c4bfce-dce9-4bf8-bb86-4058c8fe1ecd
checkpoint-group |  |  | section | Incoming Material Inspection
checkpoint-status |  |  | checkpoint | Types of material delivered
label | 615d1f10-9322-5ef9-8dcb-a7cef17dffbf |  | note | Feature Fins
label | ec672fc1-102b-5513-9f99-2670fd703fac |  | note | 150 x 50mm RHS
label | 67f378f6-cf8c-5d7f-8dba-42918402c9d6 |  | note | 100 x 50mm U channel
checkpoint-status |  |  | checkpoint | Confirm location setout, setting out check
checkpoint-status |  |  | checkpoint | Cleanliness of floor
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Apply set out marks for U channels
checkpoint-status |  |  | checkpoint | Hammer drill set out marks
checkpoint-status |  |  | checkpoint | Install U channels & fix to slab
checkpoint-status |  |  | checkpoint | Install RHS & fix to U channel as per set out
checkpoint-status |  |  | checkpoint | Protection
checkpoint-status |  |  | checkpoint | Quality Checks