## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Chipseal Surfacing | itp |  |  |  |  | ITP - Chipseal Surfacing
section | Design
checkpoint | Treatment Selection
label | VERIFICATION ACTIVITY - Physical / Site video/photographic record
label | METHODS OR REFERENCE - Asset Team - Base Preservation
label | FREQUENCY - Annually Pre-reseal
label | ACCEPTANCE CRITERIA - Documented approval from at time of Tender -Team/Client
label | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client Approval
label | RECORDS - Approved Seal Designs
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Chipseal Design
label | VERIFICATION ACTIVITY - Peer review by Authorised Seal Design Approver
label | METHODS OR REFERENCE - Chipsealing in NZ
label | FREQUENCY - One per design prior to commencing onsite
label | ACCEPTANCE CRITERIA - Design meets requirements of P17
label | HOLD / WITNESS POINT - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
label | RECORDS - Peer Reviewed Seal Designs
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials Testing
checkpoint | Size (Grades 2-5) & Shape (Grades 2-4)
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6
label | FREQUENCY - 1/500m3
label | ACCEPTANCE CRITERIA -
label | Size (ald mm)
label | – G2 9.5-12.0
label | – G3 7.5-10.0
label | – G4 5.5-8.0
label | – G5 Report
label | Shape
label | – AGD/ALD Ratio G2,3,4 = 2.25 max
label | – G2,3,4 = min 98% with 2+ broken faces
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
checkpoint | Cleanliness (Grades 2-6)
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6
label | FREQUENCY - 1/500m3
label | ACCEPTANCE CRITERIA -
label | Cleanness value
label | ○ G2 = 89
label | ○ G3 = 87
label | ○ G4 = 85
label | ○ G5 & G6 Report only
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
checkpoint | Compatibility (Multi Layered seals)
label | VERIFICATION ACTIVITY - Comparison Of Chip ALD
label | METHODS OR REFERENCE - Chipsealing in New Zealand NZTA (NZTA 2005)
label | FREQUENCY - 11.5, 7.2
label | ACCEPTANCE CRITERIA - Two Coat Seal Aggregate Compatibility
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
checkpoint | Bitumen Distributor
label | VERIFICATION ACTIVITY - IANZ Lab E/2 Results
label | METHODS OR REFERENCE - Code of Compliance
label | FREQUENCY - Annual
label | ACCEPTANCE CRITERIA - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
label | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client - Engineer Witness
label | RECORDS - RNZ E2 Certificate
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Emulsion/PME Testing
label | VERIFICATION ACTIVITY - Lab Testing
label | METHODS OR REFERENCE - Manufacture Specification
label | FREQUENCY - Per Emulsion/Bitumen Production Batch
label | ACCEPTANCE CRITERIA - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Road Science
section | Surface Inspection
checkpoint | Surface Texture - Measurement
label | VERIFICATION ACTIVITY - Sandcircle Measurement
label | ○ ARRB Hawkeye or NZTA HSD
label | METHODS OR REFERENCE - NZTA T/3
label | FREQUENCY - At time of Seal Inspection
label | ACCEPTANCE CRITERIA - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Sandcircle Data
label | ○ Hawkeye Data
label | ○ High Speed Data
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
checkpoint | Pre Seal Survey
label | VERIFICATION ACTIVITY - Downer Survey or MS Forms Pre Reseal Inspection
label | METHODS OR REFERENCE - Downer Survey or MS Forms Pre Reseal Inspection
label | FREQUENCY - At time of Seal Inspection
label | ACCEPTANCE CRITERIA - Record & any noted issues / Client
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Lucidity
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
checkpoint | Construction Compliance testing
label | FREQUENCY - 24 hours in advance of seal construction commencement
label | ACCEPTANCE CRITERIA - Confirmation from renewals manager all testing has met requirements
label | HOLD / WITNESS POINT - Hold Point
label | RECORDS - Email Confirmation
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Seal Construction
checkpoint | Go/No Go Survey
label | VERIFICATION ACTIVITY - Visual, Zeus, Iris
label | METHODS OR REFERENCE - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
label | FREQUENCY - Prior to sealing on each site
label | ACCEPTANCE CRITERIA - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Lucidity
label | RESPONSIBLE PERSON - Supervisor / Foreperson / QA
checkpoint | Pavement Markings/RRPMs
label | VERIFICATION ACTIVITY - Tagging of existing Pavement Markings, Removal of RRPMs
label | METHODS OR REFERENCE - Pavement Marking Set Out Sheet, CBP
label | FREQUENCY - Prior to sealing on each site
label | ACCEPTANCE CRITERIA - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - None
label | RESPONSIBLE PERSON - Foreperson / QA
checkpoint | Road Furniture & Sumps protected
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - Crew Breifing Plan / Visual
label | FREQUENCY - Prior to sealing on each site
label | ACCEPTANCE CRITERIA - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - None
label | RESPONSIBLE PERSON - Foreperson
checkpoint | Surface Condition/Temp
label | VERIFICATION ACTIVITY - Physical / Visual Inspection
label | METHODS OR REFERENCE - Visual / NZTA T/3
label | FREQUENCY - Prior to sealing on each site
label | ACCEPTANCE CRITERIA - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - None
label | RESPONSIBLE PERSON - Foreperson / QA
checkpoint | Stockpiles
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - CBP
label | FREQUENCY - Each Stockpile
label | ACCEPTANCE CRITERIA - Correct Source, Grade and quantity. Uniquely Identified.
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Sealing Data Docket
label | RESPONSIBLE PERSON - Foreperson
checkpoint | Spraying
label | VERIFICATION ACTIVITY - Paper Start and Finish all runs
label | METHODS OR REFERENCE - Spray Runs
label | FREQUENCY - All Runs
label | ACCEPTANCE CRITERIA - Mark out start / Finish
label | HOLD / WITNESS POINT - Witness Point
label | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
checkpoint | Sealing
label | VERIFICATION ACTIVITY - Longitudinal Joints out side of wheel tracks
label | METHODS OR REFERENCE - Spray Runs
label | FREQUENCY - All Runs
label | ACCEPTANCE CRITERIA - Mark out lane lines by construction team
label | HOLD / WITNESS POINT - Witness Point
label | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
checkpoint | Binder Application Rate
label | VERIFICATION ACTIVITY - Tank Level dips prior to and after spray run
label | METHODS OR REFERENCE - Dipstick
label | FREQUENCY - At Beginning of the day
label | ○ After 1st spray run of site
label | ○ After last spray run of site
label | ○ At end of tank prior to loading
label | ACCEPTANCE CRITERIA - Quantities used to be within the desired tolerance of design Spray Rate
label | HOLD / WITNESS POINT - Mandatory HOLD POINT
label | RECORDS - Spray Sheets
label | RESPONSIBLE PERSON - QA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Chip Spread Rate
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - Crew Briefing Plan/Visual
label | FREQUENCY - On going whilst seal being constructed
label | ACCEPTANCE CRITERIA - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Data Docket
label | RESPONSIBLE PERSON - QA/Foreperson
checkpoint | Removal of Surplus Chip
label | VERIFICATION ACTIVITY - Physical / Visual
label | METHODS OR REFERENCE - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
label | FREQUENCY - At conclusion of positive traffication within 48 hours
label | ACCEPTANCE CRITERIA - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Post Seal Inspection
label | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
section | Post Seal Construction
checkpoint | Post Seal Traffic Management
label | VERIFICATION ACTIVITY - Physical / Visual
label | METHODS OR REFERENCE - As per TMP
label | FREQUENCY - Full length and width of carriageway
label | ACCEPTANCE CRITERIA - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
label | HOLD / WITNESS POINT - Hold Point
label | RECORDS - Zeus or suitable recorded weather data
label | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Post Seal Inspection
label | VERIFICATION ACTIVITY - On Site Visual
label | METHODS OR REFERENCE - Lucidity Post Seal Inpsection
label | FREQUENCY - After sealing is complete
label | ACCEPTANCE CRITERIA - Engineers requirements. Any defects identified, repairs programmed and costs estimated
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - Post Seal Inpsection
label | RESPONSIBLE PERSON - Sealing Contract Engineer / Manager / QA
checkpoint | Asbuilts and RAMM data
label | VERIFICATION ACTIVITY - RAMM Update Sheet
label | METHODS OR REFERENCE - RAMM Database
label | FREQUENCY - After sealing is complete
label | ACCEPTANCE CRITERIA - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
label | HOLD / WITNESS POINT - Witness Point
label | RECORDS - As built information / RAMM Update Sheet
label | RESPONSIBLE PERSON - Sealing Contract Manager/ QA/QE