## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN Rev 1 | itp | ITP - CHIPSEAL RENEWAL INSPECTION TESTING PLAN |  | edab29c4-40a0-4f1d-ba6c-91106dfa89a4
| section | Preliminaries
| checkpoint | 1.01 - PQE
2a8efb71-c07e-5558-9f60-8bedf0e4e67d | note | Material Test Method Requirement - Has all preseal repairs been completed?
db36277c-66e8-560c-ae4c-46fc40d1fd6c | note | Reference Documents - Insert Layer Acceptance ITP No
5d634e2c-0ac7-5e5d-bc38-cdac560ffa1b | note | Material Acceptance Criteria (Method) - Workpack closeout record
6dfa3419-4c55-5cf2-805c-92e9a65724eb | note | Material Test Frequency - Prior to sealing commencing
386b0241-2ff4-562c-9497-74f33ff6ead7 | note | Target Criteria - All underlying layers meets project requirements
26b26df6-80c9-5cd8-9ea8-0a56172e3f99 | note | Action Point Records Required - Hold Point
4791d770-510f-557f-990b-95098293dae7 | note | Responsibility - SE / CE / PM / PQE
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - PQE
6381a9b7-263c-56b2-8df5-f15a51cdcc75 | note | Material Test Method Requirement - Bitumen Sprayer
e57ac68e-b0cc-540d-a1ac-e454c75cf25c | note | Reference Documents - TNZ P3
2b921693-4be5-5dc8-910b-4a0fed4a4c20 | note | Material Acceptance Criteria (Method) - Certification provided
f87b7fbb-b838-5fb1-9b89-390d746b7ef4 | note | Material Test Frequency - Prior to starting
593cdcc9-318e-565d-84ef-d784f8c74199 | note | Target Criteria - Current E/2 Certificate
ee71efea-9091-5f75-849e-d5ba482eaa6a | note | Action Point Records Required - Certificate Sheet
5804a00f-7df1-57ff-a86e-214c9b960ceb | note | Responsibility - SE / CE / PM / PQE
| section | Chip Seal Application
| checkpoint | 2.01 - PQE.
6a6f238e-323a-570b-ab43-248242d70c0c | note | Material Test Method Requirement - Seal Design
706d4f37-0dc5-592e-81bf-c3e19cab58c8 | note | Reference Documents - INSERT SEAL DESIGN
7cd69426-a0c4-5dfd-910a-edfc0c188d04 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
ed77fd80-290b-59de-9317-2859d2b923d2 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
d7287ebe-8a44-5b63-b9b6-de6a416445d1 | note | Target Criteria - Meets project requirements
c062c19f-0aec-533a-bf7b-f44098153af5 | note | Action Point Records Required - Hold Point
ef5009a9-44ae-560e-a963-ec334635fb14 | note | Responsibility - PQE / CE / PM
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.02 - Field
bb9d8ae4-8964-54e1-aadd-dddc70a9f093 | note | Material Test Method Requirement - GO/NO GO Survey
281ed66e-a750-5811-b15c-f6c8d302ea33 | note | Reference Documents - Downer survay sealing Go/NO GO , road science Zeus app & Downer Iris app.
492c3a4a-c3c7-5a5b-b73b-6d30cec36735 | note | Material Acceptance Criteria (Method) - Downers Procedures
fcd04599-5bec-5678-81e5-eeaae74a43f6 | note | Material Test Frequency - prior to sealing on each site
cf42247e-e94e-553f-8d12-379c545c1c8c | note | Target Criteria - Pass on GO/NO GO , Marginal &discussion with contract manager or approval from Rehab manager
a1aba39f-a2b1-5f65-842d-dd332949cbd4 | note | Action Point Records Required - Hold Point
e271a0f6-4cbc-59ad-a897-221f0d0a55ce | note | Responsibility - PQE / CE / PM
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.03 - PQE
b367becb-c924-5be8-a275-cea65ce5a29c | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
1c3a8faa-4e13-53ca-8e53-a90ef413ed04 | note | Reference Documents - Insert Material Testing
3d658994-6bec-5cf9-b3ec-769940a2d7a2 | note | Material Acceptance Criteria (Method) - See PQE
c3b227b6-aaf6-5065-b5d8-a4fa24416431 | note | Material Test Frequency - Prior to construction commencing
6f34686e-653d-5970-bbd7-49ac7f12c4f1 | note | Target Criteria - Material meets project requirements
d5dbb0d5-431a-5b33-ba34-9e6fce2d811f | note | Action Point Records Required - Hold Point
c6b62254-00bc-5c6f-8fea-3ca7e95a7c07 | note | Responsibility - PQE / CE / PM
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Field
9ff5638e-d672-53ca-a553-e9a0848d3bd7 | note | Material Test Method Requirement - Pre-seal Inspection
51c14599-b6b4-5b24-806d-1d442669cf5c | note | Reference Documents - TNZ P3:1995.7
3495d175-e53a-5079-8690-8d7f697cfe23 | note | Material Acceptance Criteria (Method) - Downers Procedures
d3915da8-a274-5eb0-9c51-44eb0072a82d | note | Material Test Frequency - 100% of Surface Prior to sealing
72b129e5-b24e-5216-8ed5-ebd2b911e889 | note | Target Criteria - The surface shall then be swept clean of loose aggregate, dust, dirt and other deleterious matter.
9e5fbfc4-bbe6-56a3-be7e-f1f45a64fda8 | note | ○ Street Furniture and Start and End poitns have been taped and/or masked for overspray
f0a4720a-26cd-5a64-abc7-3432fbf38440 | note | ○ Line marking tags are in place.
b5eecb47-fe9b-51d8-92de-3c071774de01 | note | Action Point Records Required - Hold Point
e39980f9-57c3-5c0a-b7cb-cec194a5e1c8 | note | Responsibility - PQE / CE / PM
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.05 - Field
46860edd-de23-5bee-8c15-3752ee258ace | note | Material Test Method Requirement - Road temp
001b8b3d-742f-53f0-b821-1d2e2b861f1f | note | Reference Documents - TNZ P3:1995.18
9d8668f5-ebb2-53de-aa14-3c11d7314fc4 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
9efc10ea-b80d-5714-801f-ff0db13621bd | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
cdcab9c4-dc7f-5303-b18b-6d3aa70aa3b5 | note | Target Criteria - Air temp >10°C
c912cfca-d91a-5ad0-89f3-fa96ee7ad913 | note | Action Point Records Required - Spray Sheet
eab79de5-3d23-5ec1-8124-8305ab1be4cb | note | Responsibility - SE / CE / PM
| checkpoint | 2.06 - Field
f01a08c0-cde0-597c-b541-b1a51aa753fa | note | Material Test Method Requirement - Application Rate
4790a93f-2c02-5e84-b72f-5eeed0e03fe5 | note | Reference Documents - TNZ P3 : 1995.18
b8562673-11a7-5b5f-b380-641606ac78d9 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
d88d7bae-ff94-5021-b214-26519ed2c2cc | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
6b8ec101-5326-52b5-95e3-828abaecb1ef | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
f52fa8c5-c3b8-5362-b693-9c8cb269c8d2 | note | Action Point Records Required - Spray Sheet
e9d30898-75da-5a93-becb-d8b56891778e | note | Responsibility - SE / CE / PM
| checkpoint | 2.07 - Field
3aafe76a-32e5-5a99-9a5f-1c263238f809 | note | Material Test Method Requirement - Chip spread rate
5001eded-e342-5f9e-b42c-e1aa549ddc7f | note | Reference Documents - TNZ P3: 1995.21
00098d81-0f14-5298-87e2-fc328a40ff02 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
1ed35fff-8d36-54b6-a818-5e3c3d61c94f | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
a5910637-a7df-5667-81f6-2d2990bd323d | note | Target Criteria - Visual checks meets seal design requirements
6d04ef63-bdc8-58fd-8c18-07b7acda6ab0 | note | Action Point Records Required - Witness Point/Spray sheet
63f6ba5f-4a5c-5a32-a4b3-dbb2aa604d28 | note | Responsibility - SE / CE / PM
| checkpoint | 2.08 - Field
666f1e8b-3a73-502e-b867-ff0ee62a79eb | note | Material Test Method Requirement - Rolling Checks
88ae3b1b-1585-5bc5-988d-ef811f683a3d | note | Reference Documents - TNZ P3: 1995.22
a0eed3ca-c1f1-599f-987c-b002abeb6782 | note | Material Acceptance Criteria (Method) - Sealing Record
d42cac64-7c6e-50bc-8d52-db54c90c2ff6 | note | Material Test Frequency - for each sealing site per day
1e22f789-3066-544e-a6a2-c5cc6a640e1d | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
6eba2edd-0a3d-52b7-b1d2-d919e64e67bd | note | Action Point Records Required - Witness Point/Spray sheet
b494cfd0-e326-5a35-adc8-4ce57d7759e2 | note | Responsibility - SE / CE / PM
| checkpoint | 2.09 - Field
605c49a4-a115-52c5-ac68-75ebe8023c57 | note | Material Test Method Requirement - Post-seal Inspection
ddc3154f-225c-5189-b9f1-fce1eb50bcc0 | note | Reference Documents - TNZ P3: 1995
5bdde5fc-d4e8-59b5-a599-7b8eb83412ca | note | Material Acceptance Criteria (Method) - Engineers Inspection
2ed639d7-ef4f-5f80-8917-40b7d28add72 | note | Material Test Frequency - 100% of Site After sealing (within 5 days)
c0e21395-f41e-56da-b126-5eb860329f81 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
a2f34c7f-8177-5c34-a812-fb13d8d93820 | note | ○ Line marking has been reinstated
a4747e55-62d8-5d7d-a74f-bb8b41b80b0c | note | ○ All excess chip has been removed from site
ca3c39b7-006f-54fb-b6a5-93d40cf41983 | note | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
d537749b-40e4-5f69-87a4-01198dced3b0 | note | Action Point Records Required - Hold Point
a25c5ab8-4ce6-511a-881e-24cec60112eb | note | Responsibility - SE / CE / PM / ER
| signoff | AUTHORITY HOLDPOINT
| section | Post Completion
| checkpoint | 3.01 - Field
7c1a2b60-fec7-55d7-8b9b-cfc09137e21c | note | Material Test Method Requirement - Asbuilt and RAMM Data
a88c8179-c342-5eaf-a645-be12fcc9050c | note | Reference Documents - RAMM update sheet
33a55897-f0f2-5231-bfff-adc869a613ff | note | Material Acceptance Criteria (Method) - See Asset Management Information Plan
c48cc83f-5bef-5357-8b24-3cfeb86f96d6 | note | Material Test Frequency - After works complete
d360882f-7d5c-5288-ba9c-d1eeafd8bf62 | note | Target Criteria - RAMM sheet 100% complete and accurate.
09e11103-942d-5ddb-9838-9169073bb738 | note | Action Point Records Required - RAMM Asset Update Sheet
1e4bb71e-45f9-5499-b395-aa24f6f7c3a8 | note | Responsibility - PQE / CE / PM / ER